## Start here
Drop 0 Configuration Inputs
Every configuration input BDOI provides before go-live for Drop 0 and the platform set-up Drop 1 depends on
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Scope |  | Drop 0 (BRD-03, BRD-11, BRD-13) and the platform set-up Drop 1 depends on
Version and date |  | Version 2.1, 8 October 2026
Go-live |  | Go-live is proposed for Monday 3 January 2028 (T), at the year-end boundary (option A of the Data Migration set, for Comptrollership to confirm).
Owner |  | Program Manager, Business Project Services, with the BDOI owner of each item
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | The index below lists every configuration input of Drop 0 and of the platform set-up that Drop 1 depends on, one row per item, by due date; within a due date the templates come in the order they are filled in, a template whose codes others use first.
2 | Each item has one route. Template: fill in the template sheet (Open →); its rows are then entered or uploaded on the named screen and authorised by a second user. Screen: enter the item on the named BIBS screen and record the decision in BDOI comments. Migration object: the item comes from the legacy systems through the named object of the Migration Workbook (BRD-13); it is not typed here.
3 | On a template sheet, read the header block and the guide above each column (Mandatory, Format, Allowed values, What to enter; * marks a mandatory column), overwrite or delete the grey example row and enter one row per record. Drop-downs offer the allowed values (sheet Reference lists) and the codes of the templates filled in before; a mandatory cell left empty turns red.
4 | The sheets starting with Ref list every list of values, system parameter, numbering prefix, notification event, document template and accounting event of BIBS, and the migration cross-reference; set the value wanted, the decision or the comment on each row you own.
5 | Set the Status of each item, follow Rows entered and Mandatory cells missing, raise questions on the sheet Questions and comments, and return the workbook to the iorta TechNXT project team by each due date. The status is reviewed at the weekly programme meeting. Codes must be the codes of the other sheets: branch codes of D0-02, accounts of D0-06, cost centres of D0-04, bank accounts of D0-11, group profiles of UA-02 and users of UA-01.
Configuration inputs by due date, templates in the order they are filled in
Step | ID | Configuration item | What BDOI provides | Owner (BDOI unit) | Due | Route | Entered or loaded on | Prepared in | Depends on | Rows entered | Mandatory cells missing | Status | BDOI comments | Provided on | Open
1 | CFG-023 | Legacy control accounts and Migration Clearing | The account codes of the legacy control accounts and of Migration Clearing in the production chart (proposed rule PR-DM-02) | Head, Comptrollership | 1-Dec-2026 – Drafts with the Drop 0 sign-off | Template | Finance › General Ledger › Chart of Accounts | Drop 0 template D0-09, sheet D0-09 Legacy accounts | D0-06 |  |  | Not started |  |  | D0-09 →
2 | CFG-075 | Directory sign-in and provisioning (EIAM, UIDM-ISC) | The sign-in mode, the EIAM tenant and claims, and the UIDM-ISC option (clarifications CLR-UA-01 and CLR-UA-03) | BDOI IT | 1-Dec-2026 – Drafts with the Drop 0 sign-off | Screen | Setup & Administration › Administration › System Parameters | This index row (decision and values in BDOI comments) | - |  |  | Not started
3 | CFG-002 | Branches and invoicing branches | Every BDOI branch with its region, address, opening date, head-office flag, contact and weekly rest days; the legacy branch codes are mapped to them by the migration (R02, check only) | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Setup & Administration › Setup › Branches | Drop 0 template D0-02, sheet D0-02 Branches | - |  |  | Not started |  |  | D0-02 →
4 | CFG-004 | Cost centres and business lines | The cost centres and business lines used on journal lines and in the cost-centre rules; the legacy cost centres are mapped by code map COST_CENTER | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Setup & Administration › Setup › Dimensions | Drop 0 template D0-04, sheet D0-04 Dimensions | - |  |  | Not started |  |  | D0-04 →
5 | CFG-021 | Account categories and numbering scheme | The GL categories (with the bank categories) and the numbering scheme under each parent (separator and width) | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Finance › General Ledger › Chart of Accounts | Drop 0 template D0-07, sheet D0-07 Categories and numbering | - |  |  | Not started |  |  | D0-07 →
6 | CFG-052 | Account numbering scheme | Covered by CFG-021: the separator and width of the account codes under each parent | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template |  | Drop 0 template D0-07, sheet D0-07 Categories and numbering | - |  |  | Not started |  |  | D0-07 →
7 | CFG-020 | Chart of accounts | The production chart of accounts of BDOI in the chart upload template: every account with its parent, class, level, control and sub-ledger flags, currencies and report group | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Finance › General Ledger › Chart Upload | Drop 0 template D0-06, sheet D0-06 Chart of accounts | D0-07 |  |  | Not started |  |  | D0-06 →
8 | CFG-003 | Holiday calendar | Public and company holidays of 2027 and 2028, company-wide or per branch; they drive the working days of service levels, value dates and jobs | Head, Comptrollership; Human Resources | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Setup & Administration › Setup › Holiday Calendar | Drop 0 template D0-03, sheet D0-03 Holiday calendar | D0-02 |  |  | Not started |  |  | D0-03 →
9 | CFG-040 | Company bank accounts | Every BDOI bank account used for collections and disbursements: bank, account number, currency, branch, GL account and PDC clearing account | Head, Comptrollership; Treasury | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Finance › Disbursement › Bank Accounts and Checks | Drop 0 template D0-11, sheet D0-11 Bank accounts | D0-06, D0-02 |  |  | Not started |  |  | D0-11 →
10 | CFG-001 | Company | The BDOI company record: code, registered name, TIN, address, base currency, fiscal year start and the value-date window of postings | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Setup & Administration › Setup › Companies | Drop 0 template D0-01, sheet D0-01 Company | D0-06 |  |  | Not started |  |  | D0-01 →
11 | CFG-022 | Accounting rules per event | For each accounting event of the platform, the debit and credit accounts per amount component, business line and currency | Head, Comptrollership | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Template | Finance › Accounting Engine › Accounting Rules | Drop 0 template D0-08, sheet D0-08 Accounting rules | D0-04, D0-06 |  |  | Not started |  |  | D0-08 →
12 | CFG-111 | Role-to-permission matrix | BRD-11 template CI-02 | Business Administration with the unit heads; reviewed and signed by BDOI Information Security | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Template | Setup & Administration › User Access › Group Profile Requests | BRD-11 template CI-02, sheet UA-02 Role matrix | - |  |  | Not started |  |  | UA-02 →
13 | CFG-045 | Bank list (mortgagee banks) | The banks named as mortgagee or payout bank; the legacy bank codes are mapped to this list by code map BANK | Product Owner, BDOI (New Business) | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Template | Setup & Administration › Broking Setup › Lists of Values | This workbook, sheet Ref Lists of values | - |  |  | Not started |  |  | Open →
14 | CFG-060 | Lists of values (every list of the platform) | For every list: its owner, and the values BDOI keeps, adds or retires. The lists whose values come from the legacy systems are loaded by R01; the others are entered on Lists of Values under maker-checker (see the sheet Ref Lists of values for the route of each list) | BDOI IT | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Template | Setup & Administration › Broking Setup › Lists of Values | This workbook, sheet Ref Lists of values | - |  |  | Not started |  |  | Open →
15 | CFG-090 | Product catalogue | Product lines, cover types and products (risk codes) with their features, prepared in BRD-03 template CI-01 | Product Owner, Marketing Business System (MBS) | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Migration object | Data migration object R05 Product lines, cover types, products and risk codes; after go-live: Client & Policy › Product Maintenance › Products | BRD-03 template CI-01, sheet PM-01 Product catalogue; delivered in the layout of R05 | PM-09 |  |  | Not started |  |  | PM-01 →
16 | CFG-100 | Insurers and insurer branches | The insurer panel with accreditation, placement e-mails and credit days, and the insurer branches with their LGT rate (BRD-03 template CI-05) | Head, Operations Services | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Migration object | Data migration object R04 Insurers and insurer branches; after go-live: Client & Policy › Product Maintenance › Insurers | BRD-03 template CI-05, sheet PM-05 Insurers; delivered in the layout of R04 | PM-01 |  |  | Not started |  |  | PM-05 →
17 | CFG-101 | Commission rates by insurer and product | The commission rates in force at cut-over and later (commission rows of BRD-03 template CI-05) | Head, Operations Services | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Migration object | Data migration object R07 Commission rates by insurer and product; after go-live: Client & Policy › Product Maintenance › Insurers | BRD-03 template CI-05, sheet PM-05 Insurers; delivered in the layout of R07 | PM-01 |  |  | Not started |  |  | PM-05 →
18 | CFG-007 | Sales organisation (regions, departments, teams, unit heads, account officers) | The sales units and account officers in force, and the inactive officers of open items; after go-live maintained on Sales Organisation | Product Owner, BDOI (New Business) | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Migration object | Data migration object R03 Sales organisation (regions, departments, teams, unit heads, account officers); after go-live: Client & Policy › Product Maintenance › Sales Organisation | Migration Workbook, layout R03 | - |  |  | Not started |  |  | R03 →
19 | CFG-103 | Payees | Active payees of EBIX, loaded by the payee registration of Disbursement if BDOI brings R09 into scope (conditional object, DMQ30); otherwise registered on Payees | Head, Comptrollership | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Migration object | Data migration object R09 Payees; after go-live: Finance › Disbursement › Payees | Migration Workbook, layout R09 | - |  |  | Not started |  |  | R09 →
20 | CFG-095 | Package map (legacy package to BIBS package version) | BRD-03 template CI-07, loaded as reference data for the package check of the Renewal sanitation | Product Owner, Marketing Business System (MBS) | 18-Jun-2027 – Code maps approved (M5) | Migration object | Data migration object R06 Package code map (legacy package and version to BIBS package version); after go-live: Data Migration › Data Migration › Code Maps | BRD-03 template CI-07, sheet PM-07 Package map; delivered in the layout of R06 | PM-01, PM-05, PM-06 |  |  | Not started |  |  | PM-07 →
21 | CFG-024 | Chart of accounts mapping (legacy GL account to BIBS account) | The map of every legacy GL account of EBIX and ISYS to a BIBS account; control accounts to Migration Clearing | Program Manager, Business Project Services (Data Migration) | 18-Jun-2027 – Code maps approved (M5) | Migration object | Data migration object R08 Chart of accounts mapping (legacy GL account to BIBS account); after go-live: Data Migration › Data Migration › Code Maps | Migration Workbook, layout R08 | - |  |  | Not started |  |  | R08 →
22 | CFG-061 | Values of the lists used by migrated records | The legacy values of the lists mapped by the code maps LOV and MIS, and the BIBS value of each | Program Manager, Business Project Services (Data Migration) | 18-Jun-2027 – Code maps approved (M5) | Migration object | Data migration object R01 Lists of values and MIS values; after go-live: Data Migration › Data Migration › Code Maps | Migration Workbook, layout R01 | - |  |  | Not started |  |  | R01 →
23 | CFG-140 | Code maps of the reference data | The approved versions of the code maps (branches, sales units, officers, users, cost centres, banks, currencies, dispositions, statuses) that turn legacy codes into BIBS codes | Program Manager, Business Project Services (Data Migration) | 18-Jun-2027 – Code maps approved (M5) | Migration object | Data migration object R01 Lists of values and MIS values; after go-live: Data Migration › Data Migration › Code Maps | Migration Workbook, layout R01 | - |  |  | Not started |  |  | R01 →
24 | CFG-141 | Branch code map | The map of every legacy branch and invoicing branch to a BIBS branch of CFG-002 | Program Manager, Business Project Services (Data Migration) | 18-Jun-2027 – Code maps approved (M5) | Migration object | Data migration object R02 Branches and invoicing branches; after go-live: Data Migration › Data Migration › Code Maps | Migration Workbook, layout R02 | - |  |  | Not started |  |  | R02 →
25 | CFG-097 | Lists and parameters of Product Maintenance | BRD-03 template CI-09 (the lists and parameters it names are listed with this route on the sheets Ref Lists of values and Ref System parameters) | Product Owner, MBS; System Administrator (entry) | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Broking Setup › Lists of Values | BRD-03 template CI-09, sheet PM-09 Lists and parameters | - |  |  | Not started |  |  | PM-09 →
26 | CFG-005 | Employees | Employees with their branch and cost centre, for the cost-centre rules, petty cash custodians and staff advances | Human Resources; Head, Comptrollership | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Setup › Employees | Drop 0 template D0-05, sheet D0-05 Employees | D0-02, D0-04 |  |  | Not started |  |  | D0-05 →
27 | CFG-113 | Separation-of-duties rules | BRD-11 template CI-04 | BDOI Information Security | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › User Access › Separation of Duties | BRD-11 template CI-04, sheet UA-04 SoD rules | UA-02 |  |  | Not started |  |  | UA-04 →
28 | CFG-091 | Coverages, perils and field rules | BRD-03 template CI-02 | MBS | 16-Jul-2027 – Values for UAT | Template | Client & Policy › Product Maintenance › Coverages & Clauses | BRD-03 template CI-02, sheet PM-02 Coverages and rules | PM-09, PM-01 |  |  | Not started |  |  | PM-02 →
29 | CFG-092 | Clause library | BRD-03 template CI-03 | TSU (wordings); MBS (maintenance) | 16-Jul-2027 – Values for UAT | Template | Client & Policy › Product Maintenance › Coverages & Clauses | BRD-03 template CI-03, sheet PM-03 Clause library | PM-09, PM-01 |  |  | Not started |  |  | PM-03 →
30 | CFG-025 | Tax codes and forms | The withholding, VAT and percentage tax codes with their ATC, rate, GL account and effective dates; the RDO code | Head, Comptrollership (Tax) | 16-Jul-2027 – Values for UAT | Template | Finance › Tax & Statutory › Tax Codes & Forms | Drop 0 template D0-10, sheet D0-10 Tax codes | D0-06 |  |  | Not started |  |  | D0-10 →
31 | CFG-114 | Approval limits and matrices of the modules | The approval levels by amount, sum insured or segment of Submitted Policies, Employee Benefits, Sanction Screening and Disbursement, with the approver role and the signatory | Owners of the modules; Head, Comptrollership for the amounts | 16-Jul-2027 – Values for UAT | Template |  | Drop 0 template D0-15, sheet D0-15 Approval limits | UA-02, UA-01 |  |  | Not started |  |  | D0-15 →
32 | CFG-093 | Rate tables | BRD-03 template CI-04 | Product Owner, MBS; Comptrollership (taxes) | 16-Jul-2027 – Values for UAT | Template | Client & Policy › Product Maintenance › Rates & Taxes | BRD-03 template CI-04, sheet PM-04 Rate tables | PM-01 |  |  | Not started |  |  | PM-04 →
33 | CFG-096 | Incentive criteria | BRD-03 template CI-10 | Incentive Maintenance user (MBS); Comptrollership (CPC2 definition, PQ04) | 16-Jul-2027 – Values for UAT | Template | Client & Policy › Product Maintenance › Incentive Criteria | BRD-03 template CI-10, sheet PM-10 Incentive criteria | PM-09, PM-01 |  |  | Not started |  |  | PM-10 →
34 | CFG-112 | Approvers, approval rules and authorisation limits | BRD-11 template CI-03: the access approvers and the authorisation limit of each user who approves by amount | Business Administration; BDOI Information Security for the second approval; Comptrollership for the authorisation limits | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › User Access › New Request | BRD-11 template CI-03, sheet UA-03 Approval rules | UA-01 |  |  | Not started |  |  | UA-03 →
35 | CFG-043 | Bank statement layouts | The column layout of the statement file of each bank account for the bank reconciliation | Head, Comptrollership; Treasury | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Setup › Bank Statement Layouts | Drop 0 template D0-14, sheet D0-14 Statement layouts | D0-11 |  |  | Not started |  |  | D0-14 →
36 | CFG-098 | Package document templates | BRD-03 template CI-08: the texts of the package documents | TSU and MBS (texts); Business Administrator (maintenance) | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Broking Setup › Document Templates | BRD-03 template CI-08, sheet PM-08 Document templates | - |  |  | Not started |  |  | PM-08 →
37 | CFG-071 | Sign-in, password, session and access-request parameters | The security values agreed with BDOI Information Security (BRD-11 template CI-05) | BDOI Information Security; BDOI IT for the sign-in mode | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Administration › System Parameters | BRD-11 template CI-05, sheet UA-05 Parameters | - |  |  | Not started |  |  | UA-05 →
38 | CFG-051 | Document number prefixes | The prefix of every numbered document (quotations, proposals, slips, package requests, renewals, submitted policies, screening cases); the year and the running number follow the prefix | BDOI IT | 16-Jul-2027 – Values for UAT | Template |  | This workbook, sheet Ref Document numbering | - |  |  | Not started |  |  | Open →
39 | CFG-070 | System parameters (every parameter of the platform) | For every parameter: the value BDOI wants against the value proposed, with the reason and the approver (see the sheet Ref System parameters) | BDOI IT | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Administration › System Parameters | This workbook, sheet Ref System parameters | - |  |  | Not started |  |  | Open →
40 | CFG-080 | Notification events and recipients | For every notification event: in-app and e-mail by default, and any unit mailbox that must receive it besides the users of the step (see the sheet Ref Notifications) | BDOI IT | 16-Jul-2027 – Values for UAT | Template | Operations › Operations › Notification Settings | This workbook, sheet Ref Notifications | - |  |  | Not started |  |  | Open →
41 | CFG-081 | Fixed recipients and sender address | The sender address of BIBS e-mails and the recipients of job failures and watchlist loads (parameters MAIL_FROM_ADDRESS, JOB_FAILURE_RECIPIENTS, SCR_INGEST_ALERT_RECIPIENTS) | BDOI IT | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Administration › System Parameters | This workbook, sheet Ref System parameters | - |  |  | Not started |  |  | Open →
42 | CFG-082 | Document templates (letters, slips, advices, e-mails) | The BDOI wording and layout of every generated document (see the sheet Ref Document templates) | BDOI IT | 16-Jul-2027 – Values for UAT | Template | Setup & Administration › Broking Setup › Document Templates | This workbook, sheet Ref Document templates | - |  |  | Not started |  |  | Open →
43 | CFG-006 | Cost-centre rules | Which cost centre an automatic posting takes by module, event, branch, party or account | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Setup › Cost-Centre Rules | This index row (decision and values in BDOI comments) | - |  |  | Not started
44 | CFG-008 | Production targets | The 2028 production targets per sales unit and officer for the New Business reports | Product Owner, BDOI (New Business) | 16-Jul-2027 – Values for UAT | Screen | Reports › New Business Reports › Production Targets | This index row (decision and values in BDOI comments) | - |  |  | Not started
45 | CFG-010 | Currencies and exchange rates | The currencies in use and the source and owner of the daily BOOK rate; the legacy currency codes are mapped by code map CURRENCY | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Setup › Currencies & Rates | This index row (decision and values in BDOI comments) | - |  |  | Not started
46 | CFG-026 | Financial statement formats and account schedules | The lines of the financial statements and MIS formats and the accounts in each, as Comptrollership reports them | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Finance › Accounting Reports › Account Schedules | This index row (decision and values in BDOI comments) | - |  |  | Not started
47 | CFG-028 | Asset categories | Fixed-asset categories with their useful life, method and accounts | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Finance › Assets & Investments › Asset Categories | This index row (decision and values in BDOI comments) | - |  |  | Not started
48 | CFG-029 | Investment portfolios | The investment portfolios and their accounts, when BDOI keeps investments in BIBS | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Finance › Assets & Investments › Investment Portfolios | This index row (decision and values in BDOI comments) | - |  |  | Not started
49 | CFG-030 | GL-SL reconciliation controls (ACSL) | The control accounts reconciled against their sub-ledgers and the tolerance of each | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Finance › ACSL › GL-SL Reconciliation | This index row (decision and values in BDOI comments) | - |  |  | Not started
50 | CFG-031 | Service fee rates | The service fee rates per segment and their recipients | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Finance › Accounting Reports › Service Fee Rates | This index row (decision and values in BDOI comments) | - |  |  | Not started
51 | CFG-044 | Payment file layouts of the collection channels | Confirmation of the payment files received from Bills Payment, Trade, Direct Credit, CLPC and PMS and their field names | Head, Operations Services | 16-Jul-2027 – Values for UAT | Screen | Finance › Cashiering › Cashiering Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
52 | CFG-072 | Exception codes and alert thresholds | Which exceptions raise an alert, with their severity and the amount or day threshold of each | BDOI IT | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Administration › Exception Codes | This index row (decision and values in BDOI comments) | - |  |  | Not started
53 | CFG-073 | Scheduled job times | The run time of each daily and monthly job in Philippine time, and the blackout windows | BDOI IT | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Administration › Scheduled Jobs | This index row (decision and values in BDOI comments) | - |  |  | Not started
54 | CFG-074 | Data retention rules | Years online and in the archive per record type, and the action at the end, as Compliance sets them | Compliance | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Broking Setup › Data Retention | This index row (decision and values in BDOI comments) | - |  |  | Not started
55 | CFG-083 | Screening forms and STR layout | The screening forms and the STR report layout Compliance submits | Compliance | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Compliance Setup › Templates | This index row (decision and values in BDOI comments) | - |  |  | Not started
56 | CFG-102 | Business partners other than insurers (suppliers, service providers) | Suppliers and other partners paid through Payables, with TIN, address and bank details | Head, Comptrollership | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Setup › Business Partners | This index row (decision and values in BDOI comments) | - |  |  | Not started
57 | CFG-104 | Insurer location references (claims) | The claim location references of each insurer, entered or uploaded on Insurer Location References | Product Owner, Claims | 16-Jul-2027 – Values for UAT | Screen | Claims › Claims Handling › Insurer Location References | This index row (decision and values in BDOI comments) | - |  |  | Not started
58 | CFG-115 | User scope of Submitted Policies | The segments and units each Submitted Policies user may see | Product Owner, Submitted Policies | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Submitted Policies › Submitted Policies Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
59 | CFG-120 | Booking rules and incentive rules | The automatic booking rules and the booking incentive rules | Product Owner, BDOI (New Business) | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Booking › Booking Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
60 | CFG-121 | Remittance incentive rules | The incentive deductions applied at remittance | Head, Operations Services | 16-Jul-2027 – Values for UAT | Screen | Finance › Remittance › Incentive Rules | This index row (decision and values in BDOI comments) | - |  |  | Not started
61 | CFG-122 | Commission incentive schemes | The commission incentive schemes and their rates | VP and Head, BDOI Operations (Collections) | 16-Jul-2027 – Values for UAT | Screen | Finance › Commission Receivables › Incentive Schemes | This index row (decision and values in BDOI comments) | - |  |  | Not started
62 | CFG-123 | Collections assignment and escalation rules | How accounts are assigned to collectors and when they escalate to the team lead and the unit head | VP and Head, BDOI Operations (Collections) | 16-Jul-2027 – Values for UAT | Screen | Finance › Collections › Collections Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
63 | CFG-124 | Renewal buckets and decision matrix | The renewal bucket rules, the decision matrix and the non-renewable risk codes | Product Owner, Renewal | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Renewal › Renewal Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
64 | CFG-125 | Submitted Policies rules, limits and letters | The processing rules, insurer rules and limits, and the letter rules of Submitted Policies | Product Owner, Submitted Policies | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Submitted Policies › Submitted Policies Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
65 | CFG-126 | Screening configuration | Match rules, risk categories and rules, assignment, service levels and validation rules of Sanction Screening | Compliance | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Compliance Setup › Configuration Versions | This index row (decision and values in BDOI comments) | - |  |  | Not started
66 | CFG-127 | Watchlist sources and entries | The sanctions and PEP list sources, their load schedule and the first load | Compliance | 16-Jul-2027 – Values for UAT | Screen | Setup & Administration › Compliance Setup › List Sources and Runs | This index row (decision and values in BDOI comments) | - |  |  | Not started
67 | CFG-128 | Employee Benefits set-up | The required documents per process and the other Employee Benefits settings | Product Owner, Employee Benefits | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Employee Benefits › EB Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
68 | CFG-129 | Claims handlers and set-up | The claims handlers per unit and the Claims settings | Product Owner, Claims | 16-Jul-2027 – Values for UAT | Screen | Claims › Claims Handling › Claims Setup | This index row (decision and values in BDOI comments) | - |  |  | Not started
69 | CFG-130 | Production reconciliation extract schedules | The insurers and the schedule of the production extracts sent for reconciliation | Head, Operations Services | 16-Jul-2027 – Values for UAT | Screen | Client & Policy › Production Reconciliation › Extract Schedules | This index row (decision and values in BDOI comments) | - |  |  | Not started
70 | CFG-131 | New Business report variants | The report variants the units use | Product Owner, BDOI (New Business) | 16-Jul-2027 – Values for UAT | Screen | Reports › New Business Reports › New Business Reports | This index row (decision and values in BDOI comments) | - |  |  | Not started
71 | CFG-110 | Users at go-live | BRD-11 template CI-01, uploaded as a bulk request and approved; users are not migrated (R10 excluded, legacy user IDs only mapped) | Business Administration, with the unit heads who name their users | 1-Nov-2027 – Production values before the dress rehearsal | Template | Setup & Administration › User Access › Bulk Request | BRD-11 template CI-01, sheet UA-01 Users and roles | UA-06, UA-02 |  |  | Not started |  |  | UA-01 →
72 | CFG-094 | Packages in force at go-live | BRD-03 template CI-06: one package request per package, set up and validated before the map freeze | TSU (prepares); Product Owner, MBS (approves) | 1-Nov-2027 – Production values before the dress rehearsal | Template | Client & Policy › Product Maintenance › New Package Request | BRD-03 template CI-06, sheet PM-06 Packages | PM-01, PM-02, PM-05, PM-03 |  |  | Not started |  |  | PM-06 →
73 | CFG-041 | Check books | The check books in stock per bank account at go-live: first, last and next check number | Treasury; Product Owner, Comptrollership - Disbursement | 1-Nov-2027 – Production values before the dress rehearsal | Template | Finance › Disbursement › Bank Accounts and Checks | Drop 0 template D0-12, sheet D0-12 Check books | D0-11 |  |  | Not started |  |  | D0-12 →
74 | CFG-042 | Petty cash funds | Each petty cash fund: branch, custodian, imprest amount, GL account and replenishment bank account | Head, Comptrollership | 1-Nov-2027 – Production values before the dress rehearsal | Template | Finance › Payables & Cash › Petty Cash | Drop 0 template D0-13, sheet D0-13 Petty cash funds | D0-02, D0-05, D0-06, D0-11 |  |  | Not started |  |  | D0-13 →
75 | CFG-009 | Financial year and periods | Financial year 2028 and its periods, opened by Comptrollership; FY2027 stays in legacy (year-end option A) | Head, Comptrollership | 1-Nov-2027 – Production values before the dress rehearsal | Screen | Finance › General Ledger › Financial Periods | This index row (decision and values in BDOI comments) | - |  |  | Not started
76 | CFG-027 | Recurring journals | The monthly accruals and allocations Comptrollership posts as recurring journals from January 2028 | Head, Comptrollership | 1-Nov-2027 – Production values before the dress rehearsal | Screen | Finance › General Ledger › Recurring Journals | This index row (decision and values in BDOI comments) | - |  |  | Not started
77 | CFG-050 | Receipt series in use (AR and OR) | The BIR-authorised AR and OR series of each branch in use at the freeze (ATP, range and next number), so BIBS continues them without gap or overlap | Head, Operations Services | 27-Dec-2027 – Map freeze (T-7) | Migration object | Data migration object R11 Receipt series in use (AR and OR, ATP and next number); after go-live: Finance › Cashiering › Receipt Series | Migration Workbook, layout R11 | - |  |  | Not started |  |  | R11 →
Due milestones
Due | Milestone |  |  | Due date | Before go-live | Items | Why this date
D1 | Drafts with the Drop 0 sign-off |  |  | 1-Dec-2026 | T-56 weeks | 2 | Sign-off of BRD-11 on 1-Dec-2026, the last of the three Drop 0 sets
D2 | Platform set-up for Drop 1 SIT |  |  | 4-Jan-2027 | T-52 weeks | 9 | Drop 1 SIT runs Jan - Jul 2027 on the BDOI organisation, chart of accounts and banks
D3 | Reference data for Trial migration 1 (M4) |  |  | 9-Apr-2027 | T-38 weeks | 8 | Extracts for Trial migration 1; reference data and clients first
D4 | Code maps approved (M5) |  |  | 18-Jun-2027 | T-28 weeks | 5 | Code maps approved for Trial migration 2, including the package code map
D5 | Values for UAT |  |  | 16-Jul-2027 | T-24 weeks | 46 | UAT plans and sign-off forms due 16-Jul-2027; UAT Aug - Dec 2027 runs on the production values
D6 | Production values before the dress rehearsal |  |  | 1-Nov-2027 | T-9 weeks | 6 | Dress rehearsal in November 2027; the values loaded for it are the go-live values
D7 | Map freeze (T-7) |  |  | 27-Dec-2027 | T-1 weeks | 1 | No change of a code map or reference value after the freeze except by change request
Reference sheets and other sheets
Sheet |  |  | What it holds
Ref Lists of values |  |  | Every list of values of BIBS with its owner and its one route
Ref System parameters |  |  | Every system parameter with the value proposed and the value BDOI wants
Ref Document numbering |  |  | Prefixes of the numbered documents; receipt series come from object R11, check numbers from D0-12
Ref Notifications |  |  | Every notification event with its default channels; users choose their own channels in Notification Settings
Ref Document templates |  |  | Every generated document with the unit that gives its BDOI wording and layout
Ref Accounting events |  |  | The accounting events that need a rule of template D0-08; owner Head, Comptrollership
Ref Migration cross-reference |  |  | Reference data loaded by the migration and the register items it carries
Reference lists |  |  | Every list of allowed values of the drop-downs, with code and label
Questions and comments |  |  | Questions and comments per template and column, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## D0-02 Branches
D0-02 Branches | [11 empty] | Step 1 of 31
← Back to Start here | Step 1 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [10 empty] | Ask a question →
Purpose | Every BDOI branch and invoicing branch
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Branches (Setup & Administration), before the first migration mock; the legacy branches are mapped to them by the code map BRANCH (object R02)
Source | BDOI branch list; EBIX branch codes for the code map BRANCH
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | Yes | Yes | Yes | No | No | No | No | No
Format | Up to 10 capitals | Up to 120 characters | Text | Text | dd-MMM-yyyy | Y or N | Y or N | Text | E-mail address | Name | SAT, SUN | EBIX codes separated by commas
Allowed values | Free entry, up to 10 characters | Free entry, up to 120 characters | Free entry | Free entry | A date, for example 15-Jan-2028 | Y or N | Y or N | Free entry | Free entry | Free entry | Free entry | Free entry
What to enter | Code of the branch; unique | Name shown on screens and documents | Region of the branch | Address printed on documents | Date the branch opened | Y for one branch only | May receive and pay in foreign currency | Branch telephone | Branch mailbox | Head of the branch | Days the branch is closed each week | For the code map BRANCH (R02)
Row | Branch code * | Branch name * | Region | Address | Opening date * | Head office * | Foreign currency authorised * | Contact phone | Contact e-mail | Branch manager | Weekly rest days | Legacy branch codes
Example – overwrite or delete | HO | Head Office | NCR | 7899 Makati Avenue, Makati City | 2010-01-01 | Y | Y | (02) 8888-0000 | ho@bdoi.example.ph |  | SAT,SUN | 001
Note on B16: Branch code Code of the branch; unique Mandatory: Yes Format: Up to 10 capitals Allowed values: Free entry, up to 10 characters Example: HO
Note on C16: Branch name Name shown on screens and documents Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Head Office
Note on D16: Region Region of the branch Mandatory: No Format: Text Allowed values: Free entry Example: NCR
Note on E16: Address Address printed on documents Mandatory: No Format: Text Allowed values: Free entry Example: 7899 Makati Avenue, Makati City
Note on F16: Opening date Date the branch opened Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2010
Note on G16: Head office Y for one branch only Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on H16: Foreign currency authorised May receive and pay in foreign currency Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on I16: Contact phone Branch telephone Mandatory: No Format: Text Allowed values: Free entry Example: (02) 8888-0000
Note on J16: Contact e-mail Branch mailbox Mandatory: No Format: E-mail address Allowed values: Free entry Example: ho@bdoi.example.ph
Note on K16: Branch manager Head of the branch Mandatory: No Format: Name Allowed values: Free entry
Note on L16: Weekly rest days Days the branch is closed each week Mandatory: No Format: SAT, SUN Allowed values: Free entry Example: SAT,SUN
Note on M16: Legacy branch codes For the code map BRANCH (R02) Mandatory: No Format: EBIX codes separated by commas Allowed values: Free entry Example: 001

## D0-04 Dimensions
D0-04 Cost centres and business lines |  |  |  |  | Step 2 of 31
← Back to Start here | Step 2 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  | Ask a question →
Purpose | The values of the dimensions of journal lines
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Dimensions (Setup & Administration); the legacy cost centres are mapped by the code map COST_CENTER
Source | Current cost centre list of Comptrollership; the product lines for the business lines
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes
Format | COST_CENTER or BUSINESS_LINE | Up to 20 capitals or digits | Up to 120 characters | Y or N
Allowed values | COST_CENTER, BUSINESS_LINE (list Dimension) | Free entry, up to 20 characters | Free entry, up to 120 characters | Y or N
What to enter | Dimension of the value | Code of the value | Name shown on screens and reports | N keeps the value for history only
Row | Dimension * | Code * | Name * | Active *
Example – overwrite or delete | COST_CENTER | FIN | Finance and Accounting | Y
Note on B16: Dimension Dimension of the value Mandatory: Yes Format: COST_CENTER or BUSINESS_LINE Allowed values: COST_CENTER, BUSINESS_LINE (list Dimension) Example: COST_CENTER
Note on C16: Code Code of the value Mandatory: Yes Format: Up to 20 capitals or digits Allowed values: Free entry, up to 20 characters Example: FIN
Note on D16: Name Name shown on screens and reports Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Finance and Accounting
Note on E16: Active N keeps the value for history only Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y

## D0-07 Categories and numbering
D0-07 Account categories and numbering | [7 empty] | Step 3 of 31
← Back to Start here | Step 3 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The GL categories and the numbering scheme under each parent account
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Chart of Accounts (General Ledger)
Source | The BDOI chart of accounts
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: NUMBERING | Conditional: NUMBERING | Conditional: NUMBERING
Format | CATEGORY or NUMBERING | Up to 20 capitals | Text | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE | Y or N | Account code of D0-06 | . or - or none | 1 to 6
Allowed values | CATEGORY, NUMBERING (list Category or numbering row) | Free entry, up to 20 characters | Free entry | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list Account class) | Y or N | Free entry | Free entry | A whole number from 1 to 6
What to enter | What the row defines | GL category | Name of the category | Class of the accounts of the category | Y for the accounts of bank accounts (D0-11) | Parent whose children are numbered | Between the parent code and the running number | Digits of the running number
Row | Row * | Category code | Category name | Account class | Bank category | Parent account | Separator | Width
Example – overwrite or delete | CATEGORY | CASH_IN_BANK | Cash in bank | ASSET | Y | 1110 | . | 2
Note on B16: Row What the row defines Mandatory: Yes Format: CATEGORY or NUMBERING Allowed values: CATEGORY, NUMBERING (list Category or numbering row) Example: CATEGORY
Note on C16: Category code GL category Mandatory: Conditional: CATEGORY Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: CASH_IN_BANK
Note on D16: Category name Name of the category Mandatory: Conditional: CATEGORY Format: Text Allowed values: Free entry Example: Cash in bank
Note on E16: Account class Class of the accounts of the category Mandatory: Conditional: CATEGORY Format: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list Account class) Example: ASSET
Note on F16: Bank category Y for the accounts of bank accounts (D0-11) Mandatory: Conditional: CATEGORY Format: Y or N Allowed values: Y or N Example: Y
Note on G16: Parent account Parent whose children are numbered Mandatory: Conditional: NUMBERING Format: Account code of D0-06 Allowed values: Free entry Example: 1110
Note on H16: Separator Between the parent code and the running number Mandatory: Conditional: NUMBERING Format: . or - or none Allowed values: Free entry Example: .
Note on I16: Width Digits of the running number Mandatory: Conditional: NUMBERING Format: 1 to 6 Allowed values: A whole number from 1 to 6 Example: 2

## PM-09 Lists and parameters
PM-09 Lists of values and parameters | [5 empty] | Step 4 of 31
← Back to Start here | Step 4 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the Product Maintenance lists (request reasons, response outcomes, advisory groups, not-proceeded reasons, incentive types, coverage kinds, clause kinds, document types, market segments) and the parameters (numbering, reply days, expiry notice, advisory groups, service levels)
Provided by | Product Owner, MBS; System Administrator (entry)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Data migration object R01 for the values used by migrated records; the other values on Lists of Values and System Parameters
Source | Delivered values (FRS chapter 9) confirmed or changed by BDOI
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: list | Yes | No | No
Format | Code of the list or parameter | Up to 40 capitals | Text; number for a parameter | Number; Y or N | dd-MMM-yyyy
Allowed values | List Product Maintenance list or parameter: 40 values, see Reference lists | Free entry, up to 40 characters | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | For example PKG_REQUEST_REASON, PKG_SLA_NEGOTIATION | Code of the value | Label shown to users, or the parameter value | Display order and status | From when the value applies
Row | List or parameter * | Value code | Label or value * | Order / Active | Effective from
Example – overwrite or delete | PKG_REQUEST_REASON | LOSS_EXPERIENCE | Loss experience | 50; Y | 2026-11-01
Note on B16: List or parameter For example PKG_REQUEST_REASON, PKG_SLA_NEGOTIATION Mandatory: Yes Format: Code of the list or parameter Allowed values: List Product Maintenance list or parameter: 40 values, see Reference lists Example: PKG_REQUEST_REASON
Note on C16: Value code Code of the value Mandatory: Conditional: list Format: Up to 40 capitals Allowed values: Free entry, up to 40 characters Example: LOSS_EXPERIENCE
Note on D16: Label or value Label shown to users, or the parameter value Mandatory: Yes Format: Text; number for a parameter Allowed values: Free entry Example: Loss experience
Note on E16: Order / Active Display order and status Mandatory: No Format: Number; Y or N Allowed values: Free entry Example: 50; Y
Note on F16: Effective from From when the value applies Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Nov-2026

## UA-02 Role matrix
UA-02 Role-to-permission matrix | [7 empty] | Step 5 of 31
← Back to Start here | Step 5 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The group profiles BDOI keeps, their privilege level and the permissions of each, starting from the User Access Matrix as delivered
Provided by | Business Administration with the unit heads; reviewed and signed by BDOI Information Security
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Group-profile requests (SCR-UA-12): one request per new or changed profile, approved in order and implemented by the System Administrator; checked with the User Group Profile Report
Source | The User Access Matrix export of this set (DO-06) and the menus by persona of FRS chapter 12
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes | No | Yes | Yes
Format | Up to 40 capital letters, digits or _ | Up to 120 characters | Up to 500 characters | Low, Standard, High or Admin | Permission code of the User Access Matrix | View only, Create, Amend, Approve / Validate | KEEP, ADD or REMOVE | Name
Allowed values | Free entry, up to 40 characters | Free entry, up to 120 characters | Free entry, up to 500 characters | Low, Standard, High, Admin (list Privilege level) | Free entry | Free entry | KEEP, ADD, REMOVE (list Change against the matrix) | Free entry
What to enter | Code of the profile; an existing code changes the profile | Name shown on screens | What the profile is for | High and Admin need a second approval when given or raised | One row per permission of the profile | As shown by the matrix, for the review | Change against the matrix as delivered | Unit head who confirms the row
Row | Group profile code * | Name * | Description | Privilege level * | Permission * | Action class | Keep / Add / Remove * | Approved by unit head *
Example – overwrite or delete | MKT_AO | Marketing Account Officer | Marketing account officers of the Combank and Corbank units | Standard | QUOTE_MAINTAIN | Create, Amend | KEEP | Carla Reyes
Note on B16: Group profile code Code of the profile; an existing code changes the profile Mandatory: Yes Format: Up to 40 capital letters, digits or _ Allowed values: Free entry, up to 40 characters Example: MKT_AO
Note on C16: Name Name shown on screens Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Marketing Account Officer
Note on D16: Description What the profile is for Mandatory: No Format: Up to 500 characters Allowed values: Free entry, up to 500 characters Example: Marketing account officers of the Combank and Corbank units
Note on E16: Privilege level High and Admin need a second approval when given or raised Mandatory: Yes Format: Low, Standard, High or Admin Allowed values: Low, Standard, High, Admin (list Privilege level) Example: Standard
Note on F16: Permission One row per permission of the profile Mandatory: Yes Format: Permission code of the User Access Matrix Allowed values: Free entry Example: QUOTE_MAINTAIN
Note on G16: Action class As shown by the matrix, for the review Mandatory: No Format: View only, Create, Amend, Approve / Validate Allowed values: Free entry Example: Create, Amend
Note on H16: Keep / Add / Remove Change against the matrix as delivered Mandatory: Yes Format: KEEP, ADD or REMOVE Allowed values: KEEP, ADD, REMOVE (list Change against the matrix) Example: KEEP
Note on I16: Approved by unit head Unit head who confirms the row Mandatory: Yes Format: Name Allowed values: Free entry Example: Carla Reyes

## UA-06 Lists of values
UA-06 Lists of values | [5 empty] | Step 6 of 31
← Back to Start here | Step 6 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the lists of user access (business unit groups and user levels, empty as delivered; deactivation reasons, to confirm with BDOI; the reason No sign-in for the dormancy period is used by the dormant-user job and stays)
Provided by | Business Administration
Due | 1-Nov-2027 – before the templates that use its codes
How it is loaded | Lists of Values (New Business set) under maker-checker; before the users of CI-01 are loaded
Source | BDOI organisation (UQ05)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | Yes
Format | UAM_BUSINESS_UNIT, UAM_USER_LEVEL or UAM_DEACTIVATION_REASON | Up to 30 capitals, digits or _ | Up to 120 characters | Whole number | dd-MMM-yyyy
Allowed values | UAM_BUSINESS_UNIT, UAM_USER_LEVEL, UAM_DEACTIVATION_REASON (list User access list) | Free entry, up to 30 characters | Free entry, up to 120 characters | A whole number | A date, for example 15-Jan-2028
What to enter | The list | Code of the value | Label shown on screens | Order in the drop-down | Date the value may be used
Row | List * | Code * | Label * | Sort order | Effective from *
Example – overwrite or delete | UAM_BUSINESS_UNIT | COMBANK_MKT | Combank Marketing | 10 | 2027-01-04
Note on B16: List The list Mandatory: Yes Format: UAM_BUSINESS_UNIT, UAM_USER_LEVEL or UAM_DEACTIVATION_REASON Allowed values: UAM_BUSINESS_UNIT, UAM_USER_LEVEL, UAM_DEACTIVATION_REASON (list User access list) Example: UAM_BUSINESS_UNIT
Note on C16: Code Code of the value Mandatory: Yes Format: Up to 30 capitals, digits or _ Allowed values: Free entry, up to 30 characters Example: COMBANK_MKT
Note on D16: Label Label shown on screens Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Combank Marketing
Note on E16: Sort order Order in the drop-down Mandatory: No Format: Whole number Allowed values: A whole number Example: 10
Note on F16: Effective from Date the value may be used Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 04-Jan-2027

## D0-05 Employees
D0-05 Employees | [6 empty] | Step 7 of 31
← Back to Start here | Step 7 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | Employees used by the cost-centre rules, petty cash and staff advances
Provided by | Human Resources; Head, Comptrollership
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Employees (Setup & Administration)
Source | HR employee list
Depends on | D0-02 Branches → |  | D0-04 Cost centres and business lines →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | No | No | No
Format | HR number | Up to 120 characters | Code of D0-02 | Cost centre of D0-04 | Text | Company e-mail | dd-MMM-yyyy
Allowed values | Free entry | Free entry, up to 120 characters | A code of D0-02 Branches, column Branch code | A code of D0-04 Cost centres and business lines, column Code | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Unique | Name of the employee | Home branch | Cost centre of the employee | Position title | For advices and statements | Date of hire
Row | Employee number * | Full name * | Branch code * | Cost centre * | Position | E-mail | Hired on
Example – overwrite or delete | 1203344 | Andrea Mercado | HO | FIN | Accounting Officer | andrea.mercado@bdoi.example.ph | 2019-03-03
Note on B16: Employee number Unique Mandatory: Yes Format: HR number Allowed values: Free entry Example: 1203344
Note on C16: Full name Name of the employee Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Andrea Mercado
Note on D16: Branch code Home branch Mandatory: Yes Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on E16: Cost centre Cost centre of the employee Mandatory: Yes Format: Cost centre of D0-04 Allowed values: A code of D0-04 Cost centres and business lines, column Code Example: FIN
Note on F16: Position Position title Mandatory: No Format: Text Allowed values: Free entry Example: Accounting Officer
Note on G16: E-mail For advices and statements Mandatory: No Format: Company e-mail Allowed values: Free entry Example: andrea.mercado@bdoi.example.ph
Note on H16: Hired on Date of hire Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 03-Mar-2019

## D0-06 Chart of accounts
D0-06 Chart of accounts | [15 empty] | Step 8 of 31
← Back to Start here | Step 8 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [14 empty] | Ask a question →
Purpose | The production chart of accounts, in the columns of the chart upload. List every parent before its children. Accounts are created pending authorization.
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Chart Upload (General Ledger): the file is checked row by row and every account is created pending authorisation by Comptrollership
Source | The BDOI chart of accounts in use, completed with the legacy control accounts (D0-09)
Depends on | D0-07 Account categories and numbering →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No
Format | Text | Text | Text | Text | Text | Text | Text | Y or N | Text | Text | Y or N | Y or N | Y or N | Text | yyyy-MM-dd | Text
Allowed values | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry | Free entry | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE, MEMORANDUM (list Account class of the chart) | GROUP, MAIN, SUB, MICRO (list Account level) | A code of D0-07 Account categories and numbering, column Category code | Y or N | Free entry | Free entry | Y or N | Y or N | Y or N | Free entry | Free entry | ALLOW, WARN, BLOCK (list Negative balance)
What to enter | Code of the parent account; blank for a top-level group | Account code; blank for the next number of the parent's scheme | Account name | Unique short code used on journal lines | Class of the account | Level of the account, one tier below the parent | GL category | Control account | Sub-ledger the account controls; blank for none | Currencies allowed on the account; blank for all | Manual journals allowed; blank for Y | Cost centre mandatory on journal lines | Revalued at month end | Financial statement line | Opening date; blank for today | What a negative balance does; blank for ALLOW
Row | Parent Code | Account Code | Account Name * | Short Code | Class * | Level * | Category | Control Account | Sub-ledger Type | Currencies | Manual Posting | Cost Centre Required | Revaluation Required | Report Group | Opened On | Negative Balance
Example – overwrite or delete |  | 1210.07 | Premium Receivable - Motor | PRMOTOR | ASSET | SUB |  | N | POLICYHOLDER | {baseCurrency} | Y | N | N | Premium Receivable | 2026-01-01 | WARN
Note on B16: Parent Code Code of the parent account; blank for a top-level group Mandatory: No Format: Text Allowed values: A code of D0-06 Chart of accounts, column Account Code
Note on C16: Account Code Account code; blank for the next number of the parent's scheme Mandatory: No Format: Text Allowed values: Free entry Example: 1210.07
Note on D16: Account Name Account name Mandatory: Yes Format: Text Allowed values: Free entry Example: Premium Receivable - Motor
Note on E16: Short Code Unique short code used on journal lines Mandatory: No Format: Text Allowed values: Free entry Example: PRMOTOR
Note on F16: Class Class of the account Mandatory: Yes Format: Text Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE, MEMORANDUM (list Account class of the chart) Example: ASSET
Note on G16: Level Level of the account, one tier below the parent Mandatory: Yes Format: Text Allowed values: GROUP, MAIN, SUB, MICRO (list Account level) Example: SUB
Note on H16: Category GL category Mandatory: No Format: Text Allowed values: A code of D0-07 Account categories and numbering, column Category code
Note on I16: Control Account Control account Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on J16: Sub-ledger Type Sub-ledger the account controls; blank for none Mandatory: No Format: Text Allowed values: Free entry Example: POLICYHOLDER
Note on K16: Currencies Currencies allowed on the account; blank for all Mandatory: No Format: Text Allowed values: Free entry Example: {baseCurrency}
Note on L16: Manual Posting Manual journals allowed; blank for Y Mandatory: No Format: Y or N Allowed values: Y or N Example: Y
Note on M16: Cost Centre Required Cost centre mandatory on journal lines Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on N16: Revaluation Required Revalued at month end Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on O16: Report Group Financial statement line Mandatory: No Format: Text Allowed values: Free entry Example: Premium Receivable
Note on P16: Opened On Opening date; blank for today Mandatory: No Format: yyyy-MM-dd Allowed values: Free entry Example: 2026-01-01
Note on Q16: Negative Balance What a negative balance does; blank for ALLOW Mandatory: No Format: Text Allowed values: ALLOW, WARN, BLOCK (list Negative balance) Example: WARN

## PM-01 Product catalogue
PM-01 Product catalogue | [21 empty] | Step 9 of 31
← Back to Start here | Step 9 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [20 empty] | Ask a question →
Purpose | Product lines, cover types and subtypes, and every product (risk code) with its features
Provided by | Product Owner, Marketing Business System (MBS)
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Data migration object R05 (product lines, cover types, products) through the catalogue services, pending authorisation; after go-live on Products (SCR-PM-11)
Source | Legacy QPS and EBIX product lists, completed by MBS
Depends on | PM-09 Lists of values and parameters →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Conditional: package products | Conditional: with the code | No | Yes | Yes | No | Yes | No | Yes | No | No | Yes | Yes | No | No | No | No | No | No
Format | Up to 30 capitals | Text | Regular expression | Up to 30 capitals | Text | Cover type code | 1 to 20 capitals or digits | Up to 200 characters | Text | Y or N | Codes separated by commas; blank = all | PAID or CLIENT_CONFIRMATION | BY_RULES, ALWAYS or NEVER | Up to four decimals | Percentage | Amount in PHP | Amount in PHP | Y or N | Y or N | Y or N | Y or N; 2 to 10 years | Y or N
Allowed values | Free entry, up to 30 characters | Free entry | Free entry | Free entry, up to 30 characters | Free entry | A code of PM-01 Product catalogue, column Cover type code | Free entry, up to 20 characters | Free entry, up to 200 characters | Free entry | Y or N | One or more codes of the list Market segment (Reference lists), separated by commas | PAID, CLIENT_CONFIRMATION (list Placement after) | BY_RULES, ALWAYS, NEVER (list TSU review) | A number from 0 to 100 | A number from 0 to 100 | A number | A number | Y or N | Y or N | Y or N | Free entry | Y or N
What to enter | Product line (level 1), for example MOTOR, PROPERTY | Name shown in the drop-downs | Naming convention of the risk codes of the line, when BDOI states one | Cover type (level 2) of the line | Name of the cover type | Only for a subtype (one level below a cover type) | Product code (level 3); unique | Name shown to users | Code of the product in QPS or EBIX, for the migration map | Y for a package product (terms change through versions) | Segments the product is offered to (list MARKET_SEGMENT) | Payment gate before placement | When TSU reviews an account of the product | Rate of a non-package product; for a package, of version 1 | Commission when no insurer rate applies | Minimum premium of the product | Above it the account goes to TSU | Several vehicles on one account | Mortgage or loan related | Premium may be paid directly to the insurer | Multi-year term and its maximum | Free First Year eligible
Row | Line code * | Line name * | Risk-code pattern | Cover type code | Cover type name | Parent cover type | Risk code * | Product name * | Legacy code | Package * | Market segments | Placement after * | TSU review | Default rate % | Default commission % * | Minimum premium * | Package TSI limit | Fleet | Mortgage related | Direct payment allowed | Multi-year / Maximum term | Free First Year
Example – overwrite or delete | MOTOR | Motor | MTR[0-9]{2} | COMPREHENSIVE | Comprehensive |  | MTR30 | Motor Fleet Plus | QPS-MFP | Y | COMBANK | PAID | BY_RULES | 1.2 | 15 | 5000 | 5000000 | Y | N | N | N | N
Note on B16: Line code Product line (level 1), for example MOTOR, PROPERTY Mandatory: Yes Format: Up to 30 capitals Allowed values: Free entry, up to 30 characters Example: MOTOR
Note on C16: Line name Name shown in the drop-downs Mandatory: Yes Format: Text Allowed values: Free entry Example: Motor
Note on D16: Risk-code pattern Naming convention of the risk codes of the line, when BDOI states one Mandatory: No Format: Regular expression Allowed values: Free entry Example: MTR[0-9]{2}
Note on E16: Cover type code Cover type (level 2) of the line Mandatory: Conditional: package products Format: Up to 30 capitals Allowed values: Free entry, up to 30 characters Example: COMPREHENSIVE
Note on F16: Cover type name Name of the cover type Mandatory: Conditional: with the code Format: Text Allowed values: Free entry Example: Comprehensive
Note on G16: Parent cover type Only for a subtype (one level below a cover type) Mandatory: No Format: Cover type code Allowed values: A code of PM-01 Product catalogue, column Cover type code
Note on H16: Risk code Product code (level 3); unique Mandatory: Yes Format: 1 to 20 capitals or digits Allowed values: Free entry, up to 20 characters Example: MTR30
Note on I16: Product name Name shown to users Mandatory: Yes Format: Up to 200 characters Allowed values: Free entry, up to 200 characters Example: Motor Fleet Plus
Note on J16: Legacy code Code of the product in QPS or EBIX, for the migration map Mandatory: No Format: Text Allowed values: Free entry Example: QPS-MFP
Note on K16: Package Y for a package product (terms change through versions) Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on L16: Market segments Segments the product is offered to (list MARKET_SEGMENT) Mandatory: No Format: Codes separated by commas; blank = all Allowed values: One or more codes of the list Market segment (Reference lists), separated by commas Example: COMBANK
Note on M16: Placement after Payment gate before placement Mandatory: Yes Format: PAID or CLIENT_CONFIRMATION Allowed values: PAID, CLIENT_CONFIRMATION (list Placement after) Example: PAID
Note on N16: TSU review When TSU reviews an account of the product Mandatory: No Format: BY_RULES, ALWAYS or NEVER Allowed values: BY_RULES, ALWAYS, NEVER (list TSU review) Example: BY_RULES
Note on O16: Default rate % Rate of a non-package product; for a package, of version 1 Mandatory: No Format: Up to four decimals Allowed values: A number from 0 to 100 Example: 1.2000
Note on P16: Default commission % Commission when no insurer rate applies Mandatory: Yes Format: Percentage Allowed values: A number from 0 to 100 Example: 15
Note on Q16: Minimum premium Minimum premium of the product Mandatory: Yes Format: Amount in PHP Allowed values: A number Example: 5000.00
Note on R16: Package TSI limit Above it the account goes to TSU Mandatory: No Format: Amount in PHP Allowed values: A number Example: 5000000.00
Note on S16: Fleet Several vehicles on one account Mandatory: No Format: Y or N Allowed values: Y or N Example: Y
Note on T16: Mortgage related Mortgage or loan related Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on U16: Direct payment allowed Premium may be paid directly to the insurer Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on V16: Multi-year / Maximum term Multi-year term and its maximum Mandatory: No Format: Y or N; 2 to 10 years Allowed values: Free entry Example: N
Note on W16: Free First Year Free First Year eligible Mandatory: No Format: Y or N Allowed values: Y or N Example: N

## UA-01 Users and roles
UA-01 Users and roles load | [10 empty] | Step 10 of 31
← Back to Start here | Step 10 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | Every BIBS user at go-live with the user data and the group profiles, in the columns of the Bulk Request template
Provided by | Business Administration, with the unit heads who name their users
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Bulk Request (SCR-UA-09): the file of this template is uploaded as a bulk batch, checked row by row and approved by an approver like single requests; users are out of the data migration scope (DMQ30)
Source | The users of the legacy systems and the unit rosters; the HR list of employees for the full names and e-mails
Depends on | UA-06 Lists of values → |  | UA-02 Role-to-permission matrix →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Conditional: ENROL | No | No | No | No | No | Conditional: ENROL | No | Yes
Format | ENROL, MODIFY, DEACTIVATE or REACTIVATE | A letter and nine digits (BDOI format a999999999) | Up to 120 characters | Company e-mail address | Windows log-on name; unique | Branch code | Code of the list Business unit group (CI-06) | Code of the list User level (CI-06) | Profile codes of CI-02 separated by ';' | yyyy-MM-dd; blank = on approval | Up to 1,000 characters
Allowed values | ENROL, MODIFY, DEACTIVATE, REACTIVATE (list Bulk request action) | Free entry, up to 10 characters | Free entry, up to 120 characters | Free entry | Free entry | Free entry | Codes of UA-06 Lists of values, column Code (one or more) | Codes of UA-06 Lists of values, column Code (one or more) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Free entry | Free entry, up to 1000 characters
What to enter | ENROL for the go-live load | The BIBS user ID; unique | Name shown on screens and reports | Receives the access-changed notices and the reset links | Used for the BDO directory sign-in when it is enabled | Home branch of the user | Business unit group | User level | The group profiles of the user | Date the change applies | Justification of the line
Row | Action * | User ID * | Full Name | E-mail | Windows ID | Home Branch Code | Business Unit | User Level | Group Profiles | Effective Date | Remarks *
Example – overwrite or delete | ENROL | a013000201 | Andrea Mercado | andrea.mercado@brokerverse-seed.ph | AMERCADO | HO |  |  | MKT_AO |  | Joined Marketing
Note on B16: Action ENROL for the go-live load Mandatory: Yes Format: ENROL, MODIFY, DEACTIVATE or REACTIVATE Allowed values: ENROL, MODIFY, DEACTIVATE, REACTIVATE (list Bulk request action) Example: ENROL
Note on C16: User ID The BIBS user ID; unique Mandatory: Yes Format: A letter and nine digits (BDOI format a999999999) Allowed values: Free entry, up to 10 characters Example: a013000201
Note on D16: Full Name Name shown on screens and reports Mandatory: Conditional: ENROL Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Andrea Mercado
Note on E16: E-mail Receives the access-changed notices and the reset links Mandatory: No Format: Company e-mail address Allowed values: Free entry Example: andrea.mercado@brokerverse-seed.ph
Note on F16: Windows ID Used for the BDO directory sign-in when it is enabled Mandatory: No Format: Windows log-on name; unique Allowed values: Free entry Example: AMERCADO
Note on G16: Home Branch Code Home branch of the user Mandatory: No Format: Branch code Allowed values: Free entry Example: HO
Note on H16: Business Unit Business unit group Mandatory: No Format: Code of the list Business unit group (CI-06) Allowed values: Codes of UA-06 Lists of values, column Code (one or more)
Note on I16: User Level User level Mandatory: No Format: Code of the list User level (CI-06) Allowed values: Codes of UA-06 Lists of values, column Code (one or more)
Note on J16: Group Profiles The group profiles of the user Mandatory: Conditional: ENROL Format: Profile codes of CI-02 separated by ';' Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: MKT_AO
Note on K16: Effective Date Date the change applies Mandatory: No Format: yyyy-MM-dd; blank = on approval Allowed values: Free entry
Note on L16: Remarks Justification of the line Mandatory: Yes Format: Up to 1,000 characters Allowed values: Free entry, up to 1000 characters Example: Joined Marketing

## D0-03 Holiday calendar
D0-03 Holiday calendar |  |  |  | Step 11 of 31
← Back to Start here | Step 11 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  | Ask a question →
Purpose | Public and company holidays of 2027 and 2028
Provided by | Head, Comptrollership; Human Resources
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Holiday Calendar (Setup & Administration); 2028 before the dress rehearsal, later years each December
Source | Proclamations of the national holidays; BDOI company holidays
Depends on | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | No | Yes | Yes
Format | Code of D0-02; blank = every branch | dd-MMM-yyyy | Up to 120 characters
Allowed values | A code of D0-02 Branches, column Branch code | A date, for example 15-Jan-2028 | Free entry, up to 120 characters
What to enter | Branch the holiday applies to | Date of the holiday | Name of the holiday
Row | Branch code | Date * | Description *
Example – overwrite or delete |  | 2028-01-01 | New Year's Day
Note on B16: Branch code Branch the holiday applies to Mandatory: No Format: Code of D0-02; blank = every branch Allowed values: A code of D0-02 Branches, column Branch code
Note on C16: Date Date of the holiday Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on D16: Description Name of the holiday Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: New Year's Day

## UA-04 SoD rules
UA-04 Separation-of-duties rules | [6 empty] | Step 12 of 31
← Back to Start here | Step 12 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | The rules BIBS enforces, for confirmation, and the combinations of profiles or permissions that BDOI Information Security does not allow one user to hold
Provided by | BDOI Information Security
Due | 16-Jul-2027 – Values for UAT
How it is loaded | The rules marked Enforced are fixed in BIBS; the privileged profiles are set by the privilege level of CI-02. Each combination of two profiles is entered on Separation of Duties (SCR-UA-19) by the Business Administrator and authorised by Information Security; BIBS then refuses every request and bulk line that breaks it. A combination of permissions is reviewed with the reports
Source | BDOI information security policy; the separation-of-duties rules of FRS chapter 13
Depends on | UA-02 Role-to-permission matrix →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: combination rule | Conditional: combination rule | Yes | Conditional: Detect by review
Format | SOD-nn | Text | Enforced, To confirm, New | Profile or permission of CI-02 | Profile or permission of CI-02 | Prevent (a rule of Separation of Duties, for two profiles), Detect by review, Second approval | Monthly, Quarterly
Allowed values | Free entry | Free entry | Enforced, To confirm, New (list Separation-of-duties rule status) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Prevent, Detect by review, Second approval (list Separation-of-duties control) | Monthly, Quarterly (list Review frequency)
What to enter | Identifier of the rule | The rule | Enforced = a fixed rule of BIBS | First profile or permission of a combination | Profile or permission that may not be held with A | How the rule is controlled | How often the reports are reviewed
Row | Rule ID * | Rule * | Status * | Profile or permission A | Profile or permission B | Control * | Review frequency
Example – overwrite or delete | SOD-01 | The requester never decides his own request | Enforced | User Access Requestor | User Access Approver | Prevent | Quarterly
Note on B16: Rule ID Identifier of the rule Mandatory: Yes Format: SOD-nn Allowed values: Free entry Example: SOD-01
Note on C16: Rule The rule Mandatory: Yes Format: Text Allowed values: Free entry Example: The requester never decides his own request
Note on D16: Status Enforced = a fixed rule of BIBS Mandatory: Yes Format: Enforced, To confirm, New Allowed values: Enforced, To confirm, New (list Separation-of-duties rule status) Example: Enforced
Note on E16: Profile or permission A First profile or permission of a combination Mandatory: Conditional: combination rule Format: Profile or permission of CI-02 Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: User Access Requestor
Note on F16: Profile or permission B Profile or permission that may not be held with A Mandatory: Conditional: combination rule Format: Profile or permission of CI-02 Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: User Access Approver
Note on G16: Control How the rule is controlled Mandatory: Yes Format: Prevent (a rule of Separation of Duties, for two profiles), Detect by review, Second approval Allowed values: Prevent, Detect by review, Second approval (list Separation-of-duties control) Example: Prevent
Note on H16: Review frequency How often the reports are reviewed Mandatory: Conditional: Detect by review Format: Monthly, Quarterly Allowed values: Monthly, Quarterly (list Review frequency) Example: Quarterly

## D0-11 Bank accounts
D0-11 Company bank accounts | [8 empty] | Step 13 of 31
← Back to Start here | Step 13 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The bank accounts of BDOI used for collections and disbursements
Provided by | Head, Comptrollership; Treasury
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Bank Accounts and Checks (Disbursement), authorised by Comptrollership
Source | BDOI bank account list
Depends on | D0-06 Chart of accounts → |  | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes
Format | Up to 20 capitals | Text | Bank name | As printed by the bank | ISO 4217 | Account of D0-06 with a bank category | Account of D0-06 | Code of D0-02 | Format of the bank advice
Allowed values | Free entry, up to 20 characters | Free entry | Free entry | Free entry | Free entry, up to 3 characters | A code of D0-06 Chart of accounts, column Account Code | A code of D0-06 Chart of accounts, column Account Code | A code of D0-02 Branches, column Branch code | Free entry
What to enter | Code of the account in BIBS | Name shown on screens | Bank of the account | Account number | Currency of the account | Cash-in-bank account | Account of issued post-dated checks | Branch that uses the account | Format of the notification to the payee
Row | Bank account code * | Name * | Bank * | Account number * | Currency * | GL account * | PDC clearing account | Branch code | Payment notification format *
Example – overwrite or delete | BDO-CA-001 | BDO Makati current account | BDO Unibank, Inc. | 000123456789 | PHP | 1110.01 | 2241 | HO | EMAIL
Note on B16: Bank account code Code of the account in BIBS Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: BDO-CA-001
Note on C16: Name Name shown on screens Mandatory: Yes Format: Text Allowed values: Free entry Example: BDO Makati current account
Note on D16: Bank Bank of the account Mandatory: Yes Format: Bank name Allowed values: Free entry Example: BDO Unibank, Inc.
Note on E16: Account number Account number Mandatory: Yes Format: As printed by the bank Allowed values: Free entry Example: 000123456789
Note on F16: Currency Currency of the account Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on G16: GL account Cash-in-bank account Mandatory: Yes Format: Account of D0-06 with a bank category Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1110.01
Note on H16: PDC clearing account Account of issued post-dated checks Mandatory: No Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 2241
Note on I16: Branch code Branch that uses the account Mandatory: No Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on J16: Payment notification format Format of the notification to the payee Mandatory: Yes Format: Format of the bank advice Allowed values: Free entry Example: EMAIL

## PM-02 Coverages and rules
PM-02 Coverages, perils and field rules | [8 empty] | Step 14 of 31
← Back to Start here | Step 14 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The coverage and peril level of each line, and the fields and documents each product needs on an account
Provided by | MBS
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Coverages & Clauses (SCR-PM-15) and on the rule tabs of Products (SCR-PM-11, SCR-PM-12) before UAT; not migrated
Source | MBS and TSU (product matrix, PQ02)
Depends on | PM-09 Lists of values and parameters → |  | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Conditional: coverage | Conditional: list, range or format rules | Conditional: document rule | Yes
Format | COVERAGE, FIELD_RULE or DOCUMENT_RULE | Line or product the row applies to; * = every product | A-Z, 0-9 and _ (coverage); field key (rule) | Text | Coverage kind (Section, Coverage, Peril, Extension); check (Presence, List of values, Number range, Format) | Y or N | List code; minimum and maximum; pattern | List DOCUMENT_TYPE | Y or N
Allowed values | COVERAGE, FIELD_RULE, DOCUMENT_RULE (list Coverage and rule record) | Codes of PM-01 Product catalogue, column Risk code (one or more) | Free entry | Free entry | Free entry | Y or N | Free entry | List Document type: 63 values, see Reference lists | Y or N
What to enter | What the row defines | Scope of the row | Coverage code or the account field checked | Coverage name or field label | Coverage kind or rule check | A package needs at least one basic coverage | Parameters of the check | Document an account needs before submission | Required or optional
Row | Record * | Line code / Risk code * | Code or field key * | Name or label * | Kind or check * | Basic | Parameters | Document type | Mandatory *
Example – overwrite or delete | COVERAGE | MOTOR | OD_THEFT | Own damage and theft | Coverage | Y |  |  | Y
Note on B16: Record What the row defines Mandatory: Yes Format: COVERAGE, FIELD_RULE or DOCUMENT_RULE Allowed values: COVERAGE, FIELD_RULE, DOCUMENT_RULE (list Coverage and rule record) Example: COVERAGE
Note on C16: Line code / Risk code Scope of the row Mandatory: Yes Format: Line or product the row applies to; * = every product Allowed values: Codes of PM-01 Product catalogue, column Risk code (one or more) Example: MOTOR
Note on D16: Code or field key Coverage code or the account field checked Mandatory: Yes Format: A-Z, 0-9 and _ (coverage); field key (rule) Allowed values: Free entry Example: OD_THEFT
Note on E16: Name or label Coverage name or field label Mandatory: Yes Format: Text Allowed values: Free entry Example: Own damage and theft
Note on F16: Kind or check Coverage kind or rule check Mandatory: Yes Format: Coverage kind (Section, Coverage, Peril, Extension); check (Presence, List of values, Number range, Format) Allowed values: Free entry Example: Coverage
Note on G16: Basic A package needs at least one basic coverage Mandatory: Conditional: coverage Format: Y or N Allowed values: Y or N Example: Y
Note on H16: Parameters Parameters of the check Mandatory: Conditional: list, range or format rules Format: List code; minimum and maximum; pattern Allowed values: Free entry
Note on I16: Document type Document an account needs before submission Mandatory: Conditional: document rule Format: List DOCUMENT_TYPE Allowed values: List Document type: 63 values, see Reference lists
Note on J16: Mandatory Required or optional Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y

## PM-03 Clause library
PM-03 Clause library | [5 empty] | Step 15 of 31
← Back to Start here | Step 15 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | Warranties, clauses, exclusions and deductible wordings used in the insurer terms of package versions
Provided by | TSU (wordings); MBS (maintenance)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Coverages & Clauses › Clause Library (SCR-PM-15); not migrated
Source | Current package slips and insurer wordings
Depends on | PM-09 Lists of values and parameters → |  | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes | Yes (from)
Format | A-Z, 0-9 and _ | WARRANTY, CLAUSE, EXCLUSION or DEDUCTIBLE_WORDING | Line code; blank = every line | Text | Full text | dd-MMM-yyyy
Allowed values | Free entry | WARRANTY, CLAUSE, EXCLUSION, DEDUCTIBLE_WORDING (list Clause kind) | A code of PM-01 Product catalogue, column Line code | Free entry | Free entry | Free entry
What to enter | Unique code | Code of the list CLAUSE_KIND | Lines the clause is offered for | Title shown in the pickers | Wording printed on the package documents | Validity of the wording
Row | Clause code * | Kind * | Line code | Title * | Wording * | Effective from / to *
Example – overwrite or delete | FLEET_REPAIR | CLAUSE | MOTOR | Accredited repair shops for fleets | Repairs are made at the accredited shops of the insurer... | 01-Jan-2027
Note on B16: Clause code Unique code Mandatory: Yes Format: A-Z, 0-9 and _ Allowed values: Free entry Example: FLEET_REPAIR
Note on C16: Kind Code of the list CLAUSE_KIND Mandatory: Yes Format: WARRANTY, CLAUSE, EXCLUSION or DEDUCTIBLE_WORDING Allowed values: WARRANTY, CLAUSE, EXCLUSION, DEDUCTIBLE_WORDING (list Clause kind) Example: CLAUSE
Note on D16: Line code Lines the clause is offered for Mandatory: No Format: Line code; blank = every line Allowed values: A code of PM-01 Product catalogue, column Line code Example: MOTOR
Note on E16: Title Title shown in the pickers Mandatory: Yes Format: Text Allowed values: Free entry Example: Accredited repair shops for fleets
Note on F16: Wording Wording printed on the package documents Mandatory: Yes Format: Full text Allowed values: Free entry Example: Repairs are made at the accredited shops of the insurer...
Note on G16: Effective from / to Validity of the wording Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2027

## PM-05 Insurers
PM-05 Insurers, branches and commission rates | [8 empty] | Step 16 of 31
← Back to Start here | Step 16 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The insurer panel with accreditation and placement e-mails, the branches with their LGT rate, and the commission rates per product
Provided by | Head of Operations; MBS (commission per package)
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Data migration objects R04 (insurers, branches, business partners) and R07 (commission rates); after go-live on Insurers (SCR-PM-17, SCR-PM-18)
Source | Legacy QPS and EBIX insurer masters
Depends on | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes (name) | No | No | Conditional: for package insurers | No | Conditional: branch rows | Conditional: branch rows | Conditional: commission rows
Format | INS- followed by capitals | Text | 000-000-000-000; text | Text; dd-MMM-yyyy | Addresses separated by commas | 0 to 365 | Text | 0 to 100 | Risk code or blank for all; percentage; dd-MMM-yyyy
Allowed values | Free entry | Free entry | Free entry | Free entry | Free entry | A whole number from 0 to 365 | Free entry | A number from 0 to 100 | Codes of PM-01 Product catalogue, column Risk code (one or more)
What to enter | Insurer code; unique | Registered and short name | Business partner details | Insurance Commission accreditation | Where quotation and placement slips are sent | Default credit days | Branch of the insurer | Local government tax on premium | Commission rate of the insurer
Row | Partner code * | Name / Short name * | TIN / Address | IC accreditation no. / Accredited until | Placement e-mails | Credit days | Branch code / Branch name / City | LGT % | Commission product / Commission % / From / To
Example – overwrite or delete | INS-MGIC | Mabuhay General Insurance Corp. | 123-456-789-000 | IC-2026-001; 31-Dec-2027 | placement@insurer.example | 30 | MKT; Makati; Makati City | 0.5 | MTR30; 15; 01-Jan-2028; -
Note on B16: Partner code Insurer code; unique Mandatory: Yes Format: INS- followed by capitals Allowed values: Free entry Example: INS-MGIC
Note on C16: Name / Short name Registered and short name Mandatory: Yes (name) Format: Text Allowed values: Free entry Example: Mabuhay General Insurance Corp.
Note on D16: TIN / Address Business partner details Mandatory: No Format: 000-000-000-000; text Allowed values: Free entry Example: 123-456-789-000
Note on E16: IC accreditation no. / Accredited until Insurance Commission accreditation Mandatory: No Format: Text; dd-MMM-yyyy Allowed values: Free entry Example: IC-2026-001; 31-Dec-2027
Note on F16: Placement e-mails Where quotation and placement slips are sent Mandatory: Conditional: for package insurers Format: Addresses separated by commas Allowed values: Free entry Example: placement@insurer.example
Note on G16: Credit days Default credit days Mandatory: No Format: 0 to 365 Allowed values: A whole number from 0 to 365 Example: 30
Note on H16: Branch code / Branch name / City Branch of the insurer Mandatory: Conditional: branch rows Format: Text Allowed values: Free entry Example: MKT; Makati; Makati City
Note on I16: LGT % Local government tax on premium Mandatory: Conditional: branch rows Format: 0 to 100 Allowed values: A number from 0 to 100 Example: 0.5000
Note on J16: Commission product / Commission % / From / To Commission rate of the insurer Mandatory: Conditional: commission rows Format: Risk code or blank for all; percentage; dd-MMM-yyyy Allowed values: Codes of PM-01 Product catalogue, column Risk code (one or more) Example: MTR30; 15; 01-Jan-2028; -

## D0-01 Company
D0-01 Company | [8 empty] | Step 17 of 31
← Back to Start here | Step 17 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The company record of BDOI
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Companies (Setup & Administration), entered by the System Administrator and authorised by Comptrollership
Source | BDOI registration documents and the current chart of accounts
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Up to 10 capitals | Up to 200 characters | 000-000-000-00000 | Text | ISO 4217 | 1 to 12 | Whole number | Whole number | Account code of D0-06
Allowed values | Free entry, up to 10 characters | Free entry, up to 200 characters | Free entry | Free entry | Free entry, up to 3 characters | A whole number from 1 to 12 | A whole number from 0 to 365 | A whole number from 0 to 365 | A code of D0-06 Chart of accounts, column Account Code
What to enter | Code of the company on every record | Name as registered with the SEC | Tax identification number with branch code | Address printed on receipts and BIR forms | Currency of the books | First month of the financial year | How many days before today a posting may be dated | How many days after today a posting may be dated | Account that receives the year-end result
Row | Company code * | Registered name * | TIN * | Registered address * | Base currency * | Fiscal year start month * | Back-value days * | Forward-value days * | Retained earnings account *
Example – overwrite or delete | BDOI | BDO Insurance and Reinsurance Brokers, Inc. | 000-000-000-00000 | 7899 Makati Avenue, Makati City | PHP | 1 | 5 | 0 | 3200
Note on B16: Company code Code of the company on every record Mandatory: Yes Format: Up to 10 capitals Allowed values: Free entry, up to 10 characters Example: BDOI
Note on C16: Registered name Name as registered with the SEC Mandatory: Yes Format: Up to 200 characters Allowed values: Free entry, up to 200 characters Example: BDO Insurance and Reinsurance Brokers, Inc.
Note on D16: TIN Tax identification number with branch code Mandatory: Yes Format: 000-000-000-00000 Allowed values: Free entry Example: 000-000-000-00000
Note on E16: Registered address Address printed on receipts and BIR forms Mandatory: Yes Format: Text Allowed values: Free entry Example: 7899 Makati Avenue, Makati City
Note on F16: Base currency Currency of the books Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on G16: Fiscal year start month First month of the financial year Mandatory: Yes Format: 1 to 12 Allowed values: A whole number from 1 to 12 Example: 1
Note on H16: Back-value days How many days before today a posting may be dated Mandatory: Yes Format: Whole number Allowed values: A whole number from 0 to 365 Example: 5
Note on I16: Forward-value days How many days after today a posting may be dated Mandatory: Yes Format: Whole number Allowed values: A whole number from 0 to 365 Example: 0
Note on J16: Retained earnings account Account that receives the year-end result Mandatory: Yes Format: Account code of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 3200

## D0-08 Accounting rules
D0-08 Accounting rules | [9 empty] | Step 18 of 31
← Back to Start here | Step 18 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The debit and credit accounts of each accounting event of the platform
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Accounting Rules (Accounting Engine), checked with the Rule Simulator and authorised by Comptrollership
Source | The posting rules of EBIX and ISYS; the accounting events listed on the sheet Ref Accounting events
Depends on | D0-04 Cost centres and business lines → |  | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No
Format | Code of the sheet Ref Accounting events | Text | Code of D0-04; blank = every line | ISO 4217; blank = every currency | dd-MMM-yyyy | 1, 2, 3 | DEBIT or CREDIT | Account of D0-06 | Component of the event | Text
Allowed values | List Accounting event: 90 values, see Reference lists | Free entry | A code of D0-04 Cost centres and business lines, column Code | Free entry | A date, for example 15-Jan-2028 | A whole number from 1 to 99 | DEBIT, CREDIT (list Debit or credit) | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry
What to enter | Event that the rule posts | Name of the rule | Line the rule applies to | Currency the rule applies to | First posting date of the rule | Order of the line in the entry | Side of the line | Account posted | Amount the line posts | Text of the journal line
Row | Event type * | Rule name * | Business line | Currency | Effective from * | Line * | Debit or credit * | Account code * | Amount component * | Narration
Example – overwrite or delete | PREMIUM_BOOKED | Premium booked - non-life |  |  | 2028-01-01 | 1 | DEBIT | 1210.07 | GROSS_PREMIUM | Premium receivable
Note on B16: Event type Event that the rule posts Mandatory: Yes Format: Code of the sheet Ref Accounting events Allowed values: List Accounting event: 90 values, see Reference lists Example: PREMIUM_BOOKED
Note on C16: Rule name Name of the rule Mandatory: Yes Format: Text Allowed values: Free entry Example: Premium booked - non-life
Note on D16: Business line Line the rule applies to Mandatory: No Format: Code of D0-04; blank = every line Allowed values: A code of D0-04 Cost centres and business lines, column Code
Note on E16: Currency Currency the rule applies to Mandatory: No Format: ISO 4217; blank = every currency Allowed values: Free entry
Note on F16: Effective from First posting date of the rule Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on G16: Line Order of the line in the entry Mandatory: Yes Format: 1, 2, 3 Allowed values: A whole number from 1 to 99 Example: 1
Note on H16: Debit or credit Side of the line Mandatory: Yes Format: DEBIT or CREDIT Allowed values: DEBIT, CREDIT (list Debit or credit) Example: DEBIT
Note on I16: Account code Account posted Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1210.07
Note on J16: Amount component Amount the line posts Mandatory: Yes Format: Component of the event Allowed values: Free entry Example: GROSS_PREMIUM
Note on K16: Narration Text of the journal line Mandatory: No Format: Text Allowed values: Free entry Example: Premium receivable

## D0-09 Legacy accounts
D0-09 Legacy control accounts | [5 empty] | Step 19 of 31
← Back to Start here | Step 19 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The accounts that carry the migrated invoices and unapplied payments until they run off, and Migration Clearing
Provided by | Head, Comptrollership
Due | 1-Dec-2026 – Drafts with the Drop 0 sign-off
How it is loaded | Created with the chart of accounts (D0-06); named in the accounting rules of the legacy items
Source | Proposed rule PR-DM-02 of the Data Migration set
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: Premium Receivable - Legacy | Yes | No | No
Format | Premium Receivable - Legacy (per component), PR 2307 - Legacy, Due to Insurers - Legacy, Commission Receivable - Legacy, Unrealised Commission - Legacy, Deferred Output VAT - Legacy, Unapplied Collections - Legacy, Migration Clearing | Basic premium, DST, premium tax or VAT, LGT, FST, other charges | Account of D0-06 | EBIX and ISYS account codes separated by commas | Text
Allowed values | List Legacy control account: 8 values, see Reference lists | Free entry | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry
What to enter | One row per account | Component the account holds | Account in the production chart | The legacy accounts it replaces (for the code map GL_ACCOUNT, R08) | End state after the run-off
Row | Legacy account * | Component | BIBS account code * | Legacy GL accounts | Remarks
Example – overwrite or delete | Migration Clearing |  | 1990.01 | 1210-01 | Nets to 0.00 after the opening
Note on B16: Legacy account One row per account Mandatory: Yes Format: Premium Receivable - Legacy (per component), PR 2307 - Legacy, Due to Insurers - Legacy, Commission Receivable - Legacy, Unrealised Commission - Legacy, Deferred Output VAT - Legacy, Unapplied Collections - Legacy, Migration Clearing Allowed values: List Legacy control account: 8 values, see Reference lists Example: Migration Clearing
Note on C16: Component Component the account holds Mandatory: Conditional: Premium Receivable - Legacy Format: Basic premium, DST, premium tax or VAT, LGT, FST, other charges Allowed values: Free entry
Note on D16: BIBS account code Account in the production chart Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1990.01
Note on E16: Legacy GL accounts The legacy accounts it replaces (for the code map GL_ACCOUNT, R08) Mandatory: No Format: EBIX and ISYS account codes separated by commas Allowed values: Free entry Example: 1210-01
Note on F16: Remarks End state after the run-off Mandatory: No Format: Text Allowed values: Free entry Example: Nets to 0.00 after the opening

## D0-10 Tax codes
D0-10 Tax codes | [9 empty] | Step 20 of 31
← Back to Start here | Step 20 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The tax codes with their ATC, rate and GL account
Provided by | Head, Comptrollership (Tax)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Tax Codes & Forms (Tax & Statutory), authorised by Comptrollership
Source | BIR ATC list; current tax set-up
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: withholding | No | Yes | Yes | No | Yes | No
Format | Up to 20 capitals | Text | EWT, FWT, VAT, PT | BIR ATC | List PAYEE_CLASS | 0 to 100 | Account of D0-06 | Text | dd-MMM-yyyy | dd-MMM-yyyy
Allowed values | Free entry, up to 20 characters | Free entry | EWT, FWT, VAT, PT (list Tax type) | Free entry | SUPPLIER, INSURER, EMPLOYEE, CLIENT, GOVERNMENT, OTHER (list Payee class) | A number from 0 to 100 | A code of D0-06 Chart of accounts, column Account Code | Free entry | A date, for example 15-Jan-2028 | A date, for example 15-Jan-2028
What to enter | Code of the tax | Name shown on screens | Kind of tax | Alphanumeric tax code | Payees it applies to | Rate of the tax | Account of the tax | Nature of the income payment | First date of the rate | Last date of the rate
Row | Tax code * | Name * | Tax type * | ATC | Payee class | Rate % * | GL account * | Income nature | Effective from * | Effective to
Example – overwrite or delete | EWT_WC158 | EWT 1% - goods | EWT | WC158 | CORPORATE | 1 | 2150.02 | Purchase of goods | 2028-01-01
Note on B16: Tax code Code of the tax Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: EWT_WC158
Note on C16: Name Name shown on screens Mandatory: Yes Format: Text Allowed values: Free entry Example: EWT 1% - goods
Note on D16: Tax type Kind of tax Mandatory: Yes Format: EWT, FWT, VAT, PT Allowed values: EWT, FWT, VAT, PT (list Tax type) Example: EWT
Note on E16: ATC Alphanumeric tax code Mandatory: Conditional: withholding Format: BIR ATC Allowed values: Free entry Example: WC158
Note on F16: Payee class Payees it applies to Mandatory: No Format: List PAYEE_CLASS Allowed values: SUPPLIER, INSURER, EMPLOYEE, CLIENT, GOVERNMENT, OTHER (list Payee class) Example: CORPORATE
Note on G16: Rate % Rate of the tax Mandatory: Yes Format: 0 to 100 Allowed values: A number from 0 to 100 Example: 1
Note on H16: GL account Account of the tax Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 2150.02
Note on I16: Income nature Nature of the income payment Mandatory: No Format: Text Allowed values: Free entry Example: Purchase of goods
Note on J16: Effective from First date of the rate Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on K16: Effective to Last date of the rate Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028

## D0-15 Approval limits
D0-15 Approval limits and matrices | [8 empty] | Step 21 of 31
← Back to Start here | Step 21 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The approval levels by amount, sum insured or segment of the modules that approve by level
Provided by | Owners of the modules; Head, Comptrollership for the amounts
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Submitted Policies Setup, EB Setup, Compliance Setup (Configuration Versions) and Disbursement approver routing; the authorisation limit of a user is in UA-03
Source | BDOI approval matrix and signing authorities
Depends on | UA-02 Role-to-permission matrix → | UA-01 Users and roles load →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | No | Yes | Yes | No | No
Format | Submitted Policies, Employee Benefits, Sanction Screening, Disbursement | Text | Segment, benefit line or case type | PHP | PHP; blank = no limit | 1, 2, 3 | Group profile of UA-02 | User ID of UA-01 | Text
Allowed values | Submitted Policies, Employee Benefits, Sanction Screening, Disbursement (list Module of an approval matrix) | Free entry | Free entry | A number | A number | A whole number from 1 to 9 | A code of UA-02 Role-to-permission matrix, column Group profile code | A code of UA-01 Users and roles load, column User ID | Free entry
What to enter | Module of the approval | What is approved | Scope of the row | Lower bound (sum insured, premium or amount) | Upper bound | Order of the approval | Profile that approves | Only when one person approves | Title printed on the document
Row | Module * | Document or transaction * | Segment or case type | From amount | To amount | Approval level * | Approver role * | Named approver | Signatory title
Example – overwrite or delete | Submitted Policies | Terms of reference | CBG | 0 | 10000000 | 1 | SBM_APPROVER |  | Unit Head, Combank
Note on B16: Module Module of the approval Mandatory: Yes Format: Submitted Policies, Employee Benefits, Sanction Screening, Disbursement Allowed values: Submitted Policies, Employee Benefits, Sanction Screening, Disbursement (list Module of an approval matrix) Example: Submitted Policies
Note on C16: Document or transaction What is approved Mandatory: Yes Format: Text Allowed values: Free entry Example: Terms of reference
Note on D16: Segment or case type Scope of the row Mandatory: No Format: Segment, benefit line or case type Allowed values: Free entry Example: CBG
Note on E16: From amount Lower bound (sum insured, premium or amount) Mandatory: No Format: PHP Allowed values: A number Example: 0.00
Note on F16: To amount Upper bound Mandatory: No Format: PHP; blank = no limit Allowed values: A number Example: 10000000.00
Note on G16: Approval level Order of the approval Mandatory: Yes Format: 1, 2, 3 Allowed values: A whole number from 1 to 9 Example: 1
Note on H16: Approver role Profile that approves Mandatory: Yes Format: Group profile of UA-02 Allowed values: A code of UA-02 Role-to-permission matrix, column Group profile code Example: SBM_APPROVER
Note on I16: Named approver Only when one person approves Mandatory: No Format: User ID of UA-01 Allowed values: A code of UA-01 Users and roles load, column User ID
Note on J16: Signatory title Title printed on the document Mandatory: No Format: Text Allowed values: Free entry Example: Unit Head, Combank

## PM-04 Rate tables
PM-04 Rate tables | [6 empty] | Step 22 of 31
← Back to Start here | Step 22 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | Statutory charges and rating factors, the short-period table and the motor BI / PD limit premiums
Provided by | Product Owner, MBS; Comptrollership (taxes)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Rates & Taxes (SCR-PM-19), pending authorisation; not migrated (effective-dated from go-live)
Source | BIR and LGU rates; current rating tables
Depends on | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: TAX | No | Conditional: TAX, SHORT_PERIOD | Conditional: SHORT_PERIOD | Conditional: MOTOR_LIMIT | Yes (from)
Format | TAX, SHORT_PERIOD or MOTOR_LIMIT | DST, premium tax, VAT, fire service tax, motor factors | Line; blank = every line | Up to four decimals, 0 to 100 | 1 to 12 | BI or PD; amounts in PHP | dd-MMM-yyyy
Allowed values | TAX, SHORT_PERIOD, MOTOR_LIMIT (list Rate table) | Free entry | A code of PM-01 Product catalogue, column Line code | A number from 0 to 100 | A whole number from 1 to 12 | Free entry | Free entry
What to enter | Table of the row | Charge or factor | Line the rate applies to | Rate, or % of the annual premium | Months covered, up to | Limit and its premium | Validity of the row
Row | Table * | Rate | Line code | Rate % | Months covered | Coverage / Limit / Premium | Effective from / to *
Example – overwrite or delete | TAX | DST |  | 12.5 | 6 | BI; 100000.00; 350.00 | 01-Jan-2028
Note on B16: Table Table of the row Mandatory: Yes Format: TAX, SHORT_PERIOD or MOTOR_LIMIT Allowed values: TAX, SHORT_PERIOD, MOTOR_LIMIT (list Rate table) Example: TAX
Note on C16: Rate Charge or factor Mandatory: Conditional: TAX Format: DST, premium tax, VAT, fire service tax, motor factors Allowed values: Free entry Example: DST
Note on D16: Line code Line the rate applies to Mandatory: No Format: Line; blank = every line Allowed values: A code of PM-01 Product catalogue, column Line code
Note on E16: Rate % Rate, or % of the annual premium Mandatory: Conditional: TAX, SHORT_PERIOD Format: Up to four decimals, 0 to 100 Allowed values: A number from 0 to 100 Example: 12.5000
Note on F16: Months covered Months covered, up to Mandatory: Conditional: SHORT_PERIOD Format: 1 to 12 Allowed values: A whole number from 1 to 12 Example: 6
Note on G16: Coverage / Limit / Premium Limit and its premium Mandatory: Conditional: MOTOR_LIMIT Format: BI or PD; amounts in PHP Allowed values: Free entry Example: BI; 100000.00; 350.00
Note on H16: Effective from / to Validity of the row Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028

## PM-10 Incentive criteria
PM-10 Incentive criteria | [5 empty] | Step 23 of 31
← Back to Start here | Step 23 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The incentive criteria (for example CPC2) with their value, the products matrix and the effective dates
Provided by | Incentive Maintenance user (MBS); Comptrollership (CPC2 definition, PQ04)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Incentive Criteria (SCR-PM-16), pending authorisation; the copied booking rules are reviewed there
Source | Current incentive programmes; the booking incentive rules copied into the catalogue
Depends on | PM-09 Lists of values and parameters → | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes (basis) | No | Yes (one product) | Yes (from)
Format | A-Z, 0-9, _ and -; text | List INCENTIVE_TYPE | Rate (%), Fixed amount or Rule; number | Parameter and value pairs separated by semicolons | Active risk codes; segment or blank | dd-MMM-yyyy
Allowed values | Free entry | OTHERS, MIGRATED (list Incentive type) | Free entry | Free entry | Codes of PM-01 Product catalogue, column Risk code (one or more) | Free entry
What to enter | Criterion | Type of criterion | Value of the criterion | Parameters of a rule criterion, as agreed with Comptrollership | Products and segments the criterion applies to | Validity; no overlap with another row of the code
Row | Code / Name * | Incentive type * | Value basis / Value * | Rule parameters | Products matrix: risk code / segment * | Effective from / to *
Example – overwrite or delete | CPC2; CPC2 campaign 2028 | CAMPAIGN | Rate (%); 1.00 | Minimum premium 5000 | MTR30; COMBANK | 01-Jan-2028
Note on B16: Code / Name Criterion Mandatory: Yes Format: A-Z, 0-9, _ and -; text Allowed values: Free entry Example: CPC2; CPC2 campaign 2028
Note on C16: Incentive type Type of criterion Mandatory: Yes Format: List INCENTIVE_TYPE Allowed values: OTHERS, MIGRATED (list Incentive type) Example: CAMPAIGN
Note on D16: Value basis / Value Value of the criterion Mandatory: Yes (basis) Format: Rate (%), Fixed amount or Rule; number Allowed values: Free entry Example: Rate (%); 1.00
Note on E16: Rule parameters Parameters of a rule criterion, as agreed with Comptrollership Mandatory: No Format: Parameter and value pairs separated by semicolons Allowed values: Free entry Example: Minimum premium 5000
Note on F16: Products matrix: risk code / segment Products and segments the criterion applies to Mandatory: Yes (one product) Format: Active risk codes; segment or blank Allowed values: Codes of PM-01 Product catalogue, column Risk code (one or more) Example: MTR30; COMBANK
Note on G16: Effective from / to Validity; no overlap with another row of the code Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028

## UA-03 Approval rules
UA-03 Approvers, approval rules and limits | [5 empty] | Step 24 of 31
← Back to Start here | Step 24 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | Who requests and who approves user access, the order of the approvers of group-profile requests, the second approvers, the implementers, and the authorisation limits of the users whose work other modules approve by amount
Provided by | Business Administration; BDOI Information Security for the second approval; Comptrollership for the authorisation limits
Due | 16-Jul-2027 – Values for UAT
How it is loaded | The users are given the Requestor, Approver, Second Approver and System Administrator profiles by requests (CI-01); the approvers are chosen on each request; UAM_ANY_APPROVER is set on System Parameters. The authorisation limit is set by an Enrol new user or Modify user request (field Authorisation Limit) decided by an approver; the bulk file has no limit column, so the limits are requested after the users are loaded
Source | BDOI's approval matrix (UQ01, UQ02)
Depends on | UA-01 Users and roles load →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: Approver | No | No
Format | Requestor, Approver, Second Approver, Group-profile requester, Implementer | User ID of CI-01 | Business unit | 1, 2, 3 | Y or N | Amount in PHP; blank = unlimited
Allowed values | Requestor, Approver, Second Approver, Group-profile requester, Implementer (list Role in user access) | A code of UA-01 Users and roles load, column User ID | Free entry | A whole number from 1 to 9 | Y or N | A number
What to enter | The user access role of the user | The user who holds the role | Unit the user requests or approves for | Usual order of the approvers of a group-profile request | Y sets UAM_ANY_APPROVER: any approver decides any request, not only the chosen one | Limit of the user's approvals by amount in the modules that use it (journals, payables)
Row | Role in user access * | User ID * | Unit * | Approver order for group profiles | Any approver may decide | Authorisation limit
Example – overwrite or delete | Approver | a013000205 | Combank Marketing | 1 | N | 500000
Note on B16: Role in user access The user access role of the user Mandatory: Yes Format: Requestor, Approver, Second Approver, Group-profile requester, Implementer Allowed values: Requestor, Approver, Second Approver, Group-profile requester, Implementer (list Role in user access) Example: Approver
Note on C16: User ID The user who holds the role Mandatory: Yes Format: User ID of CI-01 Allowed values: A code of UA-01 Users and roles load, column User ID Example: a013000205
Note on D16: Unit Unit the user requests or approves for Mandatory: Yes Format: Business unit Allowed values: Free entry Example: Combank Marketing
Note on E16: Approver order for group profiles Usual order of the approvers of a group-profile request Mandatory: Conditional: Approver Format: 1, 2, 3 Allowed values: A whole number from 1 to 9 Example: 1
Note on F16: Any approver may decide Y sets UAM_ANY_APPROVER: any approver decides any request, not only the chosen one Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on G16: Authorisation limit Limit of the user's approvals by amount in the modules that use it (journals, payables) Mandatory: No Format: Amount in PHP; blank = unlimited Allowed values: A number Example: 500000.00

## PM-06 Packages
PM-06 Packages in force at go-live | [8 empty] | Step 25 of 31
← Back to Start here | Step 25 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | For every package sold at go-live: its terms as they will be set up in BIBS through a package request (TSU) and a package version (MBS): rate scheme, dates, coverages, panel insurers and their terms
Provided by | TSU (prepares); Product Owner, MBS (approves)
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Not migrated: TSU raises a package request per package (type New package, or Update for an existing risk code) and MBS sets up and validates the version before the map freeze; the Package Request Form accepts the same fields
Source | Signed package slips and ManCom sign-offs in force
Depends on | PM-01 Product catalogue → |  | PM-02 Coverages, perils and field rules → | PM-05 Insurers, branches and commission rates → | PM-03 Clause library →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes (name, scope) | Yes (effective from, package end) | Yes (minimum, commission; rate or insurer rates) | Yes | Yes (one basic coverage) | Yes (the panel) | Yes (every insurer and included coverage) | Yes
Format | Code of CI-01 | Text; Generic or Client-specific; client code | dd-MMM-yyyy | Percentages and PHP amounts | Text | Codes of CI-02; Y or N; PHP | Codes of CI-05; Panel, Lead or Participant; shares total 100 | Codes of CI-03 separated by commas | Reference; the signed slip file
Allowed values | A code of PM-01 Product catalogue, column Risk code | Free entry | Free entry | Free entry | Free entry | Codes of PM-02 Coverages, perils and field rules, column Code or field key (one or more) | Codes of PM-05 Insurers, branches and commission rates, column Partner code (one or more) | Codes of PM-03 Clause library, column Clause code (one or more) | Free entry
What to enter | Package product | As on the Package Request Form | Dates of the version | Rate scheme of the version | How the premium is computed | Coverages of the version | Panel insurers | Terms per insurer and coverage | Evidence kept on the request
Row | Risk code * | Package name / Scope / Client code * | Effective from / Package start / Package end / Anniversary * | Package rate % / Minimum premium / Commission % / Package TSI limit * | Computation basis * | Coverage code / Included / Optional / Limit / Deductible * | Insurer code / Role / Share % / Rate % / Minimum premium * | Insurer terms: insurer / coverage / limit / deductible / clauses * | ManCom sign-off reference / Signed package slip *
Example – overwrite or delete | MTR30 | Motor Fleet Plus; Generic | 01-Jan-2028; 01-Jan-2028; 31-Dec-2028; - | 1.2000; 5000.00; 15; 5000000.00 | Comprehensive rate on the vehicle value | OD_THEFT; Y; N; -; 2000.00 | INS-MGIC; Panel; -; 1.2000; - | INS-MGIC; OD_THEFT; -; 2000.00; FLEET_REPAIR | MC-2026-017
Note on B16: Risk code Package product Mandatory: Yes Format: Code of CI-01 Allowed values: A code of PM-01 Product catalogue, column Risk code Example: MTR30
Note on C16: Package name / Scope / Client code As on the Package Request Form Mandatory: Yes (name, scope) Format: Text; Generic or Client-specific; client code Allowed values: Free entry Example: Motor Fleet Plus; Generic
Note on D16: Effective from / Package start / Package end / Anniversary Dates of the version Mandatory: Yes (effective from, package end) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028; 01-Jan-2028; 31-Dec-2028; -
Note on E16: Package rate % / Minimum premium / Commission % / Package TSI limit Rate scheme of the version Mandatory: Yes (minimum, commission; rate or insurer rates) Format: Percentages and PHP amounts Allowed values: Free entry Example: 1.2000; 5000.00; 15; 5000000.00
Note on F16: Computation basis How the premium is computed Mandatory: Yes Format: Text Allowed values: Free entry Example: Comprehensive rate on the vehicle value
Note on G16: Coverage code / Included / Optional / Limit / Deductible Coverages of the version Mandatory: Yes (one basic coverage) Format: Codes of CI-02; Y or N; PHP Allowed values: Codes of PM-02 Coverages, perils and field rules, column Code or field key (one or more) Example: OD_THEFT; Y; N; -; 2000.00
Note on H16: Insurer code / Role / Share % / Rate % / Minimum premium Panel insurers Mandatory: Yes (the panel) Format: Codes of CI-05; Panel, Lead or Participant; shares total 100 Allowed values: Codes of PM-05 Insurers, branches and commission rates, column Partner code (one or more) Example: INS-MGIC; Panel; -; 1.2000; -
Note on I16: Insurer terms: insurer / coverage / limit / deductible / clauses Terms per insurer and coverage Mandatory: Yes (every insurer and included coverage) Format: Codes of CI-03 separated by commas Allowed values: Codes of PM-03 Clause library, column Clause code (one or more) Example: INS-MGIC; OD_THEFT; -; 2000.00; FLEET_REPAIR
Note on J16: ManCom sign-off reference / Signed package slip Evidence kept on the request Mandatory: Yes Format: Reference; the signed slip file Allowed values: Free entry Example: MC-2026-017

## D0-12 Check books
D0-12 Check books | [5 empty] | Step 26 of 31
← Back to Start here | Step 26 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The check books in stock per bank account at go-live
Provided by | Treasury; Product Owner, Comptrollership - Disbursement
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Bank Accounts and Checks (Disbursement)
Source | Check book register of Treasury
Depends on | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes
Format | Code of D0-11 | Digits | Digits | Digits | dd-MMM-yyyy
Allowed values | A code of D0-11 Company bank accounts, column Bank account code | Free entry | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Account of the check book | First number of the book | Last number of the book | Next number to issue at go-live | Date the book was received
Row | Bank account code * | First check number * | Last check number * | Next check number * | Received on *
Example – overwrite or delete | BDO-CA-001 | 0001001 | 0001100 | 0001001 | 2027-12-01
Note on B16: Bank account code Account of the check book Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on C16: First check number First number of the book Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001001
Note on D16: Last check number Last number of the book Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001100
Note on E16: Next check number Next number to issue at go-live Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001001
Note on F16: Received on Date the book was received Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Dec-2027

## D0-13 Petty cash funds
D0-13 Petty cash funds | [7 empty] | Step 27 of 31
← Back to Start here | Step 27 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The petty cash funds of the branches
Provided by | Head, Comptrollership
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Petty Cash (Payables & Cash)
Source | Petty cash register
Depends on | D0-02 Branches → |  | D0-05 Employees → | D0-06 Chart of accounts → |  | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Code of D0-02 | Up to 20 capitals | Text | Employee of D0-05 | Account of D0-06 | Code of D0-11 | ISO 4217 | Amount
Allowed values | A code of D0-02 Branches, column Branch code | Free entry, up to 20 characters | Free entry | A code of D0-05 Employees, column Employee number | A code of D0-06 Chart of accounts, column Account Code | A code of D0-11 Company bank accounts, column Bank account code | Free entry, up to 3 characters | A number
What to enter | Branch of the fund | Code of the fund | Name of the fund | Custodian of the fund | Petty cash account | Account that replenishes the fund | Currency of the fund | Amount of the fund
Row | Branch code * | Fund code * | Name * | Custodian * | GL account * | Replenishment bank account * | Currency * | Imprest amount *
Example – overwrite or delete | HO | PCF-HO | Head Office petty cash | 1203344 | 1101.01 | BDO-CA-001 | PHP | 20000
Note on B16: Branch code Branch of the fund Mandatory: Yes Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on C16: Fund code Code of the fund Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: PCF-HO
Note on D16: Name Name of the fund Mandatory: Yes Format: Text Allowed values: Free entry Example: Head Office petty cash
Note on E16: Custodian Custodian of the fund Mandatory: Yes Format: Employee of D0-05 Allowed values: A code of D0-05 Employees, column Employee number Example: 1203344
Note on F16: GL account Petty cash account Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1101.01
Note on G16: Replenishment bank account Account that replenishes the fund Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on H16: Currency Currency of the fund Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on I16: Imprest amount Amount of the fund Mandatory: Yes Format: Amount Allowed values: A number Example: 20000.00

## D0-14 Statement layouts
D0-14 Bank statement layouts | [9 empty] | Step 28 of 31
← Back to Start here | Step 28 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The columns of the statement file of each bank account
Provided by | Head, Comptrollership; Treasury
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Bank Statement Layouts (Setup & Administration)
Source | Statement files of the banks
Depends on | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | No | Conditional: separate columns | Conditional: separate columns | Conditional: one signed column | No | Yes
Format | Code of D0-11 | Text | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | For example dd/MM/yyyy
Allowed values | A code of D0-11 Company bank accounts, column Bank account code | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry
What to enter | Account of the statement | Name of the layout | Column of the transaction date | Column of the description | Column of the reference | Column of the debits | Column of the credits | Column of a signed amount | Column of the running balance | Format of the dates in the file
Row | Bank account code * | Layout name * | Date column * | Description column * | Reference column | Debit column | Credit column | Amount column | Balance column | Date format *
Example – overwrite or delete | BDO-CA-001 | BDO CSV statement | Posting Date | Description | Reference No. | Debit | Credit |  | Balance | MM/dd/yyyy
Note on B16: Bank account code Account of the statement Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on C16: Layout name Name of the layout Mandatory: Yes Format: Text Allowed values: Free entry Example: BDO CSV statement
Note on D16: Date column Column of the transaction date Mandatory: Yes Format: Column header or number Allowed values: Free entry Example: Posting Date
Note on E16: Description column Column of the description Mandatory: Yes Format: Column header or number Allowed values: Free entry Example: Description
Note on F16: Reference column Column of the reference Mandatory: No Format: Column header or number Allowed values: Free entry Example: Reference No.
Note on G16: Debit column Column of the debits Mandatory: Conditional: separate columns Format: Column header or number Allowed values: Free entry Example: Debit
Note on H16: Credit column Column of the credits Mandatory: Conditional: separate columns Format: Column header or number Allowed values: Free entry Example: Credit
Note on I16: Amount column Column of a signed amount Mandatory: Conditional: one signed column Format: Column header or number Allowed values: Free entry
Note on J16: Balance column Column of the running balance Mandatory: No Format: Column header or number Allowed values: Free entry Example: Balance
Note on K16: Date format Format of the dates in the file Mandatory: Yes Format: For example dd/MM/yyyy Allowed values: Free entry Example: MM/dd/yyyy

## PM-07 Package map
PM-07 Package map (legacy package to BIBS package version) | [7 empty] | Step 29 of 31
← Back to Start here | Step 29 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | Entries from each legacy package and version to the BIBS package version that renews it, with qualifiers where one legacy package splits; read at Renewal sanitation (check PACKAGE_REMAP)
Provided by | TSU (prepares); Product Owner, MBS (approves each map version)
Due | 18-Jun-2027 – Code maps approved (M5)
How it is loaded | Data migration object R06 (loaded as reference data and handed to the Renewal package map); new map versions until the map freeze (T-7), then maintained in Renewal
Source | QPS package list of the in-force policies expiring from go-live
Depends on | PM-01 Product catalogue → | PM-05 Insurers, branches and commission rates → | PM-06 Packages in force at go-live →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | No | No | No | No | Conditional: action MAP | Yes | No
Format | As stored in QPS | Text | Risk code of CI-01 | Partner code of CI-05 | PHP amounts | A package version active in Product Maintenance | MAP or REJECT | Text
Allowed values | Free entry | Free entry | A code of PM-01 Product catalogue, column Risk code | A code of PM-05 Insurers, branches and commission rates, column Partner code | Free entry | Codes of PM-06 Packages in force at go-live, column Risk code (one or more) | MAP, REJECT (list Package map action) | Free entry
What to enter | Package of the legacy policy headers | For reading only | When one legacy package maps to several BIBS packages by product | When the split is by insurer | When the split is by sum-insured band | Target of the entry | REJECT sends the candidate to the Renewal Exception bucket | Reason of a REJECT or a split
Row | Legacy package code / Legacy version * | Legacy package name | Qualifier: risk code | Qualifier: insurer | Qualifier: sum insured from / to | BIBS risk code / BIBS version | Action * | Remarks
Example – overwrite or delete | PKG-MOTOR-FLEET; 3 | Motor fleet package 2025 | MTR30 |  |  | MTR30; 1 | MAP
Note on B16: Legacy package code / Legacy version Package of the legacy policy headers Mandatory: Yes Format: As stored in QPS Allowed values: Free entry Example: PKG-MOTOR-FLEET; 3
Note on C16: Legacy package name For reading only Mandatory: No Format: Text Allowed values: Free entry Example: Motor fleet package 2025
Note on D16: Qualifier: risk code When one legacy package maps to several BIBS packages by product Mandatory: No Format: Risk code of CI-01 Allowed values: A code of PM-01 Product catalogue, column Risk code Example: MTR30
Note on E16: Qualifier: insurer When the split is by insurer Mandatory: No Format: Partner code of CI-05 Allowed values: A code of PM-05 Insurers, branches and commission rates, column Partner code
Note on F16: Qualifier: sum insured from / to When the split is by sum-insured band Mandatory: No Format: PHP amounts Allowed values: Free entry
Note on G16: BIBS risk code / BIBS version Target of the entry Mandatory: Conditional: action MAP Format: A package version active in Product Maintenance Allowed values: Codes of PM-06 Packages in force at go-live, column Risk code (one or more) Example: MTR30; 1
Note on H16: Action REJECT sends the candidate to the Renewal Exception bucket Mandatory: Yes Format: MAP or REJECT Allowed values: MAP, REJECT (list Package map action) Example: MAP
Note on I16: Remarks Reason of a REJECT or a split Mandatory: No Format: Text Allowed values: Free entry

## PM-08 Document templates
PM-08 Document templates | [5 empty] | Step 30 of 31
← Back to Start here | Step 30 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The texts of the package documents: Package Request Form, quotation slip, comparative table, package slip, package advisory and package renewal advisory, with the merge fields each may use
Provided by | TSU and MBS (texts); Business Administrator (maintenance)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Document Templates (New Business set, SCR-NB-44) as a new template version effective from a date; not migrated
Source | BDOI layouts of the current documents (Q03)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | Yes
Format | PKG_REQUEST_FORM, PKG_QUOTATION_SLIP, PKG_COMPARATIVE, PKG_SLIP, PKG_ADVISORY, PKG_RENEWAL_ADVISORY | Text | Text with merge fields in double braces | PKG_REQUEST_FORM: reference, requestType, title; PKG_QUOTATION_SLIP: reference, roundNo, replyBy; PKG_COMPARATIVE: reference, roundNo, variant; PKG_SLIP: reference, title; advisories: productCode, productName, versionNo, effectiveFrom, reference | dd-MMM-yyyy
Allowed values | List Package document template: 6 values, see Reference lists | Free entry | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Template code | Title of the template version | Opening text of the document | Fields filled in by BIBS | Date from which the version is used
Row | Template * | Title * | Text * | Merge fields used | Effective from *
Example – overwrite or delete | PKG_ADVISORY | Package advisory | This is to advise that the package {{productCode}} - {{productName}} ... | productCode, productName, versionNo, effectiveFrom, reference | 2026-11-01
Note on B16: Template Template code Mandatory: Yes Format: PKG_REQUEST_FORM, PKG_QUOTATION_SLIP, PKG_COMPARATIVE, PKG_SLIP, PKG_ADVISORY, PKG_RENEWAL_ADVISORY Allowed values: List Package document template: 6 values, see Reference lists Example: PKG_ADVISORY
Note on C16: Title Title of the template version Mandatory: Yes Format: Text Allowed values: Free entry Example: Package advisory
Note on D16: Text Opening text of the document Mandatory: Yes Format: Text with merge fields in double braces Allowed values: Free entry Example: This is to advise that the package {{productCode}} - {{productName}} ...
Note on E16: Merge fields used Fields filled in by BIBS Mandatory: No Format: PKG_REQUEST_FORM: reference, requestType, title; PKG_QUOTATION_SLIP: reference, roundNo, replyBy; PKG_COMPARATIVE: reference, roundNo, variant; PKG_SLIP: reference, title; advisories: productCode, productName, versionNo, effectiveFrom, reference Allowed values: Free entry Example: productCode, productName, versionNo, effectiveFrom, reference
Note on F16: Effective from Date from which the version is used Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Nov-2026

## UA-05 Parameters
UA-05 Password, session and sign-in parameters | [5 empty] | Step 31 of 31
← Back to Start here | Step 31 of 31. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the sign-in, password, session and access-request parameters, as delivered and as BDOI Information Security wants them
Provided by | BDOI Information Security; BDOI IT for the sign-in mode
Due | 16-Jul-2027 – Values for UAT
How it is loaded | System Parameters (SCR-UA-18): entered by the System Administrator and approved by the Information Security Officer, audited; checked in SIT with the test plan
Source | BDOI security policy (UQ07, UQ08); the values delivered (FRS section 9.1)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: value changed | Yes
Format | LOGIN_MAX_FAILED_ATTEMPTS, SESSION_IDLE_WARNING_MINUTES, SESSION_TIMEOUT_MINUTES, SESSION_EXPIRY_WARNING_MINUTES, AUTH_MODE, USER_ID_PATTERN, USER_ID_FORMAT_TEXT, PASSWORD_HISTORY_COUNT, PASSWORD_MAX_AGE_DAYS, PASSWORD_MIN_AGE_DAYS, UAM_WORKING_HOURS, UAM_ANY_APPROVER, UAM_ROLE_APPLY_ON_APPROVAL, UAM_EXTERNAL_USERS, UAM_DORMANT_DAYS, UAM_DORMANT_NOTICE_DAYS, JOB_FAILURE_RECIPIENTS | As on System Parameters | Same type and range | Text | Name
Allowed values | List Sign-in: 17 values, see Reference lists | Free entry | Free entry | Free entry | Free entry
What to enter | One row per parameter | The value proposed with the system | The value BDOI wants | Policy reference or reason | Information Security or BDOI IT approver of the value
Row | Parameter * | Value as delivered * | Value wanted * | Reason | Approved by *
Example – overwrite or delete | PASSWORD_MAX_AGE_DAYS | 90 | 90 | BDO password policy | Ramon Dizon
Note on B16: Parameter One row per parameter Mandatory: Yes Format: LOGIN_MAX_FAILED_ATTEMPTS, SESSION_IDLE_WARNING_MINUTES, SESSION_TIMEOUT_MINUTES, SESSION_EXPIRY_WARNING_MINUTES, AUTH_MODE, USER_ID_PATTERN, USER_ID_FORMAT_TEXT, PASSWORD_HISTORY_COUNT, PASSWORD_MAX_AGE_DAYS, PASSWORD_MIN_AGE_DAYS, UAM_WORKING_HOURS, UAM_ANY_APPROVER, UAM_ROLE_APPLY_ON_APPROVAL, UAM_EXTERNAL_USERS, UAM_DORMANT_DAYS, UAM_DORMANT_NOTICE_DAYS, JOB_FAILURE_RECIPIENTS Allowed values: List Sign-in: 17 values, see Reference lists Example: PASSWORD_MAX_AGE_DAYS
Note on C16: Value as delivered The value proposed with the system Mandatory: Yes Format: As on System Parameters Allowed values: Free entry Example: 90
Note on D16: Value wanted The value BDOI wants Mandatory: Yes Format: Same type and range Allowed values: Free entry Example: 90
Note on E16: Reason Policy reference or reason Mandatory: Conditional: value changed Format: Text Allowed values: Free entry Example: BDO password policy
Note on F16: Approved by Information Security or BDOI IT approver of the value Mandatory: Yes Format: Name Allowed values: Free entry Example: Ramon Dizon

## Ref Lists of values
Reference: Lists of values
← Back to Start here | Every list of values of BIBS with its owner and its one route
List | Name | Module | Drop | Owner (BDOI unit) | Values proposed | Route | Prepared in | Due | Values to keep, add or retire | Status | BDOI comments
ACSL_CASE_TYPE | ACSL case type | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ACSL_CORRECTION_KIND | ACSL correction kind | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ADJ_RETURN_REASON | Endorsement return reason | Operations | Drop 1 | Head, Operations Services | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
AR_CLASS | Acknowledgement receipt class | Operations | Drop 1 | Head, Operations Services | 11 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_ADJUSTER | Adjuster / appraiser | Claims | Drop 2 | Product Owner, Claims | 25 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CATASTROPHE | Catastrophe code | Claims | Drop 2 | Product Owner, Claims | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CLAIM_STATUS | Claim status | Claims | Drop 2 | Product Owner, Claims | 18 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CLAIM_TYPE | Claim type | Claims | Drop 2 | Product Owner, Claims | 10 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_DIARY_TYPE | Claim diary entry type | Claims | Drop 2 | Product Owner, Claims | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_DOCUMENT_TYPE | Claim document type | Claims | Drop 2 | Product Owner, Claims | 9 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_LOSS_NATURE | Nature of loss | Claims | Drop 2 | Product Owner, Claims | 10 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_OVERRIDE_REASON | Claim override reason | Claims | Drop 2 | Product Owner, Claims | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_REOPEN_REASON | Claim reopen reason | Claims | Drop 2 | Product Owner, Claims | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_SETTLEMENT_TYPE | Requested type of settlement | Claims | Drop 2 | Product Owner, Claims | 11 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_UNIT | Claims unit | Claims | Drop 2 | Product Owner, Claims | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_UPDATE_SOURCE | Insurer update source | Claims | Drop 2 | Product Owner, Claims | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
BRANCH_EMAIL | Branch e-mail address | Operations | Drop 1 | Head, Operations Services | 0 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CANCELLATION_REASON | Cancellation reason | Operations | Drop 1 | Head, Operations Services | 36 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CIVIL_STATUS | Civil status | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Migration object | Migration Workbook, object R01, code map LOV:CIVIL_STATUS | 18-Jun-2027 (T-28 weeks) |  | Not started
CLAUSE_KIND | Clause kind | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 4 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_CONFIRMATION_CHANNEL | Client confirmation channel | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_DEACTIVATION_REASON | Client deactivation reason | New Business | Drop 1 | Product Owner, BDOI (New Business) | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_TAG | Client tag | New Business | Drop 1 | Product Owner, BDOI (New Business) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_BILLING_FREQUENCY | Billing frequency | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_EFFORT_CODE | Collection effort code | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_ESCALATION_REASON | Escalation reason | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_PR_DISPOSITION | PR collector disposition | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 8 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_UPP_DISPOSITION | Unapplied payment disposition (collector) | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CONSTRUCTION_CLASS | Construction class | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
COVERAGE_KIND | Coverage kind | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 4 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_CHANGE_REASON | Contact change reason | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_CHANNEL | Contact channel | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_DOCUMENT_TYPE | Contact centre document type | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_REFERRAL_FIELD | Change referred to the fulfilment unit | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_STATUS | Customer service status | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_STATUS_MAP | Customer service status mapping | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 14 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_VERIFY_CHECK | Caller verification check | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
DISBURSEMENT_TYPE | Disbursement type | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 12 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
DISB_CANCEL_REASON | DV cancellation reason | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
DISB_RETURN_REASON | DV return / rejection reason | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
DISPOSITION_TYPE | Unapplied payment disposition | Operations | Drop 1 | Head, Operations Services | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
DOCUMENT_TYPE | Document type | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 63 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
DP_FEEDBACK_REASON | Direct payment feedback reason | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_BENEFIT_LINE | EB benefit line | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_CAPABILITY_FACTOR | EB capability factor | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_FRANCHISE_REJECT_REASON | EB franchise rejection reason | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_LOST_REASON | EB lost / not renewed reason | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_MEMBER_CHANGE_TYPE | EB member change type | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_PROCESS_TYPE | EB process type | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_SOA_REJECT_REASON | EB SOA rejection reason | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_TEAM | EB team | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_TRACKED_ITEM_TYPE | EB tracked item type | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_DOC_TYPE | Endorsement document type | Operations | Drop 1 | Head, Operations Services | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_REQUEST_TYPE | Endorsement request type | Operations | Drop 1 | Head, Operations Services | 12 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_TYPE | Endorsement type | Operations | Drop 1 | Head, Operations Services | 14 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
EPOLICY_REJECT_REASON | E-policy rejection reason | New Business | Drop 1 | Product Owner, BDOI (New Business) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
FFY_CANCEL_REASON | FFY cancellation reason | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
HOLD_REASON | Remittance hold reason | Operations | Drop 1 | Head, Operations Services | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
ID_TYPE | Identification document | New Business | Drop 1 | Product Owner, BDOI (New Business) | 10 | Migration object | Migration Workbook, object R01, code map LOV:ID_TYPE | 18-Jun-2027 (T-28 weeks) |  | Not started
INCENTIVE_EXCLUSION_RULE | Incentive exclusion rule | New Business | Drop 1 | Product Owner, BDOI (New Business) | 2 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
INCENTIVE_TYPE | Incentive type | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 2 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
INSTRUCTION_TYPE | Special instruction type | New Business | Drop 1 | Product Owner, BDOI (New Business) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_DOCS_CORPORATE | KYC checklist - corporate | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_DOCS_INDIVIDUAL | KYC checklist - individual | New Business | Drop 1 | Product Owner, BDOI (New Business) | 2 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_RISK_RATING | KYC risk rating | New Business | Drop 1 | Product Owner, BDOI (New Business) | 3 | Migration object | Migration Workbook, object R01, code map LOV:KYC_RISK_RATING | 18-Jun-2027 (T-28 weeks) |  | Not started
LEGACY_RECORD_STATUS | Legacy record status | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 18 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
LEGACY_RECORD_TYPE | Legacy record type | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 11 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MARKET_SEGMENT | Market segment | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 5 | Migration object | Migration Workbook, object R01, code map LOV:MARKET_SEGMENT | 18-Jun-2027 (T-28 weeks) |  | Not started
MIG_ACCESS_REASON | Legacy access reason | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_BREAK_REASON | Reconciliation break reason | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_OBJECT_CATEGORY | Migration object category | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_SOURCE_SYSTEM | Legacy source system | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_TRUST_LEVEL | Data trust level | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_WAIVER_REASON | Row waiver reason | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
MORTGAGEE_BANK | Mortgagee bank | New Business | Drop 1 | Product Owner, BDOI (New Business) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
NATIONALITY | Nationality | New Business | Drop 1 | Product Owner, BDOI (New Business) | 6 | Migration object | Migration Workbook, object R01, code map LOV:NATIONALITY | 18-Jun-2027 (T-28 weeks) |  | Not started
OCCUPANCY | Occupancy | New Business | Drop 1 | Product Owner, BDOI (New Business) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
OPS_EXTERNAL_LINK | Operations external link | Operations | Drop 1 | Head, Operations Services | 0 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
OR_TYPE | Official receipt type | Operations | Drop 1 | Head, Operations Services | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PAYEE_CLASS | Payee class | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 6 | Migration object | Migration Workbook, object R01, code map LOV:PAYEE_CLASS | 18-Jun-2027 (T-28 weeks) |  | Not started
PKG_ADVISORY_GROUP | Advisory recipient group | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 5 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_BUSINESS_ORIGIN | Business origin | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_DEACTIVATION_REASON | Package deactivation reason | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_NOT_PROCEEDED_REASON | Package not proceeded reason | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 5 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_POLICY_TYPE | Policy type | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_REQUEST_REASON | Package request reason | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 8 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_REQUEST_SOURCE | Package request source | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_REQUEST_TYPE | Package request type | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 6 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_RESPONSE_OUTCOME | Insurer response outcome | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | 6 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 9-Apr-2027 (T-38 weeks) |  | Not started
PRQ_PAYMENT_MODE | Request payment mode | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
PRQ_RFP_TYPE | Request for payment type | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RECEIPT_CANCEL_REASON | Receipt cancellation reason | Operations | Drop 1 | Head, Operations Services | 17 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RECON_COMPANY_CONCERNED | Company concerned | Operations | Drop 1 | Head, Operations Services | 0 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RECON_DISPOSITION | Reconciliation disposition | Operations | Drop 1 | Head, Operations Services | 0 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REFUND_REASON | Refund reason | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REINSTATEMENT_REASON | Reinstatement reason | Operations | Drop 1 | Head, Operations Services | 9 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REMITTANCE_TYPE | Remittance type | Operations | Drop 1 | Head, Operations Services | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_DEDUCTION_SOURCE | Remittance deduction source | Operations | Drop 1 | Head, Operations Services | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_EXCLUSION_REASON | Remittance exclusion reason | Operations | Drop 1 | Head, Operations Services | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_RETURN_REASON | Remittance return reason | Operations | Drop 1 | Head, Operations Services | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RETURN_REASON | Return reason | New Business | Drop 1 | Product Owner, BDOI (New Business) | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_DISPOSITION | Renewal disposition | Renewal | Drop 1 | Product Owner, Renewal | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_FOLLOWUP_CHANNEL | Renewal follow-up channel | Renewal | Drop 1 | Product Owner, Renewal | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_FOLLOWUP_OUTCOME | Renewal follow-up outcome | Renewal | Drop 1 | Product Owner, Renewal | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_INSURER_RESPONSE | Insurer renewal response | Renewal | Drop 1 | Product Owner, Renewal | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_LAMD_STATUS | LAMD loan status | Renewal | Drop 1 | Product Owner, Renewal | 2 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_NONRENEWAL_REASON | Reason for Not for Renewal | Renewal | Drop 1 | Product Owner, Renewal | 24 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_OVERRIDE_REASON | Renewal override reason | Renewal | Drop 1 | Product Owner, Renewal | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_PLACEMENT_REJECT_REASON | Placement rejection reason | Renewal | Drop 1 | Product Owner, Renewal | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_PLACEMENT_RETURN_REASON | Return reason of a placement | Renewal | Drop 1 | Product Owner, Renewal | 39 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_RETURN_REASON | Renewal return reason | Renewal | Drop 1 | Product Owner, Renewal | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_TRANSFER_REASON | Renewal transfer reason | Renewal | Drop 1 | Product Owner, Renewal | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RRF_CATEGORY_A | Refund category A | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
RRF_CATEGORY_B | Refund category B | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 1 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_BUCKET | Submitted policy bucket | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 12 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_CONVERSION_STATUS | Conversion status | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_DECLINE_REASON | Insurer re-assignment reason | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 5 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_IAAF_FINDING | Policy review finding | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_LETTER_TYPE | Submitted policy letter type | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_LOAN_REPORT | Loan report | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_LOAN_STATUS | Loan status | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_NON_RENEWAL_REASON | Non-renewal reason (submitted policy) | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 16 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_REASON | Submitted policy reason | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 15 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_RETURN_REASON | IAAF or TOR return reason | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_SEGMENT | Submitted policy segment | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_CASE_TYPE | Screening case type | Sanction Screening | Drop 1 | Compliance | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_DISPOSITION | Screening disposition | Sanction Screening | Drop 1 | Compliance | 13 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_DOCUMENT_TYPE | Screening document type | Sanction Screening | Drop 1 | Compliance | 6 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_FORM_TYPE | Screening form type | Sanction Screening | Drop 1 | Compliance | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_LIST_TYPE | Watchlist type | Sanction Screening | Drop 1 | Compliance | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_REASSIGN_REASON | Case re-assignment reason | Sanction Screening | Drop 1 | Compliance | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_STR_REASON | STR reason | Sanction Screening | Drop 1 | Compliance | 0 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SERVICE_FEE_SEGMENT | Service fee segment | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | 3 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
SOURCE_CHANNEL | Source channel | New Business | Drop 1 | Product Owner, BDOI (New Business) | 5 | Migration object | Migration Workbook, object R01, code map MIS:BUSINESS_ORIGIN | 18-Jun-2027 (T-28 weeks) |  | Not started
SOURCE_OF_FUNDS | Source of funds | New Business | Drop 1 | Product Owner, BDOI (New Business) | 6 | Migration object | Migration Workbook, object R01, code map LOV:SOURCE_OF_FUNDS | 18-Jun-2027 (T-28 weeks) |  | Not started
SPECIAL_REMIT_CONDITION | Special remittance condition | Operations | Drop 1 | Head, Operations Services | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_BUSINESS_UNIT | Business unit group | User Access Maintenance | Drop 0 | Business Administration (User Access) | 0 | Template | BRD-11 template CI-06, sheet UA-06 Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_DEACTIVATION_REASON | User deactivation reason | User Access Maintenance | Drop 0 | Business Administration (User Access) | 6 | Template | BRD-11 template CI-06, sheet UA-06 Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_USER_LEVEL | User level | User Access Maintenance | Drop 0 | Business Administration (User Access) | 3 | Template | BRD-11 template CI-06, sheet UA-06 Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
VEHICLE_BODY_TYPE | Vehicle body type | New Business | Drop 1 | Product Owner, BDOI (New Business) | 7 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
VOID_REASON | Void reason | Operations | Drop 1 | Head, Operations Services | 4 | Template | This workbook, sheet Ref Lists of values | 9-Apr-2027 (T-38 weeks) |  | Not started
Note on A4: List: Code of the list on Lists of Values
Note on B4: Name: Name of the list
Note on C4: Module: Module that uses the list
Note on D4: Drop: Drop
Note on E4: Owner (BDOI unit): Unit that owns the values
Note on F4: Values proposed: Number of values proposed with the platform
Note on G4: Route: Template or Migration object
Note on H4: Prepared in: Template or code map where the values are given
Note on I4: Due: Due date
Note on J4: Values to keep, add or retire: The owner's decision on the values
Note on K4: Status: Status of the row
Note on L4: BDOI comments: Decision, value or comment of the owner

## Ref System parameters
Reference: System parameters
← Back to Start here | Every system parameter with the value proposed and the value BDOI wants
Parameter | Group | Module | Drop | Owner (BDOI unit) | What it controls | Type | Value proposed | Allowed range | Route | Prepared in | Due | Value wanted | Reason | Approved by | Status | BDOI comments
BROKING_CLOSE_TIME | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Time (PHT, HH:MM) at which the broking books are closed on the last day of the month | string | 23:00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BROKING_SOURCE_MODULES | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Source modules of the broking books: their postings are refused once the BROKING books of the period are closed | code list | BOOKING,OPSLEDGER,CASHIERING,REMITTANCE,ADJUSTMENT,COMMISSION,PRODRECON,DISBURSEMENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLOSE_ONLY_PREVIOUS_MONTH | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Month-end close only for the previous month and year | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EWT_RATE_TOLERANCE | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Largest difference in percentage points between the withholding rate of a document and the rate of the ATC before the EWT worksheet flags it | decimal | 0.05 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_BOOK_RATE_SOURCE | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Source of the Operations BOOK rate: CLOSING_PREV_MONTH copies the revaluation rate of the previous month end, MANUAL keeps it by hand | string | CLOSING_PREV_MONTH |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
YEAR_END_CLOSE_DEADLINE | Accounting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Month and day (MM-DD) by which the previous year must be closed; YEAR_END_CLOSE_DUE is raised before | string | 04-15 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACSL_SOA_MAX_ROWS | Acsl | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Largest number of rows of one insurer statement of account upload | integer | 20000 | 1 to 200000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_BILLING_NO_LINES | Booking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Product lines whose bookings need the insurer billing number, unique per insurer | code list | HMO,GLI,GPA |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_CWT2_SEGMENTS | Booking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Market segments whose corporate clients withhold 2% creditable tax on premium | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_WTAX_RATE | Booking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Withholding tax rate (percent) the insurer withholds on the broker commission, printed on the booked invoice and service invoice | decimal | 10 | 0 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_COMMISSION_REALIZATION | Booking | New Business | Drop 1 | Product Owner, BDOI (New Business) | When broker commission is realized: ON_COLLECTION (unrealized at booking, realized when premium is applied) or ON_BOOKING (commission income and output VAT at booking) | string | ON_COLLECTION |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SERVICE_INVOICE_CREDIT_DAYS | Booking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Credit days printed on a service invoice (payment terms merged into its template) | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_CREDIT_DAYS | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Credit days of the accounting party created for a client | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PROPOSAL_NUMBER_PREFIX | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Prefix of the PRF marketing reference (<prefix>-<yyyy>-nnnnnn) | string | PRF |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PROPOSAL_SLIP_PREFIX | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Prefix of proposal slip numbers (<prefix>-<yyyy>-nnnnnn) | string | PS |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_EXPIRING_DAYS | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Quotations whose validity ends within this many days are listed as expiring | integer | 7 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_NUMBER_PREFIX | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Prefix of package quotation numbers (<prefix>-<yyyy>-nnnnnn), shown as Proposal No. | string | QT |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_REQUEST_PREFIX | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Prefix of quotation request numbers (<prefix>-<yyyy>-nnnnnn) | string | REQ |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_SLIP_PREFIX | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Prefix of quotation slip numbers (<prefix>-<yyyy>-nnnnnn) | string | QS |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_SLIP_REPLY_DAYS | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Days given to insurers to reply to a quotation slip | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_VALIDITY_DAYS | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Default validity of a quotation in days from its creation | integer | 30 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RATE_EXCEPTION_VALIDITY_DAYS | Broking | New Business | Drop 1 | Product Owner, BDOI (New Business) | Days a rate-scheme exception stays valid when the request gives no end date | integer | 30 | 1 to 3650 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BULK_MAX_ROWS | Bulk | Platform set-up | Drop 0 | BDOI IT | Maximum number of data rows in one bulk upload file | integer | 5000 | 10 to 50000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_AGEING_BUCKETS | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Upper bounds in days of the claims ageing buckets: 0-30, 31-60, 61-90, 91-180, 181+ | integer list | 30,60,90,180 | 1 to 3650 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_AUTH_DP_POLICY | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Claims authorization code on a direct-payment cover: ALLOW, CONFIRM (insurer payment evidence attached) or BLOCK | string | CONFIRM |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_DEFAULT_CURRENCY | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Currency of a claim whose cover has none | string | PHP |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_FOLLOW_UP_DAYS | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Days from a status change to the next follow-up date when the status has no follow up days attribute | integer | 7 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PAST_DUE_DAYS | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Age in days above which an outstanding claim is past due: report and alert BCL_CLAIM_PAST_DUE | integer | 90 | 1 to 3650 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PRONE_MIN_CLAIMS | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Claims at one location that make it claims-prone | integer | 3 | 1 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PRONE_YEARS | Claims Handling | Claims | Drop 2 | Product Owner, Claims | Look-back years of the claims-prone location analysis | integer | 3 | 1 to 20 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_AGING_BASIS | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Date the aging of a collection item counts from: BOOKING or INCEPTION | string | BOOKING |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_AGING_BRACKETS | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Aging brackets of the worklist, the home chart and the reports, in days | code list | 0-30,31-45,46-60,61-90,91-120,121+ |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_EDIT_LOCK_MINUTES | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Minutes after which the "<user> is editing" lock of a collection account expires | integer | 15 | 1 to 240 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_EXPORT_MAX_ROWS | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Maximum rows of an asynchronous Collections export | integer | 50000 | 100 to 1000000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_INVOICE_NO_PATTERN | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Regular expression of the invoice number of "For application to invoice": EBIX I######## or BI-... of this system | string | ^(I\d{8}¦BI-.+)$ |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_MIN_BALANCE_THRESHOLD | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Net outstanding PR above which an invoice enters the collection worklist | decimal | 10.00 | 0 to 100000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_PROMISE_GRACE_DAYS | Collections | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Days after the promised date before an unpaid promise to pay is broken | integer | 0 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CONFIG_PROMOTION_MAX_PACKAGE_MB | Config Promotion | Platform set-up | Drop 0 | BDOI IT | Largest configuration package accepted, in megabytes once unpacked | integer | 50 | 1 to 500 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CONFIG_PROMOTION_NOTIFY | Config Promotion | Platform set-up | Drop 0 | BDOI IT | Permissions whose holders are told when a configuration import waits for approval, is applied, rejected or fails | code list | CONFIG_IMPORT_APPROVE,CONFIG_BASELINE_MANAGE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CONFIG_PROMOTION_PIPELINE_APPLY | Config Promotion | Platform set-up | Drop 0 | BDOI IT | Outside production only: when true, the deployment pipeline may apply its own dry-run import without a second user; production always needs the approval of a second user | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CONFIG_PROMOTION_PRODUCTION_WINDOW | Config Promotion | Platform set-up | Drop 0 | BDOI IT | Change window in which a configuration package may be applied in production, for example SAT-SUN 20:00-06:00 (days, then the hours; an end before the start runs into the next day); empty = no window, production imports are refused | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SUSPENSE_ACCOUNT_CODES | Controls | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | GL account codes monitored by the SUSPENSE_BALANCE exception (blank = accounts named Suspense) | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_AGE | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Minimum age in years of an individual policyholder | integer | 18 | 0 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_FIELDS_CORPORATE | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Fields a corporate client needs to be complete. Codes: TIN, ID, CONTACT, ADDRESS, MARKET_SEGMENT, SOURCE_OF_FUNDS | code list | TIN,CONTACT,ADDRESS,MARKET_SEGMENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_FIELDS_INDIVIDUAL | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Fields an individual client needs to be complete. Codes: BIRTH_DATE, TIN, ID, CONTACT, ADDRESS, MARKET_SEGMENT, NATIONALITY, SOURCE_OF_FUNDS, OCCUPATION | code list | BIRTH_DATE,TIN,ID,CONTACT,ADDRESS,MARKET_SEGMENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_DUE_WINDOW_DAYS | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Days ahead in which a KYC review is listed as coming due | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_REVIEW_MONTHS | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Months between periodic KYC reviews of standard and low risk clients | integer | 36 | 1 to 120 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_REVIEW_MONTHS_HIGH_RISK | Crm | New Business | Drop 1 | Product Owner, BDOI (New Business) | Months between periodic KYC reviews of high risk clients | integer | 12 | 1 to 120 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_LEGACY_SYNC_ENABLED | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Send contact changes to the legacy policy systems while they are still in use | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_PAYMENT_HISTORY_MONTHS | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Months of payment history the contact centre sees before Show Older | integer | 12 | 1 to 120 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_SEARCH_MAX_RESULTS | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Maximum clients a customer search returns before the contact centre officer must refine it | integer | 50 | 5 to 500 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_SEARCH_MIN_CHARS | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Minimum characters of a client name search | integer | 3 | 1 to 20 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFICATION_VALID_MINUTES | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Minutes a passed verification of a caller stays valid for a change | integer | 30 | 1 to 480 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFY_MAX_FAILS | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Failed verifications of one client in a day that raise an alert to the supervisors | integer | 3 | 1 to 20 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFY_MIN_MATCHES | Customer Service | Customer Servicing Facility | Drop 1 | Product Owner, Customer Servicing Facility | Verification checks that must match before the contact details of a client can be changed | integer | 2 | 1 to 10 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
INSURER_DEFAULT_CREDIT_DAYS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Credit days of an insurer loaded by data migration without credit days | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ACCESS_EXPORT_ALERT_ROWS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Archive records exported by one user in a day above which the unusual-access alert is raised | integer | 5000 | 1 to 1000000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_AMOUNT_TOLERANCE | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Largest amount difference accepted by the amount reconciliation | decimal | 0.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ARCHIVE_EXPORT_MAX_ROWS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Largest number of archive records exported to Excel at a time | integer | 1000 | 1 to 100000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CHUNK_SIZE | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Rows loaded per transaction | integer | 500 | 10 to 5000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CLIENT_MATCH_AUTO | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Client match score from which two legacy clients are merged automatically | integer | 90 | 60 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CLIENT_MATCH_REVIEW | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Client match score from which a pair goes to the Data Steward review queue | integer | 60 | 1 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CUTOVER_DATE | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Go-live date (yyyy-MM-dd); the first business day on BIBS | string | 2028-01-03 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ENVIRONMENT_CLASS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | PRODUCTION or NON_PRODUCTION; outside production personal data of the extracts is masked before staging | string | NON_PRODUCTION |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_FREEZE_AT | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Start of the legacy business freeze (yyyy-MM-dd HH:mm, Philippine time) | string | 2027-12-31 22:00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_GOLIVE_RENEWAL_TO | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Last expiry date of the migrated policies taken over by Renewal at go-live (yyyy-MM-dd) | string | 2028-05-31 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_INVOICE_NO_COLLISION_PREFIX | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Prefix the source system to a legacy invoice number found in two source systems | boolean | true |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LAST_LEGACY_BUSINESS_DAY | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Last business day processed in the legacy systems (yyyy-MM-dd) | string | 2027-12-29 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_ACCESS_REASON_REQUIRED | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | A reason is required before the legacy archive is searched | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_INVOICE_NO_PATTERN | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Patterns of legacy invoice numbers recognised by the payment matcher (comma separated regular expressions) | string | ^I\d{8}$ |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_LINK_EBIX | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Address of the read-only EBIX application for users who still need it | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_LINK_QPS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Address of the read-only QPS application for users who still need it | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_MAX_ERROR_RATE_FINANCIAL | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Largest percentage of failing or waived rows with which open items, unapplied payments and the trial balance may be loaded | decimal | 0 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_MAX_ERROR_RATE_MASTER | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Largest percentage of failing or waived rows with which master data may be loaded | decimal | 0.5 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_OPENING_VALUE_DATE | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Value date of the opening entries and of the opening-balance adjustments (yyyy-MM-dd) | string | 2028-01-01 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_PARTITIONS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Partitions loaded in parallel | integer | 4 | 1 to 16 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RA_MAX_LEAD_DAYS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | An advice already sent more than this number of days before expiry is loaded with a warning | integer | 140 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RENEWAL_URGENT_TO | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Migrated policies expiring up to this date are flagged urgent in the go-live renewal queue (yyyy-MM-dd) | string | 2028-01-31 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RESUBMIT_DEADLINE | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Last time a corrected resubmission of the advices already sent may be approved (yyyy-MM-dd HH:mm, Philippine time) | string | 2028-01-02 12:00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_STAGING_RETENTION_DAYS | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Days staging data and extract files are kept after the batch is signed off or rolled back | integer | 5 | 1 to 5 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_UPP_ISSUE_AR | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Issue a BIBS acknowledgement receipt for each migrated unapplied payment (no cash posting) | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_YEAR_END_OPTION | Data Migration | Data Migration | Drop 0 | Program Manager, Business Project Services (Data Migration) | Year-end cut-over option: A = provisional opening trial balance at the year-end boundary with controlled true-ups | string | A |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_AUTO_APPROVER_ROUTING | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Request types whose disbursement voucher is prepared automatically and routed straight to the approver | code list | REFUND,REMITTANCE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_CLEARING | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | ON: issued checks are credited to checks outstanding until negotiated; OFF: to the bank at approval | string | ON |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_CLEARING_ACCOUNT | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Checks outstanding clearing account credited for issued checks while DISB_CHECK_CLEARING = ON | string | 2241 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_SERIES_WARNING | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Remaining check leaves of a paying account at which CHECK_SERIES_LOW is raised | integer | 20 | 1 to 1000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_NO_PAYEE_ACTION | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Gateway request whose payee is not maintained: HOLD keeps it as NO_PAYEE, raises DISB_PAYEE_NO_MATCH and a payee request and resumes it once the payee is authorised; RETURN returns it at once to its source | string | HOLD |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_STALE_DAYS | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Days after the print date at which a printed or released check becomes stale | integer | 180 | 30 to 720 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EARLY_INCENTIVE_WTAX_RATE | Disbursement | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Withholding tax rate (percent) of the early-incentive service invoice | decimal | 2 | 0 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_ADJ_BOOKING_REQUIRES_PAYMENT | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Raise the endorsement request of a member change only after its billing is paid | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_COMPARATIVE_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days from the last proposal to the comparative sent to the client | integer | 3 | 1 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FOLLOWUP_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days between follow-ups of a pending tracked item | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FOLLOWUP_MAX | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Follow-ups sent before a tracked item is escalated | integer | 3 | 1 to 20 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_ADVICE_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days to advise the client of the franchise outcome | integer | 2 | 1 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_GRACE_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days after the franchise decision date before an undecided franchise request expires | integer | 2 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_TAT_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days for the insurer franchise decision | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_PROPOSAL_REPLY_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Working days an insurer has to answer a request for proposal | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_RA_LEAD_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Days before expiry the renewal advice is sent and the renewal cycle opened | integer | 135 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_RA_REMINDER_DAYS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Days before expiry of the RA reminders while no feedback is recorded | integer list | 90,105,120 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_BOOKING | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to book once billing is validated | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_CARDS | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to submit, validate and release member cards | integer | 10 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_COC | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days for the insurer certificate of cover | integer | 1 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_COLLECTION | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to collect the premium upon SOA / billing receipt | integer | 2 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_CONFIRMATION | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to send the client confirmation to the insurer | integer | 2 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_FRANCHISE_SUBMIT | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to submit a franchise request upon complete documents | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_MEMBER_CHANGE | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days per step of an inclusion / deletion | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_OR | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days for the insurer to submit the official receipt | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_PLACEMENT_REQUEST | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to request placement and booking upon client confirmation | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_PLACEMENT_SLIP | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: days for Processing to submit the placement slip | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_POLICY_CHECK | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to check the policy / contract against the proposal | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_POLICY_SOA | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days for the insurer policy / contract and billing / SOA | integer | 10 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_RELEASE | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to release the SOA to Collection and the policy to the client | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_RFQ_SUBMIT | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days to send the request for quotation upon franchise approval | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_SOA_VALIDATION | Employee Benefits | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | TAT: working days for Processing to validate the final SOA | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EPOLICY_PASSWORD_HINT | Issuance | New Business | Drop 1 | Product Owner, BDOI (New Business) | Text telling the client how the password of the e-policy is formed | string | The password follows the BDOI standard; it is sent to you in a separate e-mail. |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
IA_TRIGGER | Issuance | New Business | Drop 1 | Product Owner, BDOI (New Business) | When the Insurance Advice of a mortgaged account is generated automatically: ON_POLICY_ISSUE, ON_PLACEMENT or MANUAL | string | ON_POLICY_ISSUE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MAIL_FROM_ADDRESS | Messaging | Platform set-up | Drop 0 | BDOI IT | From address of e-mails sent by this system (quotations, slips, e-policies, invoices) | string | no-reply@bdoi.example.ph |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MAIL_MAX_ATTEMPTS | Messaging | Platform set-up | Drop 0 | BDOI IT | Delivery attempts before an e-mail is marked failed | integer | 3 | 1 to 10 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
NB_STALLED_DAYS | Nb Reports | New Business | Drop 1 | Product Owner, BDOI (New Business) | An open New Business account with no stage movement for this many days is reported as stalled | integer | 5 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ADJ_BASELINE_PERCENT | Operations | Operations | Drop 1 | Head, Operations Services | Over-adjustment baseline: cumulative adjustments of an invoice above this percent of its original premium need an override reason and raise ADJ_OVER_BASELINE | decimal | 100 | 1 to 1000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_AMOUNT_WORDS_UNITS | Operations | Operations | Drop 1 | Head, Operations Services | Words of the amount printed on a receipt per currency: CURRENCY=units/hundredths, separated by semicolons | string | PHP=Pesos/Centavos;USD=US Dollars/Cents |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_AR_REMARKS_REQUIRED | Operations | Operations | Drop 1 | Head, Operations Services | Y = Remarks are a required field of the AR and OR creation record (Appendix R, C25) | string | Y |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_BANK_ACCOUNT | Operations | Operations | Drop 1 | Head, Operations Services | GL account debited for payments received by check, bank or electronic channels | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_CERTIFICATE_NO_FORMAT | Operations | Operations | Drop 1 | Head, Operations Services | Acknowledgement certificate number given per printed receipt; tokens {BRANCH}, {MMYYYY} of the print date, {SEQ} (5 digits) (Appendix R, C4) | string | AC_{BRANCH}_{MMYYYY}_{SEQ} |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_CHECK_BEFORE_CASH | Operations | Operations | Drop 1 | Head, Operations Services | Y = check payments are posted and applied before cash payments of the same posting run (Appendix R, C6) | string | Y |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_CHECK_CANCEL_REASONS | Operations | Operations | Drop 1 | Head, Operations Services | Cancellation reasons allowed for a check payment; blank = every reason (Appendix R, C21) | code list | PRM_CHECK_AMOUNT,PRM_NO_SIGNATURE,PRM_INCORRECT_PAYEE,PRM_INCORRECT_CHECK |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_CHECK_DATE_RULE | Operations | Operations | Drop 1 | Head, Operations Services | ON = a check payment is refused at receipting when its date is within the holding period; OFF = accepted when presented (Appendix R, C7) | string | ON |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_CHECK_HOLDING_DAYS | Operations | Operations | Drop 1 | Head, Operations Services | Working days of the check holding period at receipting (Appendix R, C7) | integer | 4 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_COMMISSION_SCHEDULE_MODE | Operations | Operations | Drop 1 | Head, Operations Services | Commission Schedule: LINE_LEVEL = valid lines are processed; WHOLE_FILE = a file with a failed or unmatched line, or a paid amount different from the outstanding, is not processed (Appendix R, C10) | string | LINE_LEVEL |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_DIRECT_CREDIT_MODE | Operations | Operations | Drop 1 | Head, Operations Services | Direct Credit file: IDENTIFY = it identifies payments already received (BP filename and transaction number); NEW_PAYMENT = every row is a new payment with its own AR (Appendix R, C8) | string | IDENTIFY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_MAX_PAID_AMOUNT | Operations | Operations | Drop 1 | Head, Operations Services | Highest paid amount of one AR or OR creation record | decimal | 1000000000.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_MFT_COMPANY_CODE | Operations | Operations | Drop 1 | Head, Operations Services | Company that receives the payment files of the MFT folders (company code); blank = the first company | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_ON_HAND_ACCOUNT | Operations | Operations | Drop 1 | Head, Operations Services | GL account debited for payments received in cash over the counter | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_POSTING_STEP_RECEIPTS | Operations | Operations | Drop 1 | Head, Operations Services | Receipt kinds whose number is issued only when a second user posts the creation record (AR, OR); blank = issue at save (Appendix R, C1) | code list | AR,OR |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_PR2307_BASE | Operations | Operations | Drop 1 | Head, Operations Services | Base of the PR 2307 of a 2% CWT account: PREMIUM = the premium amount (every premium receivable component), BASIC = the basic premium only (Appendix R, C26) | string | PREMIUM |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_RECEIPT_NO_FORMAT | Operations | Operations | Drop 1 | Head, Operations Services | Number format proposed for a new AR / OR series; tokens {PREFIX}, {YEAR}, {BRANCH} (branch indicator), {SEQ}; blank = prefix and sequence (Appendix R, C4) | string | {PREFIX}-{YEAR}-{BRANCH}-{SEQ} |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_RECORD_NO_FORMAT | Operations | Operations | Drop 1 | Head, Operations Services | Number of creation, cancellation and reinstatement records; tokens {PREFIX} (CR, CN, RE), {TYPE} (AR, OR), {YEAR}, {SEQ} (Appendix R, C3) | string | {PREFIX}-{TYPE}-{SEQ} |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_REINSTATEMENT_SCOPE | Operations | Operations | Drop 1 | Head, Operations Services | What Reinstate does: ISSUED = reverse the payment of an issued receipt, CANCELLED = restore a cancelled receipt, BOTH (Appendix R, C2) | string | BOTH |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_REMITTED_CANCELLATION | Operations | Operations | Drop 1 | Head, Operations Services | Cancellation of an AR already remitted: AR_INSURER_REFUND = the payment becomes an AR Insurer Refund; REVERSE_ALL = every application is reversed (Appendix R, C9) | string | AR_INSURER_REFUND |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_SETTLEMENT_OR_TRIGGER | Operations | Operations | Drop 1 | Head, Operations Services | When the commission and incentive ORs of an insurer settlement are issued: DISBURSEMENT_APPROVAL = once Disbursement approves the payment request, REMITTANCE_APPROVAL = at the approval of the remittance batch (Appendix R, C12) | string | DISBURSEMENT_APPROVAL |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_UNAPPLIED_MARKETING_SCOPE | Operations | Operations | Drop 1 | Head, Operations Services | What a Marketing user sees in the list of unapplied payments: OWN_UNIT = the records of his or her marketing unit, ALL = every record (Appendix R, C13) | string | OWN_UNIT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CMR_DP_COLLECTION_BANK | Operations | Operations | Drop 1 | Head, Operations Services | GL bank account proposed for direct payment commission collections (role BANK of OPS_DP_COMMISSION_COLLECT) | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CMR_FEEDBACK_WORKING_DAYS | Operations | Operations | Drop 1 | Head, Operations Services | Working days an insurer has to answer a direct payment commission billing | integer | 10 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CWT_APPLICATION_PERCENT | Operations | Operations | Drop 1 | Head, Operations Services | Share of the premium applied for accounts of clients withholding 2% creditable tax | decimal | 98 | 50 to 100 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DP_PREMIUM_TOLERANCE | Operations | Operations | Drop 1 | Head, Operations Services | Largest difference between the premium of a direct payment list and the booked gross premium that still passes the check | decimal | 1.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DP_PR_REVERSAL_POSTING | Operations | Operations | Drop 1 | Head, Operations Services | Post the GL entry of the direct payment PR reversal and reinstatement (OPS_DP_PR_REVERSAL / OPS_DP_REINSTATE). Off while booking posts no premium receivable for direct payment invoices; the ledger reversal is always recorded | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
JOB_HISTORY_DAYS | Operations | Operations | Drop 1 | Head, Operations Services | Days of scheduled job history shown in the job monitor | integer | 90 | 1 to 3650 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIN_BALANCE_AUTO_MAX | Operations | Operations | Drop 1 | Head, Operations Services | Minimal balances up to this amount are reversed automatically | decimal | 10.00 | 0 to 1000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIN_BALANCE_FILE_RANGE | Operations | Operations | Drop 1 | Head, Operations Services | Balance range of the minimal balance write-off file | string | 10.00-100.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_BOOK_RATE_TYPE | Operations | Operations | Drop 1 | Head, Operations Services | Exchange rate type of Operations postings: the Comptrollership BOOK rate, 2 decimals | string | BOOK |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PRODRECON_FILE_PATTERN | Operations | Operations | Drop 1 | Head, Operations Services | File naming convention of the production register sent to insurers | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RECON_MATCH_KEYS | Operations | Operations | Drop 1 | Head, Operations Services | Keys pairing an insurer production line with a booked invoice, tried in order: INVOICE_NO, POLICY_NO, PN_NO | code list | INVOICE_NO,POLICY_NO |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RECON_TOLERANCE | Operations | Operations | Drop 1 | Head, Operations Services | Production reconciliation tolerance: differences up to this amount are matched | decimal | 1.00 | 0 to 1000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_CHECK_HOLD_DAYS | Operations | Operations | Drop 1 | Head, Operations Services | Banking days a check must be held (and cleared) before its payment is remitted | integer | 3 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_FILE_PATTERN | Operations | Operations | Drop 1 | Head, Operations Services | File naming convention of the remittance extracts | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_PAIDAR_OVER_DTIP_MODE | Operations | Operations | Drop 1 | Head, Operations Services | Paid AR greater than DTIP: EXCLUDE the invoice from extraction or CAP the remittance at the DTIP | string | EXCLUDE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RESERVES_AUTO_RUN_COMPANIES | Operations | Operations | Drop 1 | Head, Operations Services | Company codes for which the monthly reserve valuation job prepares a run (blank = none) | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
HOLD_COVER_ALERT_DAYS | Placement | New Business | Drop 1 | Product Owner, BDOI (New Business) | Days before a hold cover expires when Processing is alerted | integer | 5 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
HOLD_COVER_DAYS | Placement | New Business | Drop 1 | Product Owner, BDOI (New Business) | Days of hold cover requested from the insurer while the placement completes | integer | 30 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OTHER_CHARGES_ENABLED | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Bill the other charges of the products (documentation, notarial and authentication fees) with the premium | boolean | false |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_ANNIVERSARY_NOTICE_DAYS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Days before the package anniversary date at which the anniversary notice is raised | integer | 90 | 1 to 365 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_EXPIRY_NOTICE_DAYS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Days before the package end date at which PACKAGE_EXPIRING is first raised; again at 30 and 7 days | integer | 90 | 1 to 365 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_EXPIRY_NOTIFY_MBS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | false: the expiry and anniversary notices go to the TSU Officers and TSU Team Leads (the bank's process); true: MBS is told as well | boolean | false |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_EXPIRY_REMINDER_DAYS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Days before the package end date at which PACKAGE_EXPIRING is raised again after the first notice | integer list | 30,7 |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_RENEWAL_AUTODRAFT | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | The expiry monitor drafts a RENEW package request for packages reaching the notice period | boolean | false |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_ADVISORY_GROUPS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Recipient groups (list PKG_ADVISORY_GROUP) proposed on a new package advisory | code list | MARKETING,TSU,MBS,OPERATIONS |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_DEACTIVATION_PREFIX | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Prefix of package deactivation request numbers; the year is appended | string | PKD- |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_DEPLOYMENT_PREFIX | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Prefix of package deployment request numbers; the year is appended | string | PDR- |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_MIN_POLICIES | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Least estimated number of policies of a package request | integer | 20 | 0 to 100000 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_MIN_PREMIUM | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Least estimated total basic premium of a package request (base currency) | decimal | 5000000 | 0 to - | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_QS_PREFIX | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Prefix of package quotation slip numbers; the year is appended | string | PQS- |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_QS_REPLY_DAYS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Days insurers have to reply to a package quotation slip | integer | 5 | 1 to 60 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_REQUEST_PREFIX | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Prefix of package request numbers; the year is appended | string | PKR- |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MANCOM | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the ManCom sign-off | integer | 72 | 1 to 720 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MBS_SETUP | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the MBS package set-up | integer | 48 | 1 to 720 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MKT_APPROVAL | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the Marketing approval of a package request | integer | 24 | 1 to 720 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_NEGOTIATION | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the insurer negotiation stage | integer | 120 | 1 to 2160 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_TSU_APPROVAL | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the TSU Team Head approval | integer | 24 | 1 to 720 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_TSU_REVIEW | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SLA hours of the TSU Team Lead review and recommendation | integer | 24 | 1 to 720 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PLACEMENT_UPDATE_DAY | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Weekday of the scheduled Consolidated Placement Update Report (MONDAY to SUNDAY) | string | THURSDAY |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PLACEMENT_UPDATE_DAYS | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Length of the reporting period of the Consolidated Placement Update Report in days, ending on the report date | integer | 7 | 1 to 92 | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PLACEMENT_UPDATE_SCOPE | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | QUOTATION: the report lists the quotation requests (the bank's process); QUOTATION_AND_PACKAGE: the package requests follow | string | QUOTATION |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PLACEMENT_UPDATE_TIME | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Time of the scheduled Consolidated Placement Update Report (HH:MM, business time zone) | string | 08:00 |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_DEACTIVATION_ROUTE | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | EFFECTIVE_DATED: Deactivate Package asks for the effective date, reason and approver (the bank's process); RETIRE_REQUEST: deactivation through a retirement package request | string | EFFECTIVE_DATED |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_DEPLOYMENT_REQUEST | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | AUTO: the ManCom approval forwards the package to MBS; MANUAL: the Request for Deployment button forwards it (the bank's process) | string | AUTO |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_DIRECT_MAINTENANCE | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | true: authorized users add and update Product Matrix records directly with approval (the bank's process); false: new packages come only from package requests | boolean | true |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_MANCOM_PRESIDENT | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | User ID of the President, who approves after every other selected ManCom approver | string | (blank) |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_MANCOM_ROUTING | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | SELECTED_PARALLEL_THEN_PRESIDENT: the selected ManCom approvers approve in parallel, then the President (the bank's process); ANY_MEMBER: one sign-off | string | SELECTED_PARALLEL_THEN_PRESIDENT |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PM_MARKETING_CHAIN | Product Maintenance | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | ANY_ONE: one approval by the Marketing Team Leader, Team Head or Unit Head; TL_TH_UH: approval by the Team Leader, then the Team Head, then the Unit Head (the bank's process) | string | ANY_ONE |  | Template | BRD-03 template CI-09, sheet PM-09 Lists and parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_AUTO_ASSIGN_PROCESSING | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Renewal accounts routed to Processing are assigned automatically to a Processing Officer (fewest open accounts first, then in turn) | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_AUTO_ASSIGN_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments whose renewal accounts are assigned automatically to an Account Officer of the team after the classification (* for every segment; none: the Team Leader assigns) | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_AUTO_PLACEMENT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Generate the placement slip automatically once an accepted renewal is ready for placement (off: Processing places the renewal account) | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_AUTO_PROMO_RISK_CODES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Risk codes of the Auto Promo (first year free) motor policies | code list | MTR70,MTR71,MTR72,MTR73 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_BOOK_ON_PLACEMENT_APPROVAL | Renewal | Renewal | Drop 1 | Product Owner, Renewal | The insurer's approval of the placement books and locks the renewal account (true), or leaves it For Booking for the Processing Officer to book (false) | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_BULK_INITIATION_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments whose renewals may be initiated in bulk; the others one at a time | code list | CLG |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_MOTOR_AUTO_UPDATE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | CBG Motor renewal accounts take the automatic values: depreciated sum insured, BI and PD limits stepped down, Auto Promo renewed as Regular | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_MOTOR_BI_TIERS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Bodily injury limits and their premiums (limit:premium) for the step-down of a CBG Motor renewal | string | 50000:115.00,100000:240.00,150000:310.00,200000:375.00,250000:430.00,300000:495.00,500000:650.00,750000:890.00,1000000:1100.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_MOTOR_PD_TIERS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Property damage limits and their premiums (limit:premium) for the step-down of a CBG Motor renewal | string | 50000:150.00,100000:300.00,150000:400.00,200000:480.00,250000:520.00,300000:560.00,500000:720.00,750000:950.00,1000000:1150.00 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments on the loan-driven straight-through path (no assignment to an AO) | code list | CBG |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_STP_LINES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Product lines of the straight-through path of those segments | code list | MOTOR,PROPERTY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CCM_CLIENT_ID | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Client identifier of the application at CCM | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CCM_ENDPOINT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Address of the CCM interface (given by the IT team of the bank) | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CCM_KEY_SETTING | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Name of the environment setting that holds the CCM access key (kept by BDOI IT, never shown in BIBS) | string | BROKERVERSE_CCM_API_KEY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CCM_MODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Connection of CCM: LIVE (the CCM interface at the address below) or SIMULATOR (the CCM simulator of SIT and UAT) | string | SIMULATOR |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CCM_TIMEOUT_SECONDS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Time limit of a CCM call in seconds | integer | 30 | 5 to 300 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CHANNEL_MAX_ATTEMPTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Attempts of the transmission of a message before it is Failed | integer | 3 | 1 to 10 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CHANNEL_SIMULATOR_OUTAGE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Channels the simulator reports unavailable (CCM, MFT), to test an outage in SIT and UAT | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CLEAN_AUTO_RENEWAL | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Clean renewal accounts are disposed For Renewal automatically and posted (true), or wait for the disposition of Marketing (false) | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CLPC_BILLING_DAYS_BEFORE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry at which the daily billing job puts a CBG Home account For Billing Generation in the CLPC billing file | integer | 10 | 0 to 120 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CLPC_BILLING_RECIPIENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Recipients of the CLPC billing files, separated by commas | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CLPC_FFY_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days of the month on which the billing job puts the FFY Motor accounts For Billing Generation in the CLPC billing file | code list | 10,25 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CORPORATE_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments budgeted by team and sub-team (Corporate); the others are budgeted by region | code list | CORBANK,COMBANK |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CTPL_RISK_CODES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Risk codes of the compulsory third party liability policies (renewed at their expiring values) | code list | CTP01 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_DELIVERY_CHANNEL | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Channel of the client documents (Renewal Advice, letters, proposals, Insurance Advice, e-policies): CCM, or EMAIL (protected e-mail with the password in a separate e-mail) | string | CCM |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_DISPOSITION_SET | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Dispositions offered to Marketing: SYSTEM (For Renewal, Not for Renewal, For Quotation, For Proposal, Lost Business) or CLIENT (the first four, Lost Business being a reason of Not for Renewal) | string | SYSTEM |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_DUPLICATE_CRITERIA | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Duplicate criteria per product line (LINE:CRITERIA+CRITERIA; * for every line) among CLIENT, RISK_CODE, PN and EXPIRING_POLICY | string | *:EXPIRING_POLICY+PN |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_DUPLICATE_MIN_MATCH | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Number of the duplicate criteria that must match for a potential duplicate (all of them is an exact duplicate) | integer | 1 | 1 to 4 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_ENDORSEMENT_ROUTE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Endorsements of the expiring term: ANY (every endorsement routes the renewal account to Review) or IN_PROGRESS (only an endorsement in progress) | string | ANY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_ESCALATION_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days to expiry at which an account not disposed or not accepted is at risk, per segment (* = others) | string | IBG=60,LEASING=60,*=30 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXCEPTION_AGEING_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Working days a renewal may stay in the Exception bucket before its stage owner is alerted | integer | 5 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXCLUDED_LINES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Product lines never extracted for renewal (renewed as Employee Benefits programmes) | code list | HMO,GLI,GPA |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXTRACTION_LEAD_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry at which the daily extraction takes a policy | integer | 140 | 1 to 400 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXTRACTION_LEAD_DAYS_BY_SEGMENT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Lead days per market segment, e.g. CBG=150,IBG=120; empty = the general lead days | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_FILE_NAMES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Names of the generated files: CLIENT (<Product>_RA_<Notice>_<Reference>_MMDDYYYY.pdf, <Product>_<Letter>_<Reference>_MMDDYYYY.pdf) or SYSTEM (the letter number) | string | CLIENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_FIN_IMPACT_TOLERANCE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Difference in premium, sum insured or rate above which a renewal has a financial impact | decimal | 0.00 | 0 to - | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_AUTO_NON_CBG | Renewal | Renewal | Drop 1 | Product Owner, Renewal | The hold cover of a Non-CBG renewal account is requested automatically once the client confirms the renewal, one request per insurer | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_CBG_DAYS_BEFORE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry at which the hold cover of the Clean CBG renewal accounts is requested, one file per insurer | integer | 75 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_CBG_HOME_EXTENSION | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days of the monthly hold cover extension of the CBG Home accounts | integer | 30 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_CBG_HOME_EXTENSION_DAY | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Day of the month on which the expired and unbooked CBG Home accounts receive a hold cover extension | integer | 15 | 1 to 28 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Durations in days offered for the hold cover of a renewal; the first is the default | integer list | 30,60 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_DAYS_CBG | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Default duration of the hold cover of a CBG renewal account, in days | integer | 90 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_DAYS_CBG_HOME_TRANSFER | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Duration of the hold cover of a CBG Home account moved to another insurer after a rejection, in days | integer | 30 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_DAYS_CBG_MOTOR_TRANSFER | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Duration of the hold cover of a CBG Motor account moved to another insurer after a rejection, in days | integer | 60 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_DAYS_NON_CBG | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Default duration of the hold cover of a Non-CBG renewal account, in days | integer | 30 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_EXPIRING_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | KPI card Expiring Hold Cover: confirmed hold covers ending within this number of days | integer | 7 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_EXTENSION_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Durations offered for the extension of a hold cover, in days | integer list | 15,30 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_HOLD_COVER_EXTENSION_WINDOW | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before the end of a hold cover from which its extension can be requested | integer | 7 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_INSURANCE_ADVICE_AUTO | Renewal | Renewal | Drop 1 | Product Owner, Renewal | The Insurance Advice of a mortgaged renewal account is generated when its placement is sent to the insurer, and again when the placement changes | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_INSURER_REPLY_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days the insurer has to answer a renewal batch | integer | 10 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_INVOICE_NO_REASONS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Reasons for Not for Renewal that need the number of the new invoice | code list | BOOKED_TO_NEW_INVOICE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_KYC_CLIENT_TYPES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Clients monitored for KYC review: BANK (bank clients), NON_BANK (other clients) | code list | BANK,NON_BANK |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_KYC_PRODUCTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Products whose accounts are monitored for KYC review; blank for every product | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_KYC_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments where the KYC due flag applies; empty = all | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_KYC_UPCOMING_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days ahead in which a KYC review date makes the account KYC Upcoming (inside the KYC due window it is KYC Due) | integer | 60 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_LAMD_MOTOR_PRODUCTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Words of the LAMD product description of a motor loan: its serial and motor numbers are required and matched | code list | AUTO,MOTOR,CAR |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_LMS_MODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Upload of the billing files to the shared LMS directory: LIVE (the directory of the LMS interface), SIMULATOR (test environments) or OFF | string | SIMULATOR |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_LOCK_POINT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | When Marketing can no longer change a renewal account: RA_GENERATION (when the Renewal Advice is generated) or PLACEMENT (once posted and the placement is sent) | string | RA_GENERATION |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MANUAL_INCEPTION_OFFSET_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | A renewal account created by hand starts this number of days after the expiry of the expiring account and runs one year | integer | 1 | 0 to 31 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_COMPANY_CODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Company that receives the files of the Renewal MFT inbox (company code); blank = the first company | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_ENDPOINT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Address of the MFT server (given by the IT team of the bank) | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_ENROLLED_INSURERS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Insurers enrolled in MFT: their hold cover requests, placement files and e-policies go through MFT, the others by e-mail | code list | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_INBOUND_FOLDER | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Folder of the files received from the insurers on MFT | string | /inbound |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_KEY_SETTING | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Name of the environment setting that holds the MFT access key (kept by BDOI IT, never shown in BIBS) | string | BROKERVERSE_MFT_KEY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_MODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Connection of MFT: LIVE (the MFT server below) or SIMULATOR (the MFT simulator of SIT and UAT) | string | SIMULATOR |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_MFT_OUTBOUND_FOLDER | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Folder of the files sent to the insurers on MFT | string | /outbound |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NAL_OFFSET_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after the effective expiry date of the No Advice Letter | integer | 1 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NAL_REASONS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Reasons for Not for Renewal answered with a No Advice Letter instead of a Not for Renewal Letter | code list | DIRECT_TO_INSURER,WITH_SUBMITTED_POLICY,BOOKED_TO_NEW_INVOICE,UNIT_SOLD,CANCELED_POLICY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NON_ACCEPTANCE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after expiry of the non-acceptance letter and the closure of unrenewed accounts | integer | 0 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NRL_OFFSET_DAYS_CBG | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after the effective expiry date of the Non-Renewal Letter of a CBG Motor account | integer | 1 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NRL_OFFSET_DAYS_NON_CBG | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after the effective expiry date of the Non-Renewal Letter of a Non-CBG account | integer | 3 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NRNS_REMINDER_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry of the reminder to renewals not yet submitted (NRNS) | integer | 90 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NRNS_WAITING_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after the effective expiry date before an unrenewed renewal is tagged NRNS, per segment | string | CBG=0,*=0 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_OUTSTANDING_THRESHOLD | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Open premium of the expiring invoice family above which the renewal is flagged Outstanding | decimal | 0.00 | 0 to - | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PASSWORD_CONVENTION | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Password of protected files: CLIENT (individual: first three letters of the first and last names in capitals; corporate: eight random characters) or GENERATED (a random password per file) | string | CLIENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PIPELINE_NB_STAGES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Pipeline Summary: the New Business account statuses counted in each stage | string | FOR_SURVEY:DRAFT¦RETURNED_TO_MARKETING;FOR_PROPOSAL:SUBMITTED;FOR_CONFIRM:AWAITING_PAYMENT;FOR_BOOKING:READY_FOR_PLACEMENT¦PLACED¦RETURNED_BY_INSURER¦POLICY_ISSUED;FOR_DELIVERY:BOOKED |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PIPELINE_STAGES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Pipeline Summary: the renewal statuses counted in each stage (For Survey, For Proposal, For Confirm, For Booking, For Delivery) | string | FOR_SURVEY:EXTRACTED¦EVALUATING¦UNASSIGNED¦TRANSFER_PENDING¦FOR_DISPOSITION;FOR_PROPOSAL:FOR_TL_REVIEW¦NB_PATH¦FOR_PROCESSING¦IN_PROCESSING¦WITH_INSURER;FOR_CONFIRM:RA_READY¦RA_GENERATED¦RA_SENT¦ACCEPTED;FOR_BOOKING:FOR_PLACEMENT_BOOKING;FOR_DELIVERY:RENEWED |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PLACEMENT_CUTOFF_HOUR | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Hour of the day after which a placement sent to the insurer counts from the next business day | integer | 15 | 0 to 23 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PLACEMENT_SLA_NON_PACKAGE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Target turnaround of the insurer's placement response for a non-package account, in business days | integer | 10 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PLACEMENT_SLA_PACKAGED | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Target turnaround of the insurer's placement response for a packaged account, in business days | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PLACEMENT_TAT_NON_PACKAGE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Placement turnaround time of non-package accounts in business days | integer | 10 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PLACEMENT_TAT_PACKAGED_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Placement turnaround time of packaged accounts in business days | integer | 3 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PN_REQUIRED_LINES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Product lines whose mortgaged or straight-through renewals need the PN number | code list | MOTOR,PROPERTY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_POSTING_APPROVER | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Approver of a submission for posting: REQUIRED (the officer picks the approver), OPTIONAL (the officer may pick one, else every Team Leader of the unit) or NONE | string | OPTIONAL |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PRIORITY_SEGMENTS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Market segments of the priority portfolio named in the attention flags of the renewal listing | code list | IBG,LEASING |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROCESSING_SCOPE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Renewals a Processing Officer may open: ALL (every renewal of the company; his worklist shows the renewals assigned to him) or ASSIGNED (only the renewals assigned to him); the Processing Team Lead always sees all | string | ALL |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROMO_RATE_MAP | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Regular premium rate (percent) of each Auto Promo premium rate | string | 2.4230=2.3760,1.9450=1.6060,2.0400=1.9630,3.0000=3.0000 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROMO_RISK_CODE_MAP | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Regular risk code of each Auto Promo risk code | string | MTR70=MTR22,MTR71=MTR23,MTR72=MTR25,MTR73=MTR73 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROMO_TO_REGULAR | Renewal | Renewal | Drop 1 | Product Owner, Renewal | An Auto Promo motor policy renews as a Regular policy with the risk code and rate of the maps | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROPOSAL_LINES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Product lines whose Clean renewal accounts are disposed For Proposal (personal accident and group personal accident) | code list | PERSONAL_ACCIDENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PROPOSAL_THREE_SIGNATORIES_TSI | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Total sum insured above which a Full Proposal of a non-package account needs three signatories instead of two | decimal | 500000000 | 0 to - | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_FIRST_NOTICE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry of the Renewal Advice First Notice | integer | 75 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_LAST_NOTICE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days before expiry of the Renewal Advice Last Notice | integer | 45 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_MIN_NOTICE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | A Renewal Advice generated fewer days than this before expiry needs a confirmation | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_NOTICE_MODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Renewal Advice notice: AUTOMATIC (First Notice from 75 days, Last Notice from 45 days before expiry) or MANUAL (the user chooses) | string | AUTOMATIC |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_SECOND_NOTICE_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after the first notice without acceptance before a second notice is offered | integer | 15 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_REFERENCE_PREFIX | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Prefix of the renewal reference (prefix-yyyy-nnnnnn) | string | RNW |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_REOPEN_DAYS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Days after expiry during which a Not for Renewal account can be re-opened | integer | 30 | 0 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RISK_CODE_REASON | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Reason recorded when an account is Not for Renewal because of its risk code: SYSTEM (Non-renewable Accounts) or CLIENT (Non-Renewable Risk Code) | string | SYSTEM |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RMU_UNIT | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Sales unit that receives RMU accounts; empty = tag them Not for Renewal | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_SECOND_APPROVAL | Renewal | Renewal | Drop 1 | Product Owner, Renewal | An accepted renewal account is Submitted for Approval and goes to placement only once an approver approves it (true), or goes to the payment gate and placement at once (false) | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_STATUS_NAMES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Names of the renewal statuses on the dashboards and lists: CLIENT (In Process Renewal, Submitted for Posting, Posted ...) or SYSTEM (the workflow stage names) | string | CLIENT |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_STP_SKIP_TL_REVIEW | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Automatic dispositions of the decision matrix skip the Team Leader review | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_THIRD_BUCKET | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Third panel of the renewal accounts: NON_RENEWABLE (Clean, Review, Non-Renewable and All; Exception accounts under Review) or EXCEPTION (Clean, Review, Exception and All) | string | NON_RENEWABLE |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_TOP_DEALS_OPTIONS | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Biggest Open Deals: the sizes of the ranking a user can choose | integer list | 50,75,100 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_TOTAL_LOSS_SETTLEMENT_TYPES | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Claim settlement types of a total loss: the renewal account is Not for Renewal with the reason Total Loss Claim | code list | SETTLED_TOTAL_LOSS |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_TRANSFER_MODE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Transfer to another Marketing unit: TRANSFER (the renewal account moves to the unit), REFERRAL (the unit opens a New Business account, the renewal keeps its owner) or BOTH | string | BOTH |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_TSI_ABOVE_ROUTE | Renewal | Renewal | Drop 1 | Product Owner, Renewal | Total sum insured above the threshold: QUOTATION (Clean with For Quotation, to the TSU) or REVIEW (Review with a proposal for the TSU) | string | QUOTATION |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
AGEING_BUCKETS | Reporting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Default ageing slots in days (up to 5 ascending limits) of the debtors and creditors ageing reports; users may override them per run | integer list | 30,60,90,120 | 1 to 3650 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EXPORT_FILE_NAMES_BDOI | Reporting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | true: the exported audit logs, user access reports and Product Maintenance files are named <name>_MMDDYYYY with the extraction date, for example Audit Logs_10092026.xlsx (the bank's process); false: they are named by the report code | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REPORT_FOOTER_TEXT | Reporting | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Footer text printed on exported reports | string | Confidential - for internal use only. |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_BLOCK_ON_OPEN_MATCH | Screening | Sanction Screening | Drop 1 | Compliance | When true, account submission and placement are refused while the client has an open true or potential match | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_CASE_SEQUENCE_PREFIX | Screening | Sanction Screening | Drop 1 | Compliance | Prefix of the screening case number <prefix>-yyyy-nnnnnn | string | SCR |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_COMMITTEE_RULE | Screening | Sanction Screening | Drop 1 | Compliance | How the AML Committee decides: ANY, MAJORITY or ALL of SCR_COMMITTEE_SIZE members | string | MAJORITY |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_COMMITTEE_SIZE | Screening | Sanction Screening | Drop 1 | Compliance | Members of the AML Committee counted by the MAJORITY / ALL rule | integer | 5 | 1 to 20 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_FULL_RESCREEN_DAY | Screening | Sanction Screening | Drop 1 | Compliance | Day of the month of the full rescreen of the in-scope clients; other days screen the list changes only | integer | 1 | 1 to 28 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_INGEST_ALERT_RECIPIENTS | Screening | Sanction Screening | Drop 1 | Compliance | Comma separated e-mail addresses that receive the digest of failed watchlist records | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_SCREENING_SCOPE | Screening | Sanction Screening | Drop 1 | Compliance | Client statuses screened by the periodic run | code list | PROSPECT,CONFIRMED |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_ALLOWED_NETWORKS | Security | Security settings | Drop 0 | BDOI Information Security | Company networks accepted when the device restriction is ON: addresses or CIDR ranges separated by commas, e.g. 10.20.0.0/16 | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_DEVICE_HEADER | Security | Security settings | Drop 0 | BDOI Information Security | Header the device-management gateway adds for a company-issued device, e.g. X-Managed-Device; blank = networks only | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_DEVICE_HEADER_VALUE | Security | Security settings | Drop 0 | BDOI Information Security | Value of the device header; blank = the header alone is enough | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_DEVICE_RESTRICTION | Security | Security settings | Drop 0 | BDOI Information Security | ON = the system is used only from company-issued devices (company networks or the header of the device-management gateway); OFF = any device | string | OFF |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_TOKEN_MINUTES | Security | Security settings | Drop 0 | BDOI Information Security | Minutes an access token is valid; the web client renews it while the session is in use | integer | 15 | 5 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
AUTH_MODE | Security | Security settings | Drop 0 | BDOI Information Security | Sign-in mode: LOCAL (BIBS passwords) or DIRECTORY (BDO directory sign-in by Windows ID, when the EIAM sign-in is specified) | string | LOCAL |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BREAK_GLASS_ALERT_RECIPIENTS | Security | Security settings | Drop 0 | BDOI Information Security | E-mail addresses of Information Security, separated by commas, alerted at every break-glass sign-in while single sign-on is on (the security-setting approvers are also told in the system) | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
FILE_LINK_TTL_SECONDS | Security | Security settings | Drop 0 | BDOI Information Security | Seconds a presigned file download or upload link stays valid | integer | 300 | 30 to 3600 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
JOB_FAILURE_RECIPIENTS | Security | Security settings | Drop 0 | BDOI Information Security | Comma separated e-mail addresses told of every failed batch job | string | (blank) |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
LOGIN_MAX_FAILED_ATTEMPTS | Security | Security settings | Drop 0 | BDOI Information Security | Consecutive failed logins that lock a user account; applies to all users | integer | 3 | 1 to 10 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_ISSUER_NAME | Security | Security settings | Drop 0 | BDOI Information Security | Name of the system shown next to the account in the authenticator app (blank = the system name of the deployment) | string | (blank) |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_POLICY | Security | Security settings | Drop 0 | BDOI Information Security | Who must confirm a sign-in with an authenticator app code: ALL users, PRIVILEGED users (a role of privilege level HIGH or ADMIN) or OFF (only users who enrolled themselves) | string | PRIVILEGED |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_REMEMBER_DEVICE_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days a device may be remembered after a code is confirmed, so the code is not asked again on it; 0 = never remembered | integer | 0 | 0 to 30 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_EXPIRY_NOTICE_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days before a password expires from which the user is told to change it (LOCAL mode) | integer | 7 | 1 to 90 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_HISTORY_COUNT | Security | Security settings | Drop 0 | BDOI Information Security | Previous passwords a local account may not reuse (at least the last ten) | integer | 10 | 0 to 24 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_MAX_AGE_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days after which a password must be changed, LOCAL mode; 0 = never | integer | 90 | 0 to 365 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_MIN_AGE_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days before a changed password may be changed again, LOCAL mode | integer | 1 | 0 to 30 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_RESET_BDOI_RULES | Security | Security settings | Drop 0 | BDOI Information Security | true: no forgotten-password link on the Login page, and a password is reset only by another System Administrator, with single sign-on only for the break-glass accounts (the bank's process); false: the self-service reset link for local accounts and the administrator reset of any local account | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_BDOI_DIALOG | Security | Security settings | Drop 0 | BDOI Information Security | true: the inactivity warning reads "You have been inactive for x minutes ... stay logged in or log out?" with the buttons Stay Logged In and Log Out (the bank's process); false: the earlier wording with Stay Signed In and Sign Out Now | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_EXPIRY_WARNING_MINUTES | Security | Security settings | Drop 0 | BDOI Information Security | Minutes before the system-triggered (absolute) sign-out at which the web client warns the user | integer | 30 | 1 to 240 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_IDLE_WARNING_MINUTES | Security | Security settings | Drop 0 | BDOI Information Security | Minutes of inactivity after which the web client warns that the session will sign out | integer | 15 | 1 to 480 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_TIMEOUT_MINUTES | Security | Security settings | Drop 0 | BDOI Information Security | Minutes of inactivity after which the web session signs out automatically | integer | 30 | 5 to 480 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_TIMEOUT_PAGE | Security | Security settings | Drop 0 | BDOI Information Security | true: after the inactivity sign-out the page "Your session timed out. Please log in again to continue" with the Log In button (the bank's process); false: a message on the Login page | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_ANY_APPROVER | Security | Security settings | Drop 0 | BDOI Information Security | When true, any holder of ACCESS_APPROVE may decide a request, not only the approver chosen by the requester | boolean | false |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DIRECT_ROLE_EDIT | Security | Security settings | Drop 0 | BDOI Information Security | Emergency path: when true, the System Administrator may create and edit roles directly on the Roles screen (audited, alert UAM_DIRECT_ROLE_EDIT); when false, a role changes only by implementing an approved group-profile request | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DORMANT_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days without a sign-in after which a user is deactivated by the daily dormant-user job; 0 = never | integer | 90 | 0 to 730 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DORMANT_NOTICE_DAYS | Security | Security settings | Drop 0 | BDOI Information Security | Days before the dormant-user deactivation on which the user is told to sign in; 0 = no notice | integer | 7 | 0 to 60 | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_EXTERNAL_USERS | Security | Security settings | Drop 0 | BDOI Information Security | When true, access requests may be raised for external (portal) users; stays false while no portal is installed | boolean | false |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_PROVISIONING_ROLES | Security | Security settings | Drop 0 | BDOI Information Security | true: the group profiles named in a UIDM-ISC event are given to the user; false: group profiles only through approved requests in the system | boolean | false |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_REQUEST_NOTICE_EMAIL | Security | Security settings | Drop 0 | BDOI Information Security | true: the notices of access requests are also e-mailed to each user who chose e-mail in the notification preferences (the bank's process); false: in the system only | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_ROLE_APPLY_ON_APPROVAL | Security | Security settings | Drop 0 | BDOI Information Security | When true, an approved group-profile or role-permission request applies at its last approval; when false it waits for the System Administrator to implement it | boolean | false |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_SSO_PROVISIONING | Security | Security settings | Drop 0 | BDOI Information Security | true: users are created, updated, deactivated and reactivated from the Enterprise SSO / UIDM-ISC events and from an active Enterprise SSO account (the bank's process); false: only through approved access requests | boolean | true |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_WORKING_HOURS | Security | Security settings | Drop 0 | BDOI Information Security | Working hours; an access request submitted outside them needs a second approval | string | 08:00-18:00,MON-FRI |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
USER_ID_FORMAT_TEXT | Security | Security settings | Drop 0 | BDOI Information Security | The user ID format in words, shown to the requester with the format check of USER_ID_PATTERN | string | a letter followed by nine digits, for example a013000196 |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
USER_ID_PATTERN | Security | Security settings | Drop 0 | BDOI Information Security | Regular expression of a new user ID on enrolment requests | string | ^[a-zA-Z][0-9]{9}$ |  | Template | BRD-11 template CI-05, sheet UA-05 Parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_HOLD_COVER_UNBOOKED_ALERT_DAYS | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Days before a confirmed hold cover ends at which a renewal account not yet booked is alerted | integer | 5 | 0 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_INSURER_ACCEPT_DAYS | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Days the assigned insurer has to accept the hold cover of a submitted policy renewal before the handler is alerted | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_MANUAL_RENEWAL_SEGMENTS | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Segments whose renewal the Account Officer starts by hand with Renew with BDOI; the expiry scan leaves them out | code list | NONCBG_RETAIL |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_MASTERLIST_DAYS_FROM_EXTRACTION | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Target days from the extraction of a CBG Motor policy to its masterlist record | integer | 30 | 1 to 365 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_NUMBER_PREFIX | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Prefix of the masterlist number (prefix-yyyy-nnnnnn) | string | SBM |  | Template | This workbook, sheet Ref Document numbering | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_OWN_RECORDS_ROLES | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Roles whose users see only the submitted policies they handle or whose renewal they own, unless a user scope says otherwise | code list | MKT_AO |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_RENEWAL_LEAD_DAYS | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Days before expiry at which a submitted policy for renewal is handed to Renewal, per segment (* = other segments) | string | CBG_FIRE=150,CBG_MOTOR=120,*=90 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_REVIEW_SLA_DAYS | Submitted | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Days an IAAF or TOR approval level may wait before it is alerted | integer | 5 | 1 to 60 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
IC_RBC_HURDLE_PERCENT | Tax | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Minimum risk-based capital ratio (percent) required by the Insurance Commission; the IC-RBC summary flags a shortfall | integer | 100 | 1 to 1000 | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_FBT_GROSSUP_RATE | Tax | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Gross-up of the monetary value of fringe benefits in percent (100 / 65) used by the 1603 worksheet | decimal | 153.8462 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_FBT_RATE | Tax | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Fringe benefit tax rate in percent used by the 1603 worksheet | decimal | 35 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_RCIT_RATE | Tax | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | Regular corporate income tax rate in percent used by the 1702-Q / 1702 worksheets | decimal | 25 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_RDO_CODE | Tax | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | BIR Revenue District Office code of the withholding agent, printed on the SLS/SLP/QAP exports | string | 050 |  | Template | This workbook, sheet Ref System parameters | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
Note on A4: Parameter: Parameter on System Parameters
Note on B4: Group: Group of the parameter
Note on C4: Module: Module
Note on D4: Drop: Drop
Note on E4: Owner (BDOI unit): Unit that decides the value
Note on F4: What it controls: Meaning of the parameter
Note on G4: Type: Kind of value
Note on H4: Value proposed: Value proposed with the platform
Note on I4: Allowed range: Minimum and maximum
Note on J4: Route: Template: the value is given here or in the named template
Note on K4: Prepared in: Where the value wanted is given
Note on L4: Due: Due date
Note on M4: Value wanted: Value BDOI wants
Note on N4: Reason: Policy reference or reason of a change
Note on O4: Approved by: BDOI approver of the value
Note on P4: Status: Status of the row
Note on Q4: BDOI comments: Decision, value or comment of the owner

## Ref Document numbering
Reference: Document numbering
← Back to Start here | Prefixes of the numbered documents; receipt series come from object R11, check numbers from D0-12
Parameter | Module | Numbered document | Prefix proposed | Prepared in | Owner (BDOI unit) | Prefix wanted | Status | BDOI comments
PROPOSAL_NUMBER_PREFIX | New Business | Prefix of the PRF marketing reference (<prefix>-<yyyy>-nnnnnn) | PRF | This workbook, sheet Ref Document numbering | Product Owner, BDOI (New Business) |  | Not started
PROPOSAL_SLIP_PREFIX | New Business | Prefix of proposal slip numbers (<prefix>-<yyyy>-nnnnnn) | PS | This workbook, sheet Ref Document numbering | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_NUMBER_PREFIX | New Business | Prefix of package quotation numbers (<prefix>-<yyyy>-nnnnnn), shown as Proposal No. | QT | This workbook, sheet Ref Document numbering | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_REQUEST_PREFIX | New Business | Prefix of quotation request numbers (<prefix>-<yyyy>-nnnnnn) | REQ | This workbook, sheet Ref Document numbering | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_SLIP_PREFIX | New Business | Prefix of quotation slip numbers (<prefix>-<yyyy>-nnnnnn) | QS | This workbook, sheet Ref Document numbering | Product Owner, BDOI (New Business) |  | Not started
MIG_INVOICE_NO_COLLISION_PREFIX | Data Migration | Prefix the source system to a legacy invoice number found in two source systems | true | This workbook, sheet Ref Document numbering | Program Manager, Business Project Services (Data Migration) |  | Not started
PKG_DEACTIVATION_PREFIX | Product Maintenance | Prefix of package deactivation request numbers; the year is appended | PKD- | BRD-03 template CI-09, sheet PM-09 Lists and parameters | Product Owner, Marketing Business System (MBS) |  | Not started
PKG_DEPLOYMENT_PREFIX | Product Maintenance | Prefix of package deployment request numbers; the year is appended | PDR- | BRD-03 template CI-09, sheet PM-09 Lists and parameters | Product Owner, Marketing Business System (MBS) |  | Not started
PKG_QS_PREFIX | Product Maintenance | Prefix of package quotation slip numbers; the year is appended | PQS- | BRD-03 template CI-09, sheet PM-09 Lists and parameters | Product Owner, Marketing Business System (MBS) |  | Not started
PKG_REQUEST_PREFIX | Product Maintenance | Prefix of package request numbers; the year is appended | PKR- | BRD-03 template CI-09, sheet PM-09 Lists and parameters | Product Owner, Marketing Business System (MBS) |  | Not started
RNW_REFERENCE_PREFIX | Renewal | Prefix of the renewal reference (prefix-yyyy-nnnnnn) | RNW | This workbook, sheet Ref Document numbering | Product Owner, Renewal |  | Not started
SCR_CASE_SEQUENCE_PREFIX | Sanction Screening | Prefix of the screening case number <prefix>-yyyy-nnnnnn | SCR | This workbook, sheet Ref Document numbering | Compliance |  | Not started
SBM_NUMBER_PREFIX | Submitted Policies | Prefix of the masterlist number (prefix-yyyy-nnnnnn) | SBM | This workbook, sheet Ref Document numbering | Product Owner, Submitted Policies |  | Not started
Note on A4: Parameter: Prefix parameter
Note on B4: Module: Module of the document
Note on C4: Numbered document: Document numbered with the prefix
Note on D4: Prefix proposed: Prefix proposed with the platform
Note on E4: Prepared in: Where the prefix wanted is given
Note on F4: Owner (BDOI unit): Unit that decides the prefix
Note on G4: Prefix wanted: Prefix BDOI wants; the year and a running number follow it
Note on H4: Status: Status of the row
Note on I4: BDOI comments: Decision, value or comment of the owner

## Ref Notifications
Reference: Notifications
← Back to Start here | Every notification event with its default channels; users choose their own channels in Notification Settings
Event | Name | Module | Drop | Owner (BDOI unit) | Who is told and when | In-app proposed | E-mail proposed | In-app wanted | E-mail wanted | Unit mailbox | Status | BDOI comments
ACSL_CASE_STATUS | ACSL case or correction status | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | An ACSL case you requested has a result, or a correction entry you prepared was returned, approved or posted | Y | N |  |  |  | Not started
ACSL_GLSL_DIFFERENCE | GL-SL difference found | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | The GL-SL reconciliation found a control account whose sub-ledger differs from the general ledger | Y | Y |  |  |  | Not started
ADJ_REQUEST_STATUS | Endorsement request status | Operations | Drop 1 | Head, Operations Services | An endorsement request you raised was returned, approved or posted | Y | N |  |  |  | Not started
BOOKING_BILLING_BOOKED | Booked with billing number | New Business | Drop 1 | Product Owner, BDOI (New Business) | An account was booked with its insurer billing number | Y | N |  |  |  | Not started
BOOKING_BILLING_DUPLICATE | Duplicate billing number | New Business | Drop 1 | Product Owner, BDOI (New Business) | A booking was refused because the insurer billing number is already on an invoice | Y | Y |  |  |  | Not started
CASH_APPROVAL_REQUEST | Cashiering approval request | Operations | Drop 1 | Head, Operations Services | A receipt cancellation, reinstatement or disposition waits for approval | Y | N |  |  |  | Not started
CASH_RECORD_FOR_POSTING | Cashiering record for posting | Operations | Drop 1 | Head, Operations Services | An AR / OR creation, cancellation or reinstatement record was submitted for posting | Y | N |  |  |  | Not started
CASH_RECORD_DECIDED | Cashiering record returned or posted | Operations | Drop 1 | Head, Operations Services | An AR / OR record you created was returned with a reason or posted | Y | N |  |  |  | Not started
CASH_FORM_FOR_APPROVAL | Receipt form for approval | Operations | Drop 1 | Head, Operations Services | A change of the AR or OR form waits for the approval of another authorised user | Y | N |  |  |  | Not started
BCL_FOLLOW_UP_DUE | Claim follow-up due | Claims | Drop 2 | Product Owner, Claims | A claim of yours has its next follow-up or a diary entry due today | Y | N |  |  |  | Not started
BCL_CLAIM_ASSIGNED | Claim assigned | Claims | Drop 2 | Product Owner, Claims | A claim was assigned or re-assigned to you | Y | Y |  |  |  | Not started
BCL_STATUS_CHANGED | Claim status changed | Claims | Drop 2 | Product Owner, Claims | The status of a claim of one of your accounts changed | Y | N |  |  |  | Not started
BCL_PREMIUM_REMITTED | Claim premium remitted | Claims | Drop 2 | Product Owner, Claims | The premium of a claim awaiting premium remittance was fully remitted to the insurer | Y | N |  |  |  | Not started
BCL_NEWER_COVER_VERSION | Newer cover version | Claims | Drop 2 | Product Owner, Claims | An endorsement was booked on the cover of an open claim of yours | Y | N |  |  |  | Not started
CLX_ESCALATED | Account escalated | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | A collection account was escalated to you or by your team | Y | Y |  |  |  | Not started
CLX_REASSIGNED | Account reassigned | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | Collection accounts were assigned to you or taken from you | Y | N |  |  |  | Not started
CLX_PROMISE_BROKEN | Promise to pay broken | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | A promise to pay of one of your accounts was not kept | Y | N |  |  |  | Not started
CLX_DP_RETURNED | Direct payment returned by insurer | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | An insurer returned a direct payment account; it is back in your worklist | Y | N |  |  |  | Not started
CLX_FILE_READY | Collections file ready | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | A scheduled Collections file is available for download | Y | N |  |  |  | Not started
DP_FEEDBACK_OVERDUE | Direct payment feedback overdue | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | An insurer has not answered a direct payment billing in time | Y | Y |  |  |  | Not started
CONFIG_IMPORT_TO_APPROVE | Configuration import to approve | Platform set-up | Drop 0 | BDOI IT | A configuration package was checked and waits for the approval of a second user | Y | Y |  |  |  | Not started
CONFIG_IMPORT_APPLIED | Configuration import applied | Platform set-up | Drop 0 | BDOI IT | A configuration package was applied to this environment; the reconciliation is on the import | Y | Y |  |  |  | Not started
CONFIG_IMPORT_REJECTED | Configuration import rejected | Platform set-up | Drop 0 | BDOI IT | The approver rejected a configuration import; the reason is on the import | Y | N |  |  |  | Not started
CONFIG_IMPORT_FAILED | Configuration import failed | Platform set-up | Drop 0 | BDOI IT | A configuration import could not be applied; nothing of it was kept | Y | Y |  |  |  | Not started
EB_FEEDBACK_RECEIVED | EB client feedback received | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A client gave feedback on the renewal advice of your programme | Y | N |  |  |  | Not started
EB_BOR_DECIDED | EB Broker on Record decided | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A Broker on Record you uploaded was validated or rejected | Y | N |  |  |  | Not started
EB_FRANCHISE_DECIDED | EB franchise decided | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | An insurer approved or rejected a franchise request of yours | Y | Y |  |  |  | Not started
EB_PROPOSAL_RECEIVED | EB proposal received | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | An insurer submitted a proposal to validate | Y | N |  |  |  | Not started
EB_COMPARATIVE_SIGNOFF | EB comparative to sign off | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A comparative waits for your sign-off | Y | Y |  |  |  | Not started
EB_COMPARATIVE_DECIDED | EB comparative decided | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A comparative of your programme was signed off, approved above the threshold or returned | Y | N |  |  |  | Not started
EB_THRESHOLD_APPROVAL | EB threshold approval | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A comparative above the value threshold waits for your approval | Y | Y |  |  |  | Not started
EB_CLIENT_CONFIRMED | EB client confirmation | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A client confirmed the chosen proposals of your programme | Y | N |  |  |  | Not started
EB_PLACEMENT_TRIGGERED | EB placement triggered | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | The accounts of an EB cycle were created for placement | Y | N |  |  |  | Not started
EB_ROSTER_STAGED | EB master list staged | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A master list of your programme was loaded and waits for your review | Y | N |  |  |  | Not started
EB_MEMBER_CHANGE_BILLED | EB member change billed | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | An insurer billed a member change to validate | Y | N |  |  |  | Not started
EB_SUBMISSION_SENT | EB documents submitted | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | Documents of an Employee Benefits programme were submitted to an insurer | Y | N |  |  |  | Not started
EB_SOA_RELEASED | EB SOA released | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | An insurer SOA was validated and released to Collection and the client | Y | N |  |  |  | Not started
EB_INVOICE_PAID | EB invoice paid | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | An invoice of an EB programme became paid | Y | N |  |  |  | Not started
EB_ITEM_ESCALATED | EB pending item escalated | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | A tracked item passed its follow-ups without being received | Y | Y |  |  |  | Not started
OPS_INVOICE_LOCKED | Invoice locked or released | Operations | Drop 1 | Head, Operations Services | An invoice you work on was locked by another team or released | Y | N |  |  |  | Not started
OPS_FLOW_IN_FAILED | Interface run failed | Operations | Drop 1 | Head, Operations Services | A flow-in or flow-out run failed or had failed records | Y | Y |  |  |  | Not started
OPS_DISBURSEMENT_STATUS | Disbursement status | Operations | Drop 1 | Head, Operations Services | A payment request was acknowledged, received its DV number, was paid or returned | Y | N |  |  |  | Not started
PRQ_REQUEST_STATUS | Refund / cash advance request status | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | A refund, cash-advance or check-cancellation request was validated, returned, approved or disbursed | Y | N |  |  |  | Not started
RECON_FEEDBACK_UPLOADED | Insurer reconciliation feedback | Operations | Drop 1 | Head, Operations Services | An insurer production feedback was uploaded and matched | Y | N |  |  |  | Not started
PM_DEACTIVATION_APPROVAL | Package deactivation for approval | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package deactivation request names you as its approver | Y | Y |  |  |  | Not started
PM_DEACTIVATION_DECIDED | Package deactivation decided | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Your package deactivation request was approved or rejected | Y | Y |  |  |  | Not started
PM_PACKAGE_EXPIRY | Package expiry or anniversary | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package reaches its expiry or anniversary date within the notice period | Y | Y |  |  |  | Not started
PM_TSU_REVIEW | Request for TSU review | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package request or a quotation request entered TSU review | Y | N |  |  |  | Not started
PM_MANCOM_APPROVAL | ManCom approval | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package request waits for your ManCom approval | Y | Y |  |  |  | Not started
PM_APPROVALS_COMPLETE | Package approvals complete | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | Every required approval of your package request is complete | Y | N |  |  |  | Not started
PM_DEPLOYMENT_REQUESTED | Package deployment requested | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package deployment request waits for MBS | Y | N |  |  |  | Not started
PM_PRODUCT_APPROVAL | Product Matrix record for approval | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A Product Matrix record names you as its approver | Y | Y |  |  |  | Not started
PM_MARKETING_APPROVAL | Package request for Marketing approval | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | A package request waits for the next Marketing approval | Y | N |  |  |  | Not started
PM_TERMS_AGREED | Insurers selected for the proposal | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | The requestor selected the insurers of a quotation request and asks for the proposal | Y | N |  |  |  | Not started
PM_PROPOSAL_DECIDED | Proposal approved, returned or rejected | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | The proposal of a quotation request was approved, returned or rejected | Y | N |  |  |  | Not started
PM_CLIENT_RESPONSE | Client response recorded | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | The client accepted, rejected or returned a proposal for revision | Y | N |  |  |  | Not started
PM_PLACEMENT_UPDATE | Placement Update Report generated | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | The Consolidated Placement Update Report of the week is in the repository | Y | N |  |  |  | Not started
REMIT_EXTRACTION_DONE | Remittance extraction completed | Operations | Drop 1 | Head, Operations Services | A scheduled or manual remittance extraction finished | Y | Y |  |  |  | Not started
REMIT_BATCH_FOR_APPROVAL | Remittance batch for approval | Operations | Drop 1 | Head, Operations Services | A remittance batch was submitted for approval | Y | Y |  |  |  | Not started
REMIT_BATCH_DECIDED | Remittance batch approved or returned | Operations | Drop 1 | Head, Operations Services | A remittance batch you prepared was approved or returned | Y | N |  |  |  | Not started
REMIT_NEG_ADJ_PENDING | Negative adjustment on a remittance invoice | Operations | Drop 1 | Head, Operations Services | A negative adjustment was requested on an invoice in remittance | Y | Y |  |  |  | Not started
HOLD_EXPIRING | Remittance hold expiring | Operations | Drop 1 | Head, Operations Services | A remittance hold reaches its hold date | Y | N |  |  |  | Not started
RNW_ASSIGNED | Renewal assigned | Renewal | Drop 1 | Product Owner, Renewal | Expiring accounts were assigned to you for disposition or processing | Y | N |  |  |  | Not started
RNW_TRANSFER_REQUESTED | Renewal transfer requested | Renewal | Drop 1 | Product Owner, Renewal | Another Marketing unit transferred an expiring account to your unit | Y | Y |  |  |  | Not started
RNW_TRANSFER_DECIDED | Renewal transfer decided | Renewal | Drop 1 | Product Owner, Renewal | The receiving unit accepted or declined your transfer of an expiring account | Y | N |  |  |  | Not started
RNW_RETURNED | Renewal returned | Renewal | Drop 1 | Product Owner, Renewal | An expiring account was returned to you with remarks | Y | Y |  |  |  | Not started
RNW_POSTED | Renewal posted | Renewal | Drop 1 | Product Owner, Renewal | Dispositioned accounts were posted by the Team Leader | Y | N |  |  |  | Not started
RNW_INSURER_RESPONDED | Insurer renewal response | Renewal | Drop 1 | Product Owner, Renewal | An insurer answered the renewal of an account you process | Y | N |  |  |  | Not started
RNW_ACCEPTED | Renewal accepted | Renewal | Drop 1 | Product Owner, Renewal | A client accepted the Renewal Advice of an account of yours | Y | N |  |  |  | Not started
RNW_RENEWED | Renewal booked | Renewal | Drop 1 | Product Owner, Renewal | The renewal of an account of yours was booked | Y | N |  |  |  | Not started
RNW_GOLIVE_COMPLETED | Go-live renewal extraction completed | Renewal | Drop 1 | Product Owner, Renewal | The expiring migrated policies of the go-live window were taken over as renewals | Y | Y |  |  |  | Not started
RNW_PACKAGE_DECIDED | Renewal package choice decided | Renewal | Drop 1 | Product Owner, Renewal | Your choice of the package version of a migrated policy was approved or rejected | Y | N |  |  |  | Not started
RNW_PLACEMENT_FAILED | Renewal placement not sent | Renewal | Drop 1 | Product Owner, Renewal | The placement file of an account you process could not be uploaded or sent to the insurer | Y | Y |  |  |  | Not started
RNW_PLACEMENT_RESPONDED | Renewal placement response | Renewal | Drop 1 | Product Owner, Renewal | An insurer approved or rejected the placement of an account you process | Y | N |  |  |  | Not started
SCR_CASE_ASSIGNED | Screening case assigned | Sanction Screening | Drop 1 | Compliance | A screening case was assigned or re-assigned to you | Y | Y |  |  |  | Not started
SCR_CASE_FOR_APPROVAL | Screening case for approval | Sanction Screening | Drop 1 | Compliance | A screening case waits for your approval | Y | Y |  |  |  | Not started
SCR_CASE_RETURNED | Screening case returned | Sanction Screening | Drop 1 | Compliance | A screening case was returned to you with a rationale | Y | Y |  |  |  | Not started
SCR_COMMITTEE_REVIEW | AML Committee review | Sanction Screening | Drop 1 | Compliance | A screening case waits for the vote of the AML Committee | Y | Y |  |  |  | Not started
SCR_SLA_REMINDER | Screening SLA reminder | Sanction Screening | Drop 1 | Compliance | A screening case of yours is about to pass its SLA | Y | Y |  |  |  | Not started
SCR_SLA_ESCALATION | Screening SLA escalation | Sanction Screening | Drop 1 | Compliance | A screening case passed its SLA and is escalated to you | Y | Y |  |  |  | Not started
SCR_DOCUMENT_REMINDER | Screening document reminder | Sanction Screening | Drop 1 | Compliance | Documents of a screening case are still missing | Y | N |  |  |  | Not started
SCR_NO_POLICY_HIT | Screening hit without active policy | Sanction Screening | Drop 1 | Compliance | A high-risk or PEP client without an active policy was found | Y | N |  |  |  | Not started
SCR_CONFIG_TO_APPROVE | Screening configuration to approve | Sanction Screening | Drop 1 | Compliance | A screening configuration version waits for your approval | Y | N |  |  |  | Not started
SCR_LIST_CHANGE_TO_APPROVE | Watchlist change to approve | Sanction Screening | Drop 1 | Compliance | A watchlist change waits for your approval | Y | N |  |  |  | Not started
FILE_QUARANTINED | File quarantined | Platform set-up | Drop 0 | BDOI IT | A file you uploaded, or one you review as security officer, was quarantined by the malware scan | Y | Y |  |  |  | Not started
SBM_NEW_SUBMISSION | New submitted policies | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Submitted policies were loaded from a source file | Y | N |  |  |  | Not started
SBM_MANUAL_VALIDATION | Policy document to confirm | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A submitted policy document waits for the confirmation of its details | Y | N |  |  |  | Not started
SBM_IAAF_PENDING | IAAF to approve | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | An IAAF waits for your approval | Y | Y |  |  |  | Not started
SBM_TOR_PENDING | TOR to approve | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A Terms of Reference waits for your approval | Y | Y |  |  |  | Not started
SBM_TOR_RELEASED | TOR approved | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | The Terms of Reference of your account was approved; open or download it | Y | Y |  |  |  | Not started
SBM_BUCKET_CHANGED | Submitted policy bucket changed | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Submitted policies moved to the renewal, manual disposition or non-renewal buckets | Y | N |  |  |  | Not started
SBM_FALLOUT | Submitted policies fallout | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A processing run ended with fallout to resolve | Y | N |  |  |  | Not started
SBM_EXPIRY_NEAR | Submitted policy nearing expiry | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A submitted policy for renewal is within the renewal lead days | Y | N |  |  |  | Not started
SBM_RENEWAL_STARTED | Renewal of a submitted policy started | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A submitted policy was handed to Renewal | Y | N |  |  |  | Not started
SBM_PLACEMENT_READY | Submitted policy renewal ready for placement | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | The renewal account of a submitted policy is ready for placement | Y | N |  |  |  | Not started
SBM_PLACEMENT_SENT | Submitted policy renewal placed | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | The placement slip of a submitted policy renewal was sent to the insurer | Y | N |  |  |  | Not started
SBM_HOLD_COVER_UNBOOKED | Hold cover of an unbooked renewal | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | A hold cover ends soon and the renewal account is not booked | Y | Y |  |  |  | Not started
SBM_HANDLER_ASSIGNED | Submitted policy assigned | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | Submitted policies were assigned to you | Y | N |  |  |  | Not started
UAM_REQUEST_TO_APPROVE | Access request to approve | User Access Maintenance | Drop 0 | Business Administration (User Access) | An access request waits for your approval | Y | Y |  |  |  | Not started
UAM_REQUEST_RETURNED | Access request returned | User Access Maintenance | Drop 0 | Business Administration (User Access) | Your access request was returned with remarks | Y | Y |  |  |  | Not started
UAM_REQUEST_CANCELLED | Access request cancelled | User Access Maintenance | Drop 0 | Business Administration (User Access) | An access request assigned to you was cancelled | Y | N |  |  |  | Not started
UAM_REQUEST_DECIDED | Access request decided | User Access Maintenance | Drop 0 | Business Administration (User Access) | Your access request was approved or rejected | Y | Y |  |  |  | Not started
UAM_ACCESS_CHANGED | Your access changed | User Access Maintenance | Drop 0 | Business Administration (User Access) | Your user data or group profiles were changed | Y | Y |  |  |  | Not started
UAM_SECOND_APPROVAL | Access request for second approval | User Access Maintenance | Drop 0 | Business Administration (User Access) | A privileged or out-of-hours access request waits for your second approval | Y | Y |  |  |  | Not started
UAM_FOR_IMPLEMENTATION | Group profile request to implement | User Access Maintenance | Drop 0 | Business Administration (User Access) | An approved group-profile request waits for the System Administrator | Y | Y |  |  |  | Not started
PASSWORD_EXPIRY_NOTICE | Password expires soon | User Access Maintenance | Drop 0 | Business Administration (User Access) | Your password expires within 7 days; change it on My Profile | Y | Y |  |  |  | Not started
UAM_IDENTITY_REFUSED | Identity event refused | User Access Maintenance | Drop 0 | Business Administration (User Access) | An event of the Enterprise SSO platform or UIDM-ISC could not be applied and waits for review | Y | Y |  |  |  | Not started
UAM_DORMANT_WARNING | Account deactivation soon | User Access Maintenance | Drop 0 | Business Administration (User Access) | You have not signed in for a long time; sign in before the date given or your account is deactivated | Y | Y |  |  |  | Not started
UAM_BREAK_GLASS_SIGN_IN | Break-glass sign-in | User Access Maintenance | Drop 0 | Business Administration (User Access) | A break-glass System Administrator signed in with a local password while single sign-on is on | Y | Y |  |  |  | Not started
UAM_DORMANT_DEACTIVATED | Dormant users deactivated | User Access Maintenance | Drop 0 | Business Administration (User Access) | Users who had not signed in for the dormancy period were deactivated | Y | N |  |  |  | Not started
UAM_PARAMETER_TO_APPROVE | Security setting to approve | User Access Maintenance | Drop 0 | Business Administration (User Access) | A change of a sign-in, password, session or access setting waits for your approval | Y | Y |  |  |  | Not started
UAM_SOD_TO_AUTHORIZE | Separation-of-duties rule to authorise | User Access Maintenance | Drop 0 | Business Administration (User Access) | A new or deactivated separation-of-duties rule waits for your authorisation | Y | N |  |  |  | Not started
MFA_RESET_TO_APPROVE | Second factor reset to approve | User Access Maintenance | Drop 0 | Business Administration (User Access) | A reset of a user's authenticator app waits for your approval | Y | Y |  |  |  | Not started
MFA_RESET_DONE | Second factor reset | User Access Maintenance | Drop 0 | Business Administration (User Access) | Your authenticator app was reset by the administrators; enrol it again at your next sign-in | Y | Y |  |  |  | Not started
Note on A4: Event: Notification event
Note on B4: Name: Name shown in Notification Settings
Note on C4: Module: Module
Note on D4: Drop: Drop
Note on E4: Owner (BDOI unit): Unit that confirms the event
Note on F4: Who is told and when: What the event tells the user
Note on G4: In-app proposed: Y or N
Note on H4: E-mail proposed: Y or N
Note on I4: In-app wanted: Y or N
Note on J4: E-mail wanted: Y or N
Note on K4: Unit mailbox: Mailbox that also receives the e-mail (optional)
Note on L4: Status: Status of the row
Note on M4: BDOI comments: Decision, value or comment of the owner

## Ref Document templates
Reference: Document templates
← Back to Start here | Every generated document with the unit that gives its BDOI wording and layout
Template | Title | Module | Drop | Owner (BDOI unit) | Merge fields available | Prepared in | Due | BDOI layout attached | Status | BDOI comments
BCL_LOSS_ADVICE | Loss advice {{claimNo}} - {{assuredName}} | Claims | Drop 2 | Product Owner, Claims | adjusterName, arn, assuredName, claimNo, currency, handlerName, initialReserve, insurerClaimNos, insurerName, lossDate, lossDescription, lossNature, lossPlace, policyNo, policyYear | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
CLX_SOA | Statement of account | Collections | Drop 1 | VP and Head, BDOI Operations (Collections) | arn, balance, currency, cycleFrom, cycleTo, dueDate, frequency | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_ATD | Authority to debit | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeName, valueDate | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_ATD_EMAIL | Authority to debit {{dvNo}} | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | currency, dvNo, instrumentNo, netAmount, payeeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_CHECK | Check | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, instrumentNo, netAmount, payeeName, printDate | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_CREDIT_TICKET | Credit ticket | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_MC_DD | Manager's check / demand draft request | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_PAYMENT_ADVICE | Payment advice {{dvNo}} | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | currency, dvNo, instrumentText, mode, netAmount, payeeName, valueDate | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_TT | Telegraphic transfer | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeBank, payeeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_VOUCHER | Disbursement voucher | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | currency, dvNo, mode, netAmount, payeeName, purpose, requestNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_COMPARATIVE | Comparative analysis - {{programmeName}} ({{policyYear}}) | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, comparativeNo, contactName, programmeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_FRANCHISE_ADVICE | Franchise outcome - {{programmeName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, contactName, insurerName, outcome, programmeName, reasonText | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_FRANCHISE_REQUEST | Franchise request {{franchiseNo}} - {{clientName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, clientName, dueDate, insurerName, lines | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_INDICATIVE_PROPOSAL | Indicative renewal terms - {{programmeName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, contactName, incumbentName, policyYear, programmeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_ITEM_FOLLOWUP | Follow-up: {{itemType}} for {{programmeName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, dueDate, followUpNo, itemType, programmeName, recipientName, subject | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_MEMBER_CHANGE_RELAY | Member change {{changeNo}} - {{clientName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, clientName, insurerName, memberLines, policyNo, programmeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RA_REMINDER | Reminder: renewal of {{programmeName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, contactName, expiryDate, programmeName | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RENEWAL_ADVICE | Renewal advice - {{programmeName}} ({{policyYear}}) | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, contactName, expiryDate, insurers, lines, programmeName, programmeNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_REVISION_RELAY | Revision request - {{clientName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, dueDate, insurerName, proposalNo, revisionItems | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RFP_COVER | Request for proposal {{requestNo}} - {{clientName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, clientName, dueDate, insurerName, lines | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_SOA_RELEASE | Statement of account {{soaNo}} - {{programmeName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | amount, aoName, contactName, insurerName, period, programmeName, soaNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_SUBMISSION_COVER | {{process}} documents - {{clientName}} | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | aoName, clientName, documents, insurerName, process, programmeName, remarks | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_TOR | Terms of Reference - {{programmeName}} ({{policyYear}}) | Employee Benefits | Drop 2 | Product Owner, Employee Benefits | clientName, inceptionDate, lines, programmeNo, torItems, torVersion | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
ENDORSEMENT_SLIP | Endorsement slip | Operations | Drop 1 | Head, Operations Services | arn, assured, effectiveDate, invoiceNo, policyNo, requestNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
EPOLICY_EMAIL | Your e-policy | New Business | Drop 1 | Product Owner, BDOI (New Business) | clientName, insurerName, policyNo, reference | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
HOLD_COVER_REQUEST | Request for hold cover | New Business | Drop 1 | Product Owner, BDOI (New Business) | reference, startDate | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
INSURANCE_ADVICE | Insurance advice | New Business | Drop 1 | Product Owner, BDOI (New Business) | insurerName, mortgagee, periodFrom, periodTo, policyNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_ADVISORY | Package advisory | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | effectiveFrom, productCode, productName, reference, versionNo | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_COMPARATIVE | Package comparative table | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | reference, roundNo, variant | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_QUOTATION_SLIP | Package quotation slip | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | reference, replyBy, roundNo | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_RENEWAL_ADVISORY | Package renewal advisory | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | effectiveFrom, productCode, productName, reference, versionNo | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_REQUEST_FORM | Package request form | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | reference, requestType, title | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_SLIP | Package slip | Product Maintenance | Drop 0 | Product Owner, Marketing Business System (MBS) | reference, title | BRD-03 template CI-08, sheet PM-08 Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PLACEMENT_SLIP | Placement slip | New Business | Drop 1 | Product Owner, BDOI (New Business) | reference | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PRODRECON_COVER_LETTER | Production register for reconciliation | Operations | Drop 1 | Head, Operations Services | bookingFrom, bookingTo, extractNo, insurerName, productionMonth, rowCount | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PROPOSAL_SLIP | Proposal slip | New Business | Drop 1 | Product Owner, BDOI (New Business) | clientName, reference | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_LIQUIDATION | Cash Advance Liquidation Form | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | cashAdvanced, currency, liquidationNo, overShort, payeeName, requestNo, totalExpenses | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_RFP | Request for Payment | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | amount, currency, mode, payeeName, purpose, requestDate, requestNo, rfpType | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_RRF | Refund Request Form | Accounting, Disbursement and ACSL | Drop 1 | Head, Comptrollership | amount, currency, mode, payeeName, reference, requestDate, requestNo, segment | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_LETTER | Insurance quotation | New Business | Drop 1 | Product Owner, BDOI (New Business) | clientName, productName, reference, validUntil | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_SLIP | Quotation slip | New Business | Drop 1 | Product Owner, BDOI (New Business) | reference, replyBy | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_TERMS | Terms and conditions | New Business | Drop 1 | Product Owner, BDOI (New Business) |  | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
REMITTANCE_PAYMENT_REQUEST | Payment request | Operations | Drop 1 | Head, Operations Services | amount, approvedBy, currency, insurerName, reference | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
REMITTANCE_SCHEDULE | Remittance schedule | Operations | Drop 1 | Head, Operations Services | incentiveNote, insurerName, reference, remittanceType | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_ACCOUNT_DETAILS | Renewal account details - {{renewalRef}} | Renewal | Drop 1 | Product Owner, Renewal | asOf, clientName, expiringArn | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_INSURER_COVER | Renewals for your decision - batch {{batchNo}} | Renewal | Drop 1 | Product Owner, Renewal | count, expiryFrom, expiryTo, insurerName, replyDue | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NAL | Notice on your policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NFR | Your policy {{policyNo}} will not be renewed | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, reason, renewalRef | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NON_ACCEPTANCE | Your policy {{policyNo}} has expired | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NRNS_REMINDER | Reminder: renewal of your policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_FFY | Renewal Advice (first year free) - {{assuredName}} - policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, renewalFrom, renewalRef, renewalTo, sumInsured | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_FIRST | Renewal Advice - {{assuredName}} - policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, productName, renewalFrom, renewalRef, renewalTo, sumInsured | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_SECOND | Second notice: Renewal Advice - {{assuredName}} - policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, renewalRef, sumInsured | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_SFU | Follow-up on the renewal of your mortgaged property - policy {{policyNo}} | Renewal | Drop 1 | Product Owner, Renewal | aoName, clientName, expiryDate, policyNo, renewalRef | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_IAAF | Insurance Adequacy Assessment Form {{iaafNo}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | adequacy, assuredName, borrowerName, currency, expiryDate, iaafNo, inceptionDate, insurerName, links, policyNo, reviewCount, reviews, sbmNo, sumInsured | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_NO_TOUCH_BILLING | No Touch billing statement - {{insurerName}} - {{period}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | count, currency, grossFee, insurerName, netDue, period, vat, wtax | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_REMINDER | Reminder on your policy {{policyNo}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | assuredName, bankCounterpart, expiryDate, findings, insurerName, policyNo, sbmNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_RENEWAL_NOTICE | Renewal notice - policy {{policyNo}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | assuredName, expiryDate, insurerName, policyNo, riskDescription, sbmNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_RENEWAL_PROPOSAL | Renewal proposal - policy {{policyNo}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | assuredName, currency, expiryDate, policyNo, proposedInsurer, sbmNo, sumInsured | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_TOR | Terms of Reference {{torNo}} | Submitted Policies | Drop 1 | Product Owner, Submitted Policies | accountRef, aoName, assuredName, breaches, currency, insurerName, proposedTerms, sumInsured, torNo | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
SERVICE_INVOICE_NOTE | Service invoice | New Business | Drop 1 | Product Owner, BDOI (New Business) | creditDays, reference | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
VALIDATION_SLIP | Validation slip | New Business | Drop 1 | Product Owner, BDOI (New Business) | invoiceNo, requestNo, status, validatedOn | This workbook, sheet Ref Document templates | 16-Jul-2027 (T-24 weeks) |  | Not started
Note on A4: Template: Template code on Document Templates
Note on B4: Title: Title of the template
Note on C4: Module: Module that generates the document
Note on D4: Drop: Drop
Note on E4: Owner (BDOI unit): Unit that gives the wording and layout
Note on F4: Merge fields available: Fields BIBS fills in
Note on G4: Prepared in: Where the text is given
Note on H4: Due: Due date
Note on I4: BDOI layout attached: Y when the layout is sent
Note on J4: Status: Status of the row
Note on K4: BDOI comments: Decision, value or comment of the owner

## Ref Accounting events
Reference: Accounting events
← Back to Start here | The accounting events that need a rule of template D0-08; owner Head, Comptrollership
Event type | Name | Category | Journal type | Amount components | Prepared in | Status | BDOI comments
CLAIM_RECOVERY | Salvage / subrogation recovery | Claims | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
CLAIM_RESERVE | Claim reserve change | Claims | Claims | RESERVE_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
CLAIM_SETTLEMENT | Claim settlement approved | Claims | Claims | PAID_AMOUNT, RESERVE_RELEASE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
CLAIM_COINSURANCE | Coinsurer share of a claim | Coinsurance | Claims | COINSURER_SHARE, COINSURER_RECOVERY | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
COINSURANCE_SHARE | Coinsurer share of premium | Coinsurance | Premium | COINSURER_PREMIUM | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
COMMISSION_ACCRUAL | Commission accrued | Commission | Commission | COMMISSION, WITHHOLDING_TAX, NET_COMMISSION | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_ADJ_COMMISSION | Commission adjustment without premium change | Commission | Commission | COMMISSION_RECEIVABLE, UNREALIZED_COMMISSION, DEFERRED_OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_INCENTIVE_ACCRUE | Incentive earned from insurer | Commission | Commission | INCENTIVE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_INCENTIVE_PASS_ON | Incentive pass-on to branches | Commission | Commission | PASS_ON | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_REMIT_CPC2 | CPC2 incentive per remittance batch | Commission | Commission | GROSS, CPC2_INCOME, OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_REMIT_INCENTIVE | Early remittance incentive | Commission | Commission | DUE_FOR_DISBURSEMENT, INCENTIVE_INCOME, OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
ASSET_ACQUISITION | Fixed asset capitalized | Payment | Payment | COST | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
CLAIM_PAYMENT | Claim payment | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
COMMISSION_PAYMENT | Commission payment | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
DISB_CHECK_NEGOTIATED | Check negotiated | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
DISB_CHECK_STALE | Check staled | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
DISB_VOUCHER | Disbursement voucher approved | Payment | Payment | REMITTANCE, REFUND, REFUND_FROM_INSURER, SUPPLIER, GOVERNMENT, OTHER_BANK_UNIT, EMPLOYEE, CASH_ADVANCE, SERVICE_FEE, PASS_ON, STALE_REISSUE, OTHER, PAID, EWT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
FRBS_SERVICE_FEE_ACCRUE | Service fee accrual | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
MISC_PAYMENT | Miscellaneous payment | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_REMITTANCE | Remittance to insurer | Payment | Payment | DTIP, CWT, COMMISSION_RECEIVABLE, DUE_FOR_DISBURSEMENT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_REMIT_DEDUCTION | Remittance deduction on insurer confirmation | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PDC_ISSUED_PRESENTED | Issued PDC presented | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PETTY_CASH_EXPENSE | Petty cash disbursement | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PETTY_CASH_REPLENISHMENT | Petty cash reimbursement | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PREMIUM_REFUND_PAYMENT | Premium refund payment | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PRQ_CA_LIQUIDATION | Cash advance liquidation | Payment | Payment | PER_DIEM, REPRESENTATION, TRANSPORT, LODGING, OTHER, CASH_RETURNED, SHORTAGE, ADVANCE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_SETTLEMENT_PAYMENT | Payment to reinsurer | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
SUPPLIER_INVOICE | Supplier invoice | Payment | Payment | NET_AMOUNT, INPUT_VAT, WITHHOLDING_TAX, PAYABLE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
SUPPLIER_PAYMENT | Supplier payment | Payment | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
TAX_REMITTANCE | Tax remittance | Payment | Payment | TAX_PAYABLE, TAX_CREDIT, AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
POLICY_CANCELLATION | Policy cancellation | Policy | Endorsement | GROSS_PREMIUM, DST, VAT, LGT, FST, PREMIUM_TAX, POLICY_FEE, TOTAL_DUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
POLICY_ENDORSEMENT | Policy endorsement | Policy | Endorsement | GROSS_PREMIUM, DST, VAT, LGT, FST, PREMIUM_TAX, POLICY_FEE, TOTAL_DUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
POLICY_ISSUE | Policy issued / renewed | Policy | Premium | GROSS_PREMIUM, DST, VAT, LGT, FST, PREMIUM_TAX, POLICY_FEE, TOTAL_DUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
BROKER_BOOKING | Broker booking | Premium | Premium | PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, DTIP, COMMISSION_RECEIVABLE, UNREALIZED_COMMISSION, DEFERRED_OUTPUT_VAT, COMMISSION_INCOME, OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
MIG_LEGACY_INVOICE_OPENING | Legacy invoice opening | Premium | Opening | LG_PR_BASIC, LG_PR_DST, LG_PR_PTX_VAT, LG_PR_LGT, LG_PR_FST, LG_PR_OTHER, LG_PR2307, LG_DTIP, LG_COMMISSION, LG_COMMISSION_VAT, LG_UNREALIZED, LG_DEFERRED_VAT, CLEARING | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
MIG_LEGACY_POSITION_TRUEUP | Legacy open-item adjustment | Premium | Opening | LG_PR_BASIC, LG_PR_DST, LG_PR_PTX_VAT, LG_PR_LGT, LG_PR_FST, LG_PR_OTHER, LG_PR2307, LG_DTIP, LG_COMMISSION, LG_COMMISSION_VAT, LG_UNREALIZED, LG_DEFERRED_VAT, LG_AMOUNT, CLEARING | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_AR_INSURER_SETUP | AR Insurer set-up after a remitted decrease | Premium | Premium | AR_INSURER | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_WRITE_OFF | Minimal balance write-off / credit | Premium | Premium | WRITE_OFF, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, CREDIT_BALANCE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
ASSET_DEPRECIATION | Monthly depreciation | Provision | Provision | DEPRECIATION | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
ASSET_TAKE_ON | Fixed asset opening balance | Provision | Opening | COST, ACCUMULATED_DEPRECIATION, NET_BOOK_VALUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
ASSET_TRANSFER | Inter-branch asset transfer | Provision | Provision | COST, ACCUMULATED_DEPRECIATION, NET_BOOK_VALUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
CLAIM_MARGIN_PROVISION | ULAE and risk margin provision | Provision | Provision | ULAE_CHANGE, MFAD_CHANGE, RI_MFAD_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
DAC_PROVISION | Deferred acquisition cost | Provision | Provision | DAC_CHANGE, DRC_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
IBNR_PROVISION | IBNR reserve | Provision | Provision | IBNR_CHANGE, RI_IBNR_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PREMIUM_DEFICIENCY_PROVISION | Premium deficiency reserve | Provision | Provision | PDR_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
TAKAFUL_SURPLUS | Surplus / Mudharabah distribution | Provision | Provision | SURPLUS | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
UPR_PROVISION | Unearned premium reserve | Provision | Provision | UPR_CHANGE, RI_UPR_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
ASSET_DISPOSAL | Fixed asset disposal | Receipt | Receipt | COST, ACCUMULATED_DEPRECIATION, PROCEEDS, GAIN, LOSS | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
MIG_UPP_OPENING | Legacy unapplied payment opening | Receipt | Opening | LG_AMOUNT, CLEARING | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
MISC_RECEIPT | Miscellaneous receipt | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_AP_UNAPPLIED_COMMISSION | Reinstated OR payment to AP Unapplied Commission | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_AR_INSURANCE_RECEIPT | Insurer non-premium receipt | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_AR_INSURER_REFUND | Reversed payment to AR Insurer Refund | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_AR_RECEIPT | Acknowledgement receipt (premium) | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_COMMISSION_PAYMENT_HELD | Cancelled OR payment kept for Commission Receivable | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_CWT_DTIP_OFFSET | 2307 certificate offset against DTIP | Receipt | Receipt | DTIP, PR2307 | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_CWT_RECLASS | PR reclassified to the client 2307 | Receipt | Receipt | PR2307, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_DP_COMMISSION_COLLECT | Direct payment commission collected | Receipt | Receipt | CASH, CWT, COMMISSION_RECEIVABLE, REALIZED_COMMISSION, REALIZED_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_DP_PR_REVERSAL | Direct payment PR reversal | Receipt | Receipt | DTIP, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_DP_REINSTATE | Direct payment reinstatement | Receipt | Receipt | DTIP, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_EXCESS_TO_OVERAGES | Minimal excess to AP overages | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_MINIMAL_BALANCE_REVERSAL | Premium minimal balance reversal | Receipt | Receipt | TOTAL, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_OR_ISSUE | Official receipt issued | Receipt | Receipt | CASH, CWT, SERVICE_FEE_INCOME, PROFIT_SHARE_INCOME, INCENTIVE_INCOME, OTHER_INCOME, OUTPUT_VAT, COMMISSION_COLLECTED, VAT_DUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_PAYMENT_APPLY | Payment applied to a booked invoice | Receipt | Receipt | APPLIED, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, REALIZED_COMMISSION, REALIZED_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_RECEIPT_REINSTATE | Receipt reinstated | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_UNAPPLIED_RECLASS | Unapplied payment reclassified | Receipt | Receipt | RELEASED, ASSIGNED | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_UNAPPLIED_REFUND | Unapplied payment refunded | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
OPS_UNAPPLIED_TO_INCOME | Unapplied payment reclassified to other income | Receipt | Receipt | AMOUNT, LG_AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PREMIUM_DEPOSIT | Unapplied collection | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
PREMIUM_RECEIPT | Premium collection | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_SETTLEMENT_RECEIPT | Receipt from reinsurer | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
SBM_HANDLING_FEE | Handling fee recognised | Receipt | Receipt | AMOUNT, INCOME, OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
SBM_NO_TOUCH_FEE | No Touch service fee billed | Receipt | Receipt | RECEIVABLE, INCOME, OUTPUT_VAT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
TAX_CWT_CERT_RECEIVED | Insurer 2307 certificate received | Receipt | Receipt | COMMISSION_CWT, INCENTIVE_CWT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
UNAPPLIED_APPLICATION | Application of unapplied collection | Receipt | Receipt | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_BALANCE_OFFSET | Reinsurer balance offset | Reinsurance | Reinsurance | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_CLAIM_RECOVERY | Reinsurance claim recovery | Reinsurance | Reinsurance | RECOVERY | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_PREMIUM_CEDED | Reinsurance premium ceded | Reinsurance | Reinsurance | CEDED_PREMIUM, RI_COMMISSION, NET_DUE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_RESERVE_SHARE | Reinsurers share of claim reserve | Reinsurance | Reinsurance | RESERVE_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
RI_SOA_ADJUSTMENT | Reinsurance statement adjustments | Reinsurance | Reinsurance | LEVY, PREMIUM_RESERVE, LOSS_RESERVE, INTEREST | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
BANK_TRANSFER | Bank transfer | Treasury | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
DISB_FUND_TRANSFER | Account funding transfer | Treasury | Payment | AMOUNT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_AMORTIZATION | Premium / discount amortization | Treasury | Investment | AMORTIZATION | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_FAIR_VALUE | Investment fair value change | Treasury | Revaluation | FAIR_VALUE_CHANGE | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_INTEREST_ACCRUAL | Investment interest accrual | Treasury | Investment | INTEREST | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_INTEREST_RECEIPT | Coupon / interest received | Treasury | Investment | CASH, FINAL_TAX, ACCRUED_INTEREST, INCOME_ADJUSTMENT | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_MATURITY | Investment maturity | Treasury | Investment | PROCEEDS, FINAL_TAX, FV_RESERVE, CARRYING_AMOUNT, ACCRUED_INTEREST, REALIZED_GAIN | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_PURCHASE | Investment purchase | Treasury | Investment | COST, PURCHASED_INTEREST, TOTAL | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_SALE | Investment sale | Treasury | Investment | PROCEEDS, FINAL_TAX, FV_RESERVE, CARRYING_AMOUNT, ACCRUED_INTEREST, REALIZED_GAIN | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
INVESTMENT_TAKE_ON | Investment opening balance | Treasury | Opening | CARRYING_AMOUNT, ACCRUED_INTEREST, TOTAL | Drop 0 template D0-08, sheet D0-08 Accounting rules | Not started
Note on A4: Event type: Accounting event of the platform
Note on B4: Name: Name of the event
Note on C4: Category: Category
Note on D4: Journal type: Journal type of the entries
Note on E4: Amount components: Amounts the rule lines can post
Note on F4: Prepared in: Template of the rules
Note on G4: Status: Status of the row
Note on H4: BDOI comments: Decision, value or comment of the owner

## Ref Migration cross-reference
Reference: migration cross-reference
← Back to Start here | Reference data loaded through the migration and items entered on screens: one route per item
Object | Name | Category | Proposed decision | Business owner | Extracts due | Configuration route | Duplication rule
R01 | Lists of values and MIS values | Reference | Migrate | Product Owner, Marketing Business System (MBS) | M3 | Loaded by the migration: CFG-061 Values of the lists used by migrated records; CFG-140 Code maps of the reference data | One route: not typed in this workbook
R02 | Branches and invoicing branches | Reference | Migrate | Head, Comptrollership | M3 | Loaded by the migration: CFG-141 Branch code map | One route: not typed in this workbook
R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Reference | Migrate | Heads, Retail and Corporate Marketing | M3 | Loaded by the migration: CFG-007 Sales organisation (regions, departments, teams, unit heads, account officers) | One route: not typed in this workbook
R04 | Insurers and insurer branches | Reference | Migrate | Head, Operations | M3 | Loaded by the migration: CFG-100 Insurers and insurer branches | One route: not typed in this workbook
R05 | Product lines, cover types, products and risk codes | Reference | Migrate | Product Owner, MBS | M3 | Loaded by the migration: CFG-090 Product catalogue | One route: not typed in this workbook
R06 | Package code map (legacy package and version to BIBS package version) | Reference | Migrate | Product Owner, MBS (approves); TSU (prepares) | M5; final at T-7 | Loaded by the migration: CFG-095 Package map (legacy package to BIBS package version) | One route: not typed in this workbook
R07 | Commission rates by insurer and product | Reference | Migrate | Head, Operations | M3 | Loaded by the migration: CFG-101 Commission rates by insurer and product | One route: not typed in this workbook
R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Reference | Migrate | Head, Comptrollership; Product Owner FRBS and ACSL | M3 | Loaded by the migration: CFG-024 Chart of accounts mapping (legacy GL account to BIBS account) | One route: not typed in this workbook
R09 | Payees | Reference | Conditional | Product Owner, Comptrollership - Disbursement | M3 | Loaded by the migration: CFG-103 Payees | One route: not typed in this workbook
R10 | Users and roles | Reference | Excluded | Unit Head, Analytics and Risk Management (User Access) | M5 (USER map) | Not migrated (excluded): users are created by access requests from BRD-11 template CI-01 (CFG-110); legacy user IDs are only mapped (code map USER) so the officer, handler and collector fields of migrated records resolve | -
R11 | Receipt series in use (AR and OR, ATP and next number) | Reference | Carry Forward | Operations - Financial Transactions | M3; final at T-3 | Loaded by the migration: CFG-050 Receipt series in use (AR and OR) | One route: not typed in this workbook
C01 | Client master (individual and corporate) | Client | Migrate | Product Owner, MBS; Heads, Retail and Corporate Marketing | M3; deltas daily from T-14 days | Business data, not configuration: prepared and signed in the Migration Workbook only | -
C03 | Client payout accounts (for refunds) | Client | Migrate | Product Owner, Comptrollership - Disbursement | M3 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
C04 | KYC documents and IDs | Client | Archive | Compliance | Before decommissioning | Business data, not configuration: prepared and signed in the Migration Workbook only | -
C05 | Screening results and risk ratings | Client | Excluded | Compliance | - | Business data, not configuration: prepared and signed in the Migration Workbook only | -
P01 | In-force policy headers | Policy | Conditional | Head, Operations | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
P02 | Expired policies and policy history | Policy | Archive | Head, Operations | Before decommissioning | Business data, not configuration: prepared and signed in the Migration Workbook only | -
P03 | Renewal advices already sent before go-live (RA-sent file) | Policy | Migrate | Head of the Renewal processing team | M4 (Trial migration 1); final at T-5 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
P04 | Submitted-policy masterlists | Policy | Conditional | CBG and Non-CBG Marketing (Submitted Policies) | M3 if in scope | Business data, not configuration: prepared and signed in the Migration Workbook only | -
P05 | Employee Benefits programmes | Policy | Conditional | Head, Employee Benefits | M3 if in scope | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Open item | Carry Forward | Operations - Financial Transactions; Head, Comptrollership | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F02 | Unapplied premium payments (UPP) with disposition in progress | Open item | Carry Forward | Operations - Financial Transactions | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | Open item | Carry Forward | Head, Operations (Collections) | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Open item | Conditional | Operations - Remittance | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F05 | DP billing in process and DP commission receivable | Open item | Carry Forward | Operations - Financial Transactions | With F01 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F06 | PDCs in the warehouse, check pick-ups and refunds in process | Open item | Conditional | Operations - Cashiering | M3; final at T-2 | Business data, not configuration: prepared and signed in the Migration Workbook only | -
F07 | Open claims | Open item | Conditional | Unit Head, Claims, RI and TU | M3 if in scope | Business data, not configuration: prepared and signed in the Migration Workbook only | -
G01 | GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) | GL | Migrate | Head, Comptrollership | M3; final at T-2; at each true-up | Business data, not configuration: prepared and signed in the Migration Workbook only | -
G02 | GL history (journals and balances before cutover) | History | Archive | Head, Comptrollership | Before decommissioning | Business data, not configuration: prepared and signed in the Migration Workbook only | -
G03 | FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) | GL | Migrate | Head, Comptrollership | T+16 (true-up 1); T+92 (final) | Business data, not configuration: prepared and signed in the Migration Workbook only | -
H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | History | Archive | Audit / Compliance; legacy system owners | Before decommissioning | Business data, not configuration: prepared and signed in the Migration Workbook only | -
H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | History | Archive | Audit / Compliance | Before decommissioning | Business data, not configuration: prepared and signed in the Migration Workbook only | -
Note on A4: Object: Data migration object of the Migration Workbook
Note on B4: Name: Object name
Note on C4: Category: Object category
Note on D4: Proposed decision: Decision proposed in the Data Migration set
Note on E4: Business owner: Owner of the object
Note on F4: Extracts due: Milestone of the extracts
Note on G4: Configuration route: Register items loaded by the object, or why none is
Note on H4: Duplication rule: The item is not also typed in this workbook

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | D0-02 Branches: Head office D0-02 Branches: Foreign currency authorised D0-04 Dimensions: Active D0-07 Categories and numbering: Bank category D0-06 Chart of accounts: Control Account D0-06 Chart of accounts: Manual Posting D0-06 Chart of accounts: Cost Centre Required D0-06 Chart of accounts: Revaluation Required PM-01 Product catalogue: Package PM-01 Product catalogue: Fleet PM-01 Product catalogue: Mortgage related PM-01 Product catalogue: Direct payment allowed PM-01 Product catalogue: Free First Year PM-02 Coverages and rules: Basic PM-02 Coverages and rules: Mandatory UA-03 Approval rules: Any approver may decide Ref Notifications: In-app wanted Ref Notifications: E-mail wanted Ref Document templates: BDOI layout attached | Y | Yes
|  | N | No
Market segment (MARKET_SEGMENT) | PM-01 Product catalogue: Market segments | CBG | Consumer Banking Group (CBG) | The values of the list MARKET_SEGMENT as delivered with BIBS; a new value is added with its template and may then be used here.
|  | COMBANK | Commercial Banking
|  | CORBANK | Corporate Banking
|  | RETAIL | Retail Marketing
|  | INSTITUTIONAL | Institutional Banking / SM / BDO accounts
Placement after (PLACEMENT_GATE) | PM-01 Product catalogue: Placement after | PAID | Premium paid
|  | CLIENT_CONFIRMATION | Client confirmation
TSU review (TSU_REVIEW) | PM-01 Product catalogue: TSU review | BY_RULES | By the review rules
|  | ALWAYS | Always
|  | NEVER | Never
Coverage and rule record (CI02_RECORD) | PM-02 Coverages and rules: Record | COVERAGE | Coverage or peril of a line
|  | FIELD_RULE | Field an account of the product needs
|  | DOCUMENT_RULE | Document an account of the product needs
Document type (DOCUMENT_TYPE) | PM-02 Coverages and rules: Document type | IDF | Insurance Declaration Form (IDF) | The values of the list DOCUMENT_TYPE as delivered with BIBS; a new value is added with its template and may then be used here.
|  | VALID_ID | Valid ID
|  | BIRTH_CERTIFICATE | Birth certificate
|  | ACCOUNT_LIST | List of account details (Excel)
|  | QUOTATION | Quotation / proposal
|  | CLIENT_ACCEPTANCE | Client acceptance e-mail
|  | EPOLICY | E-policy
|  | OFFICIAL_RECEIPT | Official receipt
|  | POLICY_COPY | Issued policy copy
|  | OTHERS | Others
|  | KYC_FORM | Client information sheet / KYC form
|  | PROOF_OF_ADDRESS | Proof of address
|  | SEC_CERTIFICATE | SEC / DTI certificate of registration
|  | GIS | General Information Sheet (GIS)
|  | SECRETARY_CERTIFICATE | Secretary's certificate / board resolution
|  | PKG_REQUEST_FORM | Package request form
|  | PKG_QUOTATION_SLIP | Package quotation slip
|  | PKG_INSURER_RESPONSE | Insurer package terms
|  | PKG_COMPARATIVE | Package comparative table
|  | PKG_SLIP_SIGNED | Package slip (signed)
|  | MANCOM_SIGNOFF | ManCom sign-off
|  | PKG_ADVISORY | Package advisory
|  | REQUEST_EMAIL | Quotation / proposal request e-mail
|  | QUOTATION_SLIP | Quotation slip
|  | INSURER_RESPONSE | Insurer response / terms
|  | COMPARATIVE_TABLE | Comparative table
|  | PROPOSAL_SLIP | Proposal slip
|  | PAYMENT_CONFIRMATION | Payment / client confirmation
|  | HOLD_COVER | Hold cover confirmation
|  | INSURANCE_ADVICE | Insurance Advice
|  | RENEWAL_ADVICE | Renewal advice
|  | RA_ACCEPTANCE | Renewal advice acceptance (e-mail)
|  | SIGNED_RA | Signed renewal advice
|  | LAMD_REPORT | LAMD loan report
|  | INSURER_RENEWAL_FILE | Insurer renewal file
|  | RENEWAL_LETTER | Renewal letter
|  | CLAIM_REPORT | Claims report
|  | EB_CLIENT_FEEDBACK | EB client feedback
|  | EB_BOR | Broker on Record (signed)
|  | EB_TOR | Terms of Reference (TOR)
|  | EB_MASTERLIST | Master list (named)
|  | EB_MASTERLIST_UNNAMED | Unnamed master list (census)
|  | EB_UTILIZATION | Utilization report
|  | EB_INDICATIVE_PROPOSAL | Indicative (incumbent) proposal
|  | EB_PROPOSAL | Insurer proposal
|  | EB_COMPARATIVE | Comparative analysis
|  | EB_FRANCHISE_FORM | Franchise request form
|  | EB_CLIENT_CONFIRMATION | Client confirmation of the chosen proposal
|  | EB_POLICY_FORM | EB policy form / contract
|  | EB_DIRECT_BILLING | Insurer direct billing (EB changes)
|  | EB_SOA | Insurer statement of account (EB)
|  | EB_MEMBER_CHANGE | Member change request
|  | EB_ISACOM_APPROVAL | ISACOM approval (non-accredited provider)
|  | CLIENT_REQUEST | Client request or letter
|  | CLIENT_PHOTO | Photo sent by the client
|  | SUBMITTED_POLICY | Submitted policy document
|  | SBM_IAAF | Insurance Adequacy Assessment Form (IAAF)
|  | SBM_TOR | Terms of Reference (TOR)
|  | SBM_LETTER | Submitted policy letter
|  | LEGACY_DOCUMENT | Legacy document (archive)
|  | MIG_EVIDENCE | Migration sign-off evidence
|  | PLACEMENT_SLIP | Placement slip
|  | PLACEMENT_FILE | Placement file
Clause kind (CLAUSE_KIND) | PM-03 Clause library: Kind | WARRANTY | Warranty | The values of the list CLAUSE_KIND as delivered with BIBS; a new value is added with its template and may then be used here.
|  | CLAUSE | Clause
|  | EXCLUSION | Exclusion
|  | DEDUCTIBLE_WORDING | Deductible wording
Rate table (RATE_TABLE) | PM-04 Rate tables: Table | TAX | Statutory charge or rating factor
|  | SHORT_PERIOD | Short-period table
|  | MOTOR_LIMIT | Motor BI / PD limit premium
Package map action (MAP_ACTION) | PM-07 Package map: Action | MAP | Renew with the BIBS package version
|  | REJECT | Send the candidate to the Renewal Exception bucket
Package document template (PKG_DOCUMENT) | PM-08 Document templates: Template | PKG_REQUEST_FORM | Package Request Form
|  | PKG_QUOTATION_SLIP | Package quotation slip
|  | PKG_COMPARATIVE | Package comparative table
|  | PKG_SLIP | Package slip
|  | PKG_ADVISORY | Package advisory
|  | PKG_RENEWAL_ADVISORY | Package renewal advisory
Product Maintenance list or parameter (PM_LIST_OR_PARAMETER) | PM-09 Lists and parameters: List or parameter | PKG_REQUEST_REASON | List: Package request reason
|  | PKG_RESPONSE_OUTCOME | List: Insurer response outcome
|  | PKG_ADVISORY_GROUP | List: Advisory recipient group
|  | PKG_NOT_PROCEEDED_REASON | List: Package not proceeded reason
|  | PKG_REQUEST_TYPE | List: Package request type
|  | INCENTIVE_TYPE | List: Incentive type
|  | COVERAGE_KIND | List: Coverage kind
|  | CLAUSE_KIND | List: Clause kind
|  | DOCUMENT_TYPE | List: Document type
|  | MARKET_SEGMENT | List: Market segment
|  | PKG_REQUEST_PREFIX | Parameter: Prefix of package request numbers; the year is appended
|  | PKG_QS_PREFIX | Parameter: Prefix of package quotation slip numbers; the year is appended
|  | PKG_QS_REPLY_DAYS | Parameter: Days insurers have to reply to a package quotation slip
|  | PACKAGE_EXPIRY_NOTICE_DAYS | Parameter: Days before the package end date at which PACKAGE_EXPIRING is first raised; again at 30 and 7 days
|  | PACKAGE_RENEWAL_AUTODRAFT | Parameter: The expiry monitor drafts a RENEW package request for packages reaching the notice period
|  | PKG_SLA_MKT_APPROVAL | Parameter: SLA hours of the Marketing approval of a package request
|  | PKG_SLA_TSU_REVIEW | Parameter: SLA hours of the TSU Team Lead review and recommendation
|  | PKG_SLA_TSU_APPROVAL | Parameter: SLA hours of the TSU Team Head approval
|  | PKG_SLA_NEGOTIATION | Parameter: SLA hours of the insurer negotiation stage
|  | PKG_SLA_MANCOM | Parameter: SLA hours of the ManCom sign-off
|  | PKG_SLA_MBS_SETUP | Parameter: SLA hours of the MBS package set-up
|  | PACKAGE_EXPIRY_REMINDER_DAYS | Parameter: Days before the package end date at which PACKAGE_EXPIRING is raised again after the first notice
|  | PKG_ADVISORY_GROUPS | Parameter: Recipient groups (list PKG_ADVISORY_GROUP) proposed on a new package advisory
|  | OTHER_CHARGES_ENABLED | Parameter: Bill the other charges of the products (documentation, notarial and authentication fees) with the premium
|  | PM_DEACTIVATION_ROUTE | Parameter: EFFECTIVE_DATED: Deactivate Package asks for the effective date, reason and approver (the bank's process); RETIRE_REQUEST: deactivation through a retirement package request
|  | PKG_DEACTIVATION_PREFIX | Parameter: Prefix of package deactivation request numbers; the year is appended
|  | PACKAGE_ANNIVERSARY_NOTICE_DAYS | Parameter: Days before the package anniversary date at which the anniversary notice is raised
|  | PACKAGE_EXPIRY_NOTIFY_MBS | Parameter: false: the expiry and anniversary notices go to the TSU Officers and TSU Team Leads (the bank's process); true: MBS is told as well
|  | PM_MARKETING_CHAIN | Parameter: ANY_ONE: one approval by the Marketing Team Leader, Team Head or Unit Head; TL_TH_UH: approval by the Team Leader, then the Team Head, then the Unit Head (the bank's process)
|  | PM_MANCOM_ROUTING | Parameter: SELECTED_PARALLEL_THEN_PRESIDENT: the selected ManCom approvers approve in parallel, then the President (the bank's process); ANY_MEMBER: one sign-off
|  | PM_MANCOM_PRESIDENT | Parameter: User ID of the President, who approves after every other selected ManCom approver
|  | PM_DEPLOYMENT_REQUEST | Parameter: AUTO: the ManCom approval forwards the package to MBS; MANUAL: the Request for Deployment button forwards it (the bank's process)
|  | PKG_DEPLOYMENT_PREFIX | Parameter: Prefix of package deployment request numbers; the year is appended
|  | PM_DIRECT_MAINTENANCE | Parameter: true: authorized users add and update Product Matrix records directly with approval (the bank's process); false: new packages come only from package requests
|  | PKG_MIN_POLICIES | Parameter: Least estimated number of policies of a package request
|  | PKG_MIN_PREMIUM | Parameter: Least estimated total basic premium of a package request (base currency)
|  | PLACEMENT_UPDATE_DAY | Parameter: Weekday of the scheduled Consolidated Placement Update Report (MONDAY to SUNDAY)
|  | PLACEMENT_UPDATE_TIME | Parameter: Time of the scheduled Consolidated Placement Update Report (HH:MM, business time zone)
|  | PLACEMENT_UPDATE_DAYS | Parameter: Length of the reporting period of the Consolidated Placement Update Report in days, ending on the report date
|  | PLACEMENT_UPDATE_SCOPE | Parameter: QUOTATION: the report lists the quotation requests (the bank's process); QUOTATION_AND_PACKAGE: the package requests follow
Incentive type (INCENTIVE_TYPE) | PM-10 Incentive criteria: Incentive type | OTHERS | Others (see description) | The values of the list INCENTIVE_TYPE as delivered with BIBS; a new value is added with its template and may then be used here.
|  | MIGRATED | Migrated booking incentive rule
Bulk request action (UA_ACTION) | UA-01 Users and roles: Action | ENROL | Enrol a new user
|  | MODIFY | Modify a user
|  | DEACTIVATE | Deactivate a user
|  | REACTIVATE | Reactivate a user
Privilege level (PRIVILEGE_LEVEL) | UA-02 Role matrix: Privilege level | Low | Low
|  | Standard | Standard
|  | High | High: a second approval when given or raised
|  | Admin | Admin: a second approval when given or raised
Change against the matrix (KEEP_ADD_REMOVE) | UA-02 Role matrix: Keep / Add / Remove | KEEP | Keep the permission
|  | ADD | Add the permission
|  | REMOVE | Remove the permission
Role in user access (UA_ROLE) | UA-03 Approval rules: Role in user access | Requestor | Raises access requests for the unit
|  | Approver | Approves access requests
|  | Second Approver | Second approval of High and Admin privileges
|  | Group-profile requester | Raises group-profile requests
|  | Implementer | System Administrator who implements approved requests
Separation-of-duties rule status (SOD_STATUS) | UA-04 SoD rules: Status | Enforced | A fixed rule of BIBS
|  | To confirm | Proposed; BDOI confirms
|  | New | Added by BDOI
Separation-of-duties control (SOD_CONTROL) | UA-04 SoD rules: Control | Prevent | A rule of Separation of Duties: BIBS refuses the request
|  | Detect by review | Reviewed with the reports
|  | Second approval | A second approver decides
Review frequency (REVIEW_FREQUENCY) | UA-04 SoD rules: Review frequency | Monthly | Monthly
|  | Quarterly | Quarterly
Sign-in (UA_PARAMETER) | UA-05 Parameters: Parameter | LOGIN_MAX_FAILED_ATTEMPTS | Consecutive failed logins that lock a user account; applies to all users
|  | SESSION_IDLE_WARNING_MINUTES | Minutes of inactivity after which the web client warns that the session will sign out
|  | SESSION_TIMEOUT_MINUTES | Minutes of inactivity after which the web session signs out automatically
|  | SESSION_EXPIRY_WARNING_MINUTES | Minutes before the system-triggered (absolute) sign-out at which the web client warns the user
|  | AUTH_MODE | Sign-in mode: LOCAL (BIBS passwords) or DIRECTORY (BDO directory sign-in by Windows ID, when the EIAM sign-in is specified)
|  | USER_ID_PATTERN | Regular expression of a new user ID on enrolment requests
|  | USER_ID_FORMAT_TEXT | The user ID format in words, shown to the requester with the format check of USER_ID_PATTERN
|  | PASSWORD_HISTORY_COUNT | Previous passwords a local account may not reuse (at least the last ten)
|  | PASSWORD_MAX_AGE_DAYS | Days after which a password must be changed, LOCAL mode; 0 = never
|  | PASSWORD_MIN_AGE_DAYS | Days before a changed password may be changed again, LOCAL mode
|  | UAM_WORKING_HOURS | Working hours; an access request submitted outside them needs a second approval
|  | UAM_ANY_APPROVER | When true, any holder of ACCESS_APPROVE may decide a request, not only the approver chosen by the requester
|  | UAM_ROLE_APPLY_ON_APPROVAL | When true, an approved group-profile or role-permission request applies at its last approval; when false it waits for the System Administrator to implement it
|  | UAM_EXTERNAL_USERS | When true, access requests may be raised for external (portal) users; stays false while no portal is installed
|  | UAM_DORMANT_DAYS | Days without a sign-in after which a user is deactivated by the daily dormant-user job; 0 = never
|  | UAM_DORMANT_NOTICE_DAYS | Days before the dormant-user deactivation on which the user is told to sign in; 0 = no notice
|  | JOB_FAILURE_RECIPIENTS | Comma separated e-mail addresses told of every failed batch job
User access list (UA_LIST) | UA-06 Lists of values: List | UAM_BUSINESS_UNIT | List: Business unit group
|  | UAM_USER_LEVEL | List: User level
|  | UAM_DEACTIVATION_REASON | List: User deactivation reason
Dimension (DIMENSION) | D0-04 Dimensions: Dimension | COST_CENTER | Cost centre
|  | BUSINESS_LINE | Business line
Account class (ACCOUNT_CLASS) | D0-07 Categories and numbering: Account class | ASSET | Asset
|  | LIABILITY | Liability
|  | EQUITY | Equity
|  | INCOME | Income
|  | EXPENSE | Expense
Account class of the chart (ACCOUNT_CLASS_CHART) | D0-06 Chart of accounts: Class | ASSET | Asset
|  | LIABILITY | Liability
|  | EQUITY | Equity
|  | INCOME | Income
|  | EXPENSE | Expense
|  | MEMORANDUM | Memorandum
Account level (ACCOUNT_LEVEL) | D0-06 Chart of accounts: Level | GROUP | Group
|  | MAIN | Main account
|  | SUB | Sub-account
|  | MICRO | Micro account
Negative balance (NEGATIVE_BALANCE) | D0-06 Chart of accounts: Negative Balance | ALLOW | Allowed
|  | WARN | Allowed with a warning
|  | BLOCK | Refused
Category or numbering row (CATEGORY_ROW) | D0-07 Categories and numbering: Row | CATEGORY | GL category
|  | NUMBERING | Numbering scheme under a parent account
Accounting event (ACCOUNTING_EVENT) | D0-08 Accounting rules: Event type | CLAIM_RECOVERY | Salvage / subrogation recovery
|  | CLAIM_RESERVE | Claim reserve change
|  | CLAIM_SETTLEMENT | Claim settlement approved
|  | CLAIM_COINSURANCE | Coinsurer share of a claim
|  | COINSURANCE_SHARE | Coinsurer share of premium
|  | COMMISSION_ACCRUAL | Commission accrued
|  | OPS_ADJ_COMMISSION | Commission adjustment without premium change
|  | OPS_INCENTIVE_ACCRUE | Incentive earned from insurer
|  | OPS_INCENTIVE_PASS_ON | Incentive pass-on to branches
|  | OPS_REMIT_CPC2 | CPC2 incentive per remittance batch
|  | OPS_REMIT_INCENTIVE | Early remittance incentive
|  | ASSET_ACQUISITION | Fixed asset capitalized
|  | CLAIM_PAYMENT | Claim payment
|  | COMMISSION_PAYMENT | Commission payment
|  | DISB_CHECK_NEGOTIATED | Check negotiated
|  | DISB_CHECK_STALE | Check staled
|  | DISB_VOUCHER | Disbursement voucher approved
|  | FRBS_SERVICE_FEE_ACCRUE | Service fee accrual
|  | MISC_PAYMENT | Miscellaneous payment
|  | OPS_REMITTANCE | Remittance to insurer
|  | OPS_REMIT_DEDUCTION | Remittance deduction on insurer confirmation
|  | PDC_ISSUED_PRESENTED | Issued PDC presented
|  | PETTY_CASH_EXPENSE | Petty cash disbursement
|  | PETTY_CASH_REPLENISHMENT | Petty cash reimbursement
|  | PREMIUM_REFUND_PAYMENT | Premium refund payment
|  | PRQ_CA_LIQUIDATION | Cash advance liquidation
|  | RI_SETTLEMENT_PAYMENT | Payment to reinsurer
|  | SUPPLIER_INVOICE | Supplier invoice
|  | SUPPLIER_PAYMENT | Supplier payment
|  | TAX_REMITTANCE | Tax remittance
|  | POLICY_CANCELLATION | Policy cancellation
|  | POLICY_ENDORSEMENT | Policy endorsement
|  | POLICY_ISSUE | Policy issued / renewed
|  | BROKER_BOOKING | Broker booking
|  | MIG_LEGACY_INVOICE_OPENING | Legacy invoice opening
|  | MIG_LEGACY_POSITION_TRUEUP | Legacy open-item adjustment
|  | OPS_AR_INSURER_SETUP | AR Insurer set-up after a remitted decrease
|  | OPS_WRITE_OFF | Minimal balance write-off / credit
|  | ASSET_DEPRECIATION | Monthly depreciation
|  | ASSET_TAKE_ON | Fixed asset opening balance
|  | ASSET_TRANSFER | Inter-branch asset transfer
|  | CLAIM_MARGIN_PROVISION | ULAE and risk margin provision
|  | DAC_PROVISION | Deferred acquisition cost
|  | IBNR_PROVISION | IBNR reserve
|  | PREMIUM_DEFICIENCY_PROVISION | Premium deficiency reserve
|  | TAKAFUL_SURPLUS | Surplus / Mudharabah distribution
|  | UPR_PROVISION | Unearned premium reserve
|  | ASSET_DISPOSAL | Fixed asset disposal
|  | MIG_UPP_OPENING | Legacy unapplied payment opening
|  | MISC_RECEIPT | Miscellaneous receipt
|  | OPS_AP_UNAPPLIED_COMMISSION | Reinstated OR payment to AP Unapplied Commission
|  | OPS_AR_INSURANCE_RECEIPT | Insurer non-premium receipt
|  | OPS_AR_INSURER_REFUND | Reversed payment to AR Insurer Refund
|  | OPS_AR_RECEIPT | Acknowledgement receipt (premium)
|  | OPS_COMMISSION_PAYMENT_HELD | Cancelled OR payment kept for Commission Receivable
|  | OPS_CWT_DTIP_OFFSET | 2307 certificate offset against DTIP
|  | OPS_CWT_RECLASS | PR reclassified to the client 2307
|  | OPS_DP_COMMISSION_COLLECT | Direct payment commission collected
|  | OPS_DP_PR_REVERSAL | Direct payment PR reversal
|  | OPS_DP_REINSTATE | Direct payment reinstatement
|  | OPS_EXCESS_TO_OVERAGES | Minimal excess to AP overages
|  | OPS_MINIMAL_BALANCE_REVERSAL | Premium minimal balance reversal
|  | OPS_OR_ISSUE | Official receipt issued
|  | OPS_PAYMENT_APPLY | Payment applied to a booked invoice
|  | OPS_RECEIPT_REINSTATE | Receipt reinstated
|  | OPS_UNAPPLIED_RECLASS | Unapplied payment reclassified
|  | OPS_UNAPPLIED_REFUND | Unapplied payment refunded
|  | OPS_UNAPPLIED_TO_INCOME | Unapplied payment reclassified to other income
|  | PREMIUM_DEPOSIT | Unapplied collection
|  | PREMIUM_RECEIPT | Premium collection
|  | RI_SETTLEMENT_RECEIPT | Receipt from reinsurer
|  | SBM_HANDLING_FEE | Handling fee recognised
|  | SBM_NO_TOUCH_FEE | No Touch service fee billed
|  | TAX_CWT_CERT_RECEIVED | Insurer 2307 certificate received
|  | UNAPPLIED_APPLICATION | Application of unapplied collection
|  | RI_BALANCE_OFFSET | Reinsurer balance offset
|  | RI_CLAIM_RECOVERY | Reinsurance claim recovery
|  | RI_PREMIUM_CEDED | Reinsurance premium ceded
|  | RI_RESERVE_SHARE | Reinsurers share of claim reserve
|  | RI_SOA_ADJUSTMENT | Reinsurance statement adjustments
|  | BANK_TRANSFER | Bank transfer
|  | DISB_FUND_TRANSFER | Account funding transfer
|  | INVESTMENT_AMORTIZATION | Premium / discount amortization
|  | INVESTMENT_FAIR_VALUE | Investment fair value change
|  | INVESTMENT_INTEREST_ACCRUAL | Investment interest accrual
|  | INVESTMENT_INTEREST_RECEIPT | Coupon / interest received
|  | INVESTMENT_MATURITY | Investment maturity
|  | INVESTMENT_PURCHASE | Investment purchase
|  | INVESTMENT_SALE | Investment sale
|  | INVESTMENT_TAKE_ON | Investment opening balance
Debit or credit (DEBIT_CREDIT) | D0-08 Accounting rules: Debit or credit | DEBIT | Debit
|  | CREDIT | Credit
Legacy control account (LEGACY_ACCOUNT) | D0-09 Legacy accounts: Legacy account | Premium Receivable - Legacy | Per component
PR 2307 - Legacy
Due to Insurers - Legacy
Commission Receivable - Legacy
Unrealised Commission - Legacy
Deferred Output VAT - Legacy
Unapplied Collections - Legacy
|  | Migration Clearing | Nets to zero after the opening
Tax type (TAX_TYPE) | D0-10 Tax codes: Tax type | EWT | Expanded withholding tax
|  | FWT | Final withholding tax
|  | VAT | Value-added tax
|  | PT | Percentage tax
Payee class (PAYEE_CLASS) | D0-10 Tax codes: Payee class | SUPPLIER | Supplier | The values of the list PAYEE_CLASS as delivered with BIBS; a new value is added with its template and may then be used here.
|  | INSURER | Insurer
|  | EMPLOYEE | Employee
|  | CLIENT | Client
|  | GOVERNMENT | Government agency
|  | OTHER | Others
Module of an approval matrix (APPROVAL_MODULE) | D0-15 Approval limits: Module | Submitted Policies
Employee Benefits
Sanction Screening
Disbursement
Route (ROUTE) | Ref Lists of values: Route Ref System parameters: Route | Screen
Template
Migration object
Status (STATUS) | Ref Lists of values: Status Ref System parameters: Status Ref Document numbering: Status Ref Notifications: Status Ref Document templates: Status Ref Accounting events: Status Start here: Status | Not started
In progress
Ready for review
Confirmed
Not applicable
Templates of this workbook (TEMPLATES) | Questions and comments: Template | D0-02 Branches
D0-04 Cost centres and business lines
D0-07 Account categories and numbering
PM-09 Lists of values and parameters
UA-02 Role-to-permission matrix
UA-06 Lists of values
D0-05 Employees
D0-06 Chart of accounts
PM-01 Product catalogue
UA-01 Users and roles load
D0-03 Holiday calendar
UA-04 Separation-of-duties rules
D0-11 Company bank accounts
PM-02 Coverages, perils and field rules
PM-03 Clause library
PM-05 Insurers, branches and commission rates
D0-01 Company
D0-08 Accounting rules
D0-09 Legacy control accounts
D0-10 Tax codes
D0-15 Approval limits and matrices
PM-04 Rate tables
PM-10 Incentive criteria
UA-03 Approvers, approval rules and limits
PM-06 Packages in force at go-live
D0-12 Check books
D0-13 Petty cash funds
D0-14 Bank statement layouts
PM-07 Package map (legacy package to BIBS package version)
PM-08 Document templates
UA-05 Password, session and sign-in parameters
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100