## Cover
CHANGE REGISTER
Change Management Register
For documentation and change control; does not change the platform or the FRS baseline.
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 26 September 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
How to read | Reading guide, deviation types, statuses, priorities, size classes and column definitions
Document control | Version history, review and approval, distribution; the statement that the register does not change the platform or the FRS
Register | 178 deviations from the BRDs for change control. For documentation and change control; does not change the platform or the FRS baseline. | 178
Summary | Counts and man-days by drop, BRD, deviation type, status and priority. Formulas read the Register sheet, so the figures follow any change to it.
Effort basis | How the man-days are estimated: team roles, the man-day, what is included and excluded, and the size classes.
Change control | Change-control process for deviations and new change requests, with the roles and the proposed Change Control Board (CCB).
CR form | Change request form: one per CR; the Project Manager files the signed form with the register.
Legend
Draft | Raised by the project team. Impact analysis done; the BDOI answer or decision it needs is still open.
For CCB review | Impact analysis complete; ready for the Change Control Board to approve, reject or defer.
Approved | Approved by the CCB; scheduled into a drop or release.
Rejected | Rejected by the CCB; the BRD text stands, or the item is closed without change.
For acceptance | The proposed behaviour is decided and documented and differs from the BRD text; the CCB records the acceptance. No work remains.
Status as of 26 September 2026. Baseline: FRS v1.0 of every BRD (BRD-2, BRD-6, BRD-11 and BRD-13 at v1.1 or later), discrepancy register v1.2, BDOI answers of 26 September 2026.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## Document control
Document control
For documentation and change control; does not change the platform or the FRS baseline.
Document | Change Management Register (BIBS-CMR-BRD-00)
Version | 1.0
Date | 26 September 2026
Status | Issued for BDOI review
Status as of | 26 September 2026
Baseline | FRS v1.0 of every BRD (BRD-2, BRD-6, BRD-11 and BRD-13 at v1.1 or later), discrepancy register v1.2, BDOI answers of 26 September 2026
Word summary | BIBS_Change_Register_BRD-00_Change_Management_Summary_v1.0.docx
Owner of the register | Project Manager (iorta TechNXT) on behalf of the Change Control Board
Version history
Version | Date | Author | Reviewer | Approver | Change
1.0 | 26 Sep 2026 | iorta TechNXT Business Analyst lead | iorta TechNXT Solution Architect | BIBS Product Owner (pending) | First issue: 178 deviations from BRD-00 to BRD-13 with effort in man-days
Review and approval
Role | Organisation | Name | Signature | Date | Purpose
BIBS Product Owner | BDOI |  |  |  | Chair of the CCB; approves the register
Program Manager, Business Project Services | BDO Unibank ESG |  |  |  | Plan, drops and effort
Head, Comptrollership | BDOI |  |  |  | Posting, GL, tax and BIR items
Chief Compliance Officer | BDOI |  |  |  | Screening, access and retention items
Project Manager | iorta TechNXT |  |  |  | Register owner; CCB secretary
Distribution
Recipient | Organisation | Purpose
Owners of BRD-1 to BRD-13 (department heads and product owners) | BDOI | Review the CRs of their BRD; decision owners
BDOI IT (integration owners) | BDOI | Interface and infrastructure CRs
Project team | iorta TechNXT | Impact analysis, scheduling, FRS revisions

## How to read
How to read this register
For documentation and change control; does not change the platform or the FRS baseline.
Reading guide
• | One row per deviation from a BRD requirement, merged across sources (the clarifications chapters of the FRS, the requirements baselines, the discrepancy register v1.2, the alignment pack, the cross-BRD decisions and the BDOI answers of 26 September 2026). The Source column says where each deviation is recorded.
• | Filter the Register sheet by Drop, BRD, Deviation type, Priority or CR status. The Summary sheet recounts from the Register, so it stays correct when rows are added or a status changes.
• | Effort is in man-days for the work still needed to close the deviation as proposed (Effort basis sheet). It is 0 when no work remains and the behaviour only needs acceptance. 'BRD as written' gives the indicative effort to deliver the BRD text instead, where the CCB may want to compare.
• | A CR moves Draft -> For CCB review -> Approved or Rejected. Rows marked 'For acceptance' describe decided behaviour that differs from the BRD: the CCB records the acceptance; no work remains.
• | The register does not change the FRS. An approved CR reaches the FRS only through the next FRS revision, which cites the CR ID.
Deviation types
Type | Meaning
Scope addition — beyond BRD | BIBS does more than the BRD asks, or the umbrella FRS proposes a requirement that no function BRD owns. BDOI accepts the addition or removes it.
Scope reduction / descoped | A BRD requirement is not delivered, or is delivered with less than the BRD asks, by a BDOI instruction or a proposal. BDOI confirms the descoping.
Behaviour differs from BRD | The requirement is met in a different way from the BRD text. BDOI accepts the proposed behaviour or asks for the BRD text.
Deferred pending BDOI answer | The element runs with a documented default and waits for a BDOI answer (values, layouts, rules, a yes / no on scope).
Deferred to Phase 2 | Out of phase 1 by BDOI decision; kept for phase 2.
BRD conflict resolved by decision | Two BRDs, or two parts of one BRD, conflict. A binding decision (D1-D10) or a proposed resolution settles the conflict; BDOI confirms it.
Integration dependency | The requirement depends on an interface with a BDO or insurer system that is not yet specified. BIBS runs on an upload or a manual step until the interface exists.
NFR / infrastructure change | A non-functional value (hours, availability, recovery, retention, sizing) or an infrastructure choice differs from one or more BRDs, or from the IER workbook.
Data migration | The migration or cut-over treatment differs from what a BRD assumes, or adds work that a BRD does not state.
CR status
Status | Meaning
Draft | Raised by the project team. Impact analysis done; the BDOI answer or decision it needs is still open.
For CCB review | Impact analysis complete; ready for the Change Control Board to approve, reject or defer.
Approved | Approved by the CCB; scheduled into a drop or release.
Rejected | Rejected by the CCB; the BRD text stands, or the item is closed without change.
For acceptance | The proposed behaviour is decided and documented and differs from the BRD text; the CCB records the acceptance. No work remains.
Priority
Priority | Meaning
High | Affects money (premium, commission, GL, remittance), regulatory compliance, security or access, or blocks a drop. Decide before the FRS of the area is signed off.
Medium | Changes a rule, screen, report or interface; a documented default runs until BDOI decides.
Low | Wording, labels or presentation; no effect on money, control or data.
Size classes (effort basis)
Class | Man-days
0 | Acceptance only
S | 1 to 3
M | 4 to 10
L | 11 to 25
XL | more than 25
Columns of the data sheets
Sheet | Column | Meaning | Allowed values
Register | CR ID | Change request identifier, CR-nnnn
Register | Drop | BDOI drop of the item (Drop 0 set-up and migration, Drop 1 transactional, Drop 2 independent), Programme (cross-drop) or Phase 2 | Drop 0, Drop 1, Drop 2, Programme, Phase 2
Register | BRD | Primary BRD; other BRDs involved are named in the BRD requirement column | BRD-00, BRD-01, BRD-02, BRD-03, BRD-04, BRD-05, BRD-06, BRD-07, BRD-08, BRD-09, BRD-10, BRD-11, BRD-12, BRD-13
Register | BRD requirement ID(s) and page | BRD requirement IDs with the PDF page of the source BRD
Register | FRS FR ID(s) | Functional requirement IDs of the FRS, or the FRS section that records the item
Register | Deviation type | Kind of deviation (How to read) | Scope addition — beyond BRD, Scope reduction / descoped, Behaviour differs from BRD, Deferred pending BDOI answer, Deferred to Phase 2, BRD conflict resolved by decision, Integration dependency, NFR / infrastructure change, Data migration
Register | BRD requirement | What the BRD asks, in short
Register | Proposed behaviour | The proposed behaviour of BIBS
Register | Reason | BDOI decision, open question or technical constraint behind the deviation
Register | Business impact | Effect on the business process, money, control or users
Register | Affected departments | BDOI departments affected
Register | Analysis (md) | Man-days of analysis still needed
Register | Dev. (md) | Man-days of development and configuration
Register | Test (md) | Man-days of SIT test preparation, execution and regression
Register | Doc. (md) | Man-days of documentation (FRS, test plan, guides)
Register | Total (md) | Sum of the four effort columns (formula)
Register | Size basis | Size class and chosen number: S 1-3, M 4-10, L 11-25, XL over 25; 0 = acceptance only (formula)
Register | BRD as written (md) | Indicative man-days to deliver the BRD text instead of the proposed behaviour (blank where not applicable)
Register | Priority | High, Medium or Low (How to read) | High, Medium, Low
Register | CR status | Status in the change-control process | Draft, For CCB review, Approved, Rejected, For acceptance
Register | Decision owner (BDOI) | BDOI role that decides the CR
Register | Register / question refs | Discrepancy register items (DCR-), question IDs and decisions (D1-D10)
Register | Target drop / release | Drop or release in which the CR is closed | FRS sign-off (Nov 2026), Drop 1, first release (Nov - Dec 2026), Drop 1, second release (Jan - Feb 2027), Migration functions (Nov 2026 - Mar 2027), Infrastructure before SIT (by Jan 2027), Drop 2 (Mar - Apr 2027), Before go-live (Oct - Dec 2027), Phase 2, After BDOI answer (slot set by the CCB)
Register | Source of the record | Where the deviation is recorded (FRS section, requirements baseline, register, alignment pack)

## Register
Register
178 deviations from the BRDs for change control. For documentation and change control; does not change the platform or the FRS baseline.
CR ID | Drop | BRD | BRD requirement ID(s) and page | FRS FR ID(s) | Deviation type | BRD requirement | Proposed behaviour | Reason | Business impact | Affected departments | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md) | Size basis | BRD as written (md) | Priority | CR status | Decision owner (BDOI) | Register / question refs | Target drop / release | Source of the record
CR-0001 | Phase 2 | BRD-00 | CORE-15.01-15.10; BR-153 to BR-160 (p.10-11); capability matrix (p.28); ReInsurance BRD | FRS BRD-00 section 6 (Reinsurance, phase 2); CLR-CR-01 | Deferred to Phase 2 | Reinsurance placement, slips, SOA, claims reporting and payment, net settlement (capability 15). | Out of phase 1: the ReInsurance BRD is received and is phase 2. Phase 1 keeps open reinsurer party types, template-driven slips and SOAs, report subscriptions, open-item matching and the claim party model. The insurer-side reinsurance module of the platform stays hidden from BDOI roles. | BDOI answer A3 of 26-Sep-2026: the reinsurance module is phase 2. | Reinsurance placement stays outside BIBS until phase 2; only the transactions routed through Remittance (CR-0002) are in phase 1. | Reinsurance; Comptrollership; Operations | 0 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | A3; CLR-CR-01; A-CR-04 | Phase 2 | FRS BRD-00 sections 1.2, 5, 6; Programme alignment 1.2
CR-0002 | Drop 1 | BRD-02 | Drop plan item 1.D3 (Operations BRD, Remittance Addendum; Reinsurance BRD); RMTID.001-040 (p.49-70) | FR-OP-030 to FR-OP-041 (Remittance); FRS BRD-2 v1.1 introduction | Scope addition — beyond BRD | The Operations BRD specifies remittance to insurers only. The drop plan names the Reinsurance BRD for Remittance in Drop 1. | Proposed: the named reinsurance transactions run in Remittance as remittance types with reinsurer counterparties and their own accounting rules; treaty and facultative processing stays phase 2. | BDOI answer A3 of 26-Sep-2026: Remittance handles the reinsurance transactions in Drop 1. Which transactions and their accounting are open (IQ20). | Reinsurance premium and recoveries settled through BIBS from go-live; new posting rules for Comptrollership. | Operations (Remittance); Comptrollership; Reinsurance | 4 | 12 | 6 | 2 |  |  |  | High | Draft | Head of Operations (Financial Transactions and Processing) | DCR-210; IQ20; A3 | Drop 1, second release (Jan - Feb 2027) | Register DCR-210; Programme alignment 2.2 item 1
CR-0003 | Drop 1 | BRD-02 | Drop plan items 1.D2 and 1.D3: Operations BRD (Cashiering Addendum), (Remittance Addendum) | FRS BRD-2 (Cashiering, Remittance chapters) | Deferred pending BDOI answer | The drop plan names a Cashiering Addendum and a Remittance Addendum to the Operations BRD. | The Operations pack received has only Addendum 1 (RMTID.002, ADJID.014). FRS BRD-2 is written without the two addenda; they are taken into FRS BRD-2 v1.2 when received and their impact is estimated then. | Documents not received (DCR-215, IQ20). | Cashiering and Remittance requirements may change after FRS sign-off. | Operations (Cashiering, Remittance) | 3 | 0 | 0 | 2 |  |  |  | Medium | Draft | Head of Operations (Financial Transactions and Processing) | DCR-215; IQ20 | After BDOI answer (slot set by the CCB) | Register DCR-215; Programme alignment 2.2
CR-0004 | Drop 2 | BRD-00 | CORE-14.08-14.10; BR-146 to BR-148 (p.10); BRD-7 (no claim money through BDOI) | FRS BRD-00 CLR-CR-02; FR-CM (none) | Deferred pending BDOI answer | Safekeeping of unclaimed settlement cheques, hand-over to and retrieval from Cashiering. | BRD-7 has no claim money through BDOI (CLQ10) and Claims posts no accounting entry. If BDOI holds cheques: a cheque custody register in Claims using the Cashiering cheque hand-over. | Conflict between the umbrella BRD and BRD-7; CRQ03, CLQ10, XQ13. | Without a register, cheque custody stays manual outside BIBS. | Claims; Operations (Cashiering) | 2 | 5 | 3 | 1 |  |  | 11 | Medium | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | DCR-164; CRQ03; CLQ10; XQ13 | Drop 2 (Mar - Apr 2027) | FRS BRD-00 chapter 5 (CLR-CR-02); Cross-BRD decisions XQ13
CR-0005 | Drop 1 | BRD-00 | CORE-16.06; BR-165 (p.11); BRD-9 CSF-EM10 (e-mail of 13-Feb-2026) | FRS BRD-00 CLR-CR-03; FRS BRD-9 chapter 12 | Scope reduction / descoped | CSF case resolution: add and edit case details and status. | Out of phase 1. BRD-9 puts case management out of scope and keeps case logging in SharePoint. If BDOI brings it in: a CSF case record in the CSF module. | BRD-9 e-mail of 13-Feb-2026; CRQ04 open; XQ12. | Contact Center cases stay in SharePoint; no case history in BIBS. | Contact Center Management; Alternative Distribution | 0 | 0 | 0 | 1 |  |  | 18 | Medium | For CCB review | Product Owner, CSF (Contact Center Management) | DCR-163; CRQ04; XQ12 | FRS sign-off (Nov 2026) | FRS BRD-00 chapter 5 (CLR-CR-03); FRS BRD-9 chapter 12
CR-0006 | Programme | BRD-00 | CORE-18.01; BR-176 (p.11) | FRS BRD-00 CLR-CR-09 | Scope reduction / descoped | Include any other or additional system capabilities (emerging capabilities). | No work until the capabilities are listed: the requirement has no content to deliver or test. BDOI lists the capabilities or withdraws BR-176. | CRQ10 open. | None until BDOI names a capability; a named capability becomes its own CR. | Business Project Services | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | CRQ10; CLR-CR-09 | FRS sign-off (Nov 2026) | FRS BRD-00 section 5
CR-0007 | Programme | BRD-00 | XC-21 ALeA e-mail address encoding (p.43) | FRS BRD-00 CLR-CR-10 | Deferred pending BDOI answer | ALeA e-mail address encoding, as needed. | Not in scope; the term is not defined in the BRD pack. | CRQ20 open. | None known until BDOI explains ALeA. | BDOI IT | 1 | 0 | 0 | 0 |  |  |  | Low | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ20; CLR-CR-10 | After BDOI answer (slot set by the CCB) | FRS BRD-00 section 5
CR-0008 | Programme | BRD-00 | XC-16; BR-183 (p.23) | FRS BRD-00 traceability (OUT); A-CR-05 | Behaviour differs from BRD | The vendor uses Figma for design execution. | Screens follow the BDO UX guidelines and the BIBS design system in code; the vendor-qualification items are met by the alignment pass and persona walkthroughs. BDOI supplies the icon set and design files (CRQ17). | A-CR-05: BR-178 to BR-183 are vendor-qualification items. | None on the business process. | Business Project Services | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | BIBS Product Owner with the Program Manager, Business Project Services | CRQ17; A-CR-05 | FRS sign-off (Nov 2026) | FRS BRD-00 traceability XC-16
CR-0009 | Drop 0 | BRD-00 | CORE-17.01; BR-170 (p.11) | FR-CR-031 | Scope addition — beyond BRD | Master data change logging for users, products, insurers and LOVs. No function BRD owns it. | BIBS audits each action with a summary. Proposed: a field-level log (old and new values) for the registered master types. | Umbrella requirement without an owning BRD (Drop 0 item 0.4); CRQ07 open on the master types, approver and viewers. | Auditors can see what changed on a master record, field by field. | Business Project Services; Compliance; MBS; Comptrollership | 2 | 6 | 4 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | DCR-174; CRQ07; CLR-CR-04 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-04); register DCR-174
CR-0010 | Drop 0 | BRD-00 | CORE-17.02; BR-171 (p.11) | FR-CR-061 | Scope addition — beyond BRD | Insurer management: risk participation, payment terms, remittance schedules on the insurer. | The insurer page has no such attributes. Proposed: add the attributes and LOV INSURER_CONTACT_FUNCTION. | Umbrella requirement without an owning BRD; CRQ08 open on meaning, owners and approval. | One place for insurer terms used by Remittance and Collections. | MBS; Operations (Remittance) | 2 | 4 | 2 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ08; CLR-CR-05 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-05)
CR-0011 | Drop 0 | BRD-00 | CORE-17.04; BR-173, BR-174 (p.11) | FR-CR-062 | Scope addition — beyond BRD | MIS field definition. | Proposed: an MIS field catalogue that names existing data per entity; users do not add database fields (A-CR-06). | Umbrella requirement without an owning BRD; CRQ09 (fixed list or user-defined fields). | Consistent MIS reporting fields across modules and migration. | Business Project Services; MIS; Marketing | 2 | 6 | 3 | 1 |  |  | 30 | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ09; CLR-CR-06 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-06)
CR-0012 | Programme | BRD-00 | CORE-21.04; BR-053 (p.12) | FR-CR-042 | Scope addition — beyond BRD | Dynamic report customisation: data fields, charts and summaries. | BIBS has fixed report columns and saved parameter variants. Proposed: column layout stored in the variant. | Umbrella requirement without an owning BRD; CRQ11 open. | Users choose and order report columns without a change request. | All report users | 2 | 8 | 4 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | DCR-177; CRQ11; CLR-CR-07 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-07)
CR-0013 | Programme | BRD-00 | CORE-21.05; BR-054, BR-103 (p.12) | FR-CR-043 | Scope addition — beyond BRD | Scheduled or on-demand report generation for any report. | Only system-scheduled files exist. Proposed: report subscriptions per user (REPORT_SUBSCRIPTIONS_MAX 20; external domains limited). | Umbrella requirement without an owning BRD; CRQ11 open. | Users receive recurring reports by e-mail without manual runs. | All report users | 1 | 6 | 3 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | DCR-177; CRQ11; CLR-CR-08 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-08)
CR-0014 | Programme | BRD-00 | XC-02; BR-125, BR-152, BR-160, BR-203 (p.5, p.20-21) | FR-CR-010, FR-CR-011 | Scope addition — beyond BRD | Centralised, real-time dashboards for all roles, with drill-down. | Each module has its home page. Proposed: a role home with configurable widgets per role family (DASHBOARD_REFRESH_MINUTES 5). | Umbrella requirement without an owning BRD; CRQ06 open (figures per role). | Each role sees its work and figures on one page. | All departments | 3 | 8 | 4 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ06; CLR-CR-11 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-11)
CR-0015 | Drop 1 | BRD-00 | XC-13; BR-175 (p.23) | FR-CR-090 | Scope addition — beyond BRD | Invoice Master List across workflows. | Proposed: columns added to the Operations invoice ledger view. | Umbrella requirement without an owning BRD; CRQ13 open. | One list of invoices with their status across NB, Operations and Collections. | Operations; Collections; Comptrollership | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ13; CLR-CR-12 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-12)
CR-0016 | Drop 1 | BRD-00 | XC-19 (p.43); BRNB.100 related | FR-CR-081; FR-NB-117 | Integration dependency | Invoice batch printing, delivery to insurers by SFTP and a delivery report, daily per insurer. | Service invoices are issued and e-mailed. Proposed: daily batch per insurer at 20:00 PHT with SFTP delivery once the insurer SFTP addresses are given. | CRQ18 open (format, SFTP addresses, replaces e-mail?). | Insurers receive invoices in one daily file instead of single e-mails. | Processing; Operations; BDOI IT | 2 | 6 | 4 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | CRQ18; CLR-CR-13 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-00 chapter 5 (CLR-CR-13)
CR-0017 | Drop 0 | BRD-00 | XC-20 client migration and daily client batches (p.43); BRD-13 BRID 2.1 (p.7) | FR-CR-082; FR-DM-031, FR-DM-032 | Data migration | Umbrella BRD: one-time client migration 2020 to present plus daily midday and EOD client batches with a modification report. | Selective migration of clean client master data by the Data Migration programme; legacy read-only after cut-over; no daily client batches after go-live. | Conflict between the umbrella and BRD-13, decided in the Data Migration design; CRQ19, DMQ05 open on the client scope. | Legacy client changes stop at the freeze; BIBS is the client master from go-live. | Business Project Services; Marketing; Processing | 0 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-173; CRQ19; DMQ05; CLR-CR-14 | Migration functions (Nov 2026 - Mar 2027) | FRS BRD-00 chapter 5 (CLR-CR-14); register DCR-173
CR-0018 | Drop 1 | BRD-00 | XC-10; BR-039, BR-043 (p.14-15) | FR-CR-093 | Deferred pending BDOI answer | SOA generated with the placement report and the Insurance Advice; service invoice issued to the insurer with the SOA at booking. | Proposed after BDOI states which SOA is meant. | CRQ12 open. | Insurers and clients receive the SOA from BIBS instead of a manual document. | Processing; Operations | 1 | 3 | 2 | 1 |  |  |  | Medium | Draft | BIBS Product Owner with the Program Manager, Business Project Services | CRQ12; CLR-CR-15 | After BDOI answer (slot set by the CCB) | FRS BRD-00 chapter 5 (CLR-CR-15)
CR-0019 | Programme | BRD-00 | NFR sections of every BRD: service hours, availability, maintenance window, BCP (umbrella p.42-46) | FRS BRD-00 section 7 | NFR / infrastructure change | Service hours differ by BRD (07:00-22:00 Mon-Sat NB and RN; 06:00-20:00 Mon-Fri Claims; 08:00-18:00 Mon-Fri SANC; others); availability 99.9% to 100%; maintenance windows 19:00-07:00 (ACCT) to 00:00-04:00 (SANC, SP). | Proposed one BIBS-wide set: service 06:00-22:00 Mon-Sat plus month-end weekends; 99.9% within service hours; maintenance 00:00-04:00; batch after 22:00. | XQ08; OQ44, CQ25, AQ27, PQ18, CLQ24, EBQ25, CSQ11, SP SQ21 / SQ22, RQ28. | One service level for all departments; month-end work covered. | All departments; BDOI IT | 2 | 0 | 0 | 2 |  |  |  | High | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | DCR-133; DCR-134; DCR-138; DCR-057; XQ08 | FRS sign-off (Nov 2026) | Register DCR-133, 134, 138; FRS BRD-00 section 7
CR-0020 | Programme | BRD-00 | NFR recovery objectives: RPO 24 h (OPS, PM, EB), 4 h (CLXN, CLM, CSF); CSF backup every 15 minutes (BRCSF-011.001, p.11) | FRS BRD-00 section 7; FR-CSF-043 | NFR / infrastructure change | Recovery objectives and backup frequency differ by BRD; the DR location is not stated. | RPO 15 minutes (continuous WAL archiving) and RTO 4 hours for the whole platform, as in the IER. Proposed DR: RDS cross-region replica, S3 cross-region replication, EKS standby scaled at failover, DR runbook and a failover test. DR region to be named after the data-residency check. | IER workbook v20 (BDO IT) states RPO 15 minutes, RTO 4 hours; IQ26 open on the DR region. | One recovery target; CSF 15-minute backup met by continuous archiving. | BDOI IT; all departments | 2 | 3 | 4 | 2 |  |  |  | High | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-135; DCR-225; CSQ11; IQ26 | Before go-live (Oct - Dec 2027) | Register DCR-135, DCR-225; Programme alignment 6.2, 6.5
CR-0021 | Programme | BRD-00 | Retention: umbrella 5 years online / 15 offline (p.42-46); BRD-7 10 / 15; BRD-5, 10, 12 5 / 5; BRNB.106 (p.12) | FR-NB-137; FRS BRD-00 section 7 | NFR / infrastructure change | Retain, archive and purge per the BRD values, which differ by BRD. | Retention rules per record type with review counts (default 5 years online, 15 years archive; backup kept 7 years). Archive and purge wait until BDOI gives the retention per record type. | Q39, CRQ22 open. | Legal record keeping; database size and cost over time. | Compliance; Comptrollership; BDOI IT; all record owners | 2 | 8 | 4 | 2 |  |  |  | High | Draft | BIBS Product Owner with the Program Manager, Business Project Services | DCR-136; DCR-167; DCR-209; Q39; CRQ22 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21 (BRNB.106); register DCR-136
CR-0022 | Programme | BRD-00 | Response times: 2 s (SP) to 10 s (NB, RN, UAM); umbrella under 5 s for every role (p.42) | FRS BRD-00 section 7 | NFR / infrastructure change | Response-time targets differ by BRD. | Proposed: screens and single-record actions p95 under 2 seconds; reports and batches run as jobs with progress. Proved in the performance test (deliverable 28). | CRQ21 open. | One testable target for every screen. | All departments | 1 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | DCR-137; DCR-165; CRQ21 | FRS sign-off (Nov 2026) | Register DCR-137, DCR-165
CR-0023 | Programme | BRD-00 | Umbrella p.42: 1,344 named / 429 concurrent users; IER: about 1,200 internal users | FRS BRD-00 section 7 | NFR / infrastructure change | User counts differ between the umbrella, BRD-3, BRD-7, BRD-8 and the IER. | Sized and tested for 429 concurrent sessions as the peak case; no external users. | CRQ21, CRQ24, IQ32 open. | Infrastructure cost and the performance test depend on the figure. | BDOI IT | 1 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-166; DCR-232; IQ32; CRQ24 | FRS sign-off (Nov 2026) | Register DCR-166, DCR-232
CR-0024 | Programme | BRD-11 | BRD-4 and BRD-7 NFR: session timeout 15 minutes; BRD-1 and BRD-11 NFR 5 (p.17): warning at 15, log-out at 30 | FR-UA-004; FR-CL-094 | BRD conflict resolved by decision | BRD-4 and BRD-7 set a 15-minute session timeout; BRD-1 and BRD-11 a 15-minute warning and a 30-minute log-out. | Inactivity warning at 15 minutes and log-out at 30 minutes for all users (SESSION_IDLE_WARNING_MINUTES 15, SESSION_TIMEOUT_MINUTES 30), configurable. BRD-11 governs access BIBS-wide. | BRD-11 p.17 NFR 5 (answer to DCR-008). | Collections and Claims users get 30 minutes instead of 15. | Collections; Claims | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | UAM Product Owner with ITIO | DCR-008; DCR-140 | FRS sign-off (Nov 2026) | Register DCR-008, DCR-140
CR-0025 | Drop 0 | BRD-11 | BRD-4 NFR 10.07 (p.51-58), one session per device; BRD-7 NFR (p.32-41), concurrent sessions allowed; BRD-11 silent | FR-UA-004 | Deferred pending BDOI answer | BRD-4: one session per device, a new device logs off the old one. BRD-7: concurrent sessions allowed. | Session log kept; enforcement of a single session is a parameter, off until BDOI decides whether it applies to all users. | UQ09; XQ11. | Shared-device risk in Collections if not enforced. | Collections; Claims; BDOI IT Security | 1 | 3 | 2 | 1 |  |  |  | Medium | Draft | UAM Product Owner with ITIO | DCR-141; UQ09; XQ11 | After BDOI answer (slot set by the CCB) | Register DCR-141; Cross-BRD decisions XQ11
CR-0026 | Drop 1 | BRD-04 | BRD-4 NFR 3.04 (users may not hold several roles); BRD-11 NFR 1.d (p.13) | FRS BRD-4 chapter 12; FR-CL-094 | BRD conflict resolved by decision | BRD-4: the system does not allow users to have multiple roles. | Several roles per user allowed everywhere; there is no single-role check. Incompatible role pairs can be blocked as a segregation rule. | Decision D5 (CQ23 answered by BRD-11: "User can have more than one role"). | A collector who also works in another unit keeps one user ID. | Collections; ITIO | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of BDOI Operations (Collections) | DCR-045; D5; CQ23 | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12; Cross-BRD decisions D5
CR-0027 | Programme | BRD-00 | IER workbook v20: architecture diagram (multi-tenant microservices), Kubernetes sheets (ten bv-* services) | FRS BRD-00 section 7; ARCHITECTURE_OPTION_DECISION | NFR / infrastructure change | The IER sizes ten microservices, three tenants, Aurora and MongoDB per tenant, Istio and EventBridge. | BIBS stays a modular monolith on one PostgreSQL database, deployed on EKS as four workloads (web, jobs, integration, frontend) with RDS, ElastiCache, MSK and S3; internal ALB with AWS WAF for users; Apigee X for system APIs; TLS on every hop, deny-by-default network policies, IRSA; no service mesh. Infrastructure work: workload roles, backend HTTPS, data-service TLS, Apigee token validation, deployment values with HPA and PDB. | Decision D10, confirmed by BDOI on 26-Sep-2026 ("go ahead with the best practices"); IQ25. | The IER is restated; infrastructure cost follows the real workloads. | BDOI IT; BDO Cloud and Digital Operations Engineering | 3 | 15 | 6 | 4 |  |  |  | High | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-222; DCR-223; D10; IQ25 | Infrastructure before SIT (by Jan 2027) | Architecture option decision 5.3-5.4; Programme alignment 6.2
CR-0028 | Programme | BRD-00 | BDOI answer A4 of 26-Sep-2026 (documents in S3 only); every BRD that stores files | FRS BRD-00 section 4 (document generation, data management) | NFR / infrastructure change | Documents and attachments are stored in an S3 bucket only. | Proposed: every file in S3 with its metadata in PostgreSQL; signed links after the permission check and audit; quarantine until the malware scan passes; retention and legal hold; every module moved to the S3 store and the existing files copied with a checksum check. | Decision D9 (option C of DOCUMENT_STORAGE_DECISION, approved 26-Sep-2026); five design points still to confirm (IQ31). | Smaller database and backups; encryption with BDOI keys; Object Lock for records under legal hold. | BDOI IT; Compliance; all departments that upload or print documents | 3 | 22 | 8 | 3 |  |  |  | High | For CCB review | BDOI IT (integration owner) with the BIBS Product Owner | DCR-227; D9; A4; IQ31; DSQ01-DSQ04 | Drop 1, first release (Nov - Dec 2026) | Document storage proposal section 4; Programme alignment 6.3
CR-0029 | Programme | BRD-00 | IER HW and SW sheet: ElastiCache Redis 7 "(cluster)" in Pre-Prod and PROD | FRS BRD-00 section 7 | NFR / infrastructure change | The IER asks for ElastiCache in cluster mode. | BIBS runs Redis 7 with cluster mode disabled (one shard, Multi-AZ replica); the cache clear and the job lock assume one shard. | Technical constraint; IQ34 open. | None if accepted; cluster mode enabled needs a code change. | BDOI IT | 0 | 0 | 0 | 1 |  |  | 10 | Low | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-228; IQ34 | Infrastructure before SIT (by Jan 2027) | Register DCR-228; Programme alignment 6.2
CR-0030 | Programme | BRD-00 | IER VDI sheet: OpenJDK 17, Node 20, Angular SPA; RDS rows "RHEL 9.x" | FRS BRD-00 section 7 | NFR / infrastructure change | The IER names JDK 17, Node 20 and an Angular front end. | BIBS runs on Java 21, Spring Boot 3.5, Node 22 and React 19. Proposed IER correction: Temurin 21, Maven 3.9, Node 22, no Angular; RDS rows without an operating system. | Technology baseline of BIBS; IQ28, IQ29. | VDI images and base images follow the real stack. | BDOI IT | 0 | 0 | 0 | 1 |  |  |  | Low | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-224; IQ28; IQ29 | Infrastructure before SIT (by Jan 2027) | Register DCR-224; Programme alignment 6.2
CR-0031 | Programme | BRD-00 | IER assumptions: non-production 12 x 5 hours | FRS BRD-00 section 7 | NFR / infrastructure change | Non-production environments run 12 hours a day, 5 days a week. | Night jobs run from 20:00 to 06:00 PHT and would never fire. Proposed: non-production crons moved into the window by environment variables; extended hours booked for batch, month-end and migration rehearsal cycles. | Technical constraint; IQ27 open. | SIT and UAT can test the batch cycle and month-end. | BDOI IT; QA | 1 | 1 | 1 | 1 |  |  |  | Medium | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-226; IQ27 | Infrastructure before SIT (by Jan 2027) | Register DCR-226; Programme alignment 6.5
CR-0032 | Programme | BRD-00 | IER workbook v20 (HW and SW sheet, infrastructure diagram, architecture diagram): GitLab runner, Jenkins, ArgoCD and Helm | FRS BRD-00 section 7 | NFR / infrastructure change | Three CI / CD toolchains appear in the IER; the BDO standard is not named. | Proposed: a Helm chart or Kustomize overlays per environment and a pipeline on the toolchain BDO IT names (container registry, image base, code-quality server). | IQ29 open. | Releases follow BDO change management and tooling. | BDOI IT | 1 | 5 | 2 | 1 |  |  |  | Medium | Draft | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-224; IQ29 | Infrastructure before SIT (by Jan 2027) | Programme alignment 6.2, 6.6
CR-0033 | Programme | BRD-00 | IER: Dynatrace (VDI, K8s sheets) against CloudWatch, X-Ray, Prometheus, Loki, Grafana (diagram); BRD-11 NFR remote log server (p.14) | FRS BRD-11 interfaces (remote log server, on hold) | NFR / infrastructure change | Two observability stacks named; BRD-11 asks for logs on a remote log server. | Health checks, metrics for Prometheus and structured logs. Proposed: monitoring collectors and log shipping for the stack BDO IT chooses; alert routing per the alert catalogue (deliverable 38). | IQ30 open. | Production support sees BIBS in the BDO monitoring tools. | BDOI IT; production support | 1 | 4 | 2 | 1 |  |  |  | Medium | Draft | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | IQ30 | Infrastructure before SIT (by Jan 2027) | Programme alignment 6.2; FRS BRD-11 interfaces
CR-0034 | Programme | BRD-00 | Hosting appendix (access restricted to personnel in the Philippines); IER VDI sheet (15 users) | FRS BRD-00 section 7 | NFR / infrastructure change | Access is restricted to personnel in the Philippines; the IER plans 15 VDI users without saying where they sit. | Proposed: production and UAT reachable only from the Philippines; DEV and SIT with masked data reachable by named vendor staff through VDI. | IQ28 open. | Defines who can support the platform from where. | BDOI IT; Compliance | 1 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | BDO Cloud and Digital Operations Engineering (IER owner) with BDOI IT | DCR-231; IQ28 | Infrastructure before SIT (by Jan 2027) | Register DCR-231
CR-0035 | Programme | BRD-00 | Concept paper "Advance Implementation of Renewal Processing" V1.0 (MANCOM, 06-Sep-2026); timeline slide | FRS BRD-6 v1.1 introduction; FRS BRD-13 (FR-DM-120) | BRD conflict resolved by decision | The signed concept paper proposes an early renewal release by 15-Aug-2027 for January to May 2028 expiries, with early migration of client and reference data. | Superseded: every module goes live together in January 2028; no early release and no early migration. Its capabilities stay in scope for January 2028. | BDOI answer A1 of 26-Sep-2026. | One cut-over; renewals of January to May 2028 run in BIBS after go-live (CR-0139). | Marketing; Processing; Business Project Services | 0 | 0 | 0 | 1 |  |  |  | High | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | DCR-218; DCR-240; A1 | FRS sign-off (Nov 2026) | Programme alignment 3; register DCR-218, DCR-240
CR-0036 | Programme | BRD-00 | Drop plan: BRD-10 Sanction Screening and CSF service requests not placed; Drop 0 items 0.1, 0.4, 0.5 without a BRD | FRS BRD-00 section 3; FRS BRD-10; FRS BRD-9 | BRD conflict resolved by decision | The drop plan does not place BRD-10 or the CSF service-request functions, and names Drop 0 items without a governing BRD. | Proposed: BRD-10 in Drop 1 with Client Onboarding; CSF service requests in Drop 2; Drop 0 acceptance on BRD-11 plus EIAM (item 0.1), CORE-17 of the umbrella (item 0.4) and the workflows of each BRD (item 0.5). Documents are filed by this map. | IQ23, IQ24 open. | Test and sign-off windows for the two BRDs. | Compliance; Contact Center Management; Business Project Services | 0 | 0 | 0 | 1 |  |  |  | Medium | For CCB review | BIBS Product Owner with the Program Manager, Business Project Services | DCR-213; DCR-214; IQ23; IQ24 | FRS sign-off (Nov 2026) | Programme alignment 2.2 items 5-6
CR-0037 | Programme | BRD-00 | BRD-8 BRID-022.01 (PDF/XLSX/CSV/WORD); other BRDs Excel and PDF; FRBS 3.2.0 (p.63) board schedules in Word | FRS BRD-00 (report generation); FRS BRD-5 Vol.1 chapter 12 | Scope addition — beyond BRD | BRD-8 asks for Word export of reports; BRD-5 asks for board schedules in Word; the other BRDs ask for Excel and PDF. | Word export for every report, Word on documents and schedules (GL-SCHEDULE, GL-BVA, FRBS-MANCOM-MARKET, RI-SOA, FIN-AP-VOUCHER), and a Word copy of each composed business document. | Work item P2; FRS BRD-5 Vol.1 clarification CLR-AC-10. | All departments can export to Word, beyond what their BRD asks. | All report users; Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | BIBS Product Owner with the Program Manager, Business Project Services | DCR-161; P2; EBQ21 | FRS sign-off (Nov 2026) | Deliverables plan item 17; register DCR-161
CR-0038 | Programme | BRD-00 | BRD-7, BRD-4, BRD-10, BRD-2, BRD-1 shared-drive and FS04 targets; BRNB.110 (p.14); SNSRP-706 (p.19-20) | FR-NB-038; FR-SS-071; FR-CM-064; FR-OP (extracts) | Behaviour differs from BRD | Several BRDs send files or lists to a shared drive or a designated folder. | Files are kept in BIBS with download and notification; a shared-drive or SFTP drop is added only where a downstream system reads the file (for example FS04, CR-0104). | BRD-12 asks for one master database instead of shared-drive files; OQ17, CLQ21. | No uncontrolled copies on shared drives; users download from BIBS. | Claims; Compliance; Operations; Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | BIBS Product Owner with the Program Manager, Business Project Services | DCR-152; OQ17; CLQ21 | FRS sign-off (Nov 2026) | Register DCR-152; FRS BRD-1 chapter 21
CR-0039 | Programme | BRD-00 | Ageing buckets: ACSL 2.14.x (p.124); Claims report list; BRCLXN reports; Cashiering reports | FR-CM-060; FR-CL (reports); FR-AS (ACSL reports) | BRD conflict resolved by decision | Ageing buckets differ: ACSL 0-30 to over 730 days; Claims 0-30 to 181+; Collections and Cashiering without buckets. | Proposed: ageing buckets configurable per report family, ACSL buckets as the default, as a shared setting. | Conflict between BRDs; OQ43. | Ageing reports agree across departments. | Comptrollership; Claims; Collections; Operations | 1 | 3 | 2 | 0 |  |  |  | Low | Draft | BIBS Product Owner with the Program Manager, Business Project Services | DCR-158; OQ43 | Drop 1, second release (Jan - Feb 2027) | Register DCR-158
CR-0040 | Programme | BRD-00 | BRD-8 (documents restricted by process), BRD-9 BRCSF-006, 009 (p.9-10), BRD-7 claim document types | FR-CSF-030, FR-CSF-033; FR-EB-002 | BRD conflict resolved by decision | Contact Center users view and resend renewal advices and claims reports; EB restricts documents by process; claim documents may be confidential. | Access class per document type; CSF users may view RENEWAL_ADVICE and CLAIM_REPORT; the loss advice and insurer claim reports are stored as CLAIM_REPORT. Final confidentiality matrix to confirm. | XQ04, XQ05; CSQ07, EBQ15, CLQ26. | Contact Center sees only the document types it is cleared for. | Contact Center Management; Claims; Employee Benefits | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | BIBS Product Owner with the Program Manager, Business Project Services | DCR-148; XQ04; XQ05; P3 | FRS sign-off (Nov 2026) | Cross-BRD decisions 5, 6.1
CR-0041 | Programme | BRD-00 | Report List as of 27-Apr-2026: #69, #73, #168 (BDOI remarks "DELETE" / "no longer needed") | FRS BRD-00 report generation | Scope reduction / descoped | The Report List carries #69, #73 and #168. | Marked DROPPED and not in scope, per the BDOI remarks in the Report List. | Report List remarks (DCR-130, answered). | None; the data is in the Policy Transmittal and e-policy reports. | Report SMEs named in the Report List | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | BIBS Product Owner with the Program Manager, Business Project Services | DCR-130 | FRS sign-off (Nov 2026) | Register DCR-130
CR-0042 | Programme | BRD-00 | Report List TSU rows ("there should be a separate TSU module", #182) | FRS BRD-3; FRS BRD-1 (non-package placement) | Behaviour differs from BRD | The Report List asks for a separate TSU module. | TSU work stays in non-package placement and Product Maintenance, with a TSU menu section and the TSU Workbench. | Platform design; no BRD specifies a TSU module. | TSU users work in two modules from one menu section. | TSU; MBS | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head, Marketing Business Services (MBS) with the TSU Head | DCR-131 | FRS sign-off (Nov 2026) | Register DCR-131
CR-0043 | Drop 2 | BRD-00 | Drop plan INT-19 "Insurer System"; PRCID.009 (p.81); RMTID.012 (p.55-56); BRNB.071, 073 (p.116-117); ACSL 2.2.1; CLQ17 | FR-OP-070 to FR-OP-074; FR-OP-030 to 041; FR-NB-081, FR-NB-100; FR-CM-022 | Integration dependency | Insurer files are received and sent automatically: production feedback, remittance ORs, DP billing responses, renewal responses, SOAs, e-policies, claims. | Users upload and download the files on the screens. Proposed: an SFTP or API channel per insurer and outbound drops once BDOI names the insurers and channels. | IQ18, Q06, OQ22, OQ29, CLQ17 open. | Manual upload and e-mail with insurers until the channels exist. | Operations; Processing; Claims; Comptrollership (ACSL); BDOI IT | 3 | 12 | 6 | 2 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | IQ18; Q06; OQ22; OQ29; CLQ17 | Drop 2 (Mar - Apr 2027) | Programme alignment 5 (INT-19); FRS BRD-2 chapter 12 (PRCID.009); FRS BRD-1 chapter 21 (BRNB.071, 073)
CR-0044 | Drop 2 | BRD-00 | Drop plan INT-16 EDP - Data Ingestion (SD 11) | FRS BRD-00 integration and data flow | Integration dependency | BIBS data is ingested by the BDO Enterprise Data Platform. No BRD specifies the data, frequency or format. | Integration events (9 topics) and report exports. Proposed: daily extracts to an S3 drop per SD 11, with masking rules. | IQ15 open ("SD 11" not explained). | Group analytics receives BIBS data. | BDOI IT; MIS | 3 | 10 | 5 | 2 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | DCR-233; IQ15 | Drop 2 (Mar - Apr 2027) | Programme alignment 5 (INT-16)
CR-0045 | Drop 2 | BRD-00 | Drop plan INT-18 CARMS | None | Integration dependency | The drop plan names CARMS for Drop 2 without a description. | Purpose, data and direction unknown. Analysis only until BDOI explains it; the delivery becomes its own CR. | IQ17 open. | Unknown. | BDOI IT | 2 | 0 | 0 | 1 |  |  |  | Low | Draft | BDOI IT (integration owner) with the BIBS Product Owner | IQ17 | After BDOI answer (slot set by the CCB) | Programme alignment 5 (INT-18)
CR-0046 | Drop 0 | BRD-00 | Drop plan INT-12 ECM; decision D9 (final issued records archived to ECM) | FRS BRD-00 document generation | Integration dependency | ECM is named as a Drop 0 integration; BDOI answer A4 places every document in S3. | Documents live in S3 (CR-0028). Proposed: transfer of final issued records to ECM and, if ECM holds them, legacy documents into the archive. | IQ13 open; D9. | Records management follows the BDO ECM policy. | BDOI IT; Compliance | 2 | 5 | 3 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | IQ13; D9 | Drop 1, second release (Jan - Feb 2027) | Programme alignment 5 (INT-12); Cross-BRD decisions D9
CR-0047 | Drop 0 | BRD-00 | Drop plan INT-13 CCM (e-mail sending); every BRD that sends e-mail or protected documents | FR-NB-013; FR-RN (letters); messaging | Integration dependency | All outbound e-mail goes through CCM. | BIBS sends e-mail through SMTP with an outbox. Proposed: SMTP relay to CCM (configuration); an API interface with delivery status only if CCM requires it. | IQ11 open (SMTP or API, attachment limit, bounces). | Renewal advices and protected PDFs leave through the BDO mail platform. | BDOI IT; Marketing; Processing | 1 | 2 | 2 | 0 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | IQ11 | Drop 1, second release (Jan - Feb 2027) | Programme alignment 5 (INT-13)
CR-0048 | Drop 1 | BRD-01 | BRNB.005 (p.50-51); BRNB.014 (p.56) | FR-NB-014, FR-NB-051 | Behaviour differs from BRD | Multi-level approval TL, TH, UH. | One approval stage per document; the approver permission decides who approves. | Q05 open (approval chain). | Fewer approval hops; a chain needs a CR if BDOI requires it. | Marketing; TSU | 0 | 0 | 0 | 0 |  |  | 13 | Medium | For acceptance | Product Owner, New Business (Marketing and Processing) | Q05 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0049 | Drop 1 | BRD-01 | BRNB.015 (p.56) | FR-NB-015 | Integration dependency | Data synchronised with the BDOI tracking systems. | Internal events only; the external feed is on hold until BDOI names the systems. | Q08 open. | Other BDOI systems do not receive NB data automatically. | Marketing; BDOI IT | 2 | 5 | 3 | 1 |  |  |  | Low | Draft | BDOI IT (integration owner) with the BIBS Product Owner | Q08 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21
CR-0050 | Drop 1 | BRD-01 | BRNB.018 (p.57); Report List #182 | FR-NB-126; FR-RN-112 | Deferred pending BDOI answer | Late Renewal Requests Report in New Business. | Neither the RN BRD nor the Report List defines it (#182 is a package report). Proposed: a variant of the renewal listing (renewals booked after expiry). | Q09, RQ29, XQ09 open. | Late renewals are visible in the Renewal status report until then. | Marketing; Processing | 1 | 2 | 2 | 1 |  |  |  | Low | Draft | Product Owner, New Business (Marketing and Processing) | DCR-009; Q09; RQ29; XQ09 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-1 chapter 21; register DCR-009
CR-0051 | Drop 1 | BRD-01 | BRNB.019 (p.58); BRNB.094 (p.5-6) | FR-NB-012 | Behaviour differs from BRD | Delete in-process records. | Void with a reason; records are kept and hidden from standard lists. | Audit trail and record retention. | Voided records remain available to audit. | Marketing; Processing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | CRQ05 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0052 | Drop 1 | BRD-01 | BRNB.022 (p.60-61) | FR-NB-010 | Behaviour differs from BRD | One status list including "Endorsed". | Stages of four workflows (client, quotation, proposal, account); endorsements are invoices on a booked account. | Q10 (master list of stages). | Status reporting reads the workflow stages. | Marketing; Processing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | Q10 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0053 | Drop 0 | BRD-01 | BRNB.023 (p.61); Submitted Policies HLS report; CLPC HLS billing | FR-NB-040 | Integration dependency | Quotation requests come directly from HLS with a source check. | The user uploads the HLS extract; the direct interface is on hold. HLS (Drop 0) and LOAS (Drop 2) are one system, HL-LOAS; proposed one interface specification delivered in Drop 0. | Q11, IQ07 open. | Home-loan quotation requests are uploaded by hand until the interface exists. | Marketing (CBG); BDOI IT | 2 | 6 | 4 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | DCR-216; Q11; IQ07 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-1 chapter 21; Programme alignment 5 (INT-04)
CR-0054 | Drop 1 | BRD-01 | BRNB.029 (p.68-69); BRNB.063 (p.109-110) | FR-NB-041, FR-NB-046 | BRD conflict resolved by decision | BRNB.029 requires a client code for a quotation; BRNB.063 allows a quotation without a client code. | A prospect client code is created automatically at quotation; a confirmed client is required from account creation. | Contradiction within BRD-1 resolved by proposal. | Walk-in and bank-referred prospects can be quoted. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Product Owner, New Business (Marketing and Processing) | DCR-001; Q13; Q20 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21; register DCR-001
CR-0055 | Drop 1 | BRD-01 | BRNB.031 (p.71-72) | FR-NB-124 | Behaviour differs from BRD | Print on A4 or Letter; summary or detail. | A4 only; summary and detail are separate reports. | BDO document template is A4. | Letter-size printing not offered. | Marketing; Processing | 0 | 0 | 0 | 0 |  |  | 2 | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0056 | Drop 1 | BRD-01 | BRNB.032 (p.72-73) | FR-NB-033, FR-NB-063 | Behaviour differs from BRD | Account duplicates checked by e-mail, phone and ID. | Clients are checked on identity keys (TIN, ID, name with birth date; e-mail and mobile warn); accounts on vehicle and location keys. | Duplicate rules per record type. | Fewer false duplicates on accounts of the same client. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | DMQ04 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0057 | Drop 1 | BRD-01 | BRNB.036 (p.77-78) | FR-NB-111 | Behaviour differs from BRD | Edit or delete accounts before batch booking. | Edit the booking date and cost center, remove from the queue, cancel the batch. | Account data is fixed once approved for booking. | Corrections go back through the account workflow. | Processing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0058 | Drop 1 | BRD-01 | BRNB.041 (p.94); BRNB.073 (p.116-117) | FR-NB-040, FR-NB-100 | Integration dependency | Requests received by e-mail and e-policies received from insurers are read automatically. | Requests are captured manually with the e-mail attached; e-policies are uploaded by Processing. Proposed: a mailbox reader through Microsoft Graph (M365 Exchange) if BDOI confirms its role against CCM. | Q12, Q31, IQ12 open. | Manual capture of e-mailed requests and e-policies. | Marketing; Processing; BDOI IT | 2 | 8 | 4 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | Q12; Q31; IQ12 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21; Programme alignment 5 (INT-14)
CR-0059 | Drop 1 | BRD-01 | BRNB.047, BRNB.065 (p.97-98, p.110-111) | FR-NB-035 | Behaviour differs from BRD | Save draft and cancel in bulk updates. | Review before commit; valid rows are saved directly. | Bulk framework design. | No draft bulk batches. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | Q14 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0060 | Programme | BRD-01 | BRNB.057 (p.106); Claims dynamic reports (Q40) | FR-NB-123; FR-CM-064 | Scope reduction / descoped | Users create dynamic reports. | Saved report variants; no ad-hoc report builder. | Q40 open (scope of dynamic reports). | New report layouts need a change request (see also CR-0012). | Marketing; Claims; all report users | 0 | 0 | 0 | 0 |  |  | 33 | Medium | For CCB review | Product Owner, New Business (Marketing and Processing) | Q40 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21; BRD-7 requirements baseline (Q40)
CR-0061 | Drop 1 | BRD-01 | BRNB.062 (p.109); BRD 2.1.16 reactivate cancelled placements (p.180) | FR-NB-085, FR-NB-086 | Behaviour differs from BRD | A cancelled placement returns to the previous workflow; reactivation is in the role matrix without a BRNB ID. | Stage "Placement cancelled" until reactivated to "Ready for placement"; reactivation as in BRD 2.1.16. | DCR-002 (no BRNB ID); Q25. | Cancelled placements are visible until reactivated. | Processing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | DCR-002; Q25 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21 and traceability
CR-0062 | Drop 1 | BRD-01 | BRNB.067 (p.114-115); BRNB.068 (p.115) | FR-NB-090, FR-NB-091 | Integration dependency | The billing file is forwarded to CLPC automatically; QPS reference used. | The user downloads the billing file and uploads the payment report; the ARN replaces the QPS reference. Proposed: automated transfer once LMS / HL-LOAS layouts and transport are given. | Q28, IQ06 open. | Manual file hand-over with CLPC. | Processing; Operations (Cashiering); BDOI IT | 2 | 5 | 3 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | Q28; IQ06; DCR-027 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-1 chapter 21; Programme alignment 5 (INT-03)
CR-0063 | Drop 1 | BRD-01 | BRNB.072 (p.116); BRNB.103 (p.10-11) | FR-NB-082, FR-NB-083 | Behaviour differs from BRD | The hold cover request is sent automatically. | Sent when Processing clicks Request Hold Cover. | Q27 open (accounts needing an automatic hold cover). | One click per hold cover. | Processing | 0 | 0 | 0 | 0 |  |  | 7 | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | Q27 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0064 | Drop 1 | BRD-01 | BRNB.075 (p.117-118) | FR-NB-122 | Behaviour differs from BRD | Production per system; QPS placement report. | Production per region, department, team and officer; Placement Summary. | QPS is replaced by BIBS. | None. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0065 | Drop 1 | BRD-01 | BRNB.080 (p.120) | FR-NB-011 | Behaviour differs from BRD | Assign and re-assign workload. | Manual claim and assignment; no automatic allocation. | No allocation rule given in the BRD. | Team leads assign work by hand. | Marketing; Processing | 0 | 0 | 0 | 0 |  |  | 12 | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0066 | Drop 1 | BRD-01 | BRNB.083 (p.121) | FR-NB-132 | Behaviour differs from BRD | Delete LOVs. | Values are deactivated, never deleted. | Historical records keep their values. | None. | MBS; System Administrator | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21
CR-0067 | Drop 1 | BRD-01 | BRNB.091 (p.4) | FR-NB-036 | Deferred pending BDOI answer | Tags and instructions are enforced. | Banner only (warn); blocking is on hold until BDOI lists the tags that block. | Q18 open. | Users can proceed past a tag after the warning. | Marketing; Compliance | 1 | 3 | 2 | 1 |  |  |  | Medium | Draft | Product Owner, New Business (Marketing and Processing) | Q18 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21
CR-0068 | Drop 1 | BRD-01 | BRNB.092 (p.5) | FR-NB-020 | Deferred pending BDOI answer | Authoritative source per data element. | Proposed: a data governance register naming the authoritative source per data element, once BDOI answers Q37. | Q37 open. | Source of truth per data element is documented outside BIBS. | Business Project Services; MIS | 2 | 4 | 2 | 1 |  |  |  | Low | Draft | Product Owner, New Business (Marketing and Processing) | Q37 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21 and traceability
CR-0069 | Drop 1 | BRD-01 | BRNB.097 (p.6-7); BRRN.033 (p.10); BRID-022.01; BRIDSP-26, 27 | FR-NB-119; FR-RN; FR-EB-061; FR-SP | BRD conflict resolved by decision | NB and Renewal classification per transaction, from creation to the invoice and as a report filter (four BRDs). | Business type on the account (BT0), carried to the invoice and used as a report filter; NB booking stamps New Business. | Decision D1. | Production reports split NB and Renewal consistently. | Marketing; Processing; Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Product Owner, New Business (Marketing and Processing) | DCR-010; D1; BT0 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21; Cross-BRD decisions D1, 6.1
CR-0070 | Drop 1 | BRD-01 | BRNB.099 (p.8) | FR-NB-037 | Deferred pending BDOI answer | Leads management. | Prospects only; leads management is on hold. | Q19 open. | Leads are tracked outside BIBS. | Marketing | 2 | 8 | 4 | 1 |  |  |  | Low | Draft | Product Owner, New Business (Marketing and Processing) | Q19 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21
CR-0071 | Drop 1 | BRD-01 | BRNB.104 (p.11); BRIDSP-02 (p.8) | FR-NB-101; FR-SP-002 | Deferred pending BDOI answer | Extraction from uploaded documents, including scanned submitted policies. | Text PDFs are extracted; OCR of scanned documents waits for BDOI (SP SQ03). | Q24 open (documents to extract; OCR). | Scanned documents are keyed by the user. | Processing; Submitted Policies | 2 | 8 | 5 | 1 |  |  |  | Medium | Draft | Product Owner, New Business (Marketing and Processing) | Q24 | After BDOI answer (slot set by the CCB) | FRS BRD-1 chapter 21; FRS BRD-12 scope
CR-0072 | Drop 1 | BRD-01 | BRNB.107 (p.12-13); PMADD07, PMADD08 (p.5-6) | FR-NB-118; FR-PM-080 | Behaviour differs from BRD | Incentive indicator on booking. | The indicator comes from the BRD-3 incentive criteria on the products matrix; the booking incentive rules are frozen. | One incentive master (DCR-037). | Incentive criteria maintained once by MBS. | Processing; MBS | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, New Business (Marketing and Processing) | DCR-037 | FRS sign-off (Nov 2026) | FRS BRD-1 chapter 21; BRD-3 requirements baseline
CR-0073 | Drop 1 | BRD-01 | BRNB.040, BRNB.087 (p.93-94, p.122); BRD-11 NFR (p.13-14, 17); BRD-4, BRD-7 NFR (Windows credentials); BRCSF-001 (p.6) | FR-UA-003; FR-NB-130; FR-CM-001; FR-CSF-001 | Integration dependency | Sign-in with the BDO profile: Windows ID through BDO EUA, LDAP / AD or SSO. | BIBS sign-in with user ID and password. BDOI named EIAM on Microsoft Entra ID: proposed OpenID Connect sign-in (authorisation code with PKCE), identity mapped to the BIBS user, roles kept in BIBS, BIBS sign-in kept for a break-glass administrator. | Decision D6; drop plan Drop 0 (EIAM); IQ04 open. | Single sign-on for all internal users; password, MFA and lock-out move to Entra ID. | All departments; ITIO; BDOI IT | 3 | 12 | 6 | 2 |  |  |  | High | Draft | UAM Product Owner with ITIO | DCR-143; DCR-230; D6; IQ04; Q42; UQ04 | Drop 1, first release (Nov - Dec 2026) | FRS BRD-11 v1.1 (FR-UA-003); FRS BRD-1 chapter 21; Programme alignment 5 (INT-01)
CR-0074 | Drop 1 | BRD-01 | Drop plan item 1.U6 (EB placement in Drop 1); BRD-8 in Drop 2 | FR-EB-046, FR-EB-051; FR-NB (placement) | BRD conflict resolved by decision | EB placement and EB upstream reports are in Drop 1 while the EB module is in Drop 2. | Proposed: EB programmes are placed through the NB placement screens in Drop 1; each Report List item goes with the drop of its owning module. | IQ22 open. | EB placement is tested with NB in Drop 1. | Employee Benefits; Processing | 1 | 0 | 1 | 1 |  |  |  | Low | For CCB review | Product Owner, Employee Benefits | DCR-235; IQ22 | FRS sign-off (Nov 2026) | Programme alignment 2.2 item 8
CR-0075 | Drop 1 | BRD-02 | BRQID.003 (p.17) | FR-OP-003 | Behaviour differs from BRD | Users customise or filter the Operations sections. | Sections are filtered by role; a personal pin or hide of sections is not proposed. | Role menus meet the access need. | Users cannot hide sections they do not use. | Operations | 0 | 0 | 0 | 0 |  |  | 3 | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0076 | Drop 1 | BRD-02 | RMTID.040 (p.69-70) | FR-OP (remittance locks) | Deferred pending BDOI answer | Lock the invoice while it is "still with Comptrollership". | Remittance and Adjustment lock the invoice while they work on it; no Comptrollership lock until BDOI names the activity. | OQ28 open. | An invoice under Comptrollership review can still be adjusted. | Operations; Comptrollership | 1 | 2 | 1 | 0 |  |  |  | Medium | Draft | Head of Operations (Financial Transactions and Processing) | OQ28 | After BDOI answer (slot set by the CCB) | FRS BRD-2 chapter 12
CR-0077 | Drop 1 | BRD-02 | MKTID.001 (p.70-71); RMTID.016 (p.57-58) | FR-OP (remittance schedule) | Behaviour differs from BRD | Marketing initiates the request to send the schedule. | The Remittance processor sends the approved schedule from the batch, once. | OQ22. | Marketing no longer triggers the schedule. | Operations (Remittance); Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ22 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0078 | Drop 1 | BRD-02 | RMTID.002 (p.50); Addendum 1 (p.4-5) | FR-OP (remittance extraction) | BRD conflict resolved by decision | Main BRD: edit the extracted file online and push it with or without edits. | Addendum 1 governs: rows are excluded and restored with a reason; financial fields cannot be edited. | Operations Addendum 1 (DCR-011 answered). | No editing of financial data in the remittance file. | Operations (Remittance) | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | DCR-011 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12; register DCR-011
CR-0079 | Drop 1 | BRD-02 | CSHID.001-005 (p.23-28) | FR-OP (receipt cancellation and reinstatement) | Scope addition — beyond BRD | Cancellation and reinstatement of receipts without a stated approver. | A cancellation or reinstatement is a request approved by a Cashiering TL / TH (four eyes) before it posts. | OQ06; control over receipts. | One more approval step per cancellation. | Operations (Cashiering) | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ06 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0080 | Drop 1 | BRD-02 | CSHID.007 (p.29) | FR-OP (OR issue) | Behaviour differs from BRD | One OR per remittance batch, or per payment unless consolidated. | Remittance approval issues one commission OR per batch; the Collection upload issues one OR per insurer, certificate and payment. | OQ49. | OR count follows batch and insurer. | Operations (Cashiering); Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ49 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0081 | Drop 0 | BRD-02 | CSHID.008 (p.29-32); DIS 2.22.0 (p.93); DIS 2.16.1 (p.88) | FR-OP-015; FR-DS (bank uploads, DCTF) | Integration dependency | Payment files are encrypted and cannot be edited; Trade, CLPC and Direct Credit run by IT. Drop plan: OBPCS, Old BOB, PMS, TFS, AFTS and CMS / New BOB channels. | Operations users upload the files; each file is stored read-only with its SHA-256 and a duplicate is refused; layouts are configurable. Disbursement uses a minimal CSV for bank uploads and a DCTF without trailer. Proposed: layouts per channel in the layout table, the CMS / New BOB outward file in Disbursement, automated transfer where BDO IT offers it; AFTS purpose to confirm. | OQ03, OQ04, AQ09, IQ09, IQ10, IQ14 open. | Bank files handled by upload until the layouts and transport are given. | Operations (Cashiering); Comptrollership (Disbursement); BDOI IT | 3 | 10 | 6 | 1 |  |  |  | High | Draft | BDOI IT (integration owner) with the BIBS Product Owner | DCR-234; OQ03; OQ04; AQ09; IQ09; IQ10; IQ14 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-2 chapter 12; FRS BRD-5 Vol.2 chapter 12; Programme alignment 5 (INT-06 to INT-10)
CR-0082 | Drop 1 | BRD-02 | CSHID.016 (p.37-38); ADJID.026 | FR-OP (minimal balance sweep) | Behaviour differs from BRD | PR up to 10.00 reversed; file 10.00-100.00 written off (10.00 in both ranges). | The sweep skips an invoice already written off by the file, so a balance is never reversed twice. | OQ11. | No double reversal at 10.00. | Operations; Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ11 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0083 | Drop 1 | BRD-02 | RMTID.005 (p.52) | FR-OP (extraction queue) | Behaviour differs from BRD | Trigger extraction at end of day "if payment application is searched". | A user queues the searched invoice for the evening extraction run. | OQ18. | None. | Operations (Remittance) | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ18 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0084 | Drop 1 | BRD-02 | RMTID.014 (p.56-57) | FR-OP (remittance extraction rules) | Deferred pending BDOI answer | Expected result: remit the DTIP balance; acceptance criteria: flag and exclude. | Excluded by default (EXCLUDE); CAP remits the DTIP balance only. BDOI chooses the setting. | OQ19 open; register priority item DCR-015. | Remittance to insurers withheld or capped when the paid AR exceeds the DTIP balance. | Operations (Remittance); Comptrollership | 0 | 0 | 1 | 0 |  |  |  | High | For CCB review | Head of Operations (Financial Transactions and Processing) | DCR-015; OQ19 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12; register priority list
CR-0085 | Drop 1 | BRD-02 | RMTID.016 (p.57-58) | FR-OP (OR comparison) | Deferred pending BDOI answer | Compare the insurer OR amount with the paid PR. | Exact comparison per invoice; no tolerance until BDOI gives one. | OQ22 open. | Small differences are flagged for manual review. | Operations (Remittance) | 0 | 1 | 1 | 0 |  |  |  | Low | Draft | Head of Operations (Financial Transactions and Processing) | OQ22 | After BDOI answer (slot set by the CCB) | FRS BRD-2 chapter 12
CR-0086 | Drop 1 | BRD-02 | RMTID.017 (p.58-59); RMTID.019 (p.59-60) | FR-OP (remittance eligibility, statuses) | Behaviour differs from BRD | Checks at least 3 banking days old and cleared; eight statuses that mix payment and remittance states. | Banking days counted from the last applied value date on the BDOI banking-day calendar, cleared status from the payment application; the invoice keeps a payment status and a remittance status, and the batch has its own stages. | OQ20, OQ21. | Status reports show two statuses per invoice. | Operations | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ20; OQ21 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0087 | Drop 1 | BRD-02 | PRCID.002 (p.79); PRCID.030 (p.85) | FR-OP-070 to FR-OP-074 | Scope addition — beyond BRD | Only the Remarks column is editable; four reconciliation statuses. | Remarks and Incentive columns and 200 blank rows are editable so the insurer can add unbooked production; a fifth status BDOI_ONLY marks booked accounts the insurer did not return. | PRCID.022; analysis R6 5.1. | Unbooked production is captured in the same file. | Operations (Production Reconciliation) | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | PRCID.022 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0088 | Drop 2 | BRD-02 | PRCID.014, PRCID.021 (p.82); Annex IV #5 | FR-OP-070 to FR-OP-074 | Scope reduction / descoped | Filter by BDOI location; Sum Insured on the production register. | Items filter by AO, sales unit, segment and product line; the location filter is on the reports only. Sum Insured is left out: the invoice ledger does not hold it. | Data not held in the invoice ledger. | Sum Insured read from the account when needed. | Operations (Production Reconciliation) | 0 | 0 | 0 | 0 |  |  | 4 | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0089 | Drop 1 | BRD-02 | ADJID.001 (p.89); ADJID.008 (p.92-93) | FR-OP-050 to FR-OP-055 | Behaviour differs from BRD | Multiple accounts in one transaction; prompt the AO to prepare a quotation. | One request per invoice; the wizard and the upload raise several requests at once. A hand-off to Marketing; the quotation number is linked on the request by reference. | Analysis R6 4.1. | Approvals are per invoice. | Operations (Adjustment); Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of Operations (Financial Transactions and Processing) | - | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0090 | Drop 1 | BRD-02 | ADJID.003 (p.90) | FR-OP-052 | Behaviour differs from BRD | Marketing updates the account through a non-financial endorsement. | Booking records the non-financial endorsement with its description; the account data are not changed. | OQ32 open (endorsement ownership). | Account fields are corrected through the account workflow. | Marketing; Operations | 0 | 0 | 0 | 0 |  |  | 8 | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ32 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0091 | Drop 1 | BRD-02 | MKTID.012 (p.75-76) | FR-OP (DP PR reversal) | Behaviour differs from BRD | Auto-reverse the DP premium receivable. | The ledger reversal is always recorded; its GL entry is off because booking posts no PR for DP invoices. | OQ07 (chart and default entries). | No GL entry for a PR that was never posted. | Operations (Commission); Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | OQ07 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12
CR-0092 | Drop 1 | BRD-03 | PMADD07, PMADD08 (p.5-6); DIS 3.29.1, 3.29.2 (Add. p.7-9); CMRID.005, 006 (p.108-109); BRCLXN.061-064 | FR-PM-080; FR-OP-095; FR-DS (CPC2); FR-CL (incentives) | BRD conflict resolved by decision | Incentives are specified in four BRDs: criteria on the products matrix (BRD-3), CPC2 and early incentive (BRD-5), No Touch, Top Up and Motor Mania (BRD-2), incentive receivables (BRD-4 draft). | Criteria kept once in Product Maintenance; CPC2 and early incentive computed in Remittance; schemes in Commission reference the criteria. Schemes stay inactive until BDOI gives targets, amounts and the CPC2 base and VAT treatment. | DCR-037 proposal; OQ39, AQ24, PQ04, Q33 open. | Incentive income not computed until the schemes are set up. | MBS; Operations (Remittance, Commission); Comptrollership | 2 | 2 | 3 | 1 |  |  |  | High | For CCB review | Head, Marketing Business Services (MBS) with the TSU Head | DCR-037; OQ39; AQ24; PQ04; Q33 | After BDOI answer (slot set by the CCB) | Register DCR-037; FRS BRD-2 chapter 12; FRS BRD-5 Vol.2 chapter 12
CR-0093 | Drop 1 | BRD-02 | BRQID.004 (p.18); CSHID.009; MKTID.010, 013; CMRID.001; DBMID.001 (p.46); RMTID.034; MKTID.009 (p.74) | FR-OP-130 to FR-OP-132 | BRD conflict resolved by decision | Operations integrates with Collection, Accounting, Disbursement, Marketing and Claims as other systems. | Collections, Disbursement, FRBS and Claims are BIBS modules; Operations uses in-app ports. The claims condition of a special remittance is confirmed through the Claims feed. | DCR-022 answered by BRD-4, BRD-5 and BRD-7. | No file interfaces between these functions. | Operations; Collections; Comptrollership; Claims | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head of Operations (Financial Transactions and Processing) | DCR-022; OQ01; OQ02; OQ45; OQ46 | FRS sign-off (Nov 2026) | FRS BRD-2 chapter 12; register DCR-022
CR-0094 | Drop 1 | BRD-02 | BRNB.067 (p.114-115), 068 (p.115), 076 (p.118), 081 (p.120), 094 (p.5-6), 114 (p.17); CSHID.008 (p.29-32); ADJID.001 (p.89), 003 (p.90), 011 (p.94) | FR-NB-090, FR-NB-116; FR-OP-015; FR-OP-050 | BRD conflict resolved by decision | The same functions are specified in BRD-1 and BRD-2: CLPC payment matching, endorsements and cancellation, DP tagging. | Cashiering is the single payment intake and placement reads its result; Adjustment owns endorsements and cancellations after booking; Marketing raises the request. | Conflict between BRDs resolved by proposal. | One place for each function. | Marketing; Processing; Operations | 0 | 0 | 0 | 0 |  |  |  | High | For acceptance | Head of Operations (Financial Transactions and Processing) | DCR-027 | FRS sign-off (Nov 2026) | Register DCR-027
CR-0095 | Drop 0 | BRD-03 | BRD revision log of 27-Oct-2025 (p.11); April 2026 addendum | FRS BRD-3 section 1.2 (out of scope) | Scope reduction / descoped | Maintenance of non-package products. | Out of this phase: the revision log moved it to an addendum and the April 2026 addendum does not add it. | PQ19 open. | Non-package products keep today's set-up in the catalog without the package request workflow. | MBS; TSU | 0 | 0 | 0 | 1 |  |  | 15 | Medium | For CCB review | Head, Marketing Business Services (MBS) with the TSU Head | PQ19 | FRS sign-off (Nov 2026) | FRS BRD-3 section 1.2
CR-0096 | Drop 0 | BRD-03 | BRPM.022 (p.31) | FR-PM-081; FR-CR-063 | Integration dependency | Product master changes synchronised with BDOI tracking systems and repositories. | Each change of the product master is logged; transfer to other BDOI systems waits for PQ16. | PQ16 open. | Other systems do not receive product changes automatically. | MBS; BDOI IT | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | BDOI IT (integration owner) with the BIBS Product Owner | PQ16 | After BDOI answer (slot set by the CCB) | FRS BRD-3 section 1.2 and interfaces
CR-0097 | Drop 0 | BRD-03 | PMADD07, PMADD08 (p.5-6) | FR-PM-080 | Scope reduction / descoped | Incentive criteria on the products matrix, "i.e. CPC2". | Criteria only; computation and payout of incentives are out of BRD-3 (they run in Remittance and Commission, CR-0092). | Q33. | None beyond CR-0092. | MBS | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head, Marketing Business Services (MBS) with the TSU Head | Q33; DCR-037 | FRS sign-off (Nov 2026) | FRS BRD-3 section 1.2
CR-0098 | Drop 1 | BRD-04 | BRCLXN.013-015 (p.27 / p.47) | FR-CL (daily refresh) | Behaviour differs from BRD | Daily batch extracts all data from EBIX after the 22:00 EOD. | EBIX is replaced by BIBS booking: the job reads the BIBS invoice ledger at 22:15 and the balance of a listed account is also refreshed after each payment. | EBIX replaced by BIBS. | Collectors see balances updated during the day. | Collections | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of BDOI Operations (Collections) | CQ07 | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12
CR-0099 | Drop 1 | BRD-04 | BRCLXN.010 (p.27 / p.47); BRCLXN.011 (p.27) | FR-CL (worklist rules) | Behaviour differs from BRD | Exclude negative balances of transaction type C; filter by Unit Head. | Negatives of cancellations and return invoices are never listed; other negatives are kept on a Credit Balances tab. The Unit Head is the head of the invoice's sales unit, maintained on Collections Setup. | CQ04, CQ05. | Credit balances are visible for follow-up. | Collections | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of BDOI Operations (Collections) | CQ04; CQ05 | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12
CR-0100 | Drop 1 | BRD-04 | BRCLXN.012 (p.27 / p.47) | FR-CL (data scope) | Deferred pending BDOI answer | Show only the accounts of the selected segment and Unit Head. | Server-side filters; no default data scope per user: every CLX_VIEW user sees every account and filters. | CQ06 open (CSF users see all accounts; other roles open). | Collectors see accounts outside their segment. | Collections; Compliance | 1 | 3 | 2 | 1 |  |  |  | Medium | Draft | Head of BDOI Operations (Collections) | CQ06 | After BDOI answer (slot set by the CCB) | FRS BRD-4 chapter 12
CR-0101 | Drop 1 | BRD-04 | BRCLXN.024, 026 (p.28-29 / p.48); BRCLXN.030, 032 (p.29) | FR-CL (hand-offs) | Scope addition — beyond BRD | A monthly batch "generates the file"; request application of payment. | The file is also a hand-off: a DP PR disposition goes at once to the Commission DP list, a PR 2307 disposition to Cashiering's 2307 intake; the monthly file is the audit copy. Application requests go to Cashiering's Incoming Requests and the Operations disposition workflow. | OQ15, OQ16, OQ38. | Faster reversal and application. | Collections; Operations | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of BDOI Operations (Collections) | OQ15; OQ16; OQ38 | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12
CR-0102 | Drop 1 | BRD-04 | BRCLXN.026 (p.29 / p.48) | FR-CL (COLLECTION_CWT2307 hand-off) | Behaviour differs from BRD | 2307 accounts reach Operations for reversal. | Proposed: Cashiering takes the COLLECTION_CWT2307 hand-offs in its 2307 intake; a hand-off not taken within one day raises the alert CLX_OUTBOX_STALE. | The BRD does not name the Cashiering step for the 2307 accounts. | Double handling of 2307 accounts until closed. | Collections; Operations (Cashiering) | 1 | 3 | 2 | 0 |  |  |  | Medium | Draft | Head of BDOI Operations (Collections) | FRS BRD-4 CLR-CL-06 | Drop 1, first release (Nov - Dec 2026) | FRS BRD-4 chapter 12
CR-0103 | Drop 1 | BRD-04 | BRCLXN.036 (p.31 / p.49) | FR-CL (account view columns) | Deferred pending BDOI answer | UH, AO and bank officer shown as names; booker name; Processing Stage, Business Origin, Client Code Match, System Remarks. | User names shown for UH and AO; booker and bank officer names, Business Origin and System Remarks are not shown; "Processing Stage" is the Cashiering tab. | CQ11 open. | Collectors look up the missing fields on the account. | Collections | 1 | 2 | 1 | 0 |  |  |  | Low | Draft | Head of BDOI Operations (Collections) | CQ11 | After BDOI answer (slot set by the CCB) | FRS BRD-4 chapter 12
CR-0104 | Drop 2 | BRD-04 | BRCLXN.041-042 (p.32 / p.49); BRCLXN.047 (p.33) | FR-CL (CLX-APPLICATION-TO-INVOICE) | Integration dependency | Text file loaded to FS04 before 06:00; EBIX invoice number format I########. | The pipe-delimited file is written at 05:00 to the in-system folder FS04/CLX_APPLICATION_TO_INVOICE; the transport to FS04 is on hold. Invoice pattern accepts EBIX and BIBS numbers. | OQ17, CQ12, CQ13; keep FS04 only if a downstream system reads it. | Downstream readers of FS04 need the transport. | Collections; BDOI IT | 1 | 2 | 2 | 0 |  |  |  | Low | Draft | BDOI IT (integration owner) with the BIBS Product Owner | DCR-046; OQ17; CQ12; CQ13 | Drop 2 (Mar - Apr 2027) | FRS BRD-4 chapter 12; register DCR-046
CR-0105 | Drop 1 | BRD-04 | BRCLXN.051 (Add. p.5 / p.17) | FR-CL (bulk update) | Behaviour differs from BRD | Bulk update of several invoices. | The worklist updates several accounts with a disposition or effort and reassigns them; promises and escalations are recorded in bulk on their screens. The upload records promises and escalations only; its disposition, effort and remarks columns are refused. Proposed: accept those columns in the upload. | FRS BRD-4 Gap G1. | Dispositions are bulk-updated on screen, not by file. | Collections | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | Head of BDOI Operations (Collections) | CLR-CR-01 (FRS BRD-4) | Drop 1, second release (Jan - Feb 2027) | FRS BRD-4 chapter 12
CR-0106 | Drop 1 | BRD-04 | BRCLXN.053 (Add. p.5-6); BRCLXN.055 (Add. p.6); BRCLXN.059 (Add. p.7-8) | FR-CL (installments, promises, CR billing) | Behaviour differs from BRD | Installment schedule per account; broken promises per installment; CR billing needs Premium Receivable confirmation. | Plans made in Collections (policy years, generated or manual); a promise is KEPT, PARTIALLY_KEPT or BROKEN by the payments in the promise window (grace 0 days); Commission bills a DP account after the CRU reviewer confirms it fully paid to the insurer. | CQ15, CQ16, OQ38. | Installment terms are not taken from the quotation. | Collections; Operations (Commission) | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of BDOI Operations (Collections) | CQ15; CQ16; OQ38 | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12
CR-0107 | Drop 1 | BRD-04 | BRCLXN.056 (Add. p.6-7); BRCLXN.060 (Add. p.8) | FR-CL (billing statements, ageing) | Deferred pending BDOI answer | Delivery date and receipt date on billing statements; ageing from billing statements, invoice dates and policy periods. | The first AR date is shown as the receipt date; the delivery date is blank. CLX_AGING_BASIS takes BOOKING or INCEPTION; ageing from the SOA due date is not proposed. | CQ14, CQ17 open. | Statement delivery tracking and ageing from the SOA due date wait for the BDOI answers to CQ14 and CQ17. | Collections | 1 | 3 | 2 | 0 |  |  |  | Low | Draft | Head of BDOI Operations (Collections) | CQ14; CQ17 | After BDOI answer (slot set by the CCB) | FRS BRD-4 chapter 12
CR-0108 | Drop 1 | BRD-04 | BRCLXN.061-064 (Add. p.8-9, draft) | FR-CL-091 to FR-CL-094 (commission receivable and incentives, draft) | Deferred pending BDOI answer | Draft requirements on commission receivables and incentives (drop plan item 1.D7). | Proposed in FRS BRD-4 section 4.10 for confirmation of the draft addendum. | CQ01 open (unsigned draft). | Commission receivable collection for these rows stays manual. | Collections; Operations (Commission) | 3 | 12 | 6 | 2 |  |  |  | Medium | Draft | Head of BDOI Operations (Collections) | CQ01 | After BDOI answer (slot set by the CCB) | FRS BRD-4 chapter 12; Programme alignment 2.1 (1.D7)
CR-0109 | Drop 1 | BRD-04 | BRD-4 NFR audit logging (p.51-58): source IP of each event; BRCLXN.043 (p.32 / p.49) | FR-CL (audit); FR-CR-030 | Behaviour differs from BRD | Record the source IP address of each event and of back-office actions. | The audit trail records user, time and change, not the source IP. Proposed: add source IP and resource to the audit record. | Platform audit design. | Investigations cannot trace the device. | Collections; Compliance; BDOI IT Security | 1 | 2 | 1 | 0 |  |  |  | Medium | Draft | Head of BDOI Operations (Collections) | DCR-145 | Drop 1, second release (Jan - Feb 2027) | Register DCR-145
CR-0110 | Drop 1 | BRD-04 | BRD-4 p.93 caveat (exports may slow the system) | FR-CL-084 | Scope addition — beyond BRD | The BRD warns that exports may slow the system. | Exports run in the background, capped at CLX_EXPORT_MAX_ROWS, under their own permission CLX_EXPORT. | Performance and data-protection control. | Export needs a separate permission. | Collections | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head of BDOI Operations (Collections) | - | FRS sign-off (Nov 2026) | FRS BRD-4 chapter 12
CR-0111 | Drop 2 | BRD-04 | Drop plan item 2.1 "Marketing Collection (extraction)" | FRS BRD-4; FR-OP (Marketing Collection items) | Integration dependency | Drop 2 lists "Marketing Collection (extraction)", which suggests a feed from BIBS to a separate collection system. | BRD-4 is a BIBS module fed by the Operations ledger, replacing the Collection Management System. Proposed: the item means the Collections daily files; BRD-4 is tested in Drop 2 except the DP rows (Drop 1). | IQ21 open. | If a separate system is kept, a new extract interface is needed. | Collections; Marketing; BDOI IT | 1 | 0 | 0 | 1 |  |  | 15 | Medium | For CCB review | Head of BDOI Operations (Collections) | DCR-212; DCR-221; IQ21 | FRS sign-off (Nov 2026) | Programme alignment 2.2 item 3
CR-0112 | Drop 1 | BRD-05 | FRBS 2.2.0 (p.51); FRBS 3.5.0 (p.65) | FR-AC (revaluation) | Behaviour differs from BRD | Input the revaluation rate monthly; revalue daily (previous date against current date). | The monthly rate is the CLOSING rate of the month end, copied as the BOOK rate of the next month; revaluation runs per period with automatic reversal. Daily revaluation only if BDOI confirms. | AQ03, OQ08 open. | Foreign-currency balances revalued monthly, not daily. | Comptrollership (FRBS) | 0 | 0 | 0 | 0 |  |  | 6 | Medium | For CCB review | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ03; OQ08 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.1 chapter 12
CR-0113 | Drop 1 | BRD-05 | FRBS 2.3.2 (p.52); FRBS 2.5.7 (p.57); FRBS 2.6.0 (p.58); FRBS 2.8.1 (p.60) | FR-AC (chart, journals, close) | Behaviour differs from BRD | Account number generated by the system; return a posting request; close the previous month on a preferred date; reversal posts in GL and sub-ledger. | A number is proposed from the parent's scheme when the code is left blank; "Reject" is labelled "Return to Maker" and the journal is resubmitted; FRBS schedules the close (proposal: 2nd banking day, 17:00); manual journals record no sub-ledger items, so the reversal posts in the GL only. | AQ01, AQ04. | None on the accounting result. | Comptrollership (FRBS) | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ01; AQ04 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.1 chapter 12
CR-0114 | Drop 1 | BRD-05 | FRBS 2.5.4 (p.56); FRBS 2.8.4 | FR-AC (posting checks) | Deferred pending BDOI answer | Prevent posting with a negative balance. | Each account has a policy ALLOW, WARN or BLOCK; only BLOCK accounts refuse the journal. BDOI names the accounts that may never be negative. | AQ30 open. | Until set, negative balances are allowed with a warning. | Comptrollership (FRBS) | 1 | 0 | 1 | 0 |  |  |  | Medium | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ30 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.1 chapter 12
CR-0115 | Drop 1 | BRD-05 | FRBS 3.4.0-3.4.1 (p.64) | FR-AC (broking-books close) | Behaviour differs from BRD | Close the broking books automatically. | The broking books close on the last day of the month at 23:00 Manila; the pending list shows the items the broking modules report. Proposed: each broking module reports its pending items to the close checklist. | The broking modules report their pending items (D-AC-07). | The close can run with open broking items not listed. | Comptrollership; Operations | 1 | 4 | 2 | 1 |  |  |  | High | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ04 | Drop 1, second release (Jan - Feb 2027) | FRS BRD-5 Vol.1 chapter 12
CR-0116 | Drop 1 | BRD-05 | FRBS 3.1.2 (Add. p.6) | FR-AC (incentive income account) | Deferred pending BDOI answer | Early incentives reported as Other Income. | The incentive component posts to its own account; placing 4130 under Other Income is a change to BDOI's chart for FRBS. | AQ01. | Financial statement grouping of incentive income. | Comptrollership (FRBS) | 1 | 0 | 1 | 0 |  |  |  | Low | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ01 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.1 chapter 12
CR-0117 | Drop 1 | BRD-05 | FRBS 3.2.0 (p.63), Appendix A (138 reports) | FR-AC (report pack); FRS BRD-5 Vol.1 Appendix A | Deferred pending BDOI answer | The 138 reports and schedules of Appendix A. | 28 schedule definitions and 58 report-pack entries with draft layouts; lease, DTA, ECL and placement data are not in BIBS; payroll outputs are out of scope (BIBS has no payroll). Proposed: final layouts once BDOI supplies them. | AQ05, AQ06 open. | Part of the board and regulatory pack stays manual until layouts are final. | Comptrollership (FRBS) | 4 | 15 | 8 | 2 |  |  |  | High | For CCB review | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ05; AQ06 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.1 chapter 12
CR-0118 | Drop 1 | BRD-05 | FRBS 3.2.0 (VII) BIR books and forms (p.63); BRNB.100 (p.8-9) service invoice | FR-AC (BIR); FR-NB-117 | Scope reduction / descoped | BIR books and forms; service invoice transmission. | Worksheets and loose-leaf books; not eFPS, DAT or CAS files. Service invoices are not transmitted to BIR electronically. Comptrollership uploads the forms manually. | AQ07 open. | Manual BIR filing continues. | Comptrollership (Tax) | 0 | 0 | 0 | 0 |  |  | 23 | High | For CCB review | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ07 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.1 chapter 12; FRS BRD-1 interfaces (BIR CAS)
CR-0119 | Drop 0 | BRD-05 | BASAU 2.3.2 (p.129); BASAU 2.4.1, 2.5.3, 2.6.x (p.130) | FR-AC-072; FR-UA (access requests) | Behaviour differs from BRD | Assign functionality to a role; return requests; select several requests. | A change of role permissions is an access request approved by a second user. The API returns a request with remarks, lets the requester resubmit it and approves in bulk; the Access Requests screen and My Approvals do not show Return, Resubmit or bulk approval yet. Proposed: add the three actions on the screens. | PQ17; FRS BRD-5 Vol.1 Gap G2. | Approvers approve one by one on screen. | Comptrollership; ITIO | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | PQ17; CLR-CR-02 (FRS BRD-5 Vol.1) | Drop 1, first release (Nov - Dec 2026) | FRS BRD-5 Vol.1 chapter 12
CR-0120 | Drop 1 | BRD-05 | DIS 3.25.0 (p.95); DIS 2.2.4 (p.70); DIS 2.7.6 (p.80); DIS 3.27.0 (p.99) | FR-DS (payee, request intake, proforma) | Behaviour differs from BRD | Auto-reject a request whose payee is not maintained; delete payee details; proforma entry editable. | By default the request waits as No Payee, a payee request is raised and an alert sent; DISB_NO_PAYEE_ACTION = RETURN returns it as the BRD says. Only a never-used draft payee is deleted; others are deactivated with authorisation. Lines are editable until approval and marked Edited. | AQ11, AQ12, AQ13. | Fewer rejected requests; payee history kept. | Comptrollership (Disbursement) | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ11; AQ12; AQ13 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.2 chapter 12
CR-0121 | Drop 1 | BRD-05 | DIS 2.8.1 (p.83); DIS 2.16.2 | FR-DS (check printing) | Deferred pending BDOI answer | Check statuses; checks printed at EOD. | A check takes the next leaf of the paying account's cheque book when printed; the layout is a draft template until BDOI gives the bank layout. | AQ14 open. | Checks cannot be printed on bank stock until the layout is final. | Comptrollership (Disbursement) | 1 | 2 | 2 | 0 |  |  |  | Medium | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ14 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.2 chapter 12
CR-0122 | Drop 1 | BRD-05 | DIS 2.20.0 (p.92); MKT 1.19.0 (p.110); DIS 2.17.x (p.90) | FR-DS (DV cancellation, funding); FR-PQ | Behaviour differs from BRD | Cancel an approved DV and regularise the source data; cancellation of a disbursed check routed to Disbursement; funding through BOB with a verifier and two approvers. | The DV journal is reversed and the request goes back to its source (for a remittance DV the batch is returned to review and sent again under a new cycle); Marketing cancellations are handed to the Disbursement approvers; funding is a BIBS four-eyes workflow and the BOB transaction itself is done in BOB with its reference recorded. | AQ10, AQ15. | None on control; BOB stays the funding system. | Comptrollership (Disbursement); Operations (Remittance); Marketing | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ10; AQ15 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.2 chapter 12
CR-0123 | Drop 1 | BRD-05 | DIS 2.10.x (p.86); DIS 2.11.x (p.86) | FR-DS (OR / AR tagging, CWT tagging) | Deferred pending BDOI answer | OR / AR tagging on DVs; CWT tagging. | Every approved DV counts as unregularised until tagged; which DVs need an OR / AR back is open. The CWT tag records the certificate on the DV; insurer certificates on commission are kept in one register in Tax. | AQ16, AQ17 open. | The unregularised DV list includes DVs that need no OR. | Comptrollership (Disbursement, Tax) | 1 | 1 | 1 | 0 |  |  |  | Low | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ16; AQ17 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.2 chapter 12
CR-0124 | Drop 1 | BRD-05 | DIS 3.27.2 (p.100); ACSL 2.16.0 (p.126) | FR-DS (invoice family); FR-OP (Invoice 360) | Behaviour differs from BRD | One invoice number for related transactions (booking, adjustment, cancellation). | Endorsements and cancellations keep their own BIR invoice number and carry the root invoice number; Invoice 360 shows the family. | BIR numbering rules; AQ29. | Users trace a policy's transactions through the root number. | Comptrollership; Operations; Processing | 0 | 0 | 0 | 0 |  |  |  | High | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | DCR-058; AQ29 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.2 chapter 12; register DCR-058
CR-0125 | Drop 1 | BRD-05 | DIS 3.29.1 (Add. p.7-8) | FR-DS (early incentive); FR-OP (remittance) | Deferred pending BDOI answer | Service invoice of the early incentive issued automatically with 2% withholding. | One service invoice per batch; until AQ25 is answered the incentive is deducted in full from the remittance and the insurer's 2% withholding is not posted. | AQ25 open. | Remittance deduction overstated by the withholding until closed. | Operations (Remittance); Comptrollership (Tax) | 1 | 3 | 2 | 1 |  |  |  | High | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ25 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.2 chapter 12
CR-0126 | Drop 1 | BRD-05 | DIS 3.29.0 (Add. p.7) | FR-DS (CPC2 report) | Behaviour differs from BRD | CPC2 report. | The CPC2 amounts are on the remittance batch and its schedule. Proposed: a CPC2 report. | FRS BRD-5 Vol.2 Gap G4. | CPC2 figures are read from each batch. | Operations (Remittance); MBS | 1 | 2 | 1 | 0 |  |  |  | Low | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | CLR-CR-04 (FRS BRD-5 Vol.2) | Drop 1, second release (Jan - Feb 2027) | FRS BRD-5 Vol.2 chapter 12
CR-0127 | Drop 1 | BRD-05 | MKT 1.7.0 (p.106); MKT 1.10.0; MKT 1.12.0, 1.13.0 (p.108); MKT 2.25.0 (p.112) | FR-PQ (Marketing payment requests) | Scope reduction / descoped | Unapplied payment report for Marketing; upload .txt files and preview documents side by side; CA / SA on the client record. | Marketing runs the Cashiering reports (no segment filter); .txt is not an accepted type and files open one at a time; CA / SA recorded on approval with the BDO account number checked as 10 to 16 digits until AQ19. | AQ18, AQ19. | Marketing uses the Cashiering report; no side-by-side preview. | Marketing; Operations (Cashiering) | 0 | 0 | 0 | 0 |  |  | 6 | Low | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ18; AQ19 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.2 chapter 12
CR-0128 | Drop 1 | BRD-05 | BRD-5 Appendix D (p.152-153), cash-advance liquidation form; MKT 1.10.0 (p.107) | FR-PQ (liquidation, return, post) | Scope addition — beyond BRD | The form is in Appendix D; its scope is to be confirmed. | Liquidation, return and posting of cash advances. | AQ18 open on scope. | Cash advances liquidated in BIBS. | Marketing; Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ18 | FRS sign-off (Nov 2026) | FRS BRD-5 Vol.2 chapter 12
CR-0129 | Drop 1 | BRD-05 | ACSL 2.4.0 (p.117); ACSL 2.9.2 (Add. p.13); ACSL 2.13.2 (p.121) | FR-AS (SOA reconciliation, deductions, GL-SL reconciliation) | Deferred pending BDOI answer | Upload SOA files that trigger reconciliation; remittance deduction on insurer confirmation; GL-SL reconciliation also at period end. | The SOA file is read in one request (up to ACSL_SOA_MAX_ROWS) and reconciled once loaded, layouts per insurer as configuration; the deduction stays Confirmed while batches consume it and is Applied when every batch has the insurer OR (sources and spanning batches wait for BDOI); GL-SL reconciliation runs nightly and on demand, a period-end stop is not proposed. | AQ21, AQ23 open. | Period-end GL-SL evidence is the last nightly run. | Comptrollership (ACSL); Operations (Remittance) | 2 | 4 | 4 | 0 |  |  |  | Medium | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | AQ21; AQ23 | After BDOI answer (slot set by the CCB) | FRS BRD-5 Vol.2 chapter 12
CR-0130 | Drop 1 | BRD-05 | ACSL 2.14.3, 2.14.4 (p.124) | FR-AS (ageing reports); FR-AC (account schedules) | Behaviour differs from BRD | Ageing and schedule reports per account family in ACSL. | Proposed: ACSL aging and schedule reports per account family, with the GL balance and the SL-GL difference. | FRS BRD-5 Vol.2 Gap G3. | ACSL users run the schedules from FRBS. | Comptrollership (ACSL) | 1 | 3 | 2 | 0 |  |  |  | Low | Draft | Head, Comptrollership (FRBS, Disbursement and ACSL) | CLR-CR-03 (FRS BRD-5 Vol.2) | Drop 1, second release (Jan - Feb 2027) | FRS BRD-5 Vol.2 chapter 12
CR-0131 | Drop 2 | BRD-05 | Drop plan INT-17 EGL; BRD-5 Appendix A II (GARD submission) | FR-AC (GL reports) | Integration dependency | BDOI accounting is delivered to the BDO Enterprise General Ledger. No BRD specifies what BIBS sends. | No GL interface; GL reports only. Proposed: daily journal extract with a code map to EGL accounts, control totals and a reconciliation report. | IQ16, AQ31 open. | Group consolidation takes BDOI figures from BIBS. | Comptrollership; BDOI IT; BDO Group Accounting | 3 | 10 | 6 | 2 |  |  |  | High | Draft | BDOI IT (integration owner) with the BIBS Product Owner | DCR-233; IQ16; AQ31 | Drop 2 (Mar - Apr 2027) | Programme alignment 5 (INT-17)
CR-0132 | Drop 1 | BRD-06 | Addendum 1 (p.34): 1.003.4.1.1.1, 1.003.4.1.1.3 (p.47-48); 2.003.1.6 (p.80); 2.006.1.2 (p.86); 2.007.4.1 (p.88); 3.003.4.1.1, 3.003.4.1.3 (p.111-112); 3.003.4.5 (p.115); 4.003.1.6 (p.150) | FR-RN-013, FR-RN-040; FRS BRD-6 out-of-scope IDs | Scope reduction / descoped | EBIX invoice number and BDOIsys reference columns; search by QPS / EBIX reference numbers. | Out of scope per Addendum 1: the BIBS expiring invoice number, the renewal reference and the ARN replace them; search by name and BIBS reference. | BRD-6 Addendum 1 p.34. | Legacy references are found through the migrated legacy reference (FR-DM-033). | Marketing; Processing | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, Renewal (Marketing and Processing) | RQ27 | FRS sign-off (Nov 2026) | FRS BRD-6 out-of-scope IDs
CR-0133 | Drop 1 | BRD-06 | BRD-6 renewal lists; BRD-8 BRID-001 (p.7) | FR-RN (extraction); FR-EB-022 | BRD conflict resolved by decision | The renewal lists cover every expiring policy; BRD-8 renews EB programmes in its own cycle. | EB programmes are excluded from the general renewal lists and renewed in the EB module; every renewal advice is stored as document type RENEWAL_ADVICE. | Decision D3. | EB renewals do not appear twice. | Marketing; Employee Benefits | 0 | 0 | 0 | 0 |  |  |  | Medium | For CCB review | Product Owner, Renewal (Marketing and Processing) | D3 | FRS sign-off (Nov 2026) | Cross-BRD decisions D3; FRS BRD-6 section 1.2
CR-0134 | Drop 1 | BRD-06 | BRRN.029 (p.8); BRIDSP-13 (p.10) | FR-RN-025; FR-SP (LAMD upload) | Deferred pending BDOI answer | BRD-6 ingests LAMD reports of paid-off loans; BRD-12 matches submitted policies against LAMD active loans. | Two LAMD intakes proposed (one per module), both matching on the PN. Proposed: one intake owned by one module and read by the other, sourced from LMS if confirmed. | XQ01, RQ20, SP SQ06, IQ06 open. | Two uploads of the same data and two owners if not decided. | Marketing; Submitted Policies; LAMD | 1 | 2 | 2 | 1 |  |  |  | High | Draft | Product Owner, Renewal (Marketing and Processing) | DCR-146; XQ01; RQ20; SP SQ06; IQ06 | Drop 1, first release (Nov - Dec 2026) | Cross-BRD decisions XQ01; register DCR-146
CR-0135 | Drop 1 | BRD-06 | BRRN.026 (p.6-7); BRD-9 Contact Center roles | FR-RN (Contact Center follow-up); FR-CSF-001 | BRD conflict resolved by decision | BRD-6 gives Contact Center users renewal lists with remarks and status updates; BRD-9 defines Contact Center users who see all accounts. | Proposed: two roles; one user may hold both (decision D5 allows several roles). | XQ02, RQ21, CSQ10 open. | Access per role stays narrow. | Contact Center Management; Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | Product Owner, Renewal (Marketing and Processing) | DCR-147; XQ02 | FRS sign-off (Nov 2026) | Cross-BRD decisions XQ02
CR-0136 | Drop 1 | BRD-06 | BRD-6 2.004.4 (p.82-83), reason "Total Loss Claim" | FR-RN-023, FR-RN-043; FR-CM | Deferred pending BDOI answer | Use "Total Loss Claim" as a non-renewal reason and show claims per account. | Renewal reads loss experience from Claims (decision D4); "Total Loss Claim" stays a manual reason until Claims records a total-loss indicator. | CLQ28, XQ10 open. | Total-loss accounts are flagged by hand. | Marketing; Claims | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | Product Owner, Renewal (Marketing and Processing) | DCR-150; CLQ28; XQ10; D4 | After BDOI answer (slot set by the CCB) | Cross-BRD decisions D4, XQ10
CR-0137 | Drop 1 | BRD-06 | Report List #135 (p.44), Renewal Persistency Report | FR-RN (reports); SBM-PERSISTENCY | Deferred pending BDOI answer | General renewal persistency report. | Submitted Policies proposes SBM-PERSISTENCY for submitted accounts; Renewal has no persistency report. Proposed: a renewal report over closed candidates. | XQ06 open (layout and definition). | Renewal persistency is measured outside BIBS until BDOI confirms the report layout and definition (XQ06). | Marketing; MIS | 1 | 3 | 2 | 1 |  |  |  | Low | Draft | Product Owner, Renewal (Marketing and Processing) | XQ06 | After BDOI answer (slot set by the CCB) | Cross-BRD decisions XQ06
CR-0138 | Drop 1 | BRD-06 | BRRN.004 (p.23-24); BRRN.011 (p.28-29) | FR-RN (Expiry List grid) | Behaviour differs from BRD | One scrollable view with no pagination. | Virtualised grid with a row count and no pager, instead of the BDO UX pager. | BDO UX guidelines use a pager. | None for users. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | Product Owner, Renewal (Marketing and Processing) | DCR-074 | FRS sign-off (Nov 2026) | Register DCR-074
CR-0139 | Drop 0 | BRD-06 | BRD-13 BRID 12.1 (p.12), renewal-driven transition; BRRN.005 (p.24-25); concept paper (superseded) | FR-RN-016; FR-DM-122, FR-DM-124, FR-DM-125 | Data migration | BRD-13 makes the transition renewal-driven without describing it; the earlier design carried the RMEL cohorts expiring T to T+140 days with their dispositions. | January to May 2028 expiries are processed in BIBS after go-live; no candidate is carried from legacy. At go-live Renewal extracts every expiry to 31-May-2028 (January urgent) and records the renewal advices already sent from the Excel trackers, rejected rows reviewed maker-checker by the Renewal processing team. | BDOI answers DMQ37 and DMQ38 of 26-Sep-2026. | Marketing works the first five months of renewals in BIBS; heavy load in January 2028. | Marketing; Processing (Renewal); Business Project Services | 1 | 4 | 3 | 1 |  |  |  | High | For CCB review | Product Owner, Renewal (Marketing and Processing) | DCR-199; DCR-220; DCR-240; DCR-243; DMQ37; DMQ38 | Migration functions (Nov 2026 - Mar 2027) | FRS BRD-6 v1.1 (FR-RN-016); FRS BRD-13 (FR-DM-124, 125)
CR-0140 | Drop 0 | BRD-06 | BRRN.020 (p.4) sanitation; concept paper VII, VIII, Annex C (package remapping) | FR-RN-028; FR-DM-034 | Data migration | Legacy package names must be remapped to BIBS packages; the paper asks where and by whom. | Remapping at Renewal sanitation, not at upload: the migration loads the legacy package code and the PACKAGE code map only; the check PACKAGE_REMAP sends unmapped, retired or split packages to the Exception bucket for the Renewal processing team. | BDOI answer DMQ36 of 26-Sep-2026. | Renewals of migrated policies price on the right package version. | Processing (Renewal); TSU; MBS | 1 | 4 | 3 | 1 |  |  |  | High | For CCB review | Product Owner, Renewal (Marketing and Processing) | DCR-219; DCR-241; DMQ36; IQ03 | Migration functions (Nov 2026 - Mar 2027) | FRS BRD-6 v1.1 (FR-RN-028); FRS BRD-13 (FR-DM-034)
CR-0141 | Drop 1 | BRD-06 | Umbrella CORE-06.07 (p.8) "Non-Renewal Letter (NRL)"; BRD-6 "Not for Renewal Letter (NFR)" | FR-RN-082 | BRD conflict resolved by decision | The umbrella and BRD-6 name the letter differently. | The BRD-6 name is used until BDOI answers. | CRQ14 open. | Letter title only. | Marketing | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | Product Owner, Renewal (Marketing and Processing) | DCR-168; CRQ14 | FRS sign-off (Nov 2026) | Register DCR-168
CR-0142 | Drop 2 | BRD-07 | BRD-7 p.23, assumption 1 ("enhance the existing claims module in eBIX"); BRCLM.007 (p.13) | FR-CM-013; FRS BRD-7 chapter 12 | Behaviour differs from BRD | Enhance the claims facility in eBIX; get the policy number from EBIX and upload it. | A new BIBS broker claims module; the platform's insurer-side claims module does not fit a broker. The policy number is copied from the BIBS account; no upload. | EBIX is replaced; design R5 section 2. | Claims handling moves to BIBS. | Claims | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | Product Owner, Claims (Claims, Risk Management and Analytics) | DCR-081 | FRS sign-off (Nov 2026) | FRS BRD-7 chapter 12; register DCR-081
CR-0143 | Drop 2 | BRD-07 | BRCLM.014 (p.14 / p.30); BRD-7 p.28 "Settlement Type Status values"; BRCLM.005 (p.13), BRCLM.035 (p.16) | FR-CM-043, FR-CM-045 | Deferred pending BDOI answer | Requested Type of Settlement values; a separate Settlement Type Status list maintained by the Unit Head; officers tag closures and TL / TH close. | Settlement values are outcomes and each says whether it closes the claim; officers set temporary closures and TL / TH close permanently; a separate status list waits until CLQ05 is answered. | CLQ05, CLQ06 open. | Settlement reporting uses the outcome list. | Claims | 1 | 2 | 1 | 0 |  |  |  | Low | Draft | Product Owner, Claims (Claims, Risk Management and Analytics) | CLQ05; CLQ06 | After BDOI answer (slot set by the CCB) | FRS BRD-7 chapter 12
CR-0144 | Drop 2 | BRD-07 | BRCLM.001-043 values and definitions (p.13-31) | FR-CM (parameters and LOVs) | Deferred pending BDOI answer | BDOI values and definitions for Claims (statuses, SLA, ageing, adjusters, locations per endorsement). | Documented defaults apply; 21 rows wait for BDOI values (CLQ01, CLQ02, CLQ04-CLQ08, CLQ11, CLQ15, CLQ16, CLQ20). | Open Claims questions. | Defaults may not match BDOI practice until set. | Claims | 2 | 0 | 2 | 1 |  |  |  | Medium | Draft | Product Owner, Claims (Claims, Risk Management and Analytics) | CLQ01; CLQ02; CLQ04-CLQ08; CLQ11; CLQ15; CLQ16; CLQ20 | Drop 2 (Mar - Apr 2027) | BRD-7 requirements baseline
CR-0145 | Drop 2 | BRD-07 | Report List claims rows (ISYS source, extra fields, age brackets); BRCLM.026-033 (p.16 / p.30-31) | FR-CM-060 to FR-CM-064 | BRD conflict resolved by decision | The Report List names ISYS as the source and adds fields and age brackets that BRD-7 does not list. | BIBS replaces ISYS for claims reports; columns from both documents; files kept in BIBS. | Conflict between BRD-7 and the Report List. | One set of claims reports. | Claims | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, Claims (Claims, Risk Management and Analytics) | DCR-084 | FRS sign-off (Nov 2026) | Register DCR-084
CR-0146 | Drop 0 | BRD-07 | BRD-7 assumption 3 (data migration and integration with existing systems, p.23); BRD-13 (no claims object) | FR-CM-013; FRS BRD-13 (object F07 / F11, conditional) | Data migration | BRD-7 assumes open and historical claims are migrated; BRD-13 does not mention claims. | Open claims are migrated only if BDOI puts the object in scope; history stays in legacy read-only. | CLQ14, DMQ30 open. | Without migration, open claims are finished in legacy or re-keyed. | Claims; Business Project Services | 2 | 6 | 4 | 1 |  |  |  | High | Draft | Product Owner, Claims (Claims, Risk Management and Analytics) | DCR-081; DCR-196; CLQ14; DMQ30 | Migration functions (Nov 2026 - Mar 2027) | BRD-13 requirements baseline 6.1
CR-0147 | Drop 2 | BRD-08 | BRID-005 (p.10-11); BRID-005.01 (Add. p.7-8); BRID-005.02; BRID-014 (p.20-22); portal NFRs | FR-EB-010 to FR-EB-015 (portal); FR-EB-040, FR-EB-051 | Scope reduction / descoped | Insurers and client HR use a secure portal or API: sign-in, uploads, downloads, requests for proposal, revisions. | No portal: insurers and client HR send files by e-mail or an agreed channel and EB users upload and validate them. The portal, its permissions and screens are removed; decision D7 is dormant. FRS BRD-8 and the test plan are updated. | BDOI drop plan item 2.4 "Employee Benefits (no portal feature)"; IQ22. | EB users key or upload partner documents; no external users in BIBS. | Employee Benefits; Processing | 2 | 3 | 3 | 3 |  |  | 40 | High | For CCB review | Product Owner, Employee Benefits | DCR-211; IQ22; D7; EBQ13 | Drop 2 (Mar - Apr 2027) | Programme alignment 2.2 item 2
CR-0148 | Drop 2 | BRD-08 | BRID-008 (p.14-15); BRIDSP-07 (p.9); BRIDSP-18 (p.10) | FR-EB-031; FR-SP-041 | Deferred pending BDOI answer | The system validates that the BOR is signed; IAAF and TOR carry a signature. | BOR: validator attestation with a checklist; e-signature verification on hold. IAAF and TOR: stamped signature until a qualified e-signature provider is named. | EBQ06; SP e-signature question open. | Signature checks stay manual. | Employee Benefits; Submitted Policies (Policy Review); Compliance | 2 | 5 | 3 | 1 |  |  |  | Medium | Draft | Product Owner, Employee Benefits | EBQ06 | After BDOI answer (slot set by the CCB) | FRS BRD-8 chapter 12; FRS BRD-12 scope
CR-0149 | Drop 2 | BRD-08 | BRID-008 negative scenario (p.14-15); BRID-001 (p.7); TAT annex (p.42) | FR-EB-031, FR-EB-022, FR-EB-052 | Behaviour differs from BRD | A BOR uploaded for a renewal transaction is invalid; RA a set number of days before expiry (example 180); booking in EBIX. | The BOR is required for renewals that remarket; RA default 135 days from the TAT annex; booking in BIBS. | EBQ02, EBQ05; flow charts of the BRD. | Renewal advice issued 135 days before expiry unless BDOI sets another value. | Employee Benefits | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | Product Owner, Employee Benefits | EBQ02; EBQ05 | FRS sign-off (Nov 2026) | FRS BRD-8 chapter 12
CR-0150 | Drop 2 | BRD-08 | BRID-028 (Add. p.13; main p.33) | FRS BRD-8 traceability (out of scope) | Scope reduction / descoped | Present required documents for high-risk accounts. | Out of scope per the EB addendum. | EB Addendum p.13 (DCR-089 answered). | None. | Employee Benefits | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | Product Owner, Employee Benefits | DCR-089 | FRS sign-off (Nov 2026) | FRS BRD-8 chapter 12
CR-0151 | Drop 2 | BRD-08 | BRID-013 (p.20), benefit lines HMO, GPA, GLI | FR-EB-020, FR-EB-021 | Behaviour differs from BRD | HMO providers are placement counterparties but are not insurance companies. | Proposed: HMO providers held in the insurer master with a provider type. | Platform holds counterparties as insurers. | HMO shown with insurers in lists and reports. | Employee Benefits; MBS | 1 | 2 | 1 | 0 |  |  |  | Low | Draft | Product Owner, Employee Benefits | DCR-097 | Drop 2 (Mar - Apr 2027) | Register DCR-097
CR-0152 | Drop 1 | BRD-09 | BRCSF-002 (p.7); BRD-9 p.3, p.5 footnote 3; BRD-13 BRID 11.1 (p.11-12) | FR-CSF-022; FR-CSF-011 | BRD conflict resolved by decision | Retrieve data from QPS and EBIX and send contact updates back to them. | BIBS is the source; the write-back to legacy stays off (NOT_CONFIGURED) because legacy is read-only from cut-over; accounts that exist only in legacy are found through the legacy account lookup. | BRD-13 legacy read-only (DCR-202); CSQ01. | No updates flow to legacy after go-live. | Contact Center Management | 0 | 0 | 0 | 0 |  |  | 13 | Medium | For CCB review | Product Owner, CSF (Contact Center Management) | DCR-104; DCR-202; CSQ01 | FRS sign-off (Nov 2026) | FRS BRD-9 chapter 12; register DCR-202
CR-0153 | Drop 1 | BRD-09 | BRCSF-004 (p.8) | FR-CSF-020, FR-CSF-021 | Deferred pending BDOI answer | View, add or update contact details. | Update after a recorded verification; "add" means additional contacts only if BDOI confirms. | CSQ15 open. | Contact Center users cannot add second contacts until confirmed. | Contact Center Management | 0 | 2 | 1 | 0 |  |  |  | Low | Draft | Product Owner, CSF (Contact Center Management) | CSQ15 | After BDOI answer (slot set by the CCB) | FRS BRD-9 chapter 12
CR-0154 | Drop 1 | BRD-09 | Umbrella CORE-16.04; BR-164 (p.11); BRCSF-006, BRCSF-009 | FR-CSF-030, FR-CSF-033 | BRD conflict resolved by decision | The umbrella asks Contact Center users to view and resend RAs and e-policies; BRD-9 asks for RAs only. | RA resend only until BDOI answers; e-policies can be viewed. | CRQ16 open. | E-policy resend stays with Processing. | Contact Center Management; Processing | 0 | 0 | 0 | 0 |  |  | 3 | Low | For CCB review | Product Owner, CSF (Contact Center Management) | DCR-172; CRQ16 | FRS sign-off (Nov 2026) | Register DCR-172
CR-0155 | Drop 1 | BRD-10 | SNSRP-301 (p.14); BRD-10 to-be diagram (p.8) | FR-SS-033 | Deferred pending BDOI answer | The BRD asks for tags, cases and notifications on a match, not for a stop on business. | No blocking. A blocking gate on quotation, account submission, placement, booking and renewal is proposed behind a parameter, off by default, if BDOI decides to block. | SANC SQ07 open; register priority item DCR-112. | Business can proceed while a match is under review. | Compliance; Marketing; Processing | 1 | 4 | 3 | 1 |  |  |  | High | Draft | Chief Compliance Officer | DCR-112; SANC SQ07 | After BDOI answer (slot set by the CCB) | FRS BRD-10 section 1.2
CR-0156 | Drop 1 | BRD-10 | SNSRP-201 (p.12); SNSRP-706 (p.19-20) | FR-SS-020; FR-SS-071 | Integration dependency | Receive the sanctions and NLDS-PEP lists in real time or on a schedule; save the STR extract to a designated folder. | Lists come in as files; direct NLDS query and provider APIs are on hold; the STR extract is downloaded, automatic saving to a folder is on hold. | SANC SQ01 open (sources and transports). | Compliance loads list files by hand. | Compliance; BDOI IT | 2 | 5 | 3 | 1 |  |  |  | Medium | Draft | BDOI IT (integration owner) with the BIBS Product Owner | SANC SQ01 | After BDOI answer (slot set by the CCB) | FRS BRD-10 section 1.2 and interfaces
CR-0157 | Drop 1 | BRD-10 | SNSRP-301 (p.14) parties screened | FR-SS-030 to FR-SS-033 | Deferred pending BDOI answer | Screening of clients; the parties are not listed. | Clients held in BIBS are screened; beneficial owners, authorised signatories and beneficiaries are not held today and not screened. | SANC SQ11 open. | Related parties are screened outside BIBS. | Compliance; Marketing | 2 | 6 | 4 | 1 |  |  |  | Medium | Draft | Chief Compliance Officer | SANC SQ11 | After BDOI answer (slot set by the CCB) | FRS BRD-10 section 1.2
CR-0158 | Drop 1 | BRD-10 | BRD-10 objectives (p.3), BSP M-2025-017 | FRS BRD-10 section 1.2 (out of scope) | Scope reduction / descoped | The objectives cite BSP M-2025-017; no requirement asks for adverse-media screening. | Adverse-media screening not in scope. | SANC SQ20 open. | Adverse media checked outside BIBS. | Compliance | 0 | 0 | 0 | 0 |  |  | 18 | Medium | For CCB review | Chief Compliance Officer | SANC SQ20 | FRS sign-off (Nov 2026) | FRS BRD-10 section 1.2
CR-0159 | Drop 1 | BRD-10 | SNSRP-101 to 109 (p.10-12), configuration; SNSRP-705, 706 (p.19-20), STR format | FR-SS (configuration); FR-SS-070, FR-SS-071 | Deferred pending BDOI answer | Production values, lists and the AMLC STR format. | Documented defaults apply; the production values and lists, the AMLC STR format and reasons, and the active-policy definition wait for BDOI. Four follow-ups: working-hour SLA calendars, accent-insensitive case search, protection of case documents against deletion, and screening after the transaction is saved. | SANC SQ02, SQ03, SQ05, SQ06, SQ08, SQ09, SQ10, SQ15 open. | Screening runs on default thresholds until set. | Compliance | 3 | 7 | 5 | 2 |  |  |  | Medium | Draft | Chief Compliance Officer | SANC SQ02; SQ03; SQ05; SQ06; SQ08; SQ09; SQ10; SQ15 | Drop 1, second release (Jan - Feb 2027) | BRD-10 requirements baseline
CR-0160 | Drop 2 | BRD-10 | Drop plan INT-20 Bridger Insight XG (manual) | FR-SS (cases, evidence) | Integration dependency | Compliance screens names in Bridger Insight XG. | Proposed: Bridger results recorded in the BIBS case with evidence; evidence document type and disposition values configured; a client export for batch screening only if asked. | IQ19 open (replace or complement BIBS list matching). | Two screening tools unless BDOI decides. | Compliance | 1 | 1 | 1 | 0 |  |  |  | Low | Draft | Chief Compliance Officer | IQ19 | Drop 2 (Mar - Apr 2027) | Programme alignment 5 (INT-20)
CR-0161 | Drop 0 | BRD-11 | BRD 1.002-1.009 (p.7-8), BRD 2.002 (p.8), BRD 3.002 (p.9): an approved BIBS request is the only way to change access | FR-UA-010 to FR-UA-045 | Integration dependency | BRD-11 makes an approved request in BIBS the only way to change a user or a group profile. The drop plan adds UIDM-ISC (identity governance). | Proposed: UIDM-ISC provisions users and group-profile assignments through an API (SCIM 2.0 or its connector) with the ISC request number in the change log; group-profile definitions stay in BIBS under BRD-11; aggregation export for certification. | Drop plan Drop 0 (UIDM-ISC); IQ05 open. | Joiners, movers and leavers handled by the IGA; BRD-11 request types reduced. | ITIO; BDOI IT; all departments | 3 | 15 | 7 | 2 |  |  |  | High | Draft | UAM Product Owner with ITIO | DCR-229; IQ05 | Drop 1, first release (Nov - Dec 2026) | FRS BRD-11 v1.1 interfaces; Programme alignment 5 (INT-02)
CR-0162 | Drop 0 | BRD-11 | UAM-NFR-12 (p.13), NFR 1.i external ACL | FR-UA-003 | Deferred pending BDOI answer | Authorisation of users by interfacing with an external ACL. | Authorisation stays in BIBS roles and permissions. | UQ14 open; may be covered by UIDM-ISC (CR-0161). | None while roles stay in BIBS. | ITIO | 1 | 4 | 2 | 1 |  |  |  | Low | Draft | UAM Product Owner with ITIO | UQ14 | After BDOI answer (slot set by the CCB) | BRD-11 requirements baseline
CR-0163 | Drop 0 | BRD-11 | NFR 1.j (p.13) user ID of at least ten characters, format a999999999; UAM-NFR-13 to 15 | FR-UA-011, FR-UA-052 | Deferred pending BDOI answer | User IDs in the a999999999 format; business unit and user level values; privilege levels and working hours; QPS retention values; profile deactivation while it has members. | Parameter USER_ID_PATTERN (default a999999999 for new users; existing service users exempt); the value lists and rules wait for BDOI. | UQ05, UQ07, UQ12, UQ16 open. | Defaults apply until BDOI sets the values. | ITIO | 1 | 1 | 2 | 1 |  |  |  | Low | Draft | UAM Product Owner with ITIO | DCR-118; UQ05; UQ07; UQ12; UQ16 | After BDOI answer (slot set by the CCB) | BRD-11 requirements baseline; register DCR-118
CR-0164 | Drop 0 | BRD-11 | BRD-11 written for QPS in April 2025, process diagram (p.6); UQ19 | FRS BRD-11 section 1.2 | Scope addition — beyond BRD | User access maintenance for the Quotation and Pre-processing System (QPS). | System-wide user access maintenance: every BIBS module uses the same users, group profiles and permissions. | UQ19. | One access process for all BIBS modules. | ITIO; all departments | 0 | 0 | 0 | 0 |  |  |  | Medium | For acceptance | UAM Product Owner with ITIO | UQ19 | FRS sign-off (Nov 2026) | FRS BRD-11 section 1.2
CR-0165 | Drop 0 | BRD-11 | BRD-11 infrastructure rows "Follow existing QPS set up"; UAM-NFR-30 engagement terms (p.17); data migration "N/A" (p.12) | FRS BRD-11 section 1.2 (out of scope); FR-UA-019 | Scope reduction / descoped | Servers, network, DR, environments and support follow the QPS set-up; engagement terms; user migration not applicable. | Infrastructure follows the BIBS deployment standards (CR-0027); engagement terms are outside the application; existing users are loaded with the bulk request. | BRD-11 answers with QPS references. | None on the business process. | ITIO; BDOI IT | 0 | 0 | 0 | 0 |  |  |  | Low | For acceptance | UAM Product Owner with ITIO | - | FRS sign-off (Nov 2026) | FRS BRD-11 section 1.2
CR-0166 | Drop 1 | BRD-12 | BRIDSP-01 (p.8); BRIDSP-13 (p.10); BRD-12 p.4-5 (LFS, HLS, CIU, SPI, LAMD) | FR-SP-001; FR-SP (LAMD) | Integration dependency | Receive submitted-policy details from the approved sources. | Excel uploads per source layout; direct feeds from LFS SaaS, HL-LOAS, CIU, SPI and LMS (LAMD) are on hold until specified. | IQ06, IQ07, IQ08 open; LFS not on the drop plan. | Submissions arrive by upload until the feeds exist. | Submitted Policies; CBG and Non-CBG Marketing; BDOI IT | 3 | 8 | 5 | 1 |  |  |  | High | Draft | BDOI IT (integration owner) with the BIBS Product Owner | IQ06; IQ07; IQ08; SP SQ01 | Drop 1, first release (Nov - Dec 2026) | FRS BRD-12 section 1.2 and interfaces; Programme alignment 5 (INT-03 to INT-05)
CR-0167 | Drop 1 | BRD-12 | BRIDSP-22 (p.11) | FR-SP-062 | Integration dependency | Letters and proposals sent automatically, including printed letters. | Print batches (merged PDF and control list); the mail-house (COG) transport is on hold. | Mail-house channel and layout not given. | Print batches handed to the mail house by hand. | Submitted Policies; Marketing | 1 | 4 | 2 | 1 |  |  |  | Low | Draft | BDOI IT (integration owner) with the BIBS Product Owner | SP SQ09 | After BDOI answer (slot set by the CCB) | FRS BRD-12 section 1.2 and interfaces
CR-0168 | Drop 1 | BRD-12 | BRIDSP-22, 23, 25, 26, 27, 32 (p.11-12) renewal of submitted policies; BRD-6 renewal letters | FR-SP (hand-off); FR-RN-090 | BRD conflict resolved by decision | BRD-12 requires the renewal of submitted policies (renewable list, RA / NRNS / NAL / SFU letters, hold cover, placement, booking); BRD-6 covers the same letters. | Renewal owns the renewal from the hand-off (candidate, account, hold cover, RA / NRNS / NAL / SFU); Submitted Policies keeps intake, classification, buckets, the expiry scan and the masterlist status. Renewal notice and renewal proposal letters stay in Submitted Policies until answered. | Decision D2; XQ03 (SP SQ09) open for the two letters. | One renewal process for all policies. | Submitted Policies; Marketing (Renewal) | 1 | 1 | 1 | 0 |  |  |  | High | For CCB review | Product Owner, Submitted Policies (CBG and Non-CBG Marketing) | DCR-129; D2; XQ03; SP SQ10 | FRS sign-off (Nov 2026) | Cross-BRD decisions D2, XQ03; FRS BRD-12 section 1.2
CR-0169 | Drop 1 | BRD-12 | BRD-12 p.5 (ISYS reference and ARF of the current process) | FRS BRD-12 section 1.2 | Behaviour differs from BRD | The current process uses the ISYS reference and the ARF. | The BIBS ARN replaces them; ISYS is not fed. | SP SQ20. | None after go-live. | Submitted Policies | 0 | 0 | 0 | 0 |  |  |  | Low | For CCB review | Product Owner, Submitted Policies (CBG and Non-CBG Marketing) | SP SQ20 | FRS sign-off (Nov 2026) | FRS BRD-12 section 1.2
CR-0170 | Drop 0 | BRD-13 | BRID 5.1 (p.8) | FR-DM-051 | Data migration | The system "can issue acknowledgment receipt" for a migrated UPP item. | No new AR for a migrated UPP item; the legacy AR number and date are shown on the item. | The cash was already acknowledged in legacy; DMQ14. | No double counting of receipts. | Operations (Cashiering); Comptrollership | 0 | 0 | 0 | 0 |  |  |  | High | For CCB review | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-204; DMQ14 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-204; FRS BRD-13 (FR-DM-051)
CR-0171 | Drop 0 | BRD-13 | BRID 5.5 (p.9) | FR-DM-055 | Deferred pending BDOI answer | Reclassify legacy UPP to other income with top-management approval. | New disposition RECLASS_OTHER_INCOME in batches, approved by the TL and then by a top-management approver; reversal only by a new approved batch. Criteria, GL account, frequency and notification wait for BDOI. | DMQ16 open. | Old unapplied cash stays on the books until criteria are set. | Operations (Cashiering); Comptrollership; top management | 1 | 1 | 1 | 0 |  |  |  | Medium | Draft | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-205; DMQ16 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-205; FRS BRD-13 (FR-DM-055)
CR-0172 | Drop 0 | BRD-13 | BRID 7.1, 7.2 (p.10) | FR-DM-070, FR-DM-071 | BRD conflict resolved by decision | Batch reversal of DPPR and PR2307 legacy invoices; BRD-2 reverses DP PR per invoice after confirmed collection. | Batches from an upload or from the Collections "for reversal" tags of legacy invoices, with maker-checker approval; the commission receivable entry follows the BDOI answer. | Conflict between BRD-13, BRD-2 and BRD-4. | Legacy DP and 2307 items cleared in batches. | Operations; Collections; Comptrollership | 1 | 1 | 1 | 0 |  |  |  | Medium | For CCB review | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-206 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-206
CR-0173 | Drop 0 | BRD-13 | BRID 6.1, 6.2 (p.9-10); BRCLXN.047 (p.33) | FR-DM-050; FR-DM-033 | Data migration | Legacy invoices are processed in BIBS by their legacy number; uniqueness across EBIX and QPS and component balances not stated. | The legacy number is kept as the BIBS invoice number unless it collides (then a source prefix); loaded by component, or in open-balance mode if legacy cannot split. | DMQ11, DMQ12 open. | Users find legacy invoices by their known number. | Operations; Collections; Comptrollership | 0 | 0 | 0 | 0 |  |  |  | Medium | For CCB review | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-207; DMQ11; DMQ12 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-207
CR-0174 | Drop 0 | BRD-13 | BRD-4 needs open EBIX PRs and disposition history; BRD-13 BRID 5-9 (p.8-11) | FR-DM (object F09); FR-CL | Data migration | BRD-13 carries receivables forward but says nothing about open dispositions, promises, installment plans and collector assignments. | Proposed: carry the open dispositions, promises, installment plans and assignments; history stays in the archive. | Gap between BRD-4 and BRD-13; CQ07. | Collectors continue their follow-up from day one. | Collections | 1 | 3 | 2 | 1 |  |  |  | Medium | Draft | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-203; CQ07 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-203; BRD-13 requirements baseline 6.1
CR-0175 | Drop 0 | BRD-13 | BRD-12 BRIDSP-33 (p.12); EB programme load; payee migration; BRD-13 object list (none) | FR-DM-014; FR-SP (migration); FR-EB (programme load); FR-DS (payee migration) | Data migration | Other BRDs expect data that BRD-13 does not mention: submitted-policy masterlists, in-force EB programmes, payees. | The loaders the other designs hold run under the migration framework (reconciliation and sign-off) once BDOI puts the objects in scope (P04, P05, R09). | DMQ01 open (object inventory). | All masterlists and programmes arrive through one controlled migration. | Submitted Policies; Employee Benefits; Comptrollership (Disbursement); Business Project Services | 2 | 6 | 4 | 1 |  |  |  | Medium | Draft | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-196; DMQ01 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-196; BRD-13 requirements baseline 6.1
CR-0176 | Drop 0 | BRD-13 | BRID 2.1 (p.7); BRD-10 SNSRP-301 (p.14) | FR-DM-032; FR-SS | Data migration | BRD-10 screens each client when it is created; BRD-13 loads clients in bulk and is silent on screening. | Proposed: no screening per migrated client; one full screening run after the client load; legacy risk ratings kept until the run completes. | DMQ06 open. | Compliance reviews one batch of matches after the load. | Compliance; Business Project Services | 1 | 2 | 2 | 0 |  |  |  | Medium | Draft | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-208; DMQ06 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-208
CR-0177 | Drop 0 | BRD-13 | BRD-13 cut-over aligned to RMEL (no date, p.12-13); timeline slide (go-live January 2028) | FR-DM-022, FR-DM-023, FR-DM-024; FR-DM-120, FR-DM-121 | Data migration | Cut-over aligned to RMEL; no go-live date, freeze, mocks, go / no-go criteria or treatment of the year-end. | Go-live Monday 3-Jan-2028 at the year-end boundary (option A): provisional GL opening trial balance, legacy GL kept for the FY2027 close, true-ups posted as opening-balance adjustment journals and reconciled to the legacy trial balance; mocks Apr-May, Jun-Jul, Aug and Oct 2027, dress rehearsal Nov-Dec 2027. | BDOI answer DMQ39 of 26-Sep-2026 (recommended option A); IQ01 confirmed at M6. | FY2027 is closed in legacy; BIBS books start with a provisional opening. | Comptrollership; Business Project Services; all departments (freeze) | 0 | 0 | 0 | 1 |  |  |  | High | For CCB review | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-200; DCR-217; DCR-242; DMQ39; IQ01 | Migration functions (Nov 2026 - Mar 2027) | FRS BRD-13 (FR-DM-022 to 024); register DCR-242
CR-0178 | Drop 0 | BRD-13 | BRID 11.1 (p.11-12) legacy read-only history; BRID 1.1b (p.7) extract delivery | FR-DM-110, FR-DM-111; FR-DM-010 | Data migration | Keep legacy read-only for history; receive the extracts. No retention for migration evidence; transport not stated. | Archive search with logged access; migration evidence kept 10 years as project records; staging purged within 5 days. Extracts are received by upload; an SFTP drop from BDOI IT and links into the legacy systems are on hold. | DMQ28 open (extract transport); hosting appendix (5-day purge). | Extract delivery by hand until the SFTP drop exists. | Business Project Services; BDOI IT; Compliance | 1 | 3 | 2 | 0 |  |  |  | Medium | Draft | Program Manager, Business Project Services, with Comptrollership and Operations | DCR-209; DMQ28 | Migration functions (Nov 2026 - Mar 2027) | Register DCR-209; FRS BRD-13 interfaces

## Summary
Summary
Counts and man-days by drop, BRD, deviation type, status and priority. Formulas read the Register sheet, so the figures follow any change to it.
By drop
Value | Description | CRs | High | Draft | For CCB review | For acceptance | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md)
Drop 0 | Drop 0 - Setup and Data Migration
Drop 1 | Drop 1 - Transactional (upstream and downstream)
Drop 2 | Drop 2 - Independent
Programme | Programme (cross-drop)
Phase 2 | Reinsurance module (BDOI answer A3)
Total
By BRD
Value | Description | CRs | High | Draft | For CCB review | For acceptance | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md)
BRD-00 | Core Replacement (umbrella) and programme
BRD-01 | New Business
BRD-02 | Operations
BRD-03 | Product Maintenance
BRD-04 | Collections
BRD-05 | Accounting, Disbursement and ACSL
BRD-06 | Renewal
BRD-07 | Claims
BRD-08 | Employee Benefits
BRD-09 | Customer Servicing Facility
BRD-10 | Sanction Screening
BRD-11 | User Access Maintenance
BRD-12 | Submitted Policies
BRD-13 | Data Migration
Total
By deviation type
Value | Description | CRs | High | Draft | For CCB review | For acceptance | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md)
Scope addition — beyond BRD | BIBS does more than the BRD asks, or the umbrella FRS proposes a requirement that no function BRD owns
Scope reduction / descoped | A BRD requirement is not delivered, or is delivered with less than the BRD asks, by a BDOI instruction or a proposal
Behaviour differs from BRD | The requirement is met in a different way from the BRD text
Deferred pending BDOI answer | The element runs with a documented default and waits for a BDOI answer (values, layouts, rules, a yes / no on scope)
Deferred to Phase 2 | Out of phase 1 by BDOI decision; kept for phase 2
BRD conflict resolved by decision | Two BRDs, or two parts of one BRD, conflict
Integration dependency | The requirement depends on an interface with a BDO or insurer system that is not yet specified
NFR / infrastructure change | A non-functional value (hours, availability, recovery, retention, sizing) or an infrastructure choice differs from one or more BRDs, or from the IER workbook
Data migration | The migration or cut-over treatment differs from what a BRD assumes, or adds work that a BRD does not state
Total
By CR status
Value | Description | CRs | High | Draft | For CCB review | For acceptance | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md)
Draft | Raised by the project team
For CCB review | Impact analysis complete; ready for the Change Control Board to approve, reject or defer
Approved | Approved by the CCB; scheduled into a drop or release
Rejected | Rejected by the CCB; the BRD text stands, or the item is closed without change
For acceptance | The proposed behaviour is decided and documented and differs from the BRD text; the CCB records the acceptance
Total
By priority
Value | Description | CRs | High | Draft | For CCB review | For acceptance | Analysis (md) | Dev. (md) | Test (md) | Doc. (md) | Total (md)
High | Affects money (premium, commission, GL, remittance), regulatory compliance, security or access, or blocks a drop
Medium | Changes a rule, screen, report or interface; a documented default runs until BDOI decides
Low | Wording, labels or presentation; no effect on money, control or data
Total

## Effort basis
Effort basis
How the man-days are estimated: team roles, the man-day, what is included and excluded, and the size classes.
Assumptions
1 | A man-day is 8 working hours of one team member. Figures are rounded to whole days.
2 | Effort is the work still needed to close the deviation as proposed in the "Proposed behaviour" column. It is 0 when the behaviour is decided and documented and only needs acceptance.
3 | For an item deferred pending a BDOI answer, the effort is the work to complete it once BDOI answers as proposed (interface, values, layouts, screens). A different answer is re-estimated at impact analysis.
4 | The optional column "BRD as written" gives the indicative effort to deliver the BRD text instead of the proposed behaviour, for the CCB to compare.
5 | Development includes configuration. Test covers SIT test cases (writing and running) and regression. Documentation covers the FRS, test plan and guides.
6 | Excluded: UAT support, BDOI staff time, infrastructure provisioning by BDO IT (buckets, keys, network routes, certificates), licences and third-party services, and the Phase 2 Reinsurance module.
7 | Excluded: the delivery of what the FRS specify (BRD-6, BRD-8, BRD-9, BRD-12, BRD-13, BRD-7). Only the delta caused by the deviation is estimated.
8 | Estimates are at the accuracy of an impact analysis (about plus or minus 30 percent). The CCB re-estimates an item when BDOI's answer differs from the proposal.
9 | Status and counts are as of the date on the cover and are refreshed with each issue of the register.
Team roles
| Role | Work counted in the estimate
| Business analyst | Analysis: impact analysis, BDOI workshops, rules and layouts, FRS and test plan updates (with the technical writer)
| Solution architect | Analysis of interfaces, data and infrastructure items
| Backend developer | Development: services, data changes, jobs, interfaces, reports
| Frontend developer | Development: screens, forms and lists
| QA engineer | Test: SIT test cases written and run, regression
| Technical writer | Documentation: FRS, test plan, user and configuration guides, release notes
Size classes
| Class | Man-days | CRs
| 0 | Acceptance only
| S | 1 to 3
| M | 4 to 10
| L | 11 to 25
| XL | more than 25
Man-days by activity (all CRs)
| Activity | Meaning | Man-days
| Analysis | Impact analysis, workshops, rules and layouts
| Development | Development and configuration
| Test | SIT cases written and run, regression
| Documentation | FRS, test plan, guides
Total

## Change control
Change control
Change-control process for deviations and new change requests, with the roles and the proposed Change Control Board (CCB).
Process: request, impact analysis, CCB, approval, schedule, implement, verify, close
Step | What happens | Who | Output | Time
1. Request | Anyone in BDOI or the project team raises a change request on the CR form, or the project team raises a CR from a recorded deviation (FRS clarifications, register, alignment pack). | Requester; Project Manager (iorta TechNXT) logs it | CR row in this register, status Draft | Same day
2. Impact analysis | The business analyst and solution architect assess scope, BRD and FRS references, affected modules, data, interfaces, tests, documents and drop; estimate effort in man-days (Analysis, Development, Test, Documentation). | Business analyst, Solution architect; BDOI owner of the BRD for business impact | Impact analysis on the CR form; status For CCB review | 5 working days (10 for L / XL)
3. CCB review | The Change Control Board reviews the CR at its fortnightly meeting (or ad hoc for High priority items): accept, reject, defer, or ask for more analysis. | Change Control Board | Minutes with the decision per CR | Fortnightly
4. Approval | Approved CRs are signed on the CR form by the BDOI decision owner and the BIBS Product Owner. A CR above 25 man-days, or one that moves a drop date, also needs the Program Manager. | Decision owner; BIBS Product Owner; Program Manager (L / XL, date change) | Status Approved or Rejected; signed CR form | Within 5 working days of the CCB
5. Schedule | The Project Manager places the CR in a drop or release and updates the plan, the FRS change list and the test plan scope. | Project Manager (iorta TechNXT); BDOI Program Manager | Target drop / release set; plan updated | Next planning cycle
6. Implement | The team delivers and documents the change: configuration, FRS revision, test cases, user and configuration guides. | Delivery team | Delivered change, FRS revision, test cases | As scheduled
7. Verify | QA runs the SIT cases and regression; the BDOI owner checks the behaviour in SIT or UAT against the CR. | QA engineer; BDOI owner of the BRD | Test evidence; acceptance by the owner | Within the drop SIT / UAT window
8. Close | The Project Manager records the result, the FRS version that carries it and the closing date; the CR is reported in the release notes. | Project Manager; BIBS Product Owner | Status Implemented; release note entry | At release
Change Control Board (proposed membership)
| Member | Organisation | Role on the board
| BIBS Product Owner | BDOI | Chair; casting vote on scope and priority
| Program Manager, Business Project Services | BDO Unibank ESG | Plan, drops and budget; approves L / XL items and date changes
| Owner of the BRD concerned (department head or product owner) | BDOI | Decision owner of the CR; attends for the CRs of the BRD
| Head, Comptrollership | BDOI | Member for any CR that touches posting, GL, tax or BIR reports
| Chief Compliance Officer (or delegate) | BDOI | Member for any CR that touches screening, KYC, access control or retention
| BDOI IT (integration owner) | BDOI | Member for interfaces and infrastructure items
| Project Manager | iorta TechNXT | Secretary: agenda, register, minutes, schedule
| Solution Architect | iorta TechNXT | Presents impact analysis and effort
| Business Analyst lead | iorta TechNXT | Presents BRD / FRS references and test impact
Rules of the board
• | Quorum: the chair (or a named delegate), the Program Manager and the decision owner of each CR on the agenda.
• | The CCB meets every two weeks from October 2026 to go-live, and ad hoc for High priority items that block a drop.
• | A CR above 25 man-days, or one that moves a drop or the go-live date, needs the Program Manager's approval.
• | Approved CRs reach the FRS only through an FRS revision that cites the CR ID; the FRS baseline is not changed by this register.
• | Rejected CRs keep their row with the reason; the BRD text stands.

## CR form
CR form
Change request form: one per CR; the Project Manager files the signed form with the register.
Request
CR ID | CR-nnnn, given by the Project Manager when the CR is logged
Title | Short name of the change
Requested by / date | Name, department, date
BRD and requirement ID(s), page | For example BRNB.071 (p.116)
FRS FR ID(s) | For example FR-NB-081
Drop | Drop 0 / Drop 1 / Drop 2 / Programme / Phase 2
Deviation type | One of the nine types (How to read)
What the BRD asks | Quote or summarise the BRD text
Change requested or proposed behaviour | What BIBS does or should do instead
Reason | BDOI decision, question reference or technical constraint
Impact analysis
Business impact | Effect on the process, money, control and customers
Affected departments and modules | BDOI departments; BIBS modules and screens
Interfaces and data | Systems, files, migration objects affected
Documents affected | FRS, design, test plan, guides, register
Effort (man-days) | Analysis / Development / Test / Documentation / Total; size S, M, L, XL
Effect on the plan | Drop, release, dependency on other CRs
Priority | High / Medium / Low
Decision
CCB decision and date | Approved / Rejected / Deferred, with the meeting date
Conditions | Any condition set by the CCB
Decision owner (BDOI) | Name and signature
BIBS Product Owner | Name and signature
Program Manager (L / XL or date change) | Name and signature
Implementation
Target drop / release | Drop or release
FRS version carrying the change | For example FRS BRD-1 v1.2
Verified by / date | QA and BDOI owner
Closed on | Date

## _lists (hidden)
Drop 0 | BRD-00 | Scope addition — beyond BRD | High | Draft | FRS sign-off (Nov 2026)
Drop 1 | BRD-01 | Scope reduction / descoped | Medium | For CCB review | Drop 1, first release (Nov - Dec 2026)
Drop 2 | BRD-02 | Behaviour differs from BRD | Low | Approved | Drop 1, second release (Jan - Feb 2027)
Programme | BRD-03 | Deferred pending BDOI answer |  | Rejected | Migration functions (Nov 2026 - Mar 2027)
Phase 2 | BRD-04 | Deferred to Phase 2 |  | For acceptance | Infrastructure before SIT (by Jan 2027)
| BRD-05 | BRD conflict resolved by decision |  |  | Drop 2 (Mar - Apr 2027)
| BRD-06 | Integration dependency |  |  | Before go-live (Oct - Dec 2027)
| BRD-07 | NFR / infrastructure change |  |  | Phase 2
| BRD-08 | Data migration |  |  | After BDOI answer (slot set by the CCB)
BRD-09
BRD-10
BRD-11
BRD-12
BRD-13