HYPERCARE PLAN

Hypercare, Warranty and Sign-off Plan

Hypercare after the January 2028 go-live, exit criteria, issue targets, handover to steady-state support, warranty and the acceptance certificates

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-GL-HYP-BRD-00 |
| Version | 1.0 |
| Date | 8 October 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 08 Oct 2026 | iorta TechNXT Project Manager | iorta TechNXT Service Delivery Lead | BDOI Program Manager (pending) | First issue. Hypercare from go-live to the January 2028 month-end close, daily stand-up and triage, issue targets, exit criteria, handover to the support model, a 12-month warranty and the certificates C1 UAT acceptance, C2 go-live acceptance and C3 hypercare exit |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Hypercare, certificates C2 and C3 |
| Head, BDOI IT | Approver | BDOI | Handover to steady-state support, warranty |
| BIBS Product Owner; owners of BRD-1 to BRD-13 | Approvers | BDOI | UAT acceptance per drop (C1) |
| Heads of Operations, Comptrollership, Marketing; Head of the Renewal processing team | Reviewers | BDOI | Business checks of hypercare |
| BIBS Service Owner | Reviewer | BDOI | Handover and support |
| Project and support team | Delivery | iorta TechNXT | Hypercare, fixes, warranty |

Contents

1 Introduction	4

1.1 Purpose	4

1.2 Audience	4

1.3 Reference documents	4

2 From UAT to steady state	5

3 Hypercare	6

3.1 Duration	6

3.2 Organisation and roster	6

3.3 Daily rhythm	7

3.4 Issue management	7

3.5 Issue resolution targets in hypercare	7

3.6 Releases in hypercare	8

3.7 Hypercare reporting	8

4 Exit criteria	9

5 Handover to steady-state support	11

5.1 Steps	11

5.2 What changes at handover	11

6 Warranty	12

6.1 Period	12

6.2 Scope	12

6.3 How a warranty issue is handled	12

7 Sign-off certificates	13

7.1 C1 UAT acceptance certificate (one per drop)	13

7.2 C2 Go-live acceptance certificate	14

7.3 C3 Hypercare exit and handover certificate	14

Decisions and open points for BDOI	16

Glossary	17

Sign-off	18

# 1 Introduction

## 1.1 Purpose

This plan covers the time from UAT acceptance to steady-state support: how BIBS is accepted for go-live, how the project team supports it closely after the go-live of January 2028 (hypercare), when hypercare ends, how support passes to the support model, what the warranty covers, and the certificates that BDOI signs at each step.

## 1.2 Audience

The go / no-go board and the Program Manager; the business owners of the BRDs, who sign the UAT acceptance; the BIBS Service Owner, BDOI application support and the BDO service desk, who take over support; the iorta TechNXT project and support teams.

## 1.3 Reference documents

Table 1: Reference documents

| Ref | Document | Used for |
| --- | --- | --- |
| R1 | Go-Live, Cutover and Data Migration Plan v1.0 | Go-live sequence, GNG-3, point of no return |
| R2 | Data Migration Handbook BRD-13 v2.1, Part D | Hypercare roster, daily checks, exit criteria, true-ups |
| R3 | Support Model and Support Guide v1.0 | Severities, steady-state service levels, L1 guide, handover target |
| R4 | Operations Runbook and Observability v1.0 | Daily operations check, alerts, jobs |
| R5 | Production Readiness Checklist v1.0 | Criteria carried into hypercare |
| R6 | Test plans of BRD-1 to BRD-13 (release set files 04 and 05) and the UAT plans | UAT scope and results per drop |
| R7 | Change Management Register v1.0 | Changes after acceptance |

# 2 From UAT to steady state

Figure 1 shows the path from UAT acceptance to steady-state support and the three certificates.

Figure 1: From UAT acceptance to steady-state support

Table 2: Milestones

| Milestone | Date | Evidence |
| --- | --- | --- |
| UAT acceptance Drop 2 | By 30 Nov 2027 | Certificate C1 (Drop 2) |
| UAT acceptance Drop 0 and Drop 1 (end to end, on migrated data) | By 15 Dec 2027 | Certificate C1 (Drop 0 and Drop 1) |
| Go / no-go GNG-3 | Sun 2 Jan 2028, 18:00 | Decision recorded with every criterion (R1) |
| Go-live | Mon 3 Jan 2028, 08:00 | Go-live notice |
| Point of no return | Mon 3 Jan 2028, 18:00 | Board decision (CT-069) |
| Go-live acceptance | Week-1 review, Mon 10 Jan 2028 (T+7) | Certificate C2 |
| Hypercare mid-point review | Mon 17 Jan 2028 (T+14) | Criteria status (CT-079) |
| Hypercare exit | Wed 2 Feb 2028 (T+30), after the January month-end close | Certificate C3 |
| End of warranty | Tue 2 Jan 2029 | Warranty closure note; annual maintenance from 3 Jan 2029 |

# 3 Hypercare

## 3.1 Duration

Hypercare runs from go-live, Monday 3 January 2028, to the first month-end close with the legacy control accounts, planned for Wednesday 2 February 2028 (T+30), in two stages:

Table 3: Stages of hypercare

| Stage | Days | Set-up |
| --- | --- | --- |
| Intensive | T to T+5 (3 to 8 Jan 2028) | Command centre open 07:00-20:00; infrastructure on call 24 x 7; floor support in every department and the main branches; status calls 08:00 and 17:00 |
| Stabilise | T+6 to T+30 (9 Jan to 2 Feb 2028) | Daily stand-up and twice-daily triage; daily 17:00 call; support levels of the support model working beside the project team |

Extension. If the exit criteria are not met at T+30, hypercare continues to the February 2028 month-end close (exit decision on Friday 3 March 2028, T+60) at no extra charge to BDOI. A second extension is decided by the Steering Committee with a recovery plan.

## 3.2 Organisation and roster

The roster of the cutover plan applies (R2). The names and telephone numbers are fixed at T-29 (CT-003).

Table 4: Hypercare roster (Data Migration Handbook, Part D)

| Role | Who | Hours | Reports to |
| --- | --- | --- | --- |
| Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager |
| Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager |
| Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager |
| Infrastructure | iorta TechNXT infrastructure team | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager |
| Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead |
| Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end; true-ups T+15 to T+120 | Head, Comptrollership |
| Renewal processing team | Head of the Renewal processing team; makers and checkers | 08:00-20:00 T to T+10 on the day-1 queue; P03 resubmissions on T-2 and T-1 | Program Manager |
| Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head |
| Service desk (L1) | BDOI service desk | Service hours | BDOI IT head |

Ticket routing during hypercare: users call the BDOI service desk (L1) or the floor support of their department; L1 logs every call; L2 and the iorta TechNXT application team triage together in the command centre; fixes follow section 3.5.

## 3.3 Daily rhythm

Table 5: Daily rhythm of hypercare (business days)

| Time | Meeting or task | Content | Lead |
| --- | --- | --- | --- |
| 07:00 | Daily operations check | Night batch, alerts, backups, replication, certificates (R4, section 7.2) | iorta TechNXT infrastructure team |
| 07:30 | Daily hypercare check (CT-071) | Migration Clearing 0.00 per branch and currency; legacy control accounts against their sub-ledgers; automatch results; exception queues; URGENT January renewals without an RA or insurer request; failed jobs | iorta TechNXT Migration Lead |
| 08:30 | Daily stand-up (15 minutes) | Overnight results; open P1 and P2; today's risks (deadlines, month-end, insurer due dates); help needed from the business | iorta TechNXT Project Manager |
| 10:00 and 16:00 | Triage (CT-072) | New issues: severity, category, owner, target; fixes ready for release; workarounds to publish to L1 | iorta TechNXT QA lead with Operations, Comptrollership, Renewal and L2 |
| 12:00 (T to T+5) | Midday check | Queues, Migration Clearing, legacy posting check | iorta TechNXT Migration Lead |
| 17:00 | Status call and daily hypercare report | Issues opened and closed by severity and department; checks; decisions needed | iorta TechNXT Project Manager |
| Weekly | Board review (T+7, T+14, T+21, T+30) | Issues, volumes, performance, renewal queue, user feedback, exit criteria | Program Manager |

## 3.4 Issue management

Every call and finding is an issue in the hypercare log in the ITSM tool, with: severity (P1 to P4 as in the support model), category, module, department and branch, the user, the record number, the evidence and the owner. Categories:

Table 6: Issue categories in hypercare

| Category | Meaning | Handled by |
| --- | --- | --- |
| Application fault | BIBS does not behave as the signed FRS and the accepted test cases say | iorta TechNXT (fix and release) |
| Migrated data | A migrated record is wrong or missing | Data Migration Lead and data owner decide; correction through the BIBS functions or a data correction |
| Configuration | A parameter, list, rule, workflow or role is set wrongly | BDOI business administrator or L2 (standard change) |
| Access | A user lacks a role or a data scope | User access request |
| How-to and training | The user needs guidance | Floor support and L1; knowledge article |
| Change request | A new or different requirement | Change Management Register; not a hypercare fix |
| Interface or platform | A BDO system, AWS or the network | BDOI IT or BDO Cloud Operations |

## 3.5 Issue resolution targets in hypercare

The targets are shorter than in steady state because the project team is on hand.

Table 7: Issue targets in hypercare

| Severity | Response | Workaround | Fix in production | Updates |
| --- | --- | --- | --- | --- |
| P1 | 15 minutes (24 x 7 in the intensive stage) | 2 hours | Hotfix within 24 hours, approved by the go / no-go board | Every hour on the bridge |
| P2 | 30 minutes in service hours | 4 service hours | 3 business days, in a hotfix or the next hypercare release | At each triage |
| P3 | 4 service hours | 2 business days | 10 business days, in a hypercare release | Daily report |
| P4 | 1 business day | - | Planned with the Product Owner after hypercare | Weekly |

## 3.6 Releases in hypercare

•	From T-7 to T+14 production releases are frozen; only a hotfix of a Critical (P1) issue approved by the go / no-go board is deployed (R2, freeze windows).

•	The first planned hypercare release is in the window of Sunday 23 January 2028, 00:00-04:00 (T+20), with the P2 and P3 fixes accepted by the key users in UAT.

•	No release from 27 January to 3 February 2028 (January close), except a hotfix approved by the board.

•	Every fix goes through UAT with the key user who raised the issue, then Pre-Prod, then production (Support Model, releases).

## 3.7 Hypercare reporting

The daily hypercare report (17:00) and the weekly board review show: tickets opened, closed and open by severity, category and department; P1 and P2 with status; the daily checks; the night batch; availability and response times against the SLOs; the URGENT January renewals with an RA sent or an insurer request; true-up 1 status (due T+18, 21 Jan 2028); and the status of each exit criterion.

# 4 Exit criteria

Hypercare ends when every criterion below is met, or waived by the go / no-go board with a dated plan. The cutover plan sets the business and migration criteria; this plan adds the support handover criteria.

Table 8: Exit criteria of the cutover plan

| Ref | Criterion | Source |
| --- | --- | --- |
| HX-01 | No open Critical or High issue; Medium issues have an agreed fix date | Data Migration Handbook, Part D |
| HX-02 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days | Data Migration Handbook, Part D |
| HX-03 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference | Data Migration Handbook, Part D |
| HX-04 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident | Data Migration Handbook, Part D |
| HX-05 | Staging and extract files of production purged within 5 days of sign-off (purge log) | Data Migration Handbook, Part D |
| HX-06 | True-up 1 posted, reconciled and signed | Data Migration Handbook, Part D |
| HX-07 | Every URGENT January renewal has an RA sent or an insurer request made | Data Migration Handbook, Part D |
| HX-08 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted | Data Migration Handbook, Part D |

Table 9: Support handover criteria

| Ref | Criterion | Evidence |
| --- | --- | --- |
| HX-09 | No open P1 or P2 issue; every P3 has an agreed fix date and a workaround known to L1 | Hypercare log |
| HX-10 | New tickets below 40 a business day for 5 consecutive business days, with no rising trend (about 3 per 100 named users) | Ticket report |
| HX-11 | SLOs met for 10 consecutive business days: availability 99.9 %, 95 % of screen requests within 2 seconds, night batch class A finished before 06:00 | SLO dashboard |
| HX-12 | Known errors and workarounds of hypercare published in the knowledge base; L1 guide updated | Knowledge base index |
| HX-13 | L1 analysts and L2 analysts handled tickets alone for the last 5 business days (project team in support only) | Ticket assignment report |
| HX-14 | Monitoring and alert routing working; first monthly restore spot check passed | Alert test; restore record |
| HX-15 | Configuration baseline of production recorded; environment documentation current (versions, release, addresses, backups, secrets inventory without values) | Baseline export; environment sheet |
| HX-16 | Migration roles removed; non-production staging data of the migration purged | User Access report; purge log |
| HX-17 | Contacts and escalation matrix of the support model confirmed by a call test | Call test record |
| HX-18 | Open P3 and P4 issues and approved change requests moved to the support backlog and the Change Management Register with their history | Transfer list |

# 5 Handover to steady-state support

## 5.1 Steps

Table 10: Handover steps

| Step | When | Action | Owner |
| --- | --- | --- | --- |
| H1 | T+14 | Mid-point review against the exit criteria; gaps planned | Program Manager |
| H2 | T+15 to T+25 | L1 and L2 take every ticket first; the project team supports from the second line only | BIBS Service Owner |
| H3 | T+20 | Knowledge transfer sessions on the fixes and known errors of hypercare; runbook updates | iorta TechNXT Support Manager |
| H4 | T+28 | Transfer list of open issues and change requests prepared | iorta TechNXT Project Manager |
| H5 | T+30 | Handover meeting: exit criteria evidence, transfer list, contacts; certificate C3 submitted | Program Manager; BIBS Service Owner |
| H6 | T+30 | Command centre closed; daily 17:00 call ends; monthly service review starts in March 2028 | Program Manager |

## 5.2 What changes at handover

Table 11: Hypercare and steady state

| Item | Hypercare | Steady state (support model) |
| --- | --- | --- |
| First contact | L1 and the floor support | L1 BDOI service desk |
| Triage | Twice a day in the command centre | L2 at logging; weekly operations review |
| Targets | Section 3.5 | Support Model chapter 4 |
| Releases | Hotfixes and one hypercare release | Monthly planned release; emergency releases |
| Reporting | Daily report and weekly board review | Monthly service report and review |
| Governance | Go / no-go board | BIBS Change Advisory Board; Service Owner |

# 6 Warranty

## 6.1 Period

The warranty runs for 12 months from go-live: 3 January 2028 to 2 January 2029 (proposal, OP-03). Hypercare is inside the warranty. From 3 January 2029 support continues under the annual maintenance and support agreement.

## 6.2 Scope

Table 12: Warranty scope

| Covered at no charge | Not covered (handled as noted) |
| --- | --- |
| Correction of any non-conformance of BIBS with the signed FRS, as changed by approved change requests, and with the accepted UAT test cases, reported during the warranty | New or changed requirements: Change Management Register |
| Correction of data loaded wrongly by the migration functions of BIBS, where the extract was right | Errors in the legacy data or the extracts (BDOI data stewards) |
| Security vulnerabilities of the BIBS application and its components rated Critical or High | BDO systems on the other side of an interface; AWS managed services; the network |
| Performance below the SLOs at the volumes of the performance test, when the cause is in BIBS | Volumes or users above those tested, until a capacity change is agreed |
| The fix of a regression caused by a warranty fix | Configuration changes made in production without iorta TechNXT's involvement |
| Updates of the user guides, the runbook and the knowledge articles affected by a fix | Use of BIBS contrary to the user guides; third-party products not delivered by iorta TechNXT |

## 6.3 How a warranty issue is handled

A warranty issue is a ticket of category Application fault (or Migrated data, when BIBS loaded the data wrongly). It follows the support model: the service levels of the support model apply after hypercare, the fix is delivered in a planned or emergency release, and the monthly service report lists the warranty issues opened and closed. A disagreement on whether an issue is a non-conformance or a change goes to the BIBS Change Advisory Board, then to the Program Manager and the iorta TechNXT account executive.

# 7 Sign-off certificates

Each certificate is submitted by iorta TechNXT with its evidence. BDOI signs it, or lists in writing the criteria not met with reasons, within 5 business days of submission. A certificate with open items may be signed with those items listed and dated.

## 7.1 C1 UAT acceptance certificate (one per drop)

| Certificate | C1 - UAT acceptance |
| --- | --- |
| Drop | Drop 0 and Drop 1 (end to end) / Drop 2 - one certificate each |
| BRDs covered | Drop 0: BRD-03, BRD-11, BRD-13; Drop 1: BRD-01, BRD-02, BRD-04, BRD-05, BRD-06, BRD-09, BRD-10, BRD-12; Drop 2: BRD-07, BRD-08 |
| UAT period | Aug-Dec 2027 (Drop 0 and Drop 1); Oct-Nov 2027 (Drop 2) |
| Due | 15 Dec 2027 (Drop 0 and Drop 1); 30 Nov 2027 (Drop 2) |
| Release accepted | The release package tested in UAT and recorded in the certificate |

Table 13: C1 acceptance criteria

| # | Criterion | Met (Yes / No) | Evidence reference |
| --- | --- | --- | --- |
| 1 | Every UAT test case of the drop executed; at least 98 % passed; every failed case has an issue |  | UAT results per BRD |
| 2 | No open Critical or High issue; Medium issues with fix dates and workarounds |  | Issue log |
| 3 | End-to-end scenarios across the drops passed on migrated data (Mock 3 and Mock 4) |  | Scenario results |
| 4 | Reports, letters and files of the drop checked by their business owners |  | Checklists |
| 5 | Interfaces of the drop tested end to end with the other systems' owners |  | Integration test records |
| 6 | User guides of the drop reviewed by the key users |  | Review sign-off |
| 7 | Change requests raised in UAT recorded in the Change Management Register with a decision |  | Register extract |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Business owner of each BRD of the drop | BDOI |  |  |
|  | BIBS Product Owner | BDOI |  |  |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Project Manager | iorta TechNXT |  |  |

## 7.2 C2 Go-live acceptance certificate

| Certificate | C2 - Go-live acceptance |
| --- | --- |
| Go-live | Monday 3 January 2028, 08:00 PHT |
| Point of no return | Monday 3 January 2028, 18:00 PHT - continue in BIBS |
| Signed at | Week-1 review, Monday 10 January 2028 (T+7) |

Table 14: C2 acceptance criteria

| # | Criterion | Met (Yes / No) | Evidence reference |
| --- | --- | --- | --- |
| 1 | GNG-3 passed with every criterion recorded; no waiver of a financial or clearing criterion |  | Go / No-Go report |
| 2 | Point of no return passed: no Critical issue stopping receipts, payment application, remittance or booking; Migration Clearing 0.00; no legacy posting since the freeze; every branch transacted in BIBS |  | Board decision CT-069 |
| 3 | First BIBS end-of-day runs, payment uploads, automatch, remittance extraction and Collections refresh completed (CT-067, CT-070, CT-073, CT-074) |  | Run logs |
| 4 | Daily hypercare checks clean since go-live, or each break explained |  | Daily hypercare reports |
| 5 | URGENT January renewals worked in the day-1 queue |  | Renewal report |
| 6 | Staging data and extract files of the production load purged within 5 days of sign-off |  | Purge log (CT-075) |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services (chair of the go / no-go board) | BDO Unibank ESG |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Head, Operations | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |

## 7.3 C3 Hypercare exit and handover certificate

| Certificate | C3 - Hypercare exit and handover to support |
| --- | --- |
| Hypercare period | 3 January 2028 to 2 February 2028 (extended to the February close: yes / no) |
| Warranty | 3 January 2028 to 2 January 2029 |
| Support from | The day after signature, under the Support Model and Support Guide |

Table 15: C3 exit criteria

| Ref | Criterion | Met (Yes / No / Waived) | Evidence reference |
| --- | --- | --- | --- |
| HX-01 to HX-08 | Exit criteria of the cutover plan (chapter 4) |  |  |
| HX-09 to HX-18 | Support handover criteria (chapter 4) |  |  |
| - | Open items transferred with owners and dates (attached list) |  |  |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | BIBS Service Owner | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |
|  | Support Manager | iorta TechNXT |  |  |

# Decisions and open points for BDOI

Table 16: Decisions and open points

| Ref | Point and our proposal | Owner | Needed by |
| --- | --- | --- | --- |
| OP-01 | Confirm hypercare from go-live to the January 2028 month-end close (planned exit 2 Feb 2028), with extension to the February close | Program Manager | 30 Jun 2027 |
| OP-02 | Confirm the handover ticket level of fewer than 40 new tickets a business day for 5 consecutive business days (HX-10) | BIBS Service Owner | 30 Nov 2027 |
| OP-03 | Confirm the 12-month warranty from go-live and its scope, in the support agreement | Head, BDOI IT | 30 Jun 2027 |
| OP-04 | Confirm the UAT pass rate of 98 % and the other C1 criteria per drop | BIBS Product Owner with the BRD owners | 30 Jun 2027 |
| OP-05 | Confirm the signatories of C1 per drop (the approvers of each BRD's approval sheet), C2 and C3 | Program Manager | 30 Jun 2027 |
| OP-06 | Confirm the hypercare release window of Sunday 23 January 2028 and the release freeze over the January close | Head, BDOI IT | 30 Nov 2027 |

# Glossary

| Term | Meaning |
| --- | --- |
| C1, C2, C3 | UAT acceptance, go-live acceptance and hypercare exit certificates |
| Hotfix | An emergency release of a fix for a P1 issue |
| Hypercare | Close support by the project team from go-live to the first month-end close |
| Key user | The department's trained user who tests fixes and helps colleagues |
| Warranty | The period in which iorta TechNXT corrects non-conformances of BIBS at no charge |

# Sign-off

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | BIBS Product Owner | BDOI |  |  |
|  | BIBS Service Owner | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |