## Cover
READINESS CHECKLIST
Production Readiness Checklist
Operational, security, performance, data, support, compliance and business readiness of BIBS for the January 2028 go-live
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 8 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Checklist | Production readiness criteria of BIBS with owner, evidence, gate and status | 73
Summary | Counts by area and status, recalculated from the Checklist | 8
Gates | Readiness reviews and go / no-go gates | 5
Legend
OPEN | Not started or not yet evidenced
IN PROGRESS | Work under way, evidence partial
DONE | Met; evidence filed
BLOCKED | Cannot be met without a decision or a dependency
N/A | Not applicable, with the reason in Remarks
One row per readiness criterion. The owner updates the status and files the evidence reference; the BIBS Service Owner reviews the sheet weekly from 1 October 2027 and before each gate.
A criterion is met only with its evidence. A criterion that is not met at its gate is either waived by the gate (recorded in Remarks with the approver) or blocks the gate.
Gates: ORR 15-Dec-2027, PRR 17-Dec-2027, GNG-1 19-Dec-2027, GNG-2 29-Dec-2027, GNG-3 2-Jan-2028 18:00.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Production Readiness Checklist, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Checklist | ID | Criterion identifier: area prefix and number
Checklist | Area | Readiness area | Operational, Security, Performance, Data, Support, Compliance, Business
Checklist | Criterion | What must be true before go-live
Checklist | Measure / threshold | How the criterion is judged met
Checklist | Evidence required | The record that proves it
Checklist | Owner | Accountable role
Checklist | Due | Date by which the evidence is filed
Checklist | Gate | Review or go / no-go gate that checks it | ORR, PRR, GNG-1, GNG-2, GNG-3
Checklist | Status | Status of the criterion | OPEN, IN PROGRESS, DONE, BLOCKED, N/A
Checklist | Evidence reference | Document, record or link of the evidence (filled in by the owner)
Checklist | Date met | Date the evidence was accepted (filled in by the owner)
Checklist | Remarks | Waiver with approver, dependency or comment
Summary | Area | Readiness area
Summary | Criteria | Number of criteria
Summary | Open | Criteria with status OPEN
Summary | In Progress | Criteria with status IN PROGRESS
Summary | Done | Criteria with status DONE
Summary | Blocked | Criteria with status BLOCKED
Summary | N/A | Criteria with status N/A
Summary | Met (%) | Criteria met as a share of the applicable criteria
Gates | Gate | Gate code
Gates | Name | Name of the review or decision
Gates | When | Date and time
Gates | Decided by | Chair and members
Gates | Passes when | Rule of the gate

## Checklist
Checklist
Production readiness criteria of BIBS with owner, evidence, gate and status
ID | Area | Criterion | Measure / threshold | Evidence required | Owner | Due | Gate | Status | Evidence reference | Date met | Remarks
OPS-01 | Operational | Production environment provisioned to the agreed sizing: EKS with the four workloads, RDS PostgreSQL 16 Multi-AZ, ElastiCache for Valkey 8 with replica, MSK Kafka 3.9 with three brokers, S3 buckets | Sizing of the Programme Alignment, section Kubernetes sizing; spread over three availability zones | Environment acceptance checklist; infrastructure inventory | BDO Cloud Operations | 2027-11-30 | ORR | OPEN
OPS-02 | Operational | DR region environment provisioned as warm standby with the RDS cross-region replica, S3 cross-region replication with replication time control, image and secrets replication | Replica lag below 5 minutes for 7 days; S3 replication within 15 minutes | DR environment acceptance record; replication metrics | BDO Cloud Operations | 2027-11-30 | ORR | OPEN
OPS-03 | Operational | Pre-Prod environment production-sized and used for the performance test and the dress rehearsals | Same sizing and versions as production | Environment comparison report | BDO Cloud Operations | 2027-10-01 | ORR | OPEN
OPS-04 | Operational | Network paths in place: users through the BDO network to the internal load balancer with WAF; BDO systems through Apigee X on the private route; no internet path | Connectivity test from each client network range and each Apigee source range; refused from any other range | Network test record | BDO Cloud Operations | 2027-11-30 | ORR | OPEN
OPS-05 | Operational | Certificates: browser certificate on the BDO domain under the BDO corporate PKI; in-cluster certificates from the private CA with automatic renewal | Valid for at least 90 days at go-live; renewal alarm at 30 days | Certificate inventory | BDO Cloud Operations | 2027-11-30 | ORR | OPEN
OPS-06 | Operational | Gateway API controller in place of ingress-nginx; routes for users and for the integration path tested | Routes answer through the Gateway only; health checks green | Route test record | BDO Cloud Operations | 2027-11-30 | ORR | OPEN
OPS-07 | Operational | Monitoring live: synthetic sign-in check, service dashboards, alert catalogue of the Operations Runbook with routing to L1, L2, L3 and Cloud Operations | Every alert rule of the catalogue fired once in Pre-Prod and reached its responder | Alert test record; dashboard links | iorta TechNXT infrastructure team | 2027-12-08 | ORR | OPEN
OPS-08 | Operational | Logs shipped to the BDO log platform and SIEM with the correlation id; retention 5 years online | A request found by its error reference within 5 minutes | Log search demonstration record | BDO Cloud Operations | 2027-12-08 | ORR | OPEN
OPS-09 | Operational | Backups: automated backups with point-in-time recovery, base backup every 4 hours, retention 7 years for the monthly copies; S3 versioning | Latest restorable time within 15 minutes; restore test passed | Backup configuration export; restore test record | BDO Cloud Operations | 2027-12-08 | ORR | OPEN
OPS-10 | Operational | Restore test: production-sized snapshot restored into an isolated instance and BIBS started against it | Restore within 2 hours; row counts of key records equal | Restore test record | BDO Cloud Operations | 2027-12-08 | ORR | OPEN
OPS-11 | Operational | DR drill before go-live: regional failover of Pre-Prod to the DR region and failback | RTO 4 hours and RPO 15 minutes met | DR drill report (DR plan, chapter 8) | BDO Cloud Operations | 2027-12-03 | ORR | OPEN
OPS-12 | Operational | Scheduled jobs set for production as in the jobs catalogue; non-production schedule overrides removed | Job list equals the catalogue | Scheduled Jobs printout signed by L2 lead | iorta TechNXT infrastructure team | 2027-12-19 | GNG-1 | OPEN
OPS-13 | Operational | Operations Runbook procedures rehearsed: release, back-out, job rerun, cache clear, outbox resend, certificate renewal, secret rotation | Each procedure run once in Pre-Prod by the team that runs it in production | Procedure rehearsal log | BIBS Service Owner | 2027-12-15 | ORR | OPEN
OPS-14 | Operational | Release path SIT, UAT, Pre-Prod, production with one release package; back-out to the previous package rehearsed | Back-out completed within 30 minutes in Pre-Prod | Release rehearsal record | iorta TechNXT infrastructure team | 2027-11-26 | ORR | OPEN
OPS-15 | Operational | Capacity headroom for the go-live month: CPU and memory below 60 % at the performance-test peak; database storage below 50 % | Measured at the 429-session peak | Performance test report | iorta TechNXT QA | 2027-12-10 | ORR | OPEN
SEC-01 | Security | Penetration test of the production-like environment by the BDO-appointed tester | No open Critical or High finding; Medium findings with a dated plan | Penetration test report and findings register | Information Security Officer | 2027-12-10 | ORR | OPEN
SEC-02 | Security | Vulnerability scans of the release images and libraries | No Critical or High vulnerability without an accepted exception | Scan report of the go-live release | iorta TechNXT infrastructure team | 2027-12-06 | ORR | OPEN
SEC-03 | Security | Single sign-on with EIAM (OpenID Connect) in production; break-glass administrators only with local password and second factor | Sign-in test per persona; break-glass sign-in tested and sealed | Sign-in test record; break-glass envelope log | Information Security Officer | 2027-12-06 | ORR | OPEN
SEC-04 | Security | User provisioning: every go-live user created through approved user access requests (or UIDM-ISC once live) with roles and data scope | 100 % of go-live users; no shared account | User Access Matrix report signed by the department heads | Information Security Officer | 2027-12-10 | GNG-1 | OPEN
SEC-05 | Security | Segregation of duties rules active and the access review of the go-live roles done | No conflict without an approved exception | Separation of Duties report | Information Security Officer | 2027-12-17 | PRR | OPEN
SEC-06 | Security | Secrets in the secrets store only; keys generated for production and never reused from another environment; key custody recorded | Start-up safeguards pass; key custody register signed | Secret inventory without values; custody register | BDO Cloud Operations | 2027-12-06 | ORR | OPEN
SEC-07 | Security | Encryption: TLS on every hop; database, Valkey and Kafka connections encrypted; S3 with BDOI-owned KMS keys | Configuration review; plaintext connection refused at start | Encryption review record | Information Security Officer | 2027-12-06 | ORR | OPEN
SEC-08 | Security | Malware scanning of uploads (GuardDuty Malware Protection for S3) active; quarantine alert routed | Test file quarantined and alert received | Test record | Information Security Officer | 2027-12-06 | ORR | OPEN
SEC-09 | Security | WAF rules: managed rule groups, rate rule on sign-in, integration path only from Apigee ranges, upload size rule | Rule test record | WAF configuration export | BDO Cloud Operations | 2027-12-06 | ORR | OPEN
SEC-10 | Security | Security events reach the BDO SIEM: sign-in failures, lockouts, privileged changes, legal hold actions, legacy archive exports | Each event type seen in the SIEM in Pre-Prod | SIEM test record | Information Security Officer | 2027-12-15 | ORR | OPEN
SEC-11 | Security | Migration roles granted for the migration period only; Philippines-only access to the Migration Console and the staging area | Access test from an allowed and a blocked location | Access test record (cutover task CT-006) | Information Security Officer | 2027-12-07 | GNG-1 | OPEN
PER-01 | Performance | Performance test at the peak case of 429 concurrent sessions with the BRD volumes | 95 % of screen requests within 2 s, 99 % within 5 s; error rate below 0.5 % | Performance test report (deliverable 28) | iorta TechNXT QA | 2027-12-10 | ORR | OPEN
PER-02 | Performance | Night batch at production volume fits the batch window | Class A jobs finished before 06:00 with 30 % margin | Batch run timings in Pre-Prod | iorta TechNXT QA | 2027-12-10 | ORR | OPEN
PER-03 | Performance | Month-end close at production volume (broking books close, GL period close, ACSL GL-SL reconciliation, Report Pack) | Close completed within 4 hours | Month-end test record | iorta TechNXT QA | 2027-12-10 | ORR | OPEN
PER-04 | Performance | Migration load rate proven at full volume in the dress rehearsal | Cutover window met with at least 20 % margin; about 50,000 rows an hour per partition | Dress rehearsal report (CT-001) | iorta TechNXT Migration Lead | 2027-12-04 | GNG-1 | OPEN
PER-05 | Performance | Soak test: 8 hours at 70 % of peak without growth of memory or response time | No degradation above 10 % | Soak test report | iorta TechNXT QA | 2027-12-10 | ORR | OPEN
PER-06 | Performance | Autoscaling of the web workload proven (scale out at load, scale in after) | Scale-out within 3 minutes; no failed request | Performance test report | iorta TechNXT infrastructure team | 2027-12-10 | ORR | OPEN
DAT-01 | Data | Trial migrations 1 to 4 completed with their exit criteria | Exit criteria of each cycle (Data Migration Handbook, Migration cycles) | Trial migration reports | Data Migration Lead | 2027-10-15 | PRR | OPEN
DAT-02 | Data | Dress rehearsal completed within the window with at least 20 percent margin; rollback rehearsed | CT-001 criteria | Dress rehearsal report signed | Data Migration Lead | 2027-12-04 | GNG-1 | OPEN
DAT-03 | Data | Code map versions for production approved (all sets, including the package code map) | One approved version per set | Code Map Versions report (CT-008) | Data owners | 2027-12-08 | GNG-1 | OPEN
DAT-04 | Data | Legacy control accounts, Migration Clearing and the legacy accounting rules approved in production | Test posting matched in the dress rehearsal | Chart and rules approval (CT-007) | Head, Comptrollership | 2027-12-08 | GNG-1 | OPEN
DAT-05 | Data | Reference data and clients loaded and accepted in production; daily client deltas running | G6 signed for R01-R08 and C01-C03 | Sign-off Status report | Data Migration Lead | 2027-12-29 | GNG-2 | OPEN
DAT-06 | Data | Every Day-1 object accepted (G6) | 100 percent | Sign-off Status report | Data owners | 2028-01-02 | GNG-3 | OPEN
DAT-07 | Data | Amount reconciliation of open items, unapplied payments and trial balance | 0.00 difference per currency | Reconciliation Summary report | Head, Comptrollership | 2028-01-02 | GNG-3 | OPEN
DAT-08 | Data | Migration Clearing and legacy control accounts | 0.00 per branch and currency; control accounts equal their sub-ledgers | Migration Clearing report | Head, Comptrollership | 2028-01-02 | GNG-3 | OPEN
DAT-09 | Data | Files held in the database copied to the document store and checked; legacy documents archived with checksums | Every file copied and its checksum equal | Content Migration run report | iorta TechNXT Migration Lead | 2027-12-17 | PRR | OPEN
DAT-10 | Data | Masking of personal data in every non-production environment; unmasked extracts never outside production | Masking check on SIT, UAT and Pre-Prod | Masking check record | Information Security Officer | 2027-11-15 | ORR | OPEN
DAT-11 | Data | Headers of every expiry up to 31 May 2028 loaded; RA-sent file loaded | P01 equals the legacy in-force list; P03 loaded | Go-live renewal extraction check | Head of the Renewal processing team | 2028-01-02 | GNG-3 | OPEN
DAT-12 | Data | Client review queue empty and the full sanction screening run of migrated clients complete | Queue empty; run complete; hits in the Compliance queue | Client Matching report; screening run log | Compliance | 2028-01-02 | GNG-3 | OPEN
DAT-13 | Data | Configuration baseline of production (parameters, lists of values, accounting rules, workflows, packages) approved by the business owners | Baseline export equals the approved configuration inputs | Baseline export with sign-off | BIBS Product Owner | 2027-12-20 | GNG-1 | OPEN
SUP-01 | Support | Support model approved: L1 BDOI service desk, L2 BDOI application support, L3 iorta TechNXT, BDO Cloud Operations | Support Model and Support Guide signed | Signed document | Head, BDOI IT | 2027-06-30 | ORR | OPEN
SUP-02 | Support | BIBS queue, categories, SLA clocks and knowledge base set up in the ITSM tool | Test ticket through L1, L2, L3 and back | Test ticket record | BIBS Service Owner | 2027-11-30 | ORR | OPEN
SUP-03 | Support | L1 analysts trained on the L1 troubleshooting guide; L2 analysts trained on the runbook and the support screens | 100 % of the roster trained; test calls passed | Attendance and test results | BIBS Service Owner | 2027-12-10 | ORR | OPEN
SUP-04 | Support | On-call rosters for L2, L3 and Cloud Operations from T-3 to hypercare exit, with telephone numbers | Roster complete; test page answered within 15 minutes | Roster; page test | iorta TechNXT Support Manager | 2027-12-15 | ORR | OPEN
SUP-05 | Support | Hypercare roster and command centre in place (room, bridge, chat channel) | Roster of the Data Migration Handbook named | Roster (CT-003) | BDOI Program Manager | 2027-12-05 | GNG-3 | OPEN
SUP-06 | Support | Knowledge base starting set: L1 guide, known errors of UAT, runbook procedures, user guides | Articles published and reviewed by L2 | Knowledge base index | iorta TechNXT Support Manager | 2027-12-15 | ORR | OPEN
SUP-07 | Support | Escalation matrix and contact annex agreed and tested | Every contact reached in a call test | Call test record | BIBS Service Owner | 2027-12-15 | ORR | OPEN
SUP-08 | Support | Interface owners' support contacts and hours confirmed for every integration live at go-live | One contact and hours per interface in the inventory | Integration Inventory with support contacts | BDOI IT system owners | 2027-12-15 | ORR | OPEN
SUP-09 | Support | Open UAT issues: none Critical or High; Medium with agreed fix dates and workarounds known to L1 | Issue log | UAT issue log at the UAT acceptance | iorta TechNXT QA | 2027-12-15 | PRR | OPEN
CMP-01 | Compliance | Hosting in AWS ap-southeast-1 with access restricted to personnel in the Philippines; DR region approved under the same cross-border basis | Approval of the DR region (IQ26, DSQ01) | BDOI approval memo | Compliance | 2027-06-30 | ORR | OPEN
CMP-02 | Compliance | Privacy impact assessment of BIBS and the records of processing updated | Signed by the Data Protection Officer | Privacy impact assessment | Data Protection Officer | 2027-11-30 | ORR | OPEN
CMP-03 | Compliance | Retention rules per record type configured (default 5 years online, 15 years archive) and legal holds for the record classes named by the DOA | Data Retention and Record Classes screens equal the approved schedule | Retention schedule sign-off | Compliance | 2027-12-15 | PRR | OPEN
CMP-04 | Compliance | Receipt series (AR and OR) registered with the BIR for BIBS and the next numbers set to legacy last used plus one per branch | Series registered; next numbers checked at CT-050 | BIR registration; receipt series report | Head, Comptrollership | 2027-10-31 | PRR | OPEN
CMP-05 | Compliance | BIR books of accounts and reports generated by BIBS accepted (Cash Receipts and Cash Disbursements Books, GL, subsidiary ledgers) | BIR acceptance of the computerised books, or the filing route agreed | BIR acknowledgement or Comptrollership memo | Head, Comptrollership | 2027-11-30 | PRR | OPEN
CMP-06 | Compliance | Sanction screening: active watchlist sources, configuration version and SLA matrix approved | Ingestion run green for 5 days in UAT | List Sources and Runs; configuration approval | Compliance | 2027-12-15 | PRR | OPEN
CMP-07 | Compliance | Audit trail and Legacy Inquiry access log verified by Internal Audit | Samples traced from screen to audit entry | Internal Audit memo | Internal Audit | 2027-12-15 | PRR | OPEN
CMP-08 | Compliance | Insurance Commission and AMLC reporting obligations mapped to BIBS reports with owners | Each obligation has a report and an owner | Regulatory reporting map | Compliance | 2027-11-30 | PRR | OPEN
BUS-01 | Business | UAT acceptance of Drop 2 (Claims, Employee Benefits, Production Reconciliation, Marketing Collection, other reports) | Certificate C1 signed | UAT acceptance certificate | Business process owners of Drop 2 | 2027-11-30 | PRR | OPEN
BUS-02 | Business | UAT acceptance of Drop 0 and Drop 1, end to end on migrated data | Certificate C1 signed | UAT acceptance certificate | Business process owners of Drop 0 and Drop 1 | 2027-12-15 | PRR | OPEN
BUS-03 | Business | Users of every persona trained on BIBS; super users per department named | At least 95 % of named users trained; 100 % of super users | Training attendance (CT-009) | BDOI Program Manager | 2027-12-15 | GNG-1 | OPEN
BUS-04 | Business | Renewal processing team ready for the January 2028 expiries | Staffing plan signed; day-1 queue rehearsed (CT-013) | Staffing plan | Head of the Renewal processing team | 2027-12-14 | GNG-1 | OPEN
BUS-05 | Business | Branch procedures for go-live week issued (receipts, deposits, urgent items over the holidays) | Branch close checklist and go-live checklist in every branch | Branch readiness confirmations | Head, Operations | 2027-12-22 | GNG-2 | OPEN
BUS-06 | Business | Communications to branches, insurers, bank channels and corporate clients sent | Items 1 to 7 of the cutover communication plan | Communication log | BDOI Program Manager | 2027-12-29 | GNG-2 | OPEN
BUS-07 | Business | Year-end option A confirmed and the December soft close completed | Written confirmation; soft-close checklist signed on 20-Dec-2027 | Comptrollership memo; checklist | Head, Comptrollership | 2027-12-20 | GNG-2 | OPEN
BUS-08 | Business | Business continuity procedures of the DR and BCP plan issued to the departments and walked through | Tabletop exercise per department | Exercise attendance and actions | Business process owners | 2027-12-10 | PRR | OPEN
BUS-09 | Business | Business smoke test on production passed | Checklist of CT-056 passed; no posting left open | Smoke test checklist | iorta TechNXT QA | 2028-01-02 | GNG-3 | OPEN
BUS-10 | Business | Interfaces live at go-live tested end to end in UAT with the other system's owner (EIAM, CCM, bank channels, CMS / New BOB, OBPCS, PMS, HL-LOAS, ECM) | Test across both systems passed per interface | Integration test records | BDOI IT system owners | 2027-12-15 | PRR | OPEN
BUS-11 | Business | Legacy systems can be set read-only with access logging; freeze tested | Freeze test refused a posting in each business module | Freeze test record (CT-036) | BDOI IT | 2027-12-31 | GNG-3 | OPEN

## Summary
Summary
Counts by area and status, recalculated from the Checklist
Area | Criteria | Open | In Progress | Done | Blocked | N/A | Met (%)
Operational
Security
Performance
Data
Support
Compliance
Business
Total

## Gates
Gates
Readiness reviews and go / no-go gates
Gate | Name | When | Decided by | Passes when
ORR | Operational readiness review | 15-Dec-2027 | BIBS Service Owner (chair), BDO Cloud Operations, Information Security Officer, iorta TechNXT Project Manager | Operations, security, performance and support criteria met; evidence pack accepted
PRR | Production readiness review | 17-Dec-2027 | Head, BDOI IT (chair), BIBS Product Owner, Program Manager, iorta TechNXT Project Manager | Every ORR criterion met or waived; production and DR accepted; data and business criteria on track
GNG-1 | Go / no-go 1: start the pre-load | 19-Dec-2027 (T-15) | Go / no-go board | Criteria of the Data Migration Handbook, Part D, and the PRR result
GNG-2 | Go / no-go 2: enter the legacy freeze | 29-Dec-2027 (T-5) | Go / no-go board | Reference data and clients accepted; communications sent; business readiness confirmed
GNG-3 | Go / no-go 3: go live | 2-Jan-2028 18:00 (T-1) | Go / no-go board | Every Day-1 object accepted; reconciliation 0.00; smoke test passed; support in place

## _lists (hidden)
Operational | ORR | OPEN
Security | PRR | IN PROGRESS
Performance | GNG-1 | DONE
Data | GNG-2 | BLOCKED
Support | GNG-3 | N/A
Compliance
Business