## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
Product Maintenance; goes with the FRS Product Maintenance v1.6
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-03
Version | 1.3
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Inputs | Open questions, dependencies and settings of the FRS Product Maintenance v1.6. | 37
Legend
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.3. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Inputs | No.
Inputs | What BDOI provides or decides
Inputs | Owner
Inputs | Needed by
Inputs | Status |  | Open, Received, Confirmed
Inputs | Answer

## Inputs
Inputs
Open questions, dependencies and settings of the FRS Product Maintenance v1.6.
No. | What BDOI provides or decides | Owner | Needed by | Status | Answer
Q-PM-01 | Name the President for the ManCom routing (setting PM_MANCOM_PRESIDENT) and confirm the routing. | ManCom; Product Owner | 30 Nov 2026 | Open
Q-PM-02 | Marketing approval: one approval (BRD) or Team Leader, Team Head and Unit Head (BDOI's FRS)? | Head, Retail Marketing | 30 Nov 2026 | Open
Q-PM-03 | Forwarding to MBS after ManCom: automatic (BRD) or Request for Deployment (BDOI's FRS)? | Head, MBS; Head, TSU | 30 Nov 2026 | Open
Q-PM-04 | Deactivation: effective-dated request (BDOI's FRS) or retirement package request? | Head, TSU | 30 Nov 2026 | Open
Q-PM-05 | Confirm the post-setup validation checklist and whether the Business Administrator validates. | Head, TSU; Head, MBS | 30 Nov 2026 | Open
Q-PM-06 | Confirm the service levels of each stage and who is alerted. | Head, TSU | 30 Nov 2026 | Open
Q-PM-07 | Confirm the password convention of protected documents. | Product Owner | 30 Nov 2026 | Open
Q-PM-08 | Name the systems that receive the product master file, its folder and timing. | Product Owner; BDO ITG | 30 Nov 2026 | Open
Q-PM-09 | Agree one list of status names (BDOI's list or the stages, section 9). | Product Owner | 30 Nov 2026 | Open
Q-PM-10 | Non-package quotation requests: keep in this FRS or move to the New Business FRS. | Product Owner | 30 Nov 2026 | Open
D-PM-01 | BDOI IT gives the receiving systems, folder and timing of the product master file (ICD). | BDOI IT | Before SIT | Open
D-PM-02 | BDOI IT gives the e-mail channel and sender mailbox for insurer and advisory e-mails. | BDOI IT | Before SIT | Open
D-PM-03 | BDOI gives the layouts of the request form, package slip, advisory and client comparative view. | BDOI | Before SIT | Open
D-PM-04 | BDOI defines CPC2 and the other incentive types. | BDOI | Before SIT | Open
D-PM-05 | Renewal (BRD-06) passes the version of the expiring account. | BDOI | Before SIT | Open
P-01 | Confirm the value of: PKG_REQUEST_PREFIX: package request number prefix (default PKR-) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-02 | Confirm the value of: PKG_QS_PREFIX: quotation slip number prefix (default PQS-) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-03 | Confirm the value of: PKG_DEACTIVATION_PREFIX / PKG_DEPLOYMENT_PREFIX (default PKD- / PDR-) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-04 | Confirm the value of: PKG_QS_REPLY_DAYS: days insurers have to reply (default 5) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-05 | Confirm the value of: PKG_MIN_POLICIES: least estimated policies of a request (default 20) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-06 | Confirm the value of: PKG_MIN_PREMIUM: least estimated basic premium (default 5,000,000.00) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-07 | Confirm the value of: PKG_SLA_MKT_APPROVAL / TSU_REVIEW / TSU_APPROVAL (hours) (default 24 / 24 / 24) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-08 | Confirm the value of: PKG_SLA_NEGOTIATION (hours) (default 120) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-09 | Confirm the value of: PKG_SLA_MANCOM / MBS_SETUP (hours) (default 72 / 48) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-10 | Confirm the value of: PACKAGE_EXPIRY_NOTICE_DAYS / PACKAGE_ANNIVERSARY_NOTICE_DAYS (default 90 / 90) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-11 | Confirm the value of: PACKAGE_EXPIRY_REMINDER_DAYS (default 30, 7) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-12 | Confirm the value of: PACKAGE_EXPIRY_NOTIFY_MBS (default No) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-13 | Confirm the value of: PACKAGE_RENEWAL_AUTODRAFT (default No) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-14 | Confirm the value of: PKG_ADVISORY_GROUPS: default advisory recipients (default Marketing, TSU, MBS, Operations) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-15 | Confirm the value of: PLACEMENT_UPDATE_DAY / TIME / DAYS / SCOPE (default Thursday / 08:00 / 7 / quotation requests) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-16 | Confirm the value of: PM_MARKETING_CHAIN (default ANY_ONE (one Marketing approval)) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-17 | Confirm the value of: PM_MANCOM_ROUTING / PM_MANCOM_PRESIDENT (default Selected in parallel, then the President / to be named) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-18 | Confirm the value of: PM_DEPLOYMENT_REQUEST (default AUTO) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-19 | Confirm the value of: PM_DEACTIVATION_ROUTE (default EFFECTIVE_DATED) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-20 | Confirm the value of: PM_DIRECT_MAINTENANCE (default Yes) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-21 | Confirm the value of: RATE_EXCEPTION_VALIDITY_DAYS (default 30) | Head, TSU; Head, MBS | 30 Nov 2026 | Open
P-22 | Confirm the value of: OTHER_CHARGES_ENABLED: bill other charges with the premium (default No) | Head, TSU; Head, MBS | 30 Nov 2026 | Open

## Lists
Status
Open
Received
Confirmed