## Cover
USER ACCEPTANCE
Business Unit Walkthrough Users
Product Maintenance; goes with the FRS Product Maintenance v1.6
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-03
Version | 1.3
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | One walkthrough account per persona of the FRS Product Maintenance v1.6; the people are fictitious. | 9
Script | The storyboards of the Process and Storyboards v1.6, step by step. | 40
Legend
Pass
Fail
Blocked
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.3. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona
Users | Walkthrough account
Users | Does
Users | Screens
Users | Sign-in
Script | Storyboard
Script | Step
Script | Who
Script | Screen
Script | Does
Script | Sees
Script | Result |  | Not run, Pass, Fail, Blocked

## Users
Users
One walkthrough account per persona of the FRS Product Maintenance v1.6; the people are fictitious.
Persona | Walkthrough account | Does | Screens | Sign-in
Marketing Account Officer | Aileen Torres | Raises and submits package requests; reviews the terms of a client-specific package; prices new business on a package; requests rate exceptions. | Home, Package Requests, Products, Premium Calculator | Issued separately by the iorta TechNXT Project Team
Marketing Approver | Marites Herrera | Marketing Team Leader, Team Head or Unit Head: approves or returns package requests of Marketing. | Package Requests, Dashboard | Issued separately by the iorta TechNXT Project Team
TSU Officer | Teodoro Vergara | Prepares quotation slips, keys in insurer terms, compiles the comparative table, prepares the product requirements, sends advisories, generates renewal requests. | TSU Workbench, Package Requests, Package Expiry, Placement Update Reports | Issued separately by the iorta TechNXT Project Team
TSU Team Lead | Teresa Yap | Reviews and recommends package requests, approves quotation slips of others, assigns work. | TSU Workbench, Package Requests, Dashboard | Issued separately by the iorta TechNXT Project Team
TSU Head | Tomas Villareal | Approves package requests for negotiation, reviews negotiated terms, validates and releases package versions. | TSU Workbench, Validation Queue, Dashboard | Issued separately by the iorta TechNXT Project Team
ManCom Member | Manuel Valdez; Patricia Vergara (President) | Approves the product requirements; the President approves last. | Package Requests (Routing & Approvals) | Issued separately by the iorta TechNXT Project Team
MBS | Monica Villareal | Sets up package versions, maintains coverages, clauses, field rules, insurers, rates and incentive criteria; requests deactivations; follows the product master transfer. | Products, Package Version, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Deactivation Requests, Product Master Transfers | Issued separately by the iorta TechNXT Project Team
Business Administrator | Bea Garcia | Authorises product masters, clauses, incentive criteria and the sales organisation; may validate package versions. | Products, Coverages & Clauses, Sales Organisation, Validation Queue | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Lim | Reads every Product Maintenance screen, runs the reports and the audit logs. Changes nothing. | Dashboard, Package Requests, Products, Audit Logs, reports | Issued separately by the iorta TechNXT Project Team

## Script
Script
The storyboards of the Process and Storyboards v1.6, step by step.
Storyboard | Step | Who | Screen | Does | Sees | Result
SB-01 A new package from the request to its release | 1 | MBS | Coverages & Clauses | Adds the clause 'Accredited repair shops for fleets' and saves it for authorisation. | The clause is pending authorisation. | Not run
SB-01 A new package from the request to its release | 2 | Business Administrator | Coverages & Clauses | Authorises the clause. | The clause is active. | Not run
SB-01 A new package from the request to its release | 3 | Marketing Account Officer | New Package Request | Enters the request, terms and two insurers; submits. | The request is numbered and For Marketing approval. | Not run
SB-01 A new package from the request to its release | 4 | Marketing Approver | Package Request | Approves and sends it to TSU. | For TSU review. | Not run
SB-01 A new package from the request to its release | 5 | TSU Team Lead | Package Request | Recommends it with a comment. | For TSU Head approval. | Not run
SB-01 A new package from the request to its release | 6 | TSU Head | Package Request | Approves it for negotiation. | Insurer negotiation, round 1. | Not run
SB-01 A new package from the request to its release | 7 | TSU Officer | Negotiation tab | Writes the notes to the insurers and submits the slip. | Slip for approval. | Not run
SB-01 A new package from the request to its release | 8 | TSU Team Lead | Negotiation tab | Approves and sends the slip. | Slip sent; one e-mail per insurer. | Not run
SB-01 A new package from the request to its release | 9 | TSU Officer | Negotiation tab | Keys in the two insurer responses with the reply documents. | Responses with rate and minimum premium. | Not run
SB-01 A new package from the request to its release | 10 | TSU Officer | Negotiation tab | Makes the terms final with the chosen insurer. | Negotiated terms review. | Not run
SB-01 A new package from the request to its release | 11 | TSU Officer | Comparative tab | Opens the comparative table. | Offers side by side, lowest first. | Not run
SB-01 A new package from the request to its release | 12 | TSU Head | Package Request | Sends the generic programme to the requirements. | Requirements preparation. | Not run
SB-01 A new package from the request to its release | 13 | TSU Officer | Requirements, Routing | Completes the requirements, attaches the signed package slip and sends to the selected ManCom approvers. | For ManCom sign-off. | Not run
SB-01 A new package from the request to its release | 14 | ManCom Member and President | Routing & Approvals tab | Approve, the President last. | Signed off; with MBS for set-up. | Not run
SB-01 A new package from the request to its release | 15 | MBS | Package Request | Sets up version 1 with the new risk code. | Draft version linked to the request. | Not run
SB-01 A new package from the request to its release | 16 | MBS | Package Version | Completes the insurer terms and submits for validation. | For validation. | Not run
SB-01 A new package from the request to its release | 17 | TSU Head | Package Version | Ticks the checklist and validates and releases. | Released; Marketing told. | Not run
SB-01 A new package from the request to its release | 18 | Business Administrator | Insurer | Adds the commission rate of the insurer for the new product. | Rate pending authorisation. | Not run
SB-01 A new package from the request to its release | 19 | Approver | Insurer | Authorises the commission rate. | Rate active. | Not run
SB-01 A new package from the request to its release | 20 | TSU Officer | Advisories tab | Sends the drafted new-package advisory. | Advisory sent and stored. | Not run
SB-02 New business on the released package | 1 | Marketing Account Officer | Premium Calculator | Calculates the premium on the package. | Premium on the version in force. | Not run
SB-02 New business on the released package | 2 | Marketing Account Officer | Quotation | Requests a rate exception for a lower item rate. | Exception pending approval. | Not run
SB-02 New business on the released package | 3 | Approver | Rate Exception | Approves the exception with a comment. | Exception approved, valid 30 days. | Not run
SB-02 New business on the released package | 4 | Marketing Account Officer | Quotation | Opens the quotation. | The approved exception is shown. | Not run
SB-03 Expiry, deactivation and transfer to other systems | 1 | TSU Officer | Package Expiry | Reviews the packages ending within 90 days. | Days left and renewal requests. | Not run
SB-03 Expiry, deactivation and transfer to other systems | 2 | MBS | Product | Opens Deactivate Package and enters date, reason, remarks and approver. | The request is ready to submit. | Not run
SB-03 Expiry, deactivation and transfer to other systems | 3 | MBS | Deactivation Requests | Follows the requests and decisions. | Status of each request. | Not run
SB-03 Expiry, deactivation and transfer to other systems | 4 | MBS | Product Master Transfers | Checks the changes sent to the receiving systems. | Each change with its file and status. | Not run
SB-04 Returns and refusals | 1 | Marketing Account Officer | New Package Request | Saves an empty draft. | Field messages. | Not run
SB-04 Returns and refusals | 2 | Marketing Account Officer | New Package Request | Submits a request without terms. | Completeness message. | Not run
SB-04 Returns and refusals | 3 | Marketing Approver | Package Request | Approves a request of another user. | For TSU review. | Not run
SB-04 Returns and refusals | 4 | TSU Team Lead | Package Request | Returns a request with a reason. | Back to the requester. | Not run
SB-04 Returns and refusals | 5 | TSU Team Lead | Negotiation tab | Clicks Approve and Send on the slip he prepared. | The confirmation; on confirming, the approval is refused: another officer approves (BR-PM-01). | Not run
SB-04 Returns and refusals | 6 | TSU Officer | Negotiation tab | Makes the terms final while an insurer has no outcome. | Refused: every insurer of the round needs an outcome. | Not run
SB-04 Returns and refusals | 7 | ManCom Member | Package Request | Returns the requirements to TSU. | Requirements preparation. | Not run
SB-04 Returns and refusals | 8 | TSU Officer | Requirements tab | Resubmits for ManCom sign-off. | For ManCom sign-off. | Not run
SB-04 Returns and refusals | 9 | MBS | Package Request | Returns incomplete requirements to TSU. | Requirements preparation. | Not run
SB-04 Returns and refusals | 10 | MBS | Package Version | Submits a version with a past date and no minimum premium. | Field messages. | Not run
SB-04 Returns and refusals | 11 | TSU Head | Package Version | Returns the version to MBS with a reason. | Draft again. | Not run
SB-04 Returns and refusals | 12 | MBS | Package Version | Opens the returned version. | The return reason is shown. | Not run

## Lists
Result
Not run
Pass
Fail
Blocked