## Cover
TEST PLAN
Test Plan BRD-12 Submitted Policies
Test conditions, scenarios and test cases for BRD-12 Submitted Policies
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-12
Version | 1.0
Date | 25 September 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Document Control | Version history of this test plan (same as the Word summary) | 2
Test Conditions | One row per test condition, derived from the acceptance criteria, rules and validations of each FR | 94
Scenarios | Business scenarios by persona; each test case belongs to one scenario | 9
Test Cases | Test cases with steps and expected results; execution columns start blank | 122
Coverage | Every FR and every BRD ID with its count of positive and negative cases | 64
Test Data | Named test data sets; UAT uses masked copies of production-like data | 10
Roles and Access | Who can and cannot see or do each action (one row per action and role) | 77
FRS Findings | FRS points raised for the FRS owner; the affected cases assume the proposed resolution | 10
Legend
Pass | The case ran and the actual result matches the expected result
Fail | The actual result differs; a defect ID is recorded
Blocked | The case cannot run (environment, data or a defect elsewhere)
N/A | Not applicable in this cycle, with the reason in Actual result
Source: FRS BRD-12 (FRS_BRD12_SUBMITTED_POLICIES.md). 31 FRs, 33 BRD IDs, 94 test conditions, 9 scenarios, 122 test cases (58 positive, 64 negative), 0 with an automation reference.
Status starts as Not run. Testers fill Status, Actual result, Tester, Date and Defect ID during execution.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Test Plan BRD-12 Submitted Policies, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Document Control | Version | Document version
Document Control | Date | Date of the version
Document Control | Author | Who prepared the version
Document Control | Reviewer | Who reviewed it
Document Control | Approver | Who approved it
Document Control | Change | What changed
Test Conditions | TC ID | Test condition ID: TC-<FR number>.<n>
Test Conditions | FR ID | Functional requirement of the FRS
Test Conditions | BRD ID(s) | BRD requirement IDs the FR meets
Test Conditions | Test condition | What must be shown to be true
Test Conditions | Priority | From the BRD priority of the FR (Must have = High) | High, Medium, Low
Test Conditions | Test cases | IDs of the test cases that test the condition
Scenarios | SC ID | Scenario ID
Scenarios | TC IDs | Test conditions exercised by the scenario's cases
Scenarios | Persona / role | Main persona: BIBS role code and name
Scenarios | Business scenario | The business thread the persona follows
Scenarios | Preconditions | State and data needed before the scenario starts
Scenarios | Cases | Number of test cases in the scenario
Test Cases | TC-case ID | Test case ID: <condition ID>-<nn>
Test Cases | Scenario | Scenario ID
Test Cases | FR ID | Functional requirement
Test Cases | BRD ID | BRD requirement ID(s)
Test Cases | Test case | What the case checks
Test Cases | Type | Kind of test | Positive, Negative, Boundary, Security-access, Workflow, Report-output, Upload-download
Test Cases | Persona | Role code and name (and demo user for built BRDs)
Test Cases | Screen (menu path) | Where the tester starts
Test Cases | Preconditions and test data | State before the first step and the named data set
Test Cases | Steps | Numbered steps
Test Cases | Expected result | What the system must do, with the exact message text and, for built BRDs, its code
Test Cases | Priority | High / Medium / Low | High, Medium, Low
Test Cases | Automation reference | Existing automated test (class#method) that covers the case; blank when none
Test Cases | Status | Execution status | Not run, Pass, Fail, Blocked, N/A
Test Cases | Actual result | What happened, filled by the tester
Test Cases | Tester | Who ran the case
Test Cases | Date | Date of the run
Test Cases | Defect ID | Defect raised when the case fails
Coverage | FR / BRD ID | FR of the FRS, then BRD requirement ID
Coverage | Kind | FR or BRD ID
Coverage | Title | FR title
Coverage | Traces | BRD IDs of the FR, or FRs of the BRD ID
Coverage | Conditions | Test conditions
Coverage | Positive | Cases where the action succeeds
Coverage | Negative | Cases where BIBS refuses the action
Coverage | Total | All cases
Coverage | Automated | Cases with an automation reference
Coverage | Coverage | Covered: at least one positive and one negative case (FR) or one case (BRD ID); GAP otherwise | Covered, GAP
Test Data | Data set | Data set ID
Test Data | Name | Short name used in the cases
Test Data | Content | Records and values in the set
Test Data | Source | Demo seed that provides it (built BRDs) or how to prepare it; non-production data is masked
Test Data | Cases | Number of cases that use it
Roles and Access | Case ID | Access case ID: AC-<code>-<nn>.<n>
Roles and Access | Action | Screen or action checked
Roles and Access | Screen (menu path) | Where it is done
Roles and Access | Permission | BIBS permission that grants it
Roles and Access | Role | Role tested (log in as a user who holds only this role)
Roles and Access | Access | Expected access | Allowed, Denied
Roles and Access | Expected result | What the user sees
Roles and Access | Automation reference | Existing automated test, if any
Roles and Access | Status | Execution status | Not run, Pass, Fail, Blocked, N/A
Roles and Access | Actual result | Filled by the tester
Roles and Access | Tester | Who ran the case
Roles and Access | Date | Date of the run
Roles and Access | Defect ID | Defect raised when the case fails
FRS Findings | ID | Finding ID
FRS Findings | FR ID | FR concerned
FRS Findings | Finding | Ambiguous or untestable point found while writing the cases
FRS Findings | Proposed resolution | What the test team proposes to the FRS owner

## Document Control
Document Control
Version history of this test plan (same as the Word summary)
Version | Date | Author | Reviewer | Approver | Change
0.9 | 24 Sep 2026 | iorta TechNXT QA | iorta TechNXT Business Analysis |  | Internal draft from FRS BRD-12 v1.0 and the Submitted Policies build design
1.0 | 25 Sep 2026 | iorta TechNXT QA | iorta TechNXT Project Manager | BDOI Product Owner (pending) | First issue for BDOI review, with the Excel workbook of the same version

## Test Conditions
Test Conditions
One row per test condition, derived from the acceptance criteria, rules and validations of each FR
TC ID | FR ID | BRD ID(s) | Test condition | Priority | Test cases
TC-SP-001.1 | FR-SP-001 | BRIDSP-01 | An LFS report of 300 rows creates 300 CBG Motor records with status RECEIVED, numbered SBM-yyyy-nnnnnn, and an intake run SBI-yyyy-nnnnnn. | High | TC-SP-001.1-01
TC-SP-001.2 | FR-SP-001 | BRIDSP-01 | Loading the same file a second time is refused and names the earlier run. | High | TC-SP-001.2-01
TC-SP-001.3 | FR-SP-001 | BRIDSP-01 | A row updating an existing policy changes the record and writes the history. | High | TC-SP-001.3-01
TC-SP-001.4 | FR-SP-001 | BRIDSP-01 | Invalid rows are listed with the reason and valid rows are committed; a file of a wrong type or without header row is refused. | High | TC-SP-001.4-01, TC-SP-001.4-02, TC-SP-001.4-03
TC-SP-001.5 | FR-SP-001 | BRIDSP-01 | The handlers of the segment are notified of new records. | High | TC-SP-001.5-01
TC-SP-002.1 | FR-SP-002 | BRIDSP-02 | A text PDF of a motor policy produces a proposal; after confirmation the record shows the confirmed values and status VALIDATED. | High | TC-SP-002.1-01
TC-SP-002.2 | FR-SP-002 | BRIDSP-02 | Before confirmation the masterlist is unchanged. | High | TC-SP-002.2-01
TC-SP-002.3 | FR-SP-002 | BRIDSP-02 | A scanned document without text leads to manual entry; a proposal can be rejected with a reason. | High | TC-SP-002.3-01, TC-SP-002.3-02
TC-SP-002.4 | FR-SP-002 | BRIDSP-02 | Confirmation needs the mandatory fields. | High | TC-SP-002.4-01
TC-SP-003.1 | FR-SP-003 | BRIDSP-03 | A manually created Non-CBG Corporate policy is saved as VALIDATED and appears in the masterlist. | High | TC-SP-003.1-01
TC-SP-003.2 | FR-SP-003 | BRIDSP-03 | A record tagged Non-Renewable shows the chip and appears in the Non-Renewal filter and report; the tag needs a reason. | High | TC-SP-003.2-01, TC-SP-003.2-02
TC-SP-003.3 | FR-SP-003 | BRIDSP-03 | A later processing run does not change a manual tag. | High | TC-SP-003.3-01
TC-SP-003.4 | FR-SP-003 | BRIDSP-03 | Mandatory fields per segment are required and a policy already in the masterlist is refused. | High | TC-SP-003.4-01, TC-SP-003.4-02
TC-SP-004.1 | FR-SP-004 | BRIDSP-33 | A legacy file with 1,000 rows and 12 invalid rows migrates 988 records flagged Migrated and logs 12 errors with reason codes. | High | TC-SP-004.1-01
TC-SP-004.2 | FR-SP-004 | BRIDSP-33 | A migrated record keeps its original date received and legacy reference, and its legacy status is mapped to a BIBS status and bucket. | High | TC-SP-004.2-01
TC-SP-004.3 | FR-SP-004 | BRIDSP-33 | Running the same file again creates no duplicates. | High | TC-SP-004.3-01
TC-SP-004.4 | FR-SP-004 | BRIDSP-33 | A status without a mapping or a blank mandatory column is refused per row. | High | TC-SP-004.4-01, TC-SP-004.4-02
TC-SP-010.1 | FR-SP-010 | BRIDSP-04 | After a record is updated by an upload, the masterlist shows the new values at once. | High | TC-SP-010.1-01
TC-SP-010.2 | FR-SP-010 | BRIDSP-04 | Filters by segment, business type, bucket, expiry month, insurer, handler, conversion status and Migrated return only the matching records. | High | TC-SP-010.2-01, TC-SP-010.2-02
TC-SP-010.3 | FR-SP-010 | BRIDSP-04 | The policy record shows the summary card with flag chips and the tabs; every change writes the history and the audit trail. | High | TC-SP-010.3-01
TC-SP-011.1 | FR-SP-011 | BRIDSP-28 | A CBG Motor handler does not see CBG Fire records. | High | TC-SP-011.1-01
TC-SP-011.2 | FR-SP-011 | BRIDSP-28 | An AO sees only his or her own records. | High | TC-SP-011.2-01
TC-SP-011.3 | FR-SP-011 | BRIDSP-28 | The extract follows the user's scope and is archived; a user without SBM_EXPORT cannot extract the masterlist. | High | TC-SP-011.3-01, TC-SP-011.3-02
TC-SP-012.1 | FR-SP-012 | BRIDSP-29 | A handler change shows at once in the masterlist and in the record history, and the new handler is notified; bulk Assign Handler changes several records. | High | TC-SP-012.1-01, TC-SP-012.1-02
TC-SP-012.2 | FR-SP-012 | BRIDSP-29 | The quick filter Changed since yesterday lists the records updated today. | High | TC-SP-012.2-01
TC-SP-012.3 | FR-SP-012 | BRIDSP-29 | The handler must be an active user. | High | TC-SP-012.3-01
TC-SP-020.1 | FR-SP-020 | BRIDSP-08 | A new exclusion rule applies to the next run only after the approver approves it, with an effective date. | High | TC-SP-020.1-01
TC-SP-020.2 | FR-SP-020 | BRIDSP-08 | Each run result shows the rule and version that produced it; a record with no matching rule is fallout with reason no rule. | High | TC-SP-020.2-01, TC-SP-020.2-02
TC-SP-020.3 | FR-SP-020 | BRIDSP-08 | The maker cannot approve the own rule set; a rejection keeps the version a draft. | High | TC-SP-020.3-01, TC-SP-020.3-02
TC-SP-020.4 | FR-SP-020 | BRIDSP-08 | A rule needs an outcome and conditions on known fields only. | High | TC-SP-020.4-01, TC-SP-020.4-02
TC-SP-021.1 | FR-SP-021 | BRIDSP-09 | Uploading an LFS file starts a run; each new record ends with a classification and a bucket, or fallout, through the steps in order. | High | TC-SP-021.1-01
TC-SP-021.2 | FR-SP-021 | BRIDSP-09 | A record matched to an active LAMD loan is moved to the right bucket and the handlers are notified. | High | TC-SP-021.2-01
TC-SP-021.3 | FR-SP-021 | BRIDSP-09 | Sanitation marks duplicates (same PN or same serial / motor number) For Review and incomplete records as fallout. | High | TC-SP-021.3-01
TC-SP-021.4 | FR-SP-021 | BRIDSP-09 | A run starts from the daily job and on demand, each with an SBR number. | High | TC-SP-021.4-01
TC-SP-022.1 | FR-SP-022 | BRIDSP-10 | A run with five records without PN produces a fallout list and report with the five records and their reason code, and raises the fallout alert. | High | TC-SP-022.1-01
TC-SP-022.2 | FR-SP-022 | BRIDSP-10 | A corrected record leaves the fallout after the next run. | High | TC-SP-022.2-01
TC-SP-022.3 | FR-SP-022 | BRIDSP-10 | Intake and extraction failures are listed in the document fallout report. | High | TC-SP-022.3-01
TC-SP-030.1 | FR-SP-030 | BRIDSP-11 | A record whose PN matches an active LAMD loan is Submitted. | High | TC-SP-030.1-01
TC-SP-030.2 | FR-SP-030 | BRIDSP-11 | A record whose PN is not in LAMD is Inforced. | High | TC-SP-030.2-01
TC-SP-031.1 | FR-SP-031 | BRIDSP-12 | A Submitted CBG Motor policy of an active loan with no exclusion goes to For Renewal. | High | TC-SP-031.1-01
TC-SP-031.2 | FR-SP-031 | BRIDSP-12 | A policy on the employee list goes to BDO / SM Group Employee Accounts and is not handed to renewal. | High | TC-SP-031.2-01
TC-SP-031.3 | FR-SP-031 | BRIDSP-12 | A record in For Manual Disposition is disposed by hand with a reason. | High | TC-SP-031.3-01, TC-SP-031.3-02
TC-SP-032.1 | FR-SP-032 | BRIDSP-13 | An FFY account with an active non-amortised loan gets the FFY RA template; a generic account gets the Generic RA template. | High | TC-SP-032.1-01, TC-SP-032.1-02
TC-SP-032.2 | FR-SP-032 | BRIDSP-13 | A snapshot row without PN is refused. | High | TC-SP-032.2-01
TC-SP-033.1 | FR-SP-033 | BRIDSP-14 | A No Touch account is tagged Non-Renewal and listed in the non-renewal report with reason No Touch. | High | TC-SP-033.1-01
TC-SP-033.2 | FR-SP-033 | BRIDSP-14 | An excluded record is never handed to renewal. | High | TC-SP-033.2-01
TC-SP-033.3 | FR-SP-033 | BRIDSP-14 | A handler reinstates an excluded record with a reason. | High | TC-SP-033.3-01, TC-SP-033.3-02
TC-SP-034.1 | FR-SP-034 | BRIDSP-15 | An inforced Fully Paid Loan policy marked eligible reaches For Renewal and, after hand-off, has an RA and a proposal. | High | TC-SP-034.1-01
TC-SP-034.2 | FR-SP-034 | BRIDSP-15 | An inforced policy in a bucket that is not eligible is not handed over. | High | TC-SP-034.2-01
TC-SP-040.1 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | A policy reviewed twice shows two reviews and a review count of 2 on its IAAF; findings are e-mailed to the bank counterpart and the record stays IN_REVIEW. | High | TC-SP-040.1-01
TC-SP-040.2 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | A second IAAF for the same policy is refused. | High | TC-SP-040.2-01
TC-SP-040.3 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | An IAAF linked to the previous term's record shows the link. | High | TC-SP-040.3-01
TC-SP-040.4 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | The adequacy is required, and an IAAF cannot be generated while the last review has findings. | High | TC-SP-040.4-01, TC-SP-040.4-02
TC-SP-041.1 | FR-SP-041 | BRIDSP-07 | An IAAF of a Non-CBG Corporate policy goes to level 1 and, after approval, to level 2; the last approval sets APPROVED. | High | TC-SP-041.1-01
TC-SP-041.2 | FR-SP-041 | BRIDSP-07 | The issued IAAF PDF shows the stamped name, position and time of every approver; Send to bank counterpart sets ISSUED. | High | TC-SP-041.2-01
TC-SP-041.3 | FR-SP-041 | BRIDSP-07 | The preparer cannot approve; a return needs a reason. | High | TC-SP-041.3-01, TC-SP-041.3-02
TC-SP-041.4 | FR-SP-041 | BRIDSP-07 | An IAAF with no matrix row for its segment and sum insured cannot be submitted. | High | TC-SP-041.4-01
TC-SP-050.1 | FR-SP-050 | BRIDSP-16 | A motor policy whose vehicle is older than the insurer's maximum age is flagged Insurer approval required with the limit and value, and a TOR task is created. | High | TC-SP-050.1-01
TC-SP-050.2 | FR-SP-050 | BRIDSP-16 | A policy within the limits is not flagged. | High | TC-SP-050.2-01
TC-SP-051.1 | FR-SP-051 | BRIDSP-17 | A TOR generated for a flagged record lists its breached limits and the proposed terms. | High | TC-SP-051.1-01
TC-SP-051.2 | FR-SP-051 | BRIDSP-17 | The proposed terms are required, and a TOR cannot be generated for a record without a breach. | High | TC-SP-051.2-01, TC-SP-051.2-02
TC-SP-052.1 | FR-SP-052 | BRIDSP-18 | A TOR reaches the TSU approver of its level and, after the last approval, carries the signed PDF. | High | TC-SP-052.1-01
TC-SP-052.2 | FR-SP-052 | BRIDSP-18 | The preparer never approves; a return needs a reason. | High | TC-SP-052.2-01, TC-SP-052.2-02
TC-SP-053.1 | FR-SP-053 | BRIDSP-19 | The assigned AO is notified of the approved TOR and can download it; the TOR then shows Released. | High | TC-SP-053.1-01
TC-SP-053.2 | FR-SP-053 | BRIDSP-19 | Another AO cannot open the TOR. | High | TC-SP-053.2-01
TC-SP-060.1 | FR-SP-060 | BRIDSP-23 | A For Renewal CBG Fire record 150 days before expiry is handed over with an insurer different from the expiring one; the record is RENEWAL_IN_PROGRESS and the handler and AO are notified. | High | TC-SP-060.1-01, TC-SP-060.1-02
TC-SP-060.2 | FR-SP-060 | BRIDSP-23 | A second scan does not hand the same record over again. | High | TC-SP-060.2-01
TC-SP-060.3 | FR-SP-060 | BRIDSP-23 | Before the Renewal adapter exists, the hand-off shows as pending and no letter is sent. | High | TC-SP-060.3-01
TC-SP-060.4 | FR-SP-060 | BRIDSP-23 | A record with no insurer rule stays For Renewal and appears in the fallout; Renew with BDOI works only on a For Renewal record. | High | TC-SP-060.4-01, TC-SP-060.4-02, TC-SP-060.4-03
TC-SP-061.1 | FR-SP-061 | BRIDSP-25 | The For Renewal tab for a month lists every renewable record expiring in that month in the user's scope. | High | TC-SP-061.1-01
TC-SP-061.2 | FR-SP-061 | BRIDSP-25 | The export has the same rows as the screen; AOs can be assigned in bulk. | High | TC-SP-061.2-01
TC-SP-061.3 | FR-SP-061 | BRIDSP-25 | Records outside the user's scope are not listed. | High | TC-SP-061.3-01
TC-SP-062.1 | FR-SP-062 | BRIDSP-22 | A reviewed policy with a renewal opportunity gets the reminder letter by the rule's channel and date. | High | TC-SP-062.1-01
TC-SP-062.2 | FR-SP-062 | BRIDSP-22 | A print batch contains one PDF with all letters of the day and a control list. | High | TC-SP-062.2-01
TC-SP-062.3 | FR-SP-062 | BRIDSP-22 | No RA is produced by this module; the RA of a handed-over policy appears on its Renewal record. | High | TC-SP-062.3-01
TC-SP-062.4 | FR-SP-062 | BRIDSP-22 | A delivery failure sets the letter FAILED with an alert; a client without e-mail cannot get an e-mail letter. | High | TC-SP-062.4-01, TC-SP-062.4-02
TC-SP-063.1 | FR-SP-063 | BRIDSP-32 | An insurer that has not accepted the hold cover within 5 days raises an alert. | High | TC-SP-063.1-01, TC-SP-063.1-02
TC-SP-063.2 | FR-SP-063 | BRIDSP-32 | After re-assignment the old request shows Reassigned, a new request is sent to the new insurer and the renewal account shows the new insurer. | High | TC-SP-063.2-01
TC-SP-063.3 | FR-SP-063 | BRIDSP-32 | The new insurer must differ from the current one and a reason is required. | High | TC-SP-063.3-01, TC-SP-063.3-02
TC-SP-064.1 | FR-SP-064 | BRIDSP-26 | After the client confirms and pays, the slip is sent to the insurer and the masterlist record shows Placed. | High | TC-SP-064.1-01
TC-SP-064.2 | FR-SP-064 | BRIDSP-26 | The slip is not sent before the payment gate passes. | High | TC-SP-064.2-01
TC-SP-065.1 | FR-SP-065 | BRIDSP-27 | A booked renewal shows BOOKED, the invoice number and the booking date in the masterlist; the invoice has business type RENEWAL. | High | TC-SP-065.1-01
TC-SP-065.2 | FR-SP-065 | BRIDSP-27 | A renewal that is declined, lost or expired becomes NOT_RENEWED with the reason. | High | TC-SP-065.2-01
TC-SP-070.1 | FR-SP-070 | BRIDSP-31 | A CLPC payment carrying the PN of a billed record is tagged Handling Fee and applied with an OR. | High | TC-SP-070.1-01
TC-SP-070.2 | FR-SP-070 | BRIDSP-31 | An OTC payment with an unknown location reference stays in the unapplied list; a payment matching two records stays untagged as ambiguous. | High | TC-SP-070.2-01, TC-SP-070.2-02
TC-SP-070.3 | FR-SP-070 | BRIDSP-31 | A payment already tagged cannot be tagged by hand again. | High | TC-SP-070.3-01
TC-SP-080.1 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | The Sanitation Report of a month shows the counts per the grouping of Report List row 156. | High | TC-SP-080.1-01
TC-SP-080.2 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | The process fallout report of a run lists every fallout record with its reason code; each home tile opens its filtered list. | High | TC-SP-080.2-01
TC-SP-080.3 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | A date range with the end before the start is refused; reports follow the user's scope. | High | TC-SP-080.3-01, TC-SP-080.3-02
TC-SP-081.1 | FR-SP-081 | BRIDSP-21 | SBM-MASTERLIST exported as Excel and as PDF has the same rows; ODS, CSV and XML are also offered, and exports are archived. | High | TC-SP-081.1-01
TC-SP-081.2 | FR-SP-081 | BRIDSP-21 | A user without SBM_REPORT_EXPORT cannot export. | High | TC-SP-081.2-01
TC-SP-082.1 | FR-SP-082 | BRIDSP-24 | The approvers of level 1 are notified when an IAAF is submitted. | High | TC-SP-082.1-01
TC-SP-082.2 | FR-SP-082 | BRIDSP-24 | A confirmed hold cover whose account is not booked 5 days before it ends raises the unbooked alert; one booked is not alerted. | High | TC-SP-082.2-01, TC-SP-082.2-02
TC-SP-082.3 | FR-SP-082 | BRIDSP-24 | Users follow their in-app and e-mail preferences per event type. | High | TC-SP-082.3-01

## Scenarios
Scenarios
Business scenarios by persona; each test case belongs to one scenario
SC ID | TC IDs | Persona / role | Business scenario | Preconditions | Cases
SC-SP-01 | TC-SP-001.1, TC-SP-001.2, TC-SP-001.3, TC-SP-001.4, TC-SP-001.5, TC-SP-002.1, TC-SP-002.2, TC-SP-002.3, TC-SP-002.4, TC-SP-003.1, TC-SP-003.2, TC-SP-003.3, TC-SP-003.4, TC-SP-004.1, TC-SP-004.2, TC-SP-004.3, TC-SP-004.4 | SBM_HANDLER – Submitted Handler (CBG) | Intake. Handlers upload source files, confirm extracted policy details, create records by hand and migrate the Excel masterlists. | Files TD-SP-02, documents TD-SP-03, legacy file TD-SP-04. | 23
SC-SP-02 | TC-SP-010.1, TC-SP-010.2, TC-SP-010.3, TC-SP-011.1, TC-SP-011.2, TC-SP-011.3, TC-SP-012.1, TC-SP-012.2, TC-SP-012.3 | SBM_HANDLER – Submitted Handler (CBG) | Masterlist. One masterlist with history, handler, conversion status and remarks; each user sees and extracts only the records of the own scope. | Records TD-SP-07; users TD-SP-01. | 12
SC-SP-03 | TC-SP-020.1, TC-SP-020.2, TC-SP-020.3, TC-SP-020.4, TC-SP-021.1, TC-SP-021.2, TC-SP-021.3, TC-SP-021.4, TC-SP-022.1, TC-SP-022.2, TC-SP-022.3 | SBM_SANITATION – Sanitation Handler | Rules and processing. Rule sets are approved by a checker; processing runs after intake, on schedule and on demand; fallout is reported and resolved. | Rules TD-SP-06; LAMD TD-SP-05. | 14
SC-SP-04 | TC-SP-030.1, TC-SP-030.2, TC-SP-031.1, TC-SP-031.2, TC-SP-031.3, TC-SP-032.1, TC-SP-032.2, TC-SP-033.1, TC-SP-033.2, TC-SP-033.3, TC-SP-034.1, TC-SP-034.2 | SYSTEM – BIBS scheduled job or event | Classification and buckets. Policies are classified Inforced or Submitted, bucketed, excluded or made ready for renewal with the RA template. | Records TD-SP-07; LAMD TD-SP-05; rules TD-SP-06. | 15
SC-SP-05 | TC-SP-040.1, TC-SP-040.2, TC-SP-040.3, TC-SP-040.4, TC-SP-041.1, TC-SP-041.2, TC-SP-041.3, TC-SP-041.4 | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Policy review and IAAF. The reviewer records reviews, generates one IAAF per policy and routes it through the approval matrix to the bank counterpart. | Review data TD-SP-08; IAAF matrix TD-SP-06. | 10
SC-SP-06 | TC-SP-050.1, TC-SP-050.2, TC-SP-051.1, TC-SP-051.2, TC-SP-052.1, TC-SP-052.2, TC-SP-053.1, TC-SP-053.2 | MKT_AO – Marketing AO / MAO | Limits and TOR. A limit breach is flagged, the TOR is prepared, approved by TSU and handed over to the AO. | Flagged record TD-SP-08; TSU matrix TD-SP-06. | 10
SC-SP-07 | TC-SP-060.1, TC-SP-060.2, TC-SP-060.3, TC-SP-060.4, TC-SP-061.1, TC-SP-061.2, TC-SP-061.3, TC-SP-062.1, TC-SP-062.2, TC-SP-062.3, TC-SP-062.4, TC-SP-063.1, TC-SP-063.2, TC-SP-063.3, TC-SP-064.1, TC-SP-064.2, TC-SP-065.1, TC-SP-065.2 | SBM_SANITATION – Sanitation Handler | Renewal. Expiring policies are handed to Renewal with the assigned insurer; letters are sent; the insurer is re-assigned while a hold cover is open; placement and booking update the masterlist. | Renewal candidates TD-SP-09; parameters TD-SP-10. | 24
SC-SP-08 | TC-SP-070.1, TC-SP-070.2, TC-SP-070.3 | SBM_UPP_HANDLER – Admin Team UPP handler | Handling fee. Handling-fee payments are tagged in the Unapplied Payment List and applied by Cashiering. | Handling-fee data TD-SP-08. | 4
SC-SP-09 | TC-SP-080.1, TC-SP-080.2, TC-SP-080.3, TC-SP-081.1, TC-SP-081.2, TC-SP-082.1, TC-SP-082.2, TC-SP-082.3 | SBM_TL – Team Lead (Submitted Policies) | Monitoring. The home page, the Submitted Policies reports in several formats, and the notifications and alerts of key events. | Scenarios SC-SP-01 to SC-SP-08 ran in the test period. | 10

## Test Cases
Test Cases
Test cases with steps and expected results; execution columns start blank
TC-case ID | Scenario | FR ID | BRD ID | Test case | Type | Persona | Screen (menu path) | Preconditions and test data | Steps | Expected result | Priority | Automation reference | Status | Actual result | Tester | Date | Defect ID
TC-SP-001.1-01 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | Upload an LFS report of 300 rows | Upload-download | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Upload & Intake | Data: TD-SP-02 Source files | 1. Choose source LFS insurance report; upload the 300-row file; check the counts; confirm. 2. Open the Masterlist filtered on the run. | Valid 300, invalid 0. 300 CBG Motor records with status RECEIVED and SBM numbers; the run has an SBI number and a processing run starts. | High |  | Not run
TC-SP-001.2-01 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | Same file again | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Upload & Intake | Data: TD-SP-02 Source files | 1. Upload the same file. | Refused; no record is created. Message "This file was already loaded in run SBI-2026-000001". | High |  | Not run
TC-SP-001.3-01 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | Row updating an existing policy | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist > Policy record > History tab | Data: TD-SP-02 Source files | 1. Upload the file with the changed premium; open the record's History tab. | The record shows the new premium; the history shows the old and new value with the run. | High |  | Not run
TC-SP-001.4-01 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | Rows without PN | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Upload & Intake | Data: TD-SP-02 Source files | 1. Upload the file with 5 rows without PN; download the invalid rows. | The 5 rows are listed with the reason; the other rows are committed. Message "Row 4: PN no. is required". | High |  | Not run
TC-SP-001.4-02 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | CSV without header row | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Upload & Intake | Data: TD-SP-02 Source files | 1. Upload the CSV without header row. | Refused. Message "The file has no header row". | High |  | Not run
TC-SP-001.4-03 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | PDF uploaded as a source file | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Upload & Intake | Data: TD-SP-02 Source files | 1. Upload the PDF. | Refused. Message "The file type is not allowed". | High |  | Not run
TC-SP-001.5-01 | SC-SP-01 | FR-SP-001 | BRIDSP-01 | Handlers notified | Positive | SBM_HANDLER – Submitted Handler (CBG) | Notifications (bell icon in the page header) | Data: TD-SP-02 Source files | 1. After TC-SP-001.1-01, as sbmhandler open the bell; as firehandler open the bell. | sbmhandler (CBG Motor) is notified of the new submissions; firehandler is not. | High |  | Not run
TC-SP-002.1-01 | SC-SP-01 | FR-SP-002 | BRIDSP-02 | Extract and confirm a motor policy | Upload-download | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Extraction Review | Data: TD-SP-03 Policy documents | 1. Upload the text PDF as a new record; check each proposed value and its confidence; correct the plate number; Confirm. | The record shows the confirmed values, including the corrected plate, and status VALIDATED. | High |  | Not run
TC-SP-002.2-01 | SC-SP-01 | FR-SP-002 | BRIDSP-02 | Masterlist unchanged before confirmation | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-03 Policy documents | 1. Upload the PDF; before confirming, search the masterlist for its policy number. | No record with the proposed values; handlers receive the manual-validation notice. | High |  | Not run
TC-SP-002.3-01 | SC-SP-01 | FR-SP-002 | BRIDSP-02 | Scanned document without text | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Extraction Review | Data: TD-SP-03 Policy documents | 1. Upload the scanned PDF. | Extraction returns "not readable"; the user is sent to manual entry. | High |  | Not run
TC-SP-002.3-02 | SC-SP-01 | FR-SP-002 | BRIDSP-02 | Reject without a reason | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Extraction Review | Data: TD-SP-03 Policy documents | 1. Open a proposal; Reject without a reason. | Not rejected. Message "Enter the reason of the rejection". | High |  | Not run
TC-SP-002.4-01 | SC-SP-01 | FR-SP-002 | BRIDSP-02 | Confirm with the expiry blank | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Extraction Review | Data: TD-SP-03 Policy documents | 1. Clear the expiry date; Confirm. | Not confirmed. Message "Expiry is required". | High |  | Not run
TC-SP-003.1-01 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | Create a Non-CBG Corporate policy by hand | Positive | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. Click New Policy; segment Non-CBG Corporate; NB; assured, insurer, policy number, dates, amounts, location; save. | The record is VALIDATED and listed in the masterlist. | High |  | Not run
TC-SP-003.2-01 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | Tag Non-Renewable with a reason | Positive | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-07 Masterlist records | 1. Open the record; Tag Non-Renewable; reason; save; open tab Non-Renewal and SBM-NON-RENEWAL. | The Non-Renewable chip shows; the record is in the filter and in the report with the reason. | High |  | Not run
TC-SP-003.2-02 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | Non-Renewable without a reason | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-07 Masterlist records | 1. Tag Non-Renewable without a reason. | Not saved. Message "Select the reason for Non-Renewable". | High |  | Not run
TC-SP-003.3-01 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | Run keeps the manual tag | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record > Rule Results tab | Data: TD-SP-07 Masterlist records | 1. Run processing for the record; open Rule Results. | The run records its own result; the tag stays Non-Renewable. | High |  | Not run
TC-SP-003.4-01 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | CBG Motor record without PN | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. New Policy, CBG Motor, without PN; save. | Not saved. Message "PN no. is required". | High |  | Not run
TC-SP-003.4-02 | SC-SP-01 | FR-SP-003 | BRIDSP-03 | Policy already in the masterlist | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. New Policy with the policy number of an existing record; save. | Refused. Message "Policy PC-12345 is already in the masterlist (SBM-2026-000031)". | High |  | Not run
TC-SP-004.1-01 | SC-SP-01 | FR-SP-004 | BRIDSP-33 | Migrate the NB Motor file | Upload-download | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Upload & Intake | Data: TD-SP-04 Legacy masterlist | 1. Upload the legacy file; layout NB Motor; check the result; confirm. 2. Run SBM-MIGRATION-ERRORS. | 988 records flagged Migrated; the report lists 12 rows with reason codes. | High |  | Not run
TC-SP-004.2-01 | SC-SP-01 | FR-SP-004 | BRIDSP-33 | Migrated record keeps its history data | Positive | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-04 Legacy masterlist | 1. Open a migrated record. | The original date received, legacy reference, mapped status and bucket, and the Migrated chip. | High |  | Not run
TC-SP-004.3-01 | SC-SP-01 | FR-SP-004 | BRIDSP-33 | Same file again | Negative | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Upload & Intake | Data: TD-SP-04 Legacy masterlist | 1. Run the migration of the same file again. | No duplicate; the counts show 0 created. | High |  | Not run
TC-SP-004.4-01 | SC-SP-01 | FR-SP-004 | BRIDSP-33 | Status not in the map | Negative | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Upload & Intake | Data: TD-SP-04 Legacy masterlist | 1. Open the error of the row whose status has no mapping. | The row is not migrated. Message "Row 15: status PENDING-OLD has no mapping". | High |  | Not run
TC-SP-004.4-02 | SC-SP-01 | FR-SP-004 | BRIDSP-33 | Blank expiry column | Negative | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Upload & Intake | Data: TD-SP-04 Legacy masterlist | 1. Open the error of the row with a blank expiry. | The row is not migrated. Message "Row 27: Expiry is required". | High |  | Not run
TC-SP-010.1-01 | SC-SP-02 | FR-SP-010 | BRIDSP-04 | Update shows at once | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. After TC-SP-001.3-01, open the masterlist row. | The new premium is shown without refresh delay. | High |  | Not run
TC-SP-010.2-01 | SC-SP-02 | FR-SP-010 | BRIDSP-04 | Filter by segment and expiry month | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. Filter CBG Motor and next month. | Only CBG Motor records expiring next month. | High |  | Not run
TC-SP-010.2-02 | SC-SP-02 | FR-SP-010 | BRIDSP-04 | Filter excludes other segments | Negative | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. As sbmtl filter CBG Fire; look for a CBG Motor record. | No CBG Motor record is listed. | High |  | Not run
TC-SP-010.3-01 | SC-SP-02 | FR-SP-010 | BRIDSP-04 | Record page and history | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-07 Masterlist records | 1. Open a record; change the remarks; open History and Administration > Audit Trail. | The summary card shows the chips; the tabs Details to History are present; the remarks change is in the history and the audit trail. | High |  | Not run
TC-SP-011.1-01 | SC-SP-02 | FR-SP-011 | BRIDSP-28 | CBG Motor handler and a CBG Fire record | Security-access | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-01 Test users per role and scope; TD-SP-07 Masterlist records | 1. As sbmhandler search a CBG Fire record by number; open its address. | Not listed; the address shows the no-access page. | High |  | Not run
TC-SP-011.2-01 | SC-SP-02 | FR-SP-011 | BRIDSP-28 | AO sees own records only | Security-access | MKT_AO – Marketing AO / MAO | Submitted Policies > Masterlist | Data: TD-SP-01 Test users per role and scope; TD-SP-07 Masterlist records | 1. As ao open the masterlist; open a record of ao2 by address. | Only ao's records; ao2's record does not open. | High |  | Not run
TC-SP-011.3-01 | SC-SP-02 | FR-SP-011 | BRIDSP-28 | Extract within scope | Report-output | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-01 Test users per role and scope; TD-SP-07 Masterlist records | 1. As sbmhandler filter and click Export (XLSX); open Report Archive. | The file holds only CBG Motor records with the Report List row 151 fields; the export is archived. | High |  | Not run
TC-SP-011.3-02 | SC-SP-02 | FR-SP-011 | BRIDSP-28 | Export without SBM_EXPORT | Security-access | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | API call with the user's token (tester tool, for example Postman) | Data: TD-SP-01 Test users per role and scope; TD-SP-07 Masterlist records | 1. As polreview look for Export; call the export. | No Export button; the call is refused. Message "You are not permitted to perform this action". | High |  | Not run
TC-SP-012.1-01 | SC-SP-02 | FR-SP-012 | BRIDSP-29 | Assign a handler in bulk | Workflow | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. Tick three records; Assign Handler; choose sanitation; save. | The three rows show sanitation; each history shows the change; sanitation is notified. | High |  | Not run
TC-SP-012.1-02 | SC-SP-02 | FR-SP-012 | BRIDSP-29 | Conversion status and remarks | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-07 Masterlist records | 1. Set conversion status Renewed - Inforce and remarks; save. | The list shows the new status and remarks; History shows both changes. | High |  | Not run
TC-SP-012.2-01 | SC-SP-02 | FR-SP-012 | BRIDSP-29 | Changed since yesterday | Positive | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Masterlist | Data: TD-SP-07 Masterlist records | 1. Apply the quick filter Changed since yesterday. | The records changed today, and no others. | High |  | Not run
TC-SP-012.3-01 | SC-SP-02 | FR-SP-012 | BRIDSP-29 | Handler not active | Negative | SBM_HANDLER – Submitted Handler (CBG) | API call with the user's token (tester tool, for example Postman) | Data: TD-SP-07 Masterlist records | 1. Assign the disabled user as handler through the API. | Refused. Message "uatdisabled is not an active user". | High |  | Not run
TC-SP-020.1-01 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | SM Group employee exclusion rule | Workflow | MKT_TL – NB Team Lead | My Approvals | Data: TD-SP-06 Rules and masters | 1. As badmin draft the disposition rule set; add a rule "employee list = Yes gives BDO / SM Group Employee Accounts, stop"; submit. 2. Run processing before approval; as mkttl compare and approve effective today; run again. | The first run does not apply the rule; after approval the employee record goes to BDO / SM Group Employee Accounts. | High |  | Not run
TC-SP-020.2-01 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | Rule and version on the result | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record > Rule Results tab | Data: TD-SP-06 Rules and masters | 1. Open Rule Results of the employee record. | Each step shows the rule, the rule-set version, the outcome and the reason code. | High |  | Not run
TC-SP-020.2-02 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | No matching rule | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Processing Runs | A record whose segment has no matching disposition rule. Data: TD-SP-06 Rules and masters | 1. Run processing; open the fallout. | The record is fallout with reason SBM_NO_RULE. | High |  | Not run
TC-SP-020.3-01 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | Maker approves the own rule set | Security-access | SBM_RULE_ADMIN – Rule administrator | Submitted Policies > Submitted Policies Setup | sbmtl (maker right) holds SBM_RULE_APPROVE for this case. Data: TD-SP-06 Rules and masters | 1. As sbmtl draft and submit a rule set; click Approve. | Refused. Message "A rule set is approved by someone other than its maker". | High |  | Not run
TC-SP-020.3-02 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | Reject a rule set | Workflow | MKT_TL – NB Team Lead | My Approvals | Data: TD-SP-06 Rules and masters | 1. Reject a pending version with a reason. | The version is a draft again with the reason; the active version is unchanged. | High |  | Not run
TC-SP-020.4-01 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | Rule without outcome | Negative | SBM_RULE_ADMIN – Rule administrator | Submitted Policies > Submitted Policies Setup | Data: TD-SP-06 Rules and masters | 1. Add a rule with conditions and no outcome; save. | Not saved. Message "Select the outcome of the rule". | High |  | Not run
TC-SP-020.4-02 | SC-SP-03 | FR-SP-020 | BRIDSP-08 | Condition on an unknown field | Negative | SBM_RULE_ADMIN – Rule administrator | Submitted Policies > Submitted Policies Setup | Data: TD-SP-06 Rules and masters | 1. Import a rule file with a condition on field "color". | Refused. Message "Field color cannot be used in a rule". | High |  | Not run
TC-SP-021.1-01 | SC-SP-03 | FR-SP-021 | BRIDSP-09 | Run after intake | Workflow | SYSTEM – BIBS scheduled job or event | Submitted Policies > Processing Runs | Data: TD-SP-02 Source files; TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Upload an LFS file; open the run. | An SBR run with steps Sanitation, Matching, Classification, Disposition, Limits; every record has a classification and bucket or is fallout. | High |  | Not run
TC-SP-021.2-01 | SC-SP-03 | FR-SP-021 | BRIDSP-09 | Matched record bucketed and notified | Positive | SYSTEM – BIBS scheduled job or event | Notifications (bell icon in the page header) | Data: TD-SP-02 Source files; TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Open the record whose PN is an active LAMD loan; open the bell of its handler. | The record is in its bucket; the handler is notified of the bucket change. | High |  | Not run
TC-SP-021.3-01 | SC-SP-03 | FR-SP-021 | BRIDSP-09 | Duplicate serial number | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Rule Results tab | Two records with the same motor number. Data: TD-SP-02 Source files; TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Run processing; open both records. | Both are For Review with the duplicate reason. | High |  | Not run
TC-SP-021.4-01 | SC-SP-03 | FR-SP-021 | BRIDSP-09 | Run on demand and by the job | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist | Data: TD-SP-02 Source files; TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Tick records; Run Processing; run SBM_PROCESSING from Scheduled Jobs. | Two runs with SBR numbers; the job run covers the records due. | High |  | Not run
TC-SP-022.1-01 | SC-SP-03 | FR-SP-022 | BRIDSP-10 | Five records without PN | Negative | SBM_SANITATION – Sanitation Handler | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-02 Source files | 1. Run processing of the 5 records; open the Fallout tab; run SBM-PROCESS-FALLOUT; open the bell. | The five records with their reason code; the report shows the same; alert SBM_FALLOUT. | High |  | Not run
TC-SP-022.2-01 | SC-SP-03 | FR-SP-022 | BRIDSP-10 | Correct and re-run | Workflow | SBM_SANITATION – Sanitation Handler | Submitted Policies > Processing Runs | Data: TD-SP-02 Source files | 1. Enter the PN of one record; re-run it. | The record leaves the fallout and gets a bucket. | High |  | Not run
TC-SP-022.3-01 | SC-SP-03 | FR-SP-022 | BRIDSP-10 | Document fallout report | Report-output | SBM_SANITATION – Sanitation Handler | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-02 Source files | 1. Run SBM-DOC-FALLOUT for today. | The unreadable scanned PDF and the invalid intake rows are listed with their reasons. | High |  | Not run
TC-SP-030.1-01 | SC-SP-04 | FR-SP-030 | BRIDSP-11 | PN of an active loan | Positive | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Loan & Matching tab | Data: TD-SP-05 LAMD snapshot | 1. Run processing; open Loan & Matching of the record. | Classification SUBMITTED with the matched loan. | High |  | Not run
TC-SP-030.2-01 | SC-SP-04 | FR-SP-030 | BRIDSP-11 | PN not in LAMD | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Loan & Matching tab | Data: TD-SP-05 LAMD snapshot | 1. Open a record whose PN is not in the snapshot. | Classification INFORCED; no loan matched. | High |  | Not run
TC-SP-031.1-01 | SC-SP-04 | FR-SP-031 | BRIDSP-12 | Active loan to For Renewal | Positive | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist | Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Run processing; open tab For Renewal. | The record is FOR_RENEWAL; the handlers are notified. | High |  | Not run
TC-SP-031.2-01 | SC-SP-04 | FR-SP-031 | BRIDSP-12 | Employee account not renewed | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Open the employee record; run SBM_EXPIRY_SCAN when it is within the lead days. | Bucket BDO / SM Group Employee Accounts; no hand-off. | High |  | Not run
TC-SP-031.3-01 | SC-SP-04 | FR-SP-031 | BRIDSP-12 | Manual disposition | Workflow | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Open a record in Manual Disposition; Dispose; For Renewal; reason; save. | The record is FOR_RENEWAL; the history shows the reason. | High |  | Not run
TC-SP-031.3-02 | SC-SP-04 | FR-SP-031 | BRIDSP-12 | Dispose without reason | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Dispose without a reason. | Not saved. Message "Select a reason for 'Dispose'". | High |  | Not run
TC-SP-032.1-01 | SC-SP-04 | FR-SP-032 | BRIDSP-13 | FFY RA template | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record > Loan & Matching tab | Data: TD-SP-05 LAMD snapshot | 1. Upload the LAMD snapshot; run processing; open the FFY record. | RA template FFY on the record. | High |  | Not run
TC-SP-032.1-02 | SC-SP-04 | FR-SP-032 | BRIDSP-13 | Generic RA template | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record > Loan & Matching tab | Data: TD-SP-05 LAMD snapshot | 1. Open the generic active-loan record. | RA template Generic. | High |  | Not run
TC-SP-032.2-01 | SC-SP-04 | FR-SP-032 | BRIDSP-13 | Snapshot row without PN | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Upload & Intake | Data: TD-SP-05 LAMD snapshot | 1. Upload the snapshot; read the row errors. | The row is refused. Message "Row 9: PN is required". | High |  | Not run
TC-SP-033.1-01 | SC-SP-04 | FR-SP-033 | BRIDSP-14 | No Touch account in the non-renewal report | Report-output | SYSTEM – BIBS scheduled job or event | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-06 Rules and masters; TD-SP-07 Masterlist records | 1. Run processing; run SBM-NON-RENEWAL. | The No Touch record with reason No Touch. | High |  | Not run
TC-SP-033.2-01 | SC-SP-04 | FR-SP-033 | BRIDSP-14 | Excluded record not handed over | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Data: TD-SP-06 Rules and masters; TD-SP-07 Masterlist records | 1. Run SBM_EXPIRY_SCAN when the record is within the lead days. | No hand-off; the record stays EXCLUDED. | High |  | Not run
TC-SP-033.3-01 | SC-SP-04 | FR-SP-033 | BRIDSP-14 | Reinstate with a reason | Workflow | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-06 Rules and masters; TD-SP-07 Masterlist records | 1. Reinstate; reason; save; run processing. | The record is classified again at the next run. | High |  | Not run
TC-SP-033.3-02 | SC-SP-04 | FR-SP-033 | BRIDSP-14 | Reinstate without reason | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-06 Rules and masters; TD-SP-07 Masterlist records | 1. Reinstate without a reason. | Not saved. Message "Select a reason for 'Reinstate'". | High |  | Not run
TC-SP-034.1-01 | SC-SP-04 | FR-SP-034 | BRIDSP-15 | Fully Paid Loan to renewal | Workflow | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Renewal tab | Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Run processing; run the expiry scan within the lead days; open the Renewal tab and the Renewal record. | Bucket Fully Paid Loan, FOR_RENEWAL, handed over; the Renewal record shows the RA and the proposal. | High |  | Not run
TC-SP-034.2-01 | SC-SP-04 | FR-SP-034 | BRIDSP-15 | Bucket not eligible | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Renewal tab | A Sold record (not eligible in the demo rules). Data: TD-SP-05 LAMD snapshot; TD-SP-06 Rules and masters | 1. Run the expiry scan. | No hand-off. | High |  | Not run
TC-SP-040.1-01 | SC-SP-05 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | Two reviews then IAAF | Workflow | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Policy Reviews / IAAF | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Record review 1 With findings; send the findings to the bank counterpart. 2. Record review 2 Adequate; Generate IAAF. | The findings e-mail reaches the test mailbox. The IAAF (IAAF-yyyy-nnnnnn) shows two reviews and a review count of 2. | High |  | Not run
TC-SP-040.2-01 | SC-SP-05 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | Second IAAF | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Policy Reviews / IAAF | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Click Generate IAAF again on the same policy. | Refused. Message "Policy SBM-2026-000040 already has IAAF IAAF-2026-000003". | High |  | Not run
TC-SP-040.3-01 | SC-SP-05 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | Link to the previous term | Positive | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Masterlist > Policy record > Review & IAAF tab | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Link the previous term's record by SBM number. | The IAAF shows the link. | High |  | Not run
TC-SP-040.4-01 | SC-SP-05 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | Adequacy not selected | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Policy Reviews / IAAF | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Save a review without adequacy. | Not saved. Message "Select the adequacy". | High |  | Not run
TC-SP-040.4-02 | SC-SP-05 | FR-SP-040 | BRIDSP-05, BRIDSP-06 | IAAF with findings open | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Submitted Policies > Policy Reviews / IAAF | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Record a review With findings; Generate IAAF. | Refused. Message "The last review has findings; record an adequate review first". | High |  | Not run
TC-SP-041.1-01 | SC-SP-05 | FR-SP-041 | BRIDSP-07 | Level 1 then level 2 | Workflow | MKT_TL – NB Team Lead | My Approvals | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. polreview submits the IAAF; sbmchecker approves; mkttl approves. | Level 1 then level 2 are notified in turn; the IAAF is APPROVED. | High |  | Not run
TC-SP-041.2-01 | SC-SP-05 | FR-SP-041 | BRIDSP-07 | Issued IAAF PDF | Upload-download | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | My Approvals | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Click Send to bank counterpart; open the mailbox and the PDF. | ISSUED; the PDF shows each approver's stamped name, position and time. | High |  | Not run
TC-SP-041.3-01 | SC-SP-05 | FR-SP-041 | BRIDSP-07 | Preparer approves | Security-access | SBM_TL – Team Lead (Submitted Policies) | My Approvals | sbmtl prepared the IAAF and holds IAAF_APPROVE. Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. As sbmtl click Approve. | Refused. Message "An IAAF is approved by someone other than its preparer". | High |  | Not run
TC-SP-041.3-02 | SC-SP-05 | FR-SP-041 | BRIDSP-07 | Return without reason | Negative | SBM_CHECKER – Submitted Checker | My Approvals | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Return without a reason. | Refused. Message "Select a reason for 'Return'". | High |  | Not run
TC-SP-041.4-01 | SC-SP-05 | FR-SP-041 | BRIDSP-07 | No matrix row | Negative | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | My Approvals | A CBG Fire IAAF above every sum-insured band of the matrix. Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Submit the IAAF. | Refused. Message "No approval level is defined for segment CBG Fire and sum insured PHP 250,000,000.00". | High |  | Not run
TC-SP-050.1-01 | SC-SP-06 | FR-SP-050 | BRIDSP-16 | Vehicle older than 10 years | Positive | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Rule Results tab | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Run processing of the 12-year-old vehicle record; open Rule Results and the AO's tasks. | Flag Insurer approval required; the check shows limit 10 and value 12; the handling Marketing user has a TOR task. | High |  | Not run
TC-SP-050.2-01 | SC-SP-06 | FR-SP-050 | BRIDSP-16 | Vehicle within the limit | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Rule Results tab | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Run processing of a 5-year-old vehicle record. | No flag and no TOR task. | High |  | Not run
TC-SP-051.1-01 | SC-SP-06 | FR-SP-051 | BRIDSP-17 | Generate the TOR | Workflow | MKT_AO – Marketing AO / MAO | Submitted Policies > TOR | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Open the TOR task; Generate TOR; proposed terms; Account Officer; save; submit. | TOR-yyyy-nnnnnn with the vehicle-age breach and the terms; FOR_APPROVAL after submission. | High |  | Not run
TC-SP-051.2-01 | SC-SP-06 | FR-SP-051 | BRIDSP-17 | Proposed terms blank | Negative | MKT_AO – Marketing AO / MAO | Submitted Policies > TOR | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Save the TOR without proposed terms. | Not saved. Message "Enter the proposed terms". | High |  | Not run
TC-SP-051.2-02 | SC-SP-06 | FR-SP-051 | BRIDSP-17 | Record without a breach | Negative | MKT_AO – Marketing AO / MAO | API call with the user's token (tester tool, for example Postman) | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Call Generate TOR for the 5-year-old vehicle record. | Refused. Message "Policy SBM-2026-000045 exceeds no limit". | High |  | Not run
TC-SP-052.1-01 | SC-SP-06 | FR-SP-052 | BRIDSP-18 | TSU approval | Workflow | TSU – TSU approver | My Approvals | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. As tsu open the TOR in My Approvals; approve. | APPROVED; the signed PDF is attached as type TOR. | High |  | Not run
TC-SP-052.2-01 | SC-SP-06 | FR-SP-052 | BRIDSP-18 | Preparer approves the TOR | Security-access | SBM_TL – Team Lead (Submitted Policies) | My Approvals | sbmtl prepared the TOR and holds TOR_APPROVE for this case. Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. As sbmtl click Approve. | Refused. Message "A TOR is approved by someone other than its preparer". | High |  | Not run
TC-SP-052.2-02 | SC-SP-06 | FR-SP-052 | BRIDSP-18 | Return without reason | Negative | TSU – TSU approver | My Approvals | Data: TD-SP-06 Rules and masters; TD-SP-08 Review, TOR and handling-fee data | 1. Return without a reason. | Refused. Message "Select a reason for 'Return'". | High |  | Not run
TC-SP-053.1-01 | SC-SP-06 | FR-SP-053 | BRIDSP-19 | AO downloads the TOR | Upload-download | MKT_AO – Marketing AO / MAO | Submitted Policies > TOR | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Open the notification; open the TOR; Download. | The signed PDF downloads; the TOR shows RELEASED. | High |  | Not run
TC-SP-053.2-01 | SC-SP-06 | FR-SP-053 | BRIDSP-19 | Another AO | Security-access | MKT_AO – Marketing AO / MAO | Submitted Policies > TOR | Data: TD-SP-08 Review, TOR and handling-fee data | 1. As ao2 open the TOR address. | The TOR does not open. | High |  | Not run
TC-SP-060.1-01 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | CBG Fire at 150 days | Boundary | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run SBM_EXPIRY_SCAN; open the record and the bell. | Handed over with an insurer other than INS-LAC; RENEWAL_IN_PROGRESS; handler and AO notified. | High |  | Not run
TC-SP-060.1-02 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | CBG Fire at 151 days | Boundary | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the scan for a Fire record expiring in 151 days. | Not handed over. | High |  | Not run
TC-SP-060.2-01 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | Second scan | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the scan again. | No second hand-off. | High |  | Not run
TC-SP-060.3-01 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | Renewal adapter not deployed | Positive | SYSTEM – BIBS scheduled job or event | Submitted Policies > Renewal Work List | Renewal module not deployed on the test environment. Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the scan; open tab Hand-off Pending; check the letters. | The hand-off is PENDING; no account and no letter. | High |  | Not run
TC-SP-060.4-01 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | No insurer rule | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Processing Runs | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the scan for a record whose vehicle type has no insurer rule. | The record stays For Renewal; fallout reason no insurer. | High |  | Not run
TC-SP-060.4-02 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | Renew with BDOI on a record not For Renewal | Negative | MKT_AO – Marketing AO / MAO | API call with the user's token (tester tool, for example Postman) | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Call Renew with BDOI on an EXCLUDED record. | Refused. Message "Policy SBM-2026-000050 is not For Renewal". | High |  | Not run
TC-SP-060.4-03 | SC-SP-07 | FR-SP-060 | BRIDSP-23 | Renew with BDOI (Non-CBG Retail) | Workflow | MKT_AO – Marketing AO / MAO | Submitted Policies > Masterlist | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Open the Retail record; Renew with BDOI. | The hand-off is made; RENEWAL_IN_PROGRESS. | High |  | Not run
TC-SP-061.1-01 | SC-SP-07 | FR-SP-061 | BRIDSP-25 | For Renewal of March | Positive | SBM_SANITATION – Sanitation Handler | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates | 1. Open tab For Renewal; filter March. | Every renewable record expiring in March in scope. | High |  | Not run
TC-SP-061.2-01 | SC-SP-07 | FR-SP-061 | BRIDSP-25 | Export and assign AO | Report-output | SBM_SANITATION – Sanitation Handler | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates | 1. Assign ao to three records; export SBM-RENEWABLE. | The file matches the screen; ao is notified. | High |  | Not run
TC-SP-061.3-01 | SC-SP-07 | FR-SP-061 | BRIDSP-25 | Out-of-scope records | Security-access | SBM_HANDLER – Submitted Handler (CBG) | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates | 1. As firehandler open tab For Renewal. | No CBG Motor record. | High |  | Not run
TC-SP-062.1-01 | SC-SP-07 | FR-SP-062 | BRIDSP-22 | Reminder letter by e-mail | Positive | SYSTEM – BIBS scheduled job or event | Test mailbox of the recipient | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates | 1. Run SBM_LETTER_DISPATCH on the rule's date; open the mailbox of the bank counterpart. | The reminder letter to the client c/o the bank counterpart. | High |  | Not run
TC-SP-062.2-01 | SC-SP-07 | FR-SP-062 | BRIDSP-22 | Print batch | Report-output | SYSTEM – BIBS scheduled job or event | Submitted Policies > Letters & Print Batches | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates | 1. Open today's print batch. | One merged PDF with every print letter and a control list. | High |  | Not run
TC-SP-062.3-01 | SC-SP-07 | FR-SP-062 | BRIDSP-22 | No RA from this module | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Masterlist > Policy record > Letters tab | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates | 1. Open the Letters tab of a handed-over record; open its Renewal record. | No RA on the Letters tab; the RA is on the Renewal record. | High |  | Not run
TC-SP-062.4-01 | SC-SP-07 | FR-SP-062 | BRIDSP-22 | Delivery failure | Negative | SYSTEM – BIBS scheduled job or event | Notifications (bell icon in the page header) | The mail relay refuses the address of one bank counterpart. Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates | 1. Run the dispatch; open the letter and the bell. | The letter is FAILED; alert SBM_LETTER_FAILED; the user can resend it. | High |  | Not run
TC-SP-062.4-02 | SC-SP-07 | FR-SP-062 | BRIDSP-22 | Client without e-mail | Negative | SYSTEM – BIBS scheduled job or event | Submitted Policies > Letters & Print Batches | Data: TD-SP-06 Rules and masters; TD-SP-09 Renewal candidates | 1. Run the dispatch for a client without e-mail on an e-mail rule. | The letter is not sent. Message "Client UAT Client Nine has no e-mail address". | High |  | Not run
TC-SP-063.1-01 | SC-SP-07 | FR-SP-063 | BRIDSP-32 | Alert after 5 days | Boundary | SBM_SANITATION – Sanitation Handler | Notifications (bell icon in the page header) | Data: TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run SBM_HOLD_COVER_WATCH for the request open 6 days; open the bell. | Alert SBM_INSURER_NOT_ACCEPTED; the record is on tab Insurer Not Accepted. | High |  | Not run
TC-SP-063.1-02 | SC-SP-07 | FR-SP-063 | BRIDSP-32 | No alert at 4 days | Boundary | SBM_SANITATION – Sanitation Handler | Notifications (bell icon in the page header) | Data: TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the watch for a request open 4 days. | No alert. | High |  | Not run
TC-SP-063.2-01 | SC-SP-07 | FR-SP-063 | BRIDSP-32 | Re-assign the insurer | Workflow | SBM_SANITATION – Sanitation Handler | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Re-assign Insurer; new insurer; reason; save; open the renewal account and the mailbox. | The old request is Reassigned; the new insurer receives the hold cover request; the account shows the new insurer. | High |  | Not run
TC-SP-063.3-01 | SC-SP-07 | FR-SP-063 | BRIDSP-32 | Same insurer | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Select the current insurer; save. | Refused. Message "Select an insurer other than the current one". | High |  | Not run
TC-SP-063.3-02 | SC-SP-07 | FR-SP-063 | BRIDSP-32 | No reason | Negative | SBM_SANITATION – Sanitation Handler | Submitted Policies > Renewal Work List | Data: TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Select another insurer without a reason; save. | Refused. Message "Select the reason". | High |  | Not run
TC-SP-064.1-01 | SC-SP-07 | FR-SP-064 | BRIDSP-26 | Place the renewal account | Workflow | PROCESSOR – Placement and Booking user | Placement & Booking > Placement (BRD-1 screens) | Data: TD-SP-09 Renewal candidates | 1. Confirm and pay the renewal account; generate and send the placement slip; open the masterlist record. | The insurer receives the protected slip; the record is PLACED; the handler is notified. | High |  | Not run
TC-SP-064.2-01 | SC-SP-07 | FR-SP-064 | BRIDSP-26 | Payment gate not passed | Negative | PROCESSOR – Placement and Booking user | Placement & Booking > Placement (BRD-1 screens) | Data: TD-SP-09 Renewal candidates | 1. Try to send the slip of an unpaid renewal account. | The slip is not sent; the record stays RENEWAL_IN_PROGRESS. | High |  | Not run
TC-SP-065.1-01 | SC-SP-07 | FR-SP-065 | BRIDSP-27 | Booked renewal | Workflow | PROCESSOR – Placement and Booking user | Submitted Policies > Masterlist | Data: TD-SP-09 Renewal candidates | 1. Book the placed renewal account; open the masterlist record and the invoice. | BOOKED with invoice number and date; business type RENEWAL. | High |  | Not run
TC-SP-065.2-01 | SC-SP-07 | FR-SP-065 | BRIDSP-27 | Declined renewal | Negative | PROCESSOR – Placement and Booking user | Submitted Policies > Masterlist > Policy record (Details tab) | Data: TD-SP-09 Renewal candidates | 1. Decline the renewal in the Renewal module; open the record. | NOT_RENEWED with the reason. | High |  | Not run
TC-SP-070.1-01 | SC-SP-08 | FR-SP-070 | BRIDSP-31 | CLPC payment tagged | Workflow | SYSTEM – BIBS scheduled job or event | Submitted Policies > Handling Fees | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Run SBM_HANDLING_FEE_TAGGER; open the record and Cashiering. | TAGGED then APPLIED; an OR is issued. | High |  | Not run
TC-SP-070.2-01 | SC-SP-08 | FR-SP-070 | BRIDSP-31 | Unknown OTC reference | Negative | SBM_UPP_HANDLER – Admin Team UPP handler | Collections > Unapplied Payments | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Run the tagger; open the unapplied list. | The OTC payment stays for the UPP handler. | High |  | Not run
TC-SP-070.2-02 | SC-SP-08 | FR-SP-070 | BRIDSP-31 | Payment matching two records | Negative | SBM_UPP_HANDLER – Admin Team UPP handler | Submitted Policies > Handling Fees | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Run the tagger; open the tagger results. | The payment is untagged and listed as ambiguous. | High |  | Not run
TC-SP-070.3-01 | SC-SP-08 | FR-SP-070 | BRIDSP-31 | Manual tag of a tagged payment | Negative | SBM_UPP_HANDLER – Admin Team UPP handler | API call with the user's token (tester tool, for example Postman) | Data: TD-SP-08 Review, TOR and handling-fee data | 1. Tag the CLPC payment by hand. | Refused. Message "Payment UP-2026-000101 is already tagged". | High |  | Not run
TC-SP-080.1-01 | SC-SP-09 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | Sanitation Report | Report-output | SBM_TL – Team Lead (Submitted Policies) | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-07 Masterlist records | 1. Run SBM-SANITATION for the month. | Counts under Expiring accounts, For renewal, Not for renewal and Other with the lines of row 156. | High |  | Not run
TC-SP-080.2-01 | SC-SP-09 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | Home tiles | Report-output | SBM_TL – Team Lead (Submitted Policies) | Submitted Policies > Submitted Policies Home | Data: TD-SP-07 Masterlist records | 1. Open the home page; click the fallout tile. | The list opens filtered on the last run's fallout, with the tile's count. | High |  | Not run
TC-SP-080.3-01 | SC-SP-09 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | Invalid date range | Negative | SBM_TL – Team Lead (Submitted Policies) | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-07 Masterlist records | 1. Run SBM-DISPOSITION with the end date before the start date. | Not run. Message "The end date must be on or after the start date". | High |  | Not run
TC-SP-080.3-02 | SC-SP-09 | FR-SP-080 | BRIDSP-20, BRIDSP-30 | Report scope | Security-access | SBM_HANDLER – Submitted Handler (CBG) | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-07 Masterlist records | 1. As firehandler run SBM-CLASSIFICATION. | CBG Fire records only. | High |  | Not run
TC-SP-081.1-01 | SC-SP-09 | FR-SP-081 | BRIDSP-21 | Export in five formats | Report-output | SBM_TL – Team Lead (Submitted Policies) | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-07 Masterlist records | 1. Run SBM-MASTERLIST; export to XLSX, PDF, ODS, CSV and XML; print preview; open Report Archive. | Same rows in every file; the exports are archived with user and parameters. | High |  | Not run
TC-SP-081.2-01 | SC-SP-09 | FR-SP-081 | BRIDSP-21 | Export without permission | Security-access | SBM_CHECKER – Submitted Checker | Reports > Report Centre (category Submitted Policies) | Data: TD-SP-07 Masterlist records | 1. As sbmchecker run the report; call the export. | No Export; the call is refused. Message "You are not permitted to perform this action". | High |  | Not run
TC-SP-082.1-01 | SC-SP-09 | FR-SP-082 | BRIDSP-24 | IAAF pending notice | Positive | SBM_CHECKER – Submitted Checker | Notifications (bell icon in the page header) | Data: TD-SP-08 Review, TOR and handling-fee data; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. polreview submits an IAAF; sbmchecker opens the bell. | The notice opens the IAAF. | High |  | Not run
TC-SP-082.2-01 | SC-SP-09 | FR-SP-082 | BRIDSP-24 | Unbooked hold cover at 5 days | Boundary | SYSTEM – BIBS scheduled job or event | Notifications (bell icon in the page header) | Data: TD-SP-08 Review, TOR and handling-fee data; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run SBM_HOLD_COVER_WATCH for a hold cover ending in 5 days on an unbooked account. | Alert SBM_HOLD_COVER_UNBOOKED to the handler and TL. | High |  | Not run
TC-SP-082.2-02 | SC-SP-09 | FR-SP-082 | BRIDSP-24 | Booked account not alerted | Negative | SYSTEM – BIBS scheduled job or event | Notifications (bell icon in the page header) | Data: TD-SP-08 Review, TOR and handling-fee data; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Run the watch for a booked account whose hold cover ends in 5 days. | No alert. | High |  | Not run
TC-SP-082.3-01 | SC-SP-09 | FR-SP-082 | BRIDSP-24 | E-mail preference | Positive | SBM_HANDLER – Submitted Handler (CBG) | Test mailbox of the recipient | Data: TD-SP-08 Review, TOR and handling-fee data; TD-SP-09 Renewal candidates; TD-SP-10 Parameters and jobs as delivered | 1. Set the preference for new submissions to e-mail; upload a file. | The notice arrives by e-mail. | High |  | Not run

## Coverage
Coverage
Every FR and every BRD ID with its count of positive and negative cases
FR / BRD ID | Kind | Title | Traces | Conditions | Positive | Negative | Total | Automated | Coverage
FR-SP-001 | FR | Receive submitted policy details from the approved sources | BRIDSP-01 | 5 | 3 | 4 | 7 | 0 | Covered
FR-SP-002 | FR | Extract policy details from documents and save them after confirmation | BRIDSP-02 | 4 | 1 | 4 | 5 | 0 | Covered
FR-SP-003 | FR | Create or update a policy manually and tag its renewal opportunity | BRIDSP-03 | 4 | 3 | 3 | 6 | 0 | Covered
FR-SP-004 | FR | Migrate the existing Excel masterlists | BRIDSP-33 | 4 | 2 | 3 | 5 | 0 | Covered
FR-SP-010 | FR | Keep one Submitted Masterlist | BRIDSP-04 | 3 | 3 | 1 | 4 | 0 | Covered
FR-SP-011 | FR | View and extract the masterlist by role | BRIDSP-28 | 3 | 1 | 3 | 4 | 0 | Covered
FR-SP-012 | FR | Monitor handler, conversion status and remarks | BRIDSP-29 | 3 | 3 | 1 | 4 | 0 | Covered
FR-SP-020 | FR | Define sanitation, matching, classification and disposition criteria | BRIDSP-08 | 4 | 3 | 4 | 7 | 0 | Covered
FR-SP-021 | FR | Run processing automatically after intake | BRIDSP-09 | 4 | 3 | 1 | 4 | 0 | Covered
FR-SP-022 | FR | Report fallout after processing | BRIDSP-10 | 3 | 2 | 1 | 3 | 0 | Covered
FR-SP-030 | FR | Classify policies as Inforced or Submitted | BRIDSP-11 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-031 | FR | Group Submitted policies into qualification buckets | BRIDSP-12 | 3 | 2 | 2 | 4 | 0 | Covered
FR-SP-032 | FR | Choose the RA template from the LAMD loan | BRIDSP-13 | 2 | 2 | 1 | 3 | 0 | Covered
FR-SP-033 | FR | Assign policies to non-renewal buckets | BRIDSP-14 | 3 | 2 | 2 | 4 | 0 | Covered
FR-SP-034 | FR | Group Inforced policies and create RAs and proposals | BRIDSP-15 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-040 | FR | Record policy reviews and generate one IAAF per policy | BRIDSP-05, BRIDSP-06 | 4 | 2 | 3 | 5 | 0 | Covered
FR-SP-041 | FR | Route the IAAF for approval and signature | BRIDSP-07 | 4 | 2 | 3 | 5 | 0 | Covered
FR-SP-050 | FR | Detect accounts exceeding acceptance or coverage limits | BRIDSP-16 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-051 | FR | Generate the Terms of Reference | BRIDSP-17 | 2 | 1 | 2 | 3 | 0 | Covered
FR-SP-052 | FR | Route the TOR for approval per the TSU Approval Matrix | BRIDSP-18 | 2 | 1 | 2 | 3 | 0 | Covered
FR-SP-053 | FR | Hand the approved TOR over to the Account Officer | BRIDSP-19 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-060 | FR | Detect expiring policies and hand them to Renewal | BRIDSP-23 | 4 | 3 | 4 | 7 | 0 | Covered
FR-SP-061 | FR | List the policies subject for renewal | BRIDSP-25 | 3 | 2 | 1 | 3 | 0 | Covered
FR-SP-062 | FR | Send letters and proposals when the criteria are met | BRIDSP-22 | 4 | 2 | 3 | 5 | 0 | Covered
FR-SP-063 | FR | Re-assign the insurer while a hold cover request is open | BRIDSP-32 | 3 | 2 | 3 | 5 | 0 | Covered
FR-SP-064 | FR | Process placement of the renewal account | BRIDSP-26 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-065 | FR | Show the booked status in the masterlist | BRIDSP-27 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-070 | FR | Tag handling-fee payments in the Unapplied Payment List | BRIDSP-31 | 3 | 1 | 3 | 4 | 0 | Covered
FR-SP-080 | FR | Generate Submitted Policies reports | BRIDSP-20, BRIDSP-30 | 3 | 2 | 2 | 4 | 0 | Covered
FR-SP-081 | FR | View, download and print reports in several formats | BRIDSP-21 | 2 | 1 | 1 | 2 | 0 | Covered
FR-SP-082 | FR | Send notifications and alerts for key events | BRIDSP-24 | 3 | 3 | 1 | 4 | 0 | Covered
BRIDSP-01 | BRD ID |  | FR-SP-001 | 5 | 3 | 4 | 7 | 0 | Covered
BRIDSP-02 | BRD ID |  | FR-SP-002 | 4 | 1 | 4 | 5 | 0 | Covered
BRIDSP-03 | BRD ID |  | FR-SP-003 | 4 | 3 | 3 | 6 | 0 | Covered
BRIDSP-04 | BRD ID |  | FR-SP-010 | 3 | 3 | 1 | 4 | 0 | Covered
BRIDSP-05 | BRD ID |  | FR-SP-040 | 4 | 2 | 3 | 5 | 0 | Covered
BRIDSP-06 | BRD ID |  | FR-SP-040 | 4 | 2 | 3 | 5 | 0 | Covered
BRIDSP-07 | BRD ID |  | FR-SP-041 | 4 | 2 | 3 | 5 | 0 | Covered
BRIDSP-08 | BRD ID |  | FR-SP-020 | 4 | 3 | 4 | 7 | 0 | Covered
BRIDSP-09 | BRD ID |  | FR-SP-021 | 4 | 3 | 1 | 4 | 0 | Covered
BRIDSP-10 | BRD ID |  | FR-SP-022 | 3 | 2 | 1 | 3 | 0 | Covered
BRIDSP-11 | BRD ID |  | FR-SP-030 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-12 | BRD ID |  | FR-SP-031 | 3 | 2 | 2 | 4 | 0 | Covered
BRIDSP-13 | BRD ID |  | FR-SP-032 | 2 | 2 | 1 | 3 | 0 | Covered
BRIDSP-14 | BRD ID |  | FR-SP-033 | 3 | 2 | 2 | 4 | 0 | Covered
BRIDSP-15 | BRD ID |  | FR-SP-034 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-16 | BRD ID |  | FR-SP-050 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-17 | BRD ID |  | FR-SP-051 | 2 | 1 | 2 | 3 | 0 | Covered
BRIDSP-18 | BRD ID |  | FR-SP-052 | 2 | 1 | 2 | 3 | 0 | Covered
BRIDSP-19 | BRD ID |  | FR-SP-053 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-20 | BRD ID |  | FR-SP-080 | 3 | 2 | 2 | 4 | 0 | Covered
BRIDSP-21 | BRD ID |  | FR-SP-081 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-22 | BRD ID |  | FR-SP-062 | 4 | 2 | 3 | 5 | 0 | Covered
BRIDSP-23 | BRD ID |  | FR-SP-060 | 4 | 3 | 4 | 7 | 0 | Covered
BRIDSP-24 | BRD ID |  | FR-SP-082 | 3 | 3 | 1 | 4 | 0 | Covered
BRIDSP-25 | BRD ID |  | FR-SP-061 | 3 | 2 | 1 | 3 | 0 | Covered
BRIDSP-26 | BRD ID |  | FR-SP-064 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-27 | BRD ID |  | FR-SP-065 | 2 | 1 | 1 | 2 | 0 | Covered
BRIDSP-28 | BRD ID |  | FR-SP-011 | 3 | 1 | 3 | 4 | 0 | Covered
BRIDSP-29 | BRD ID |  | FR-SP-012 | 3 | 3 | 1 | 4 | 0 | Covered
BRIDSP-30 | BRD ID |  | FR-SP-080 | 3 | 2 | 2 | 4 | 0 | Covered
BRIDSP-31 | BRD ID |  | FR-SP-070 | 3 | 1 | 3 | 4 | 0 | Covered
BRIDSP-32 | BRD ID |  | FR-SP-063 | 3 | 2 | 3 | 5 | 0 | Covered
BRIDSP-33 | BRD ID |  | FR-SP-004 | 4 | 2 | 3 | 5 | 0 | Covered

## Test Data
Test Data
Named test data sets; UAT uses masked copies of production-like data
Data set | Name | Content | Source | Cases
TD-SP-01 | Test users per role and scope | sbmhandler (SBM_HANDLER, scope CBG Motor), firehandler (SBM_HANDLER, scope CBG Fire), sbmchecker (SBM_CHECKER, IAAF level 1), sanitation (SBM_SANITATION), sbmtl (SBM_TL), polreview (SBM_POLICY_REVIEWER), badmin (SBM_RULE_ADMIN), upphandler (SBM_UPP_HANDLER), ao and ao2 (MKT_AO, own records), mkttl (MKT_TL, IAAF level 2 and rule approval), tsu (TSU), proc (PROCESSOR). | Planned demo seed V1970 of the build design; firehandler and ao2 created by the test lead with their user scope | 4
TD-SP-02 | Source files | LFS insurance report of 300 CBG Motor rows; the same file again; an LFS file with 5 rows without PN; an LFS file with one row that updates an existing policy (new premium); a CSV without header row; a PDF file. | Prepared by the test lead from the upload template of the LFS source; masked data | 14
TD-SP-03 | Policy documents | A text PDF of a motor policy (insurer with an extraction pattern); a scanned image PDF without text. | Test document folder of the test lead; masked policy copies | 5
TD-SP-04 | Legacy masterlist | NB Motor legacy Excel file of 1,000 rows, of which 12 are invalid (status not in the map, blank PN, blank expiry). | Masked extract of a BDOI masterlist prepared by the test lead | 5
TD-SP-05 | LAMD snapshot | PN rows with active non-amortised loans (FFY and generic), fully paid loans, RMU (remedial) and open-market loans; one row without PN. | Planned demo seed V1971; masked rows added by the test lead | 15
TD-SP-06 | Rules and masters | Active demo rule sets for sanitation, matching, classification and disposition; SM Group employee list; No Touch list; limit rule for insurer INS-MGIC Motor, maximum vehicle age 10 years; insurer rules by vehicle type (Motor) and different-from-expiring (Fire); letter rules; IAAF matrix (level 1 SBM_CHECKER, level 2 MKT_TL) and TSU matrix for TOR. | Planned demo seed V1970 of the build design | 43
TD-SP-07 | Masterlist records | About 60 records over the four segments, NB and RB, including migrated records, with handlers and conversion statuses. | Planned demo seed V1971 of the build design | 28
TD-SP-08 | Review, TOR and handling-fee data | A Non-CBG Corporate record IN_REVIEW with its documents; a CBG Motor record with a 12-year-old vehicle insured with INS-MGIC; billed handling-fee records with PN and location reference; a CLPC unapplied payment carrying a billed PN; an OTC payment with an unknown location reference; one payment matching two records. | Planned demo seed V1972; payments keyed in Collections by the test lead | 28
TD-SP-09 | Renewal candidates | A For Renewal CBG Fire record expiring in 150 days (expiring insurer INS-LAC); a For Renewal CBG Motor record expiring in 120 days; a Non-CBG Retail record of ao; a renewal account with a hold cover request open for 6 days. | Planned demo seeds V1971-V1972; expiry dates set by the test lead | 28
TD-SP-10 | Parameters and jobs as delivered | SBM_RENEWAL_LEAD_DAYS CBG_FIRE=150, CBG_MOTOR=120; SBM_MASTERLIST_DAYS_FROM_EXTRACTION 30; SBM_INSURER_ACCEPT_DAYS 5; SBM_HOLD_COVER_UNBOOKED_ALERT_DAYS 5; jobs SBM_PROCESSING 21:30, SBM_EXPIRY_SCAN 22:00, SBM_LETTER_DISPATCH 06:30, SBM_HOLD_COVER_WATCH 07:00 PHT, SBM_HANDLING_FEE_TAGGER every 30 minutes. | Configuration delivered with the build (FRS section 9.1) | 16

## Roles and Access
Roles and Access
Who can and cannot see or do each action (one row per action and role)
Case ID | Action | Screen (menu path) | Permission | Role | Access | Expected result | Automation reference | Status | Actual result | Tester | Date | Defect ID
AC-SP-01.1 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.2 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_CHECKER – Submitted Checker | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.3 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.4 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.5 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.6 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_UPP_HANDLER – Admin Team UPP handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.7 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | MKT_AO – Marketing AO / MAO | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.8 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | MKT_TL – NB Team Lead | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.9 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | PROCESSOR – Placement and Booking user | Allowed | The action is offered and completes. |  | Not run
AC-SP-01.10 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | SBM_RULE_ADMIN – Rule administrator | Denied | Submitted Policies is not in the menu; the list call returns HTTP 403. |  | Not run
AC-SP-01.11 | View the masterlist and records | Submitted Policies > Masterlist | SBM_VIEW | TSU – TSU approver | Denied | Submitted Policies is not in the menu; the list call returns HTTP 403. |  | Not run
AC-SP-02.1 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-02.2 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-02.3 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-02.4 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Allowed | The action is offered and completes. |  | Not run
AC-SP-02.5 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | MKT_AO – Marketing AO / MAO | Allowed | The action is offered and completes. |  | Not run
AC-SP-02.6 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | SBM_CHECKER – Submitted Checker | Denied | New Policy, Edit and the tag actions are not shown; the call returns HTTP 403. |  | Not run
AC-SP-02.7 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | MKT_TL – NB Team Lead | Denied | New Policy, Edit and the tag actions are not shown; the call returns HTTP 403. |  | Not run
AC-SP-02.8 | Create and edit records, tag renewal, confirm extraction | Submitted Policies > Masterlist > Policy record (Details tab) | SBM_MAINTAIN | PROCESSOR – Placement and Booking user | Denied | New Policy, Edit and the tag actions are not shown; the call returns HTTP 403. |  | Not run
AC-SP-03.1 | Upload sources and LAMD snapshots | Submitted Policies > Upload & Intake | SBM_INTAKE | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-03.2 | Upload sources and LAMD snapshots | Submitted Policies > Upload & Intake | SBM_INTAKE | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-03.3 | Upload sources and LAMD snapshots | Submitted Policies > Upload & Intake | SBM_INTAKE | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-03.4 | Upload sources and LAMD snapshots | Submitted Policies > Upload & Intake | SBM_INTAKE | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Denied | Upload & Intake is not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-03.5 | Upload sources and LAMD snapshots | Submitted Policies > Upload & Intake | SBM_INTAKE | MKT_AO – Marketing AO / MAO | Denied | Upload & Intake is not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-04.1 | Run processing, resolve fallout, hand off, re-assign insurer | Submitted Policies > Processing Runs | SBM_PROCESS | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-04.2 | Run processing, resolve fallout, hand off, re-assign insurer | Submitted Policies > Processing Runs | SBM_PROCESS | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-04.3 | Run processing, resolve fallout, hand off, re-assign insurer | Submitted Policies > Processing Runs | SBM_PROCESS | SBM_HANDLER – Submitted Handler (CBG) | Denied | Run Processing and Re-assign Insurer are not shown; the call returns HTTP 403. |  | Not run
AC-SP-04.4 | Run processing, resolve fallout, hand off, re-assign insurer | Submitted Policies > Processing Runs | SBM_PROCESS | MKT_AO – Marketing AO / MAO | Denied | Run Processing and Re-assign Insurer are not shown; the call returns HTTP 403. |  | Not run
AC-SP-05.1 | Maintain rule sets and matrices (maker) | Submitted Policies > Submitted Policies Setup | SBM_RULE_MAINTAIN | SBM_RULE_ADMIN – Rule administrator | Allowed | The action is offered and completes. |  | Not run
AC-SP-05.2 | Maintain rule sets and matrices (maker) | Submitted Policies > Submitted Policies Setup | SBM_RULE_MAINTAIN | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-05.3 | Maintain rule sets and matrices (maker) | Submitted Policies > Submitted Policies Setup | SBM_RULE_MAINTAIN | SBM_HANDLER – Submitted Handler (CBG) | Denied | Submitted Policies Setup is read only or not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-05.4 | Maintain rule sets and matrices (maker) | Submitted Policies > Submitted Policies Setup | SBM_RULE_MAINTAIN | MKT_TL – NB Team Lead | Denied | Submitted Policies Setup is read only or not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-06.1 | Approve rule sets | My Approvals | SBM_RULE_APPROVE | MKT_TL – NB Team Lead | Allowed | The action is offered and completes. |  | Not run
AC-SP-06.2 | Approve rule sets | My Approvals | SBM_RULE_APPROVE | SBM_RULE_ADMIN – Rule administrator | Denied | The rule set is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-06.3 | Approve rule sets | My Approvals | SBM_RULE_APPROVE | SBM_TL – Team Lead (Submitted Policies) | Denied | The rule set is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-07.1 | Prepare reviews and IAAF | Submitted Policies > Policy Reviews / IAAF | IAAF_PREPARE | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-07.2 | Prepare reviews and IAAF | Submitted Policies > Policy Reviews / IAAF | IAAF_PREPARE | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-07.3 | Prepare reviews and IAAF | Submitted Policies > Policy Reviews / IAAF | IAAF_PREPARE | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Allowed | The action is offered and completes. |  | Not run
AC-SP-07.4 | Prepare reviews and IAAF | Submitted Policies > Policy Reviews / IAAF | IAAF_PREPARE | SBM_CHECKER – Submitted Checker | Denied | Generate IAAF is not shown; the call returns HTTP 403. |  | Not run
AC-SP-07.5 | Prepare reviews and IAAF | Submitted Policies > Policy Reviews / IAAF | IAAF_PREPARE | MKT_AO – Marketing AO / MAO | Denied | Generate IAAF is not shown; the call returns HTTP 403. |  | Not run
AC-SP-08.1 | Approve an IAAF level | My Approvals | IAAF_APPROVE | SBM_CHECKER – Submitted Checker | Allowed | The action is offered and completes. |  | Not run
AC-SP-08.2 | Approve an IAAF level | My Approvals | IAAF_APPROVE | MKT_TL – NB Team Lead | Allowed | The action is offered and completes. |  | Not run
AC-SP-08.3 | Approve an IAAF level | My Approvals | IAAF_APPROVE | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Denied | The IAAF is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-08.4 | Approve an IAAF level | My Approvals | IAAF_APPROVE | SBM_HANDLER – Submitted Handler (CBG) | Denied | The IAAF is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-09.1 | Prepare a TOR | Submitted Policies > TOR | TOR_PREPARE | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-09.2 | Prepare a TOR | Submitted Policies > TOR | TOR_PREPARE | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-09.3 | Prepare a TOR | Submitted Policies > TOR | TOR_PREPARE | MKT_AO – Marketing AO / MAO | Allowed | The action is offered and completes. |  | Not run
AC-SP-09.4 | Prepare a TOR | Submitted Policies > TOR | TOR_PREPARE | TSU – TSU approver | Denied | Generate TOR is not shown; the call returns HTTP 403. |  | Not run
AC-SP-09.5 | Prepare a TOR | Submitted Policies > TOR | TOR_PREPARE | SBM_SANITATION – Sanitation Handler | Denied | Generate TOR is not shown; the call returns HTTP 403. |  | Not run
AC-SP-10.1 | Approve a TOR | My Approvals | TOR_APPROVE | TSU – TSU approver | Allowed | The action is offered and completes. |  | Not run
AC-SP-10.2 | Approve a TOR | My Approvals | TOR_APPROVE | MKT_AO – Marketing AO / MAO | Denied | The TOR is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-10.3 | Approve a TOR | My Approvals | TOR_APPROVE | SBM_TL – Team Lead (Submitted Policies) | Denied | The TOR is not offered in My Approvals; the call returns HTTP 403. |  | Not run
AC-SP-11.1 | Send and print letters | Submitted Policies > Letters & Print Batches | SBM_LETTER_SEND | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-11.2 | Send and print letters | Submitted Policies > Letters & Print Batches | SBM_LETTER_SEND | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-11.3 | Send and print letters | Submitted Policies > Letters & Print Batches | SBM_LETTER_SEND | SBM_HANDLER – Submitted Handler (CBG) | Denied | Letters & Print Batches actions are not shown; the call returns HTTP 403. |  | Not run
AC-SP-11.4 | Send and print letters | Submitted Policies > Letters & Print Batches | SBM_LETTER_SEND | MKT_AO – Marketing AO / MAO | Denied | Letters & Print Batches actions are not shown; the call returns HTTP 403. |  | Not run
AC-SP-12.1 | Handling-fee records and manual tag | Submitted Policies > Handling Fees | SBM_HANDLING_FEE | SBM_UPP_HANDLER – Admin Team UPP handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-12.2 | Handling-fee records and manual tag | Submitted Policies > Handling Fees | SBM_HANDLING_FEE | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-12.3 | Handling-fee records and manual tag | Submitted Policies > Handling Fees | SBM_HANDLING_FEE | SBM_SANITATION – Sanitation Handler | Denied | Handling Fees is not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-12.4 | Handling-fee records and manual tag | Submitted Policies > Handling Fees | SBM_HANDLING_FEE | SBM_HANDLER – Submitted Handler (CBG) | Denied | Handling Fees is not in the menu; the call returns HTTP 403. |  | Not run
AC-SP-13.1 | Migrate Excel masterlists | Submitted Policies > Upload & Intake | SBM_MIGRATE | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-13.2 | Migrate Excel masterlists | Submitted Policies > Upload & Intake | SBM_MIGRATE | SBM_HANDLER – Submitted Handler (CBG) | Denied | The Migration upload is not shown; the call returns HTTP 403. |  | Not run
AC-SP-13.3 | Migrate Excel masterlists | Submitted Policies > Upload & Intake | SBM_MIGRATE | SBM_SANITATION – Sanitation Handler | Denied | The Migration upload is not shown; the call returns HTTP 403. |  | Not run
AC-SP-14.1 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-14.2 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-14.3 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-14.4 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Denied | Export is not shown; the call returns HTTP 403. |  | Not run
AC-SP-14.5 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | SBM_CHECKER – Submitted Checker | Denied | Export is not shown; the call returns HTTP 403. |  | Not run
AC-SP-14.6 | Extract the masterlist | Submitted Policies > Masterlist | SBM_EXPORT | MKT_AO – Marketing AO / MAO | Denied | Export is not shown; the call returns HTTP 403. |  | Not run
AC-SP-15.1 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_HANDLER – Submitted Handler (CBG) | Allowed | The action is offered and completes. |  | Not run
AC-SP-15.2 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_CHECKER – Submitted Checker | Allowed | The action is offered and completes. |  | Not run
AC-SP-15.3 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_SANITATION – Sanitation Handler | Allowed | The action is offered and completes. |  | Not run
AC-SP-15.4 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_TL – Team Lead (Submitted Policies) | Allowed | The action is offered and completes. |  | Not run
AC-SP-15.5 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_POLICY_REVIEWER – Policy Review Officer (Non-CBG Corporate) | Allowed | The action is offered and completes. |  | Not run
AC-SP-15.6 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | SBM_UPP_HANDLER – Admin Team UPP handler | Denied | The Submitted Policies category is not listed; the run call returns HTTP 403. |  | Not run
AC-SP-15.7 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | MKT_AO – Marketing AO / MAO | Denied | The Submitted Policies category is not listed; the run call returns HTTP 403. |  | Not run
AC-SP-15.8 | Run Submitted Policies reports | Reports > Report Centre (category Submitted Policies) | SBM_REPORT_VIEW | TSU – TSU approver | Denied | The Submitted Policies category is not listed; the run call returns HTTP 403. |  | Not run

## FRS Findings
FRS Findings
FRS points raised for the FRS owner; the affected cases assume the proposed resolution
ID | FR ID | Finding | Proposed resolution
TF-SP-01 | FR-SP-001 | The natural key includes the expiry date, so a row for the next term of the same policy creates a new record, while acceptance criterion 3 speaks of "a row updating an existing policy". The FRS does not say which fields may change on an update and which make a new record. | List the fields that update a record and state that a new expiry date makes a new term record linked to the previous one.
TF-SP-02 | FR-SP-030 | The default classification uses "BDOI did not place the policy", which is not a field of the masterlist or LAMD; the definition is open (SP SQ04). | Name the data element that tells whether BDOI placed the policy; the cases test the PN match only.
TF-SP-03 | FR-SP-031 | Bucket precedence and the RMU / FFY conflicts are open (SP SQ05) and the conflicting rules are seeded inactive, so a record that is both FFY and RMU cannot be tested. | Answer SP SQ05 and add the precedence to the FRS; a case is added then.
TF-SP-04 | FR-SP-032 | The rule that chooses the Generic or the FFY RA is to be confirmed (SP SQ06); the cases follow the demo rule. | State the rule in the FRS when SP SQ06 is answered.
TF-SP-05 | FR-SP-040 | The FRS keeps one IAAF per policy with links, while the BRD's current process lets one IAAF cover several policies (SP SQ07). The bank counterpart may expect one form. | Confirm with BDOI; the cases test one IAAF per policy.
TF-SP-06 | FR-SP-053 | The meaning of Released is to be confirmed (SP SQ08); the default is the AO's first opening, which a preview by another user could not trigger but a download by the assigned AO does. | Define Released (first opening, first download or explicit acknowledgement) in the FRS.
TF-SP-07 | FR-SP-062 | The owner of the renewal notice and renewal proposal letters is not confirmed (XQ03); the cases may move to the BRD-6 plan. | Record the owner after XQ03; the cases here test the reminder letter and the print batch.
TF-SP-08 | FR-SP-063 | The BRD gives an acceptance window of 3-5 days; the FRS default is 5 (SP SQ12). The FRS does not say whether days are calendar or working days. | State calendar or working days; the boundary cases use calendar days.
TF-SP-09 | FR-SP-070 | Amount, VAT, OR and GL account of the handling fee are to be confirmed (SP SQ13), so the accounting of the applied payment cannot be checked. | Add the accounting entry to the FRS after SP SQ13; the cases check tagging and the OR only.
TF-SP-10 | FR-SP-080 | BRIDSP-30 repeats BRIDSP-20 word for word; the FRS traces both to one FR, which inflates the BRD ID count. | Ask the BRD owner to confirm that BRIDSP-30 is a duplicate and mark it so in the traceability.

## _lists (hidden)
High | Positive | High | Not run | Covered | Allowed | Not run
Medium | Negative | Medium | Pass | GAP | Denied | Pass
Low | Boundary | Low | Fail |  |  | Fail
| Security-access |  | Blocked |  |  | Blocked
| Workflow |  | N/A |  |  | N/A
Report-output
Upload-download