## Cover
CHANGE CONTROL
Change Request Register
BRD-11 User Access Maintenance - after the sign-off of the FRS v1.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
How to use | Raise -> assess -> approve -> schedule -> test -> close (FRS Annex AA) | 6
Register | Candidate changes known at v1.3 (status Candidate - for decision) and new requests | 15
Impact assessment form | Impact assessment form | 12
Decisions log | One row per observation of Annex Q, for the decision of the Business Unit | 77
Legend
Closed
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
How to use | Step | Step of the process
How to use | What happens
How to use | Who
How to use | Record in this workbook
Register | CR No. | Change request number
Register | Date raised | dd-Mmm-yyyy
Register | Raised by | Name and role
Register | BRD ID | BRD requirement
Register | FRS reference | FR item or annex
Register | Description | The change
Register | Reason | Why
Register | Type | Kind of change | Beyond the BRD, Added by BDOI's FRS, Proposal for best practice, Correction
Register | Impact on scope
Register | Impact on schedule
Register | Impact on cost
Register | Impact on other BRDs
Register | Impact on tests
Register | Priority |  | High, Medium, Low
Register | Status |  | Candidate - for decision, Raised, Assessed, Approved, Rejected, Scheduled, In test, Closed
Register | Decision | Decision of the approvers
Register | Approved by
Register | Decision date
Register | Target drop
Register | Linked test cases | Test cases of the Test Cases and Traceability workbook
Impact assessment form | Field | Part of the assessment
Impact assessment form | Assessment | Filled in by the project
Impact assessment form | Assessed by | Name
Decisions log | Annex Q No. | Row of Annex Q of the FRS v1.3
Decisions log | Section
Decisions log | Topic
Decisions log | Proposed in the FRS
Decisions log | Decision by
Decisions log | Decision | Adopt proposal / Keep BDOI text / Other
Decisions log | Decided by (name)
Decisions log | Date
Decisions log | CR No. (if a change follows)
Decisions log | Status |  | Open, Decided, Withdrawn

## How to use
How to use
Raise -> assess -> approve -> schedule -> test -> close (FRS Annex AA)
Step | What happens | Who | Record in this workbook
1 Raise | The change is written with the BRD ID, the FR item or annex concerned, the reason and the business priority | Any signatory or the Process Owner | Register: new row, status Raised
2 Assess | Impact on scope, schedule, cost (mandays), the other BRDs (interface lines of Annex W), the test cases and the training | iorta TechNXT Project Team with the System Analyst (BDO ITG) | Impact assessment form; status Assessed
3 Approve | Decision by the owners of every BRD touched; a change to a separation-of-duties rule, the sign-in or a security setting also by Information Security; a change to an integration also by BDOI IT | Business owner; Process Owner; Information Security; BDOI IT | Decision, approved by, date; status Approved or Rejected
4 Schedule | The change is given a drop and a version of this FRS (1.4, 1.5 and so on) | Project managers | Target drop; status Scheduled
5 Test | The test cases linked to the change are updated and run | Test lead; Business Unit testers | Linked test cases; result
6 Close | The new version of the FRS and of the workbooks is issued with the change marked | System Analyst (BDO ITG) | Status Closed

## Register
Register
Candidate changes known at v1.3 (status Candidate - for decision) and new requests
CR No. | Date raised | Raised by | BRD ID | FRS reference | Description | Reason | Type | Impact on scope | Impact on schedule | Impact on cost | Impact on other BRDs | Impact on tests | Priority | Status | Decision | Approved by | Decision date | Target drop | Linked test cases
CR-UA-001 | 09-Oct-2026 | iorta TechNXT Project Team | BRD NFR p.17 (11) | FRUM.012.01 | Separation-of-duties rules: Pairs of group profiles one user may not hold, kept by the Business Administrator and authorised by Information Security; checked on every request. | The BRD asks to monitor and escalate privilege changes; the rules are a means proposed by the project. | Beyond the BRD | None (available) | None | None | All modules (roles) | FRUM.012.01 cases | High | Candidate - for decision |  |  |  |  | TC-FRUM-012.01-AC01, TC-FRUM-012.01-AC02, TC-UA-053.1-01, TC-UA-053.2-01, TC-UA-053.2-02
CR-UA-002 | 09-Oct-2026 | iorta TechNXT Project Team | BRD NFR p.13 (1.e) | FRUM.003.04 | Dormant-user deactivation: Users without a sign-in for 90 days deactivated by a daily run, with a notice 7 days before. | Information Security practice; not in the BRD text. | Beyond the BRD | None (available) | None | None | All users | FRUM.003.04 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-003.04-AC01, TC-FRUM-003.04-AC02, TC-FRUM-003.04-AC03, TC-UA-006.1-01, TC-UA-006.2-01
CR-UA-003 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 4.001.1 | FRUM.001.06 | Break-glass administrators: Two named System Administrator accounts with a local password and second factor when the sign-in is through EIAM; each sign-in alerted to Information Security. | BDOI's FRS requires the Enterprise SSO for every sign-in; the system must stay manageable when EIAM is down. | Beyond the BRD | Alert to Information Security to add | Small | Low | - | FRUM.001.06 cases | High | Candidate - for decision |  |  |  |  | TC-FRUM-001.06-AC01, TC-FRUM-001.06-AC02, TC-FRUM-001.06-AC03, TC-UA-003.1-01, TC-UA-003.2-01
CR-UA-004 | 09-Oct-2026 | iorta TechNXT Project Team | BRD x.001.1.3 | FRUM.001.04 | Warning before the fixed end of a session: Warning 30 minutes before the fixed end of a session, besides the inactivity time-out. | BRD reads 'warning prior to system triggered log out'; BDOI's FRS gives a time-out message instead (Annex Q, C07). | Correction | None (available) | None | None | - | FRUM.001.04 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-001.04-AC01, TC-FRUM-001.04-AC02, TC-FRUM-001.04-AC03, TC-UA-002.1-01, TC-UA-002.1-02
CR-UA-005 | 09-Oct-2026 | iorta TechNXT Project Team | BRD p.5-6 | FRUM.002.02 | Synchronisation of user details and status from the Enterprise SSO / UIDM-ISC: User details and status received from UIDM-ISC with the UIDM request number, synchronisation status and on-demand synchronisation per user. | Added by BDOI's FRS (FRUM.002.02, FRUM.003.03); not available in the system today. | Added by BDOI's FRS | Provisioning interface and user screens | Medium | Medium | All modules (users) | FRUM.002.02, FRUM.003.03 cases | High | Candidate - for decision |  |  |  |  | TC-FRUM-002.02-AC01, TC-FRUM-002.02-AC02
CR-UA-006 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 1.004 | FRUM.003.02.01 | Revocation on an SSO status change: Access revoked and open sessions ended as soon as the SSO status is inactive, locked or disabled. | Added by BDOI's FRS (Annex Q, C13). | Added by BDOI's FRS | Status events from UIDM-ISC / EIAM | Small | Low | - | FRUM.003.02.01 cases | High | Candidate - for decision |  |  |  |  | TC-FRUM-003.02.01-AC01, TC-FRUM-003.02.01-AC02, TC-FRUM-003.02.01-AC03, TC-UA-006.1-01, TC-UA-006.2-01
CR-UA-007 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 4.002 | FRUM.005.01 | Record-ownership and supervisory access rules: Users with supervisory roles see the records of their assigned personnel. | Added by BDOI's FRS (Annex Q, C15); data scope by unit exists. | Added by BDOI's FRS | Rules per role | Medium | Medium | All modules (data scope) | FRUM.005.01 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-005.01-AC01, TC-FRUM-005.01-AC02, TC-FRUM-005.01-AC03, TC-UA-040.1-01, TC-UA-040.2-01
CR-UA-008 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 4.002.2 | FRUM.006.03 | Conflicting permission combinations inside a role: A role cannot hold two permissions that conflict. | Added by BDOI's FRS (Annex Q, C16); the system checks pairs of profiles today. | Added by BDOI's FRS | Rule on permission pairs | Small | Low | - | FRUM.006.03 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-006.03-AC01, TC-FRUM-006.03-AC02, TC-UA-041.1-01, TC-UA-041.2-01, TC-UA-041.2-02
CR-UA-009 | 09-Oct-2026 | iorta TechNXT Project Team | BRD p.18 | FRUM.007.02 | Export file names: Exports named <Report_Name>_MMDDYYYY and Audit Logs_MMDDYYYY. | Added by BDOI's FRS (Annex Q, C18). | Added by BDOI's FRS | File name of the downloads | Small | Low | All reports (common) | FRUM.007.02 cases | Low | Candidate - for decision |  |  |  |  | TC-FRUM-007.02-AC01, TC-UA-060.1-01, TC-UA-060.1-02, TC-UA-060.2-01, TC-UA-060.3-01
CR-UA-010 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 4.003.1 | FRUM.008.01 | IP address and role in the audit log: Each audit record shows the source IP address and the role of the user at the time. | Added by BDOI's FRS (Annex Q, C19). | Added by BDOI's FRS | Audit record and report | Small | Low | All modules (audit) | FRUM.008 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-008.01-AC01, TC-FRUM-008.01-AC02, TC-UA-004.1-01, TC-UA-004.2-01, TC-UA-004.3-01
CR-UA-011 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 2.002 | FRUM.010 | Approval times, reminders and escalation: 2 working days per approval stage, reminder on the next day, escalation to the Business Administrator after 5 working days. | No service level in the BRD; proposal (Annex Q.5). | Proposal for best practice | Reminder and escalation run | Small | Low | - | FRUM.010 cases | Medium | Candidate - for decision |  |  |  |  | TC-FRUM-010.01-AC01, TC-FRUM-010.01-AC02, TC-UA-030.1-01, TC-UA-030.2-01, TC-UA-030.3-01
CR-UA-012 | 09-Oct-2026 | iorta TechNXT Project Team | BRD NFR p.11 | FRUM.007 | Monthly access review report: User Access Report and audit log of the month sent to Information Security on the first working day. | Best practice; UA-Q51 (Annex Q.5). | Proposal for best practice | Scheduled report | Small | Low | - | FRUM.007 cases | Low | Candidate - for decision |  |  |  |  | TC-FRUM-007.01-AC01, TC-FRUM-007.01-AC02, TC-FRUM-007.01-AC03, TC-UA-060.1-01, TC-UA-060.1-02
CR-UA-013 | 09-Oct-2026 | iorta TechNXT Project Team | BRD 1.006.1.1, 1.008.1.4, 2.002.1 | FRUM.013.01 | E-mail copy of the request notices: The notices to approve, returned and decided also sent by e-mail by the user's preference. | The BRD asks for a notification (met in the system); Annex Z. | Proposal for best practice | E-mail of the notices | Small | Low | - | FRUM.013.01 cases | Low | Candidate - for decision |  |  |  |  | TC-FRUM-013.01-AC01, TC-FRUM-013.01-AC02, TC-UA-070.1-01, TC-UA-070.2-01, TC-UA-070.3-01
CR-UA-014 | 09-Oct-2026 | iorta TechNXT Project Team | BRD NFR p.13 (1.k) | FRUM.009.10 | Temporary access with an end date: Access given until an end date, removed by the daily run. | Open question CLR-UA-13 (Annex Z). | Beyond the BRD | End date on requests | Small | Low | - | FRUM.009.10 cases | Low | Candidate - for decision |  |  |  |  | TC-FRUM-009.10-AC01, TC-FRUM-009.10-AC02, TC-UA-020.1-01, TC-UA-020.2-01, TC-UA-020.3-01
CR-UA-015 | 09-Oct-2026 | iorta TechNXT Project Team | BRD NFR p.14 | FRUM.001.01 | One session per user or device: A new sign-in ends the earlier session of the same user (or device). | Open question CLR-UA-09 (Annex Z). | Beyond the BRD | Session rule | Small | Low | All users | FRUM.001 cases | Low | Candidate - for decision |  |  |  |  | TC-FRUM-001.01-AC01, TC-FRUM-001.01-AC02, TC-UA-001.1-01, TC-UA-001.1-02, TC-UA-001.2-01

## Impact assessment form
Impact assessment form
Purpose | The assessment of one change request before the decision.
Who fills it in | iorta TechNXT Project Team with the System Analyst (BDO ITG)
How it is used | Copied for each change; its conclusion goes to the Register.
Due | Within 5 working days of the request.
Depends on | Register
Mandatory: Mandatory * | Mandatory * | Optional
Format: Text | Text | Text
Allowed values: Free text | Free text | Free text
What to enter: Part of the assessment | Filled in by the project | Name
Field * | Assessment * | Assessed by
Example – overwrite or delete: CR No. | CR-UA-001 | Project analyst
CR No.
Summary of the change
BRD IDs and FR items affected
Screens, messages, e-mails affected
Other BRDs affected (Annex W)
Effort (mandays)
Schedule impact (drop)
Cost
Test cases to add or change
Training and documents
Risks
Recommendation

## Decisions log
Decisions log
One row per observation of Annex Q, for the decision of the Business Unit
Annex Q No. | Section | Topic | Proposed in the FRS | Decision by | Decision | Decided by (name) | Date | CR No. (if a change follows) | Status
Q-01 (C01) | Q.1 | Where access requests are raised and approved | Option (a): UIDM-ISC provisions the user accounts (create, deactivate, reactivate) through the standard provisioning interface, each change logged with its UIDM request number; the assignment and change of group profiles and the group-profile requests stay as requests in the system under four eyes. FRUM.009 to FRUM.011 then apply to the changes not requested in UIDM; all of them apply if BDOI keeps every request in the system. Proposed behaviour: FRUM.009.01 to FRUM.009.10 and FRUM.010.01 to FRUM.010.05: every access change is a request in the system, decided by a chosen approver under four eyes; the UIDM-ISC option is open (CLR-UA-03). Available in BIBS: user accounts are created, updated, deactivated and reactivated from the Enterprise SSO and UIDM-ISC events (setting on by default, BDOI's text) or only through approved requests; the group profiles named in a UIDM-ISC event are applied only when a second setting is on (default off, option a). | BDOI IT; Process Owner (Business Administration); Information Security |  |  |  |  | Open
Q-02 (C02) | Q.1 | Assignment of roles to a user | Assign roles through the request with four eyes; read BDOI's "authorized users" as the requester and the approver together. Proposed behaviour: FRUM.002.01, FRUM.009.02, FRUM.003.01, FRUM.009.03, FRUM.002.01, FRUM.010.02: group profiles are assigned through an enrolment or modify request approved by another user; a direct change is an audited emergency of the System Administrator (FRUM.005.01, FRUM.005.04, FRUM.002.01, FRUM.002.03). | Information Security; Process Owner (Business Administration) |  |  |  |  | Open
Q-03 (C03) | Q.1 | Creation and change of roles (group profiles) | Keep BDOI's capabilities as the System Administrator's implementation of an approved group-profile request (FRUM.005.02 to.04, FRUM.006.04). Proposed behaviour: FRUM.005.01, FRUM.005.02 to FRUM.005.01, FRUM.005.04: the Business Administrator requests, the approvers decide in order, the System Administrator implements; a direct role edit is refused unless the emergency setting is on. | Process Owner (Business Administration); Information Security |  |  |  |  | Open
Q-04 (C04) | Q.1 | Creating the user from the SSO account | Create the user from the UIDM-ISC provisioning (which carries the SSO account) or from an approved enrolment; the Windows ID is checked against EIAM at the first sign-in. A look-up of the SSO directory on the enrolment screen is a change to the system for BDOI to decide. Proposed behaviour: FRUM.001.02, FRUM.001.06, FRUM.002.01, FRUM.009.02: the system never creates a user from a sign-in; the EIAM identity is linked to an existing active user by the Windows ID or the UPN (CLR-UA-22); the user is created by an approved enrolment or, as proposed, by UIDM-ISC provisioning. Available in BIBS: the user is created from an active Enterprise SSO account when the provisioning setting is on (default). | BDOI IT |  |  |  |  | Open
Q-05 (C05) | Q.1 | Duplicate user check | Keep the Windows ID unique on its own, which is stricter than the combination and also refuses BDOI's duplicates; warn when the e-mail address is already used by another user. Proposed behaviour: FRUM.002.01, FRUM.009.02: the user ID is unique and the Windows ID is unique on its own ("Windows ID <id> belongs to another user"). | Information Security |  |  |  |  | Open
Q-06 (C06) | Q.1 | User ID and Windows ID | Keep both values; the reports and the audit log show the user ID and the Windows ID. Proposed behaviour: FRUM.002.01, FRUM.009.02, FRUM.002.01, FRUM.002.03: a user ID in the BDOI format (a letter and nine digits) and the Windows ID held separately for the single sign-on match. | Process Owner (Business Administration); BDOI IT |  |  |  |  | Open
Q-07 (C07) | Q.1 | Session timeout message or warning before the log-out | Keep both - BDOI's message and Log In button after the inactivity sign-out (adopt the wording), and the warning before the fixed end of the session that the BRD asks. Proposed behaviour: FRUM.001.01, FRUM.001.03: sign-out after 30 minutes of inactivity with the warning at 15 minutes; a separate warning 30 minutes before the fixed end of the session. Available in BIBS: after the inactivity sign-out the page 'Your session timed out' with Log In is shown (setting on by default, BDOI's text) or a message on the Login page. | Process Owner (Business Administration) |  |  |  |  | Open
Q-08 (C08) | Q.1 | Wording of the inactivity warning | Adopt BDOI's text and buttons (a screen text change, no rule change). Proposed behaviour: FRUM.001.01, FRUM.001.03 and the session dialog of the screens: "For your security the system signs you out in n minute(s)..." with the system's own buttons. Available in BIBS: the inactivity warning uses BDOI's wording and the buttons Stay Logged In and Log Out (setting on by default) or the earlier wording. | Process Owner (Business Administration) |  |  |  |  | Open
Q-09 (C09) | Q.1 | Lock-out after three invalid tries | EIAM's lock-out set to 3 invalid tries for BDO accounts (BDOI IT to confirm); 3 in the application for the break-glass accounts. Proposed behaviour: FRUM.001.01, FRUM.001.02, CLR-UA-25: with single sign-on the EIAM lock-out policy applies; the application locks the local (break-glass) accounts after 3 failed attempts. | BDOI IT; Information Security |  |  |  |  | Open
Q-10 (C10) | Q.1 | Password history | Adopt 10 for the local accounts (a setting value, no change). Proposed behaviour: FRUM-004.01, FRUM-004.02: history of 8 for local accounts (value to confirm, UQ08). Available in BIBS: the number of previous passwords that may not be reused is a security setting, delivered at 10 (BDOI's text). | Information Security |  |  |  |  | Open
Q-11 (C11) | Q.1 | Password reset and forgotten password | SSO users: BDOI's rule (no reset in the application). Break-glass accounts: reset by a second administrator only; the self-service link switched off in production. Proposed behaviour: FRUM-004.01, FRUM-004.02: for local accounts, an administrator reset and a self-service reset link; none for SSO users. Available in BIBS: no forgotten-password link and reset by another System Administrator only (setting on by default, BDOI's text) or the self-service reset of local accounts. | Information Security; BDOI IT |  |  |  |  | Open
Q-12 (C12) | Q.1 | Detail of the sign-in error messages | Keep the single message of the local sign-in; keep the not-linked message of single sign-on (the identity is already proven by EIAM, and the user needs to know to call the administrator), for Information Security to confirm. Proposed behaviour: FRUM.001.01, FRUM.001.02: one message for a wrong password, a locked and a deactivated account ("Invalid user name or password"); FRUM.001.02, FRUM.001.06: "Your sign-in was accepted by your organisation, but it is not linked to an active user of this system. Contact your administrator." | Information Security |  |  |  |  | Open
Q-13 (C13) | Q.1 | Revocation on an SSO status change and open sessions | With option (a), a leaver from UIDM-ISC deactivates the user and ends the open sessions at once (change to the system); a deactivation request does the same on approval. Proposed behaviour: FRUM.003.02.01, FRUM.009.04, FRUM.003.02.01, FRUM.003.04: deactivation by a request or the dormant-user job; EIAM refuses a disabled BDO account at the next sign-in; the open session ends at the inactivity sign-out or the session expiry. Available in BIBS: access is revoked and restored from the Enterprise SSO status when the provisioning setting is on (default). | BDOI IT; Information Security |  |  |  |  | Open
Q-14 (C14) | Q.1 | Synchronisation status and on-demand synchronisation | Show on each user the last provisioning event (time, source, UIDM request number); refuse a failed provisioning call back to UIDM-ISC and alert the System Administrator; replace the on-demand synchronisation by a re-send from UIDM-ISC. Proposed behaviour: None; the UIDM-ISC option (a) pushes changes to the system; the Users screen shows the last sign-in. Available in BIBS: synchronisation from the Enterprise SSO runs on each event and on demand when the provisioning setting is on (default). | BDOI IT |  |  |  |  | Open
Q-15 (C15) | Q.1 | Supervisory and record-ownership access | Hold the data scope on the user record (unit, team, supervisor) as part of FRUM.002.03, with the values per persona from the User Access Matrix. Proposed behaviour: Roles and permissions only in the BRD-11 FRS; the record scope of each user (own, team, unit) is set in the data scope of the user and specified by each module FRS. | Process Owner (Business Administration) |  |  |  |  | Open
Q-16 (C16) | Q.1 | Conflicting permission combinations | Keep the rules at group-profile level (what one user may hold); BDOI lists the permission pairs it means and they become rules between profiles. Proposed behaviour: FRUM.006.03, FRUM.012.01: separation-of-duties rules name pairs of group profiles one user may not hold, maintained by the Business Administrator and authorised by Information Security; FRUM.006.01, FRUM.006.03 refuses a permission both added and removed. Available in BIBS: the conflicting permission combinations are rules maintained by Information Security under a second approval. | Information Security |  |  |  |  | Open
Q-17 (C17) | Q.1 | Second approval of privileged and out-of-hours changes | Add as FRUM.010.05; BDOI names the high-privilege profiles and the working hours. Proposed behaviour: FRUM.010.05: a change to a High or Admin profile, or one submitted or approved outside working hours, needs a second approver and raises an alert. | Information Security |  |  |  |  | Open
Q-18 (C18) | Q.1 | File names of the exports | Adopt BDOI's file names (a change of the download name). Proposed behaviour: FRUM.007.01, FRUM.007.02 to FRUM.008.01, FRUM.008.01 (2nd): report name, generated by, coverage and time generated in the header; the file name is not specified. Available in BIBS: the exports are named by BDOI's convention <name>_MMDDYYYY (setting on by default) or by the report code. | Process Owner (Business Administration) |  |  |  |  | Open
Q-19 (C19) | Q.1 | Role and IP address in the audit log | Add the role at the time and the source (IP) address to the audit entries (change to the system) and keep approved by and the request number; Annex H extended. Proposed behaviour: FRUM.008.01, FRUM.008.01 (2nd), FRUM.008.01, FRUM.008.04: date, activity, from, to, done by, approved by, request number; the session log keeps the sign-in method and second factor. | Information Security; BDOI IT |  |  |  |  | Open
Q-20 (C20) | Q.1 | Inactivity and timeout in the audit trail | Show the inactivity sign-out as action Inactivity and the session expiry as action Timeout in the User Access Audit Log. Proposed behaviour: FRUM.001.04, FRUM.001.05: the session log records the end reason (log-out, inactivity, session expiry, ended by an administrator, account locked); the audit log report can include log-ins and log-outs. | Information Security |  |  |  |  | Open
Q-21 (C21) | Q.1 | Deactivating a role that has members | Allow it, as both say, with the members listed on the request and notified. Proposed behaviour: FRUM.006.02.01, FRUM.006.04: the members lose its screens on implementation and are listed and notified; whether members must be moved first is open (UQ16, CLR-UA-07). | Process Owner (Business Administration) |  |  |  |  | Open
Q-22 (C22) | Q.1 | Approvers of group-profile requests | Add as FRUM.005.03; BDOI names the approvers (UQ02). Proposed behaviour: FRUM.005.01, FRUM.005.03: one or more approvers in order; all must approve; any can reject or return. | Process Owner (Business Administration) |  |  |  |  | Open
Q-23 (C23) | Q.1 | Effective date of access changes | Add as FRUM.009.10. Proposed behaviour: FRUM.009.10: a request may carry an effective date; approved before it, it waits as Scheduled and is applied on the date. | Process Owner (Business Administration) |  |  |  |  | Open
Q-24 (C24) | Q.1 | Bulk requests | Add as FRUM.011; with option (a) the bulk request serves the group-profile changes and the go-live load of users. Proposed behaviour: FRUM.011.01: a bulk request from a template, checked row by row, decided by one approver and applied line by line. | Process Owner (Business Administration); BDOI IT |  |  |  |  | Open
Q-25 (C25) | Q.1 | Notifications of access requests and changes | Add as FRUM.013.01. Proposed behaviour: FRUM.013.01: notices to the approver, the requester and the affected user, in the system and by e-mail. Available in BIBS: the notices of access requests are also e-mailed by each user's notification preference (setting on by default) or shown in the system only. | Process Owner (Business Administration) |  |  |  |  | Open
Q-26 (C26) | Q.1 | Dormant accounts | Add as FRUM.003.04 with the values of Information Security. Proposed behaviour: FRUM.003.02.01, FRUM.003.04: users without a sign-in for 90 days are deactivated by a daily job, with a notice 7 days before; System Administrators exempt. | Information Security |  |  |  |  | Open
Q-27 (C27) | Q.1 | AD group and roles | Hold the AD group for information and for the sign-in gate only; roles stay in the system. Proposed behaviour: CLR-UA-26: no Entra ID group is mapped to a role; roles change only through requests; a 'the system users' group may gate who reaches the system. | BDOI IT |  |  |  |  | Open
Q-28 (C28) | Q.1 | Fields of the user record | Take the union - add BDOI's hierarchy names, unit / segment, department, location and UIDM request number (change to the system for the fields not held) and keep the BRD's business unit group and user level. Proposed behaviour: FRUM.002.01, FRUM.009.02, FRUM.002.01, FRUM.002.03: user ID, Windows ID, full name, e-mail, home branch, business unit group, user level, group profiles, authorisation limit, status, last sign-in. | Process Owner (Business Administration); BDOI IT |  |  |  |  | Open
Q-29 (S01) | Q.2 | Mapping row BRD 4.001.1 | Read "System Administrator"; map to FRUM.001 (FRID.001 is not an item of this FRS). | System Analyst (BDO ITG) |  |  |  |  | Open
Q-30 (S02) | Q.2 | Mapping rows BRD 4.002.1 and 4.002.2 | Map to FRUM.005.05 and FRUM.005.06 of this FRS (FRID items belong to another document). | System Analyst (BDO ITG) |  |  |  |  | Open
Q-31 (S03) | Q.2 | Mapping row BRD 3.002.2 | Read "modify". | System Analyst (BDO ITG) |  |  |  |  | Open
Q-32 (S04) | Q.2 | Mapping row BRD 1.007.1 | Read "Cancel submitted request". | System Analyst (BDO ITG) |  |  |  |  | Open
Q-33 (S05) | Q.2 | Mapping row BRD 1.003.1.1 | Read the row as BRD 1.003.1; FRUM-004 (password maintenance) does not cover a modification request - map to FRUM.003.01 and FRUM.009.03. | System Analyst (BDO ITG) |  |  |  |  | Open
Q-34 (S06) | Q.2 | Reference to the report templates | Read "Annex B - Report template" (Annex C is the User Access Matrix). | System Analyst (BDO ITG) |  |  |  |  | Open
Q-35 (S07) | Q.2 | Numbering of FRUM-004 and FRUM-008 | Read the export item as FRUM.008.03 and the entries as FRUM.004 and FRUM.008; v1.2 keeps BDOI's numbers and adds FRUM.008.04 onwards. | System Analyst (BDO ITG) |  |  |  |  | Open
Q-36 (S08) | Q.2 | Data type of Modified by (Annex E) | Read "Text". | System Analyst (BDO ITG) |  |  |  |  | Open
Q-37 (S09) | Q.2 | Titles of Annexes F and G | Read Annex F as "User Group Profile Report Fields" and Annex G as "Group Profile Membership List Fields". | System Analyst (BDO ITG) |  |  |  |  | Open
Q-38 (S10) | Q.2 | Audit fields in FRUM.008.01 and Annex H | Add Activity and IP Address to Annex H (rows added in v1.2). | System Analyst (BDO ITG) |  |  |  |  | Open
Q-39 (S11) | Q.2 | Template instructions and placeholders | BDO ITG removes the instructions and the empty table and fills in the references; v1.2 adds the references it used in a sentence and leaves BDOI's text as it is. | System Analyst (BDO ITG) |  |  |  |  | Open
Q-40 (S12) | Q.2 | No Document Revision Log | v1.2 adds a Document Revision Log after the cover with the rows 1.1 (from the cover) and 1.2. | System Analyst (BDO ITG) |  |  |  |  | Open
Q-41 (BRD 1.002.1) | Q.3 | Mapping extended | Mapped to: FRUM.002; added in v1.2: FRUM.009.01, FRUM.009.02, FRUM.009.06. The enrolment request, its draft and the chosen approver of BRD 1.002 are specified in the system as FRUM.009 (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-42 (BRD 1.003.1.1) | Q.3 | Mapping extended | Mapped to: FRUM.003, FRUM.004; added in v1.2: FRUM.003.01, FRUM.009.03. FRUM-004 (password maintenance) does not cover a modification request (slip S05); the modification is FRUM.003.01 and the request FRUM.009.03. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-43 (BRD 1.004.1) | Q.3 | Mapping extended | Mapped to: FRUM.003; added in v1.2: FRUM.003.02.01, FRUM.009.04. The deactivation request of BRD 1.004 is specified as FRUM.009.04 (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-44 (BRD 1.005) | Q.3 | Mapping extended | Mapped to: FRUM.003; added in v1.2: FRUM.003.02.02, FRUM.009.05. The reactivation request of BRD 1.005 is specified as FRUM.009.05 (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-45 (BRD 1.006.1) | Q.3 | Mapping extended | Mapped to: c/o UIDM; added in v1.2: FRUM.009.07, FRUM.013.01. BDOI maps the row "c/o UIDM"; the correction of a returned request is specified in the system as FRUM.009.07, applicable if the request is raised in BDOI-BROKERSYS (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-46 (BRD 1.007.1) | Q.3 | Mapping extended | Mapped to: c/o UIDM; added in v1.2: FRUM.009.08. BDOI maps the row "c/o UIDM"; the cancellation is specified as FRUM.009.08 (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-47 (BRD 1.008.1) | Q.3 | Mapping extended | Mapped to: c/o UIDM; added in v1.2: FRUM.009.09, FRUM.013.01. BDOI maps the row "c/o UIDM"; the view of requests and the decision notice are specified as FRUM.009.09 and FRUM.013.01 (conflict C01). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-48 (BRD 1.009.1) | Q.3 | Mapping extended | Mapped to: c/o UIDM; added in v1.2: FRUM.011.01. BDOI maps the row "c/o UIDM"; the bulk request is specified as FRUM.011.01 (conflicts C01, C24). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-49 (BRD 2.002.1) | Q.3 | Mapping extended | Mapped to: c/o UIDM; added in v1.2: FRUM.010.01, FRUM.010.02, FRUM.010.03, FRUM.010.04, FRUM.010.05. BDOI maps the row "c/o UIDM"; review, approval, rejection, return and second approval are specified as FRUM.010 (conflicts C01, C17). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-50 (BRD 3.002.1) | Q.3 | Mapping extended | Mapped to: FRUM.005; added in v1.2: FRUM.005.02, FRUM.005.03, FRUM.005.04. The group-profile request, its approvers in order and the implementation of p.6 are specified as FRUM.005.02 to FRUM.005.04 (conflicts C03, C22). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-51 (BRD 3.002.2) | Q.3 | Mapping extended | Mapped to: FRUM.005; added in v1.2: FRUM.006.04, FRUM.005.03, FRUM.005.04. The change request of a group profile is specified as FRUM.006.04 (conflict C03). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-52 (BRD 3.002.3) | Q.3 | Mapping extended | Mapped to: FRUM.006; added in v1.2: FRUM.006.04, FRUM.005.03, FRUM.005.04. The deactivation request of a group profile is specified as FRUM.006.04 (conflict C03). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-53 (BRD 3.002.4) | Q.3 | Mapping extended | Mapped to: FRUM.006; added in v1.2: FRUM.006.04, FRUM.005.03, FRUM.005.04. The reactivation request of a group profile is specified as FRUM.006.04 (conflict C03). | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-54 (BRD 4.001.1) | Q.3 | Mapping extended | Mapped to: FRID.001; added in v1.2: FRUM.001. FRID.001 is not an item of this FRS (slip S01); the log-in of the System Administrator is FRUM.001. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-55 (BRD 4.002.1) | Q.3 | Mapping extended | Mapped to: FRID.005; added in v1.2: FRUM.005.05. FRID.005 is not an item of this FRS (slip S02); the profiles of the access personas are FRUM.005.05. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-56 (BRD 4.002.2) | Q.3 | Mapping extended | Mapped to: FRID.006; added in v1.2: FRUM.005.06. FRID.006 is not an item of this FRS (slip S02); the functions assigned to profiles are FRUM.005.06. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-57 (BRD 4.003.1) | Q.3 | Mapping extended | Mapped to: FRUM-008; added in v1.2: FRUM.008.04. The activities recorded for user access are listed in FRUM.008.04. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-58 | Q.3 | BRD lines added | 137 BRD lines added under the row of their function, each with the BRD text and the FRUM items that cover it; BDOI's rows are kept as they are. | System Analyst (BDO ITG) |  |  |  |  | Open
Q-59 (Annex E) | Q.4 | Fields added to Annex E | Rows added: Windows ID, Business Unit Group, User Level, Status, Last Action, Last Action by. The BRD asks for the actor of each action (3.003.1.6) and the user fields of NFR p.14; the BIBS User Access Report shows them. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-60 (Annex F) | Q.4 | Fields added to Annex F | Rows added: Date Created, Created by, Date Modified, Added / Modified / Deactivated / Reactivated by. BRD 3.003.2.3 to 3.003.2.6 ask for the dates and actors of each group profile; Annex F does not list them. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-61 (Annex H) | Q.4 | Fields added to Annex H | Rows added: Activity, IP Address, Approved By, Request No.. FRUM.008.01 lists Activity and IP Address, which Annex H omits (slip S10); approved by and the request number come from sample D of the BRD and the BIBS audit log. | System Analyst (BDO ITG); Process Owner (Business Administration) |  |  |  |  | Open
Q-62 | Q.4 | Screenshots of New Request | The screen offers the profile picker described in FRUM.009.02 and J.7 (profiles by business area, search, details, chosen profiles listed apart, Privileged marker, separation-of-duties warning). Resolved in version 1.3: every screenshot of Annex J was taken again on 10-Oct-2026 and shows the picker. | Process Owner (Business Administration) - for information |  |  |  |  | Open
Q-63 | Q.4 | Scope of FRUM.009 to FRUM.013 | New entries FRUM.009 to FRUM.013 specify what the BRD asks; their scope follows the decision on conflict C01 (requests in UIDM or in the system). | BDOI IT; Process Owner (Business Administration) |  |  |  |  | Open
Q-64 | Q.4 | Duplicate BRD IDs | The second occurrence is shown as "(2nd)" in the mapping and in Annex P; the printed IDs are kept. | ES-BPDS (BRD owner) |  |  |  |  | Open
Q-65 | Q.4 | Non-functional rows of the BRD | Annex P lists the rows that carry a function with the IDs UAM-NFR-nn of Annex X; the infrastructure rows are answered in the Technical Specification reviewed by BDOI IT. | BDOI IT |  |  |  |  | Open
Q-66 | Q.4 | User Access Matrix (Annex C) | BDOI issues the final matrix; the system holds it as group profiles created through group-profile requests (FRUM.005), and the configuration template of the matrix is provided with the BIBS sign-off set. | Process Owner (Business Administration); Information Security |  |  |  |  | Open
Q-67 | Q.4 | Password guidelines (Annex I) | The values of Annex M for the break-glass accounts are reconciled with the guidelines once BDOI shares them; single sign-on users follow EIAM. | Information Security |  |  |  |  | Open
Q-68 | Q.4 | Acceptance criteria of version 1.2 | The numbered acceptance criteria added under each item are the basis of the test cases of the Test Cases and Traceability workbook (Annex P); BDOI accepts or amends them with the review. | Process Owner (Business Administration); Information Security |  |  |  |  | Open
Q-69 | Q.5 | E-mail copy of the request notices | The notices of requests (NT-01 to NT-06) are given in the system (bell); Annex L of version 1.2 said they were also e-mailed by preference, which the system does not do today. Annex L is corrected and the e-mail copy is a point for decision (Annex Z). | Process Owner (Business Administration) |  |  |  |  | Open
Q-70 | Q.5 | Notices not listed in version 1.2 | The two notices of the reset of a break-glass authenticator app (NT-19, NT-20) are added to Annex T. | Information Security - for information |  |  |  |  | Open
Q-71 | Q.5 | Wording of three system texts | Proposed wording for BDOI's approval: NT-17 "New rule <rule>: <reason>" instead of "The new rule of rule <rule>"; NT-13 "(emergency role edit)" instead of the setting code shown today; NT-18: the system says "<user> requests a change from ... to ..." while Annex L of version 1.2 showed "asks to change it from"; Annex L now quotes the system and BDOI chooses the wording. | Process Owner (Business Administration) |  |  |  |  | Open
Q-72 | Q.5 | Approval times, reminders and escalation | Proposed: 2 working days per approval stage, 1 for the second approval and the implementation; a reminder on the next working day and escalation to the Business Administrator after 5 working days. Not available in the system today: the age of each request is shown on the Access Requests list and report. | Process Owner (Business Administration) |  |  |  |  | Open
Q-73 | Q.5 | Scheduled access review report | Proposed as best practice: the User Access Report and the User Access Audit Log of the month sent to Information Security on the first working day of each month. Not available today (reports run on demand). | Information Security |  |  |  |  | Open
Q-74 | Q.5 | Alert of a break-glass sign-in | FRUM.001.06 asks that Information Security is alerted at every break-glass sign-in. The system records the sign-in with its method in the audit trail today; the alert is planned for the release that switches single sign-on on. | Information Security |  |  |  |  | Open
Q-75 | Q.5 | Non-functional rows without an FR item | Annex X lists all 41 rows with how each is met; version 1.2 traced only the 25 rows that carry a function (Annex P). | BDOI IT - for information |  |  |  |  | Open
Q-76 | Q.5 | Open questions answered in BDOI's FRS | The earlier questions that BDOI's FRS answers are no longer asked; each is listed with the BDOI clause that answers it in the Test Cases and Traceability workbook (sheet Answered in the BDOI FRS). Where BDOI's answer differs from the BRD, the decision stays in Annex Q. | System Analyst (BDO ITG) - for information |  |  |  |  | Open
Q-77 | Q.5 | E-mail sender and footer | The e-mails are plain text without a footer; BDOI gives the sender address of each environment and, if required, its standard footer or disclaimer (requirements collection workbook). | BDOI IT; Process Owner (Business Administration) |  |  |  |  | Open

## Lists
Type | Priority | Status | Status
Beyond the BRD | High | Candidate - for decision | Open
Added by BDOI's FRS | Medium | Raised | Decided
Proposal for best practice | Low | Assessed | Withdrawn
Correction |  | Approved
Rejected
Scheduled
In test
Closed