## Cover
UAT WALKTHROUGH
Business Unit Walkthrough Users
BRD-11 User Access Maintenance - sign-in IDs for the walkthrough
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team | 12
Walkthrough script | The walkthrough of BRD-11 for the Business Unit (FRS Annex O) | 33
Legend
Pass
Fail
Blocked
Environment: BIBS DEV environment: https://dev.brokerverse.cloud. Passwords: Issued separately by the iorta TechNXT Project Team; no password is written in this workbook.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona | Business role of the FRS
Users | User name | As shown on the screens
Users | Sign-in ID | User ID to type on the Login page
Users | Group profiles | Role held
Users | Company / branch / unit
Users | What the user does in the walkthrough
Users | Menu path to start
Users | Menus the user should see | User Access Maintenance entries of the user's menu
Users | Walkthrough steps | Steps of the sheet Walkthrough script
Users | Password | Never written here
Walkthrough script | Walkthrough
Walkthrough script | Step
Walkthrough script | Persona
Walkthrough script | Sign-in ID
Walkthrough script | Action
Walkthrough script | Expected result
Walkthrough script | Result |  | Not run, Pass, Fail, Blocked
Walkthrough script | Done by
Walkthrough script | Date
Walkthrough script | Remarks

## Users
Users
BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team
Persona | User name | Sign-in ID | Group profiles | Company / branch / unit | What the user does in the walkthrough | Menu path to start | Menus the user should see | Walkthrough steps | Password
Requestor | Rhea Access Requestor | requestor | User Access Requestor | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / User Access Maintenance | Raises user access requests: enrol, modify, deactivate, reactivate, bulk; corrects and cancels them; views own requests | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests; User Access › Bulk Request; Help › My Profile (every user) | WT-A.1, WT-A.2, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5, WT-C.11, WT-C.12 | Issued separately by the iorta TechNXT Project Team
Approver | Ulysses Access Approver | uamapprover | User Access Approver | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / User Access Maintenance | Reviews and approves, rejects or returns requests assigned to him or her | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests; User Access › Bulk Request; User Access › Group Profile Requests; User Access › User Access Matrix; User Access › User Access Reports; Help › My Profile (every user) | WT-A.3, WT-A.4, WT-B.2, WT-B.5, WT-B.9 | Issued separately by the iorta TechNXT Project Team
Approver (New Business Approver | Andres Approver | approver | Approver (requests, workload) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / New Business | Approves the access and group-profile requests assigned to him or her, as the second approver in order | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests, Group Profile Requests, Bulk Request, User Access Matrix; Help › My Profile | WT-B.6, WT-C.6 | Issued separately by the iorta TechNXT Project Team
Second approver | Selina Second Approver | secapprover | User Access Second Approver | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / User Access Maintenance | Reviews privileged or out-of-hours changes after the first approval | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests; User Access › Group Profile Requests; Help › My Profile (every user) | WT-B.3 | Issued separately by the iorta TechNXT Project Team
Business Administrator | Bea Business Admin | badmin | Business Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Business Administration | Raises group-profile requests; generates the reports; maintains the separation-of-duties rules; uploads bulk requests; supports users | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests; User Access › Bulk Request; User Access › Group Profile Requests; User Access › User Access Matrix; User Access › Separation of Duties; User Access › User Access Reports; Administration › Audit Trail; Administration › System Parameters; Administration › Scheduled Jobs; Help › My Profile (every user) | WT-B.4 | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | admin | System Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / IT - System Administration | Implements approved group-profile requests; defines the UAM group profiles and their functions; unlocks users and resets passwords; audit logs | Setup & Administration › Administration › Roles & Permissions | Home › My Approvals; User Access › Access Requests; User Access › Bulk Request; User Access › Group Profile Requests; User Access › User Access Matrix; User Access › User Access Reports; Administration › Users; Administration › Identity Synchronisation; Administration › Roles & Permissions; Administration › Second Factor; Administration › Audit Trail; Administration › System Parameters; Administration › Scheduled Jobs; Help › My Profile (every user) | WT-B.7, WT-B.10, WT-C.7, WT-C.9 | Issued separately by the iorta TechNXT Project Team
Information Security Officer | Ingrid Security Officer | infosec | Information Security Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Information Security | Views the access requests, the group-profile requests and the User Access Matrix, and the audit trail; runs the user access reports; authorises the separation-of-duties rules; approves the changes of the security settings | Setup & Administration › User Access › Access Requests | Home › My Approvals; User Access › Access Requests; User Access › Group Profile Requests; User Access › User Access Matrix; User Access › Separation of Duties; User Access › User Access Reports; Administration › Second Factor; Administration › Audit Trail; Administration › System Parameters; Help › My Profile (every user) | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | auditor | Auditor | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Internal Audit | Views requests and runs the reports and the audit log | Reports › Reports › Report Centre | Home › My Approvals; User Access › Access Requests; User Access › Group Profile Requests; User Access › User Access Matrix; User Access › User Access Reports; Administration › Audit Trail; Administration › System Parameters; Administration › Scheduled Jobs; Help › My Profile (every user) | WT-A.8, WT-D.1, WT-D.2, WT-D.3 | Issued separately by the iorta TechNXT Project Team
Subject users of the requests (Marketing AO) | SIT Enrolled User | a013000101 | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Users whose access the requests enrol, change, deactivate or unlock; a013000101 is locked and unlocked in walkthrough C | Client & Policy › Clients › Clients | The menu of the Marketing Account Officer (no User Access entry); Help › My Profile | WT-C.8 | Issued separately by the iorta TechNXT Project Team
Subject users of the requests (Marketing AO) | SIT Leaver | a013000102 | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Users whose access the requests enrol, change, deactivate or unlock; a013000101 is locked and unlocked in walkthrough C | Client & Policy › Clients › Clients | The menu of the Marketing Account Officer (no User Access entry); Help › My Profile | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Subject users of the requests (Marketing AO) | SIT Transferee | a013000103 | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Users whose access the requests enrol, change, deactivate or unlock; a013000101 is locked and unlocked in walkthrough C | Client & Policy › Clients › Clients | The menu of the Marketing Account Officer (no User Access entry); Help › My Profile | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Subject users of the requests (Marketing AO) | SIT Team Lead | a013000104 | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Users whose access the requests enrol, change, deactivate or unlock; a013000101 is locked and unlocked in walkthrough C | Client & Policy › Clients › Clients | The menu of the Marketing Account Officer (no User Access entry); Help › My Profile | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team

## Walkthrough script
Walkthrough script
The walkthrough of BRD-11 for the Business Unit (FRS Annex O)
Walkthrough | Step | Persona | Sign-in ID | Action | Expected result | Result | Done by | Date | Remarks
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.1 | Requestor | requestor | Opens User Access › Access Requests › New Request, keeps Enrol new user, enters the user ID a013000196, the full name, e-mail, Windows ID and home branch, ticks Marketing Account Officer, chooses the approver Ulysses Access Approver, writes the justification and clicks Save Draft | Toast: AR-yyyy-nnnnnn saved as a draft; the request opens as Draft with Approver Chosen on submission | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.2 | Requestor | requestor | Clicks Edit Request, checks the data and clicks Submit | Toast: AR-yyyy-nnnnnn submitted; the status is Pending Approval and the History tab lists Saved and Submitted | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.3 | Approver | uamapprover | Opens the notice Access request AR-yyyy-nnnnnn to approve, or User Access › Access Requests | The request is on the Assigned to Me tab with its change: Create user a013000196 with group profiles Marketing Account Officer | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.4 | Approver | uamapprover | Opens the request, reads the Details tab (current and requested values), clicks Approve and Apply, adds a comment and confirms | User a013000196 was created, with the temporary password shown once to be given through a secure channel; the status is Approved | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.5 | Subject users of the requests (Marketing AO) | a013000196 | The new user opens BIBS and signs in with a013000196 and the temporary password | Change Your Password: Your password was set by an administrator. Choose your own password to continue. | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.6 | Subject users of the requests (Marketing AO) | a013000196 | Enters the temporary password as the current password and a personal password twice, and clicks Change Password | Toast: Password changed; the home page opens | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.7 | Subject users of the requests (Marketing AO) | a013000196 | Opens the sidebar and My Profile | The sidebar holds exactly the entries of the Marketing Account Officer (chapter 12); My Profile lists the group profile Marketing Account Officer and its permissions, and the first session | Not run
WT-A A new user from the enrolment request to the first sign-in with the menus of the persona | WT-A.8 | Auditor | auditor | Opens User Access Reports › User Access Audit Log for today, ticks Include Log-ins and Log-outs and clicks Run Report | Enroll New User a013000196 with the from and to values of the full name, e-mail and profiles, Done By and Approved By the Approver, the request number, and the Log-in of the new user | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.1 | Requestor | requestor | Opens a New Request of type Modify user for a013000196, ticks Marketing Team Leader / Head (approver) besides the current profile, chooses the approver, writes the justification and clicks Submit | The Group Profiles show (current) after Marketing Account Officer; toast AR-yyyy-nnnnnn submitted | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.2 | Approver | uamapprover | Opens the request: the Details tab shows the group profiles added; clicks Approve and Apply | The status is Approved; the user receives Your access changed in the app and by e-mail | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.3 | Second approver | secapprover | Opens AR-2026-900008 from the Second Approval tab: the tag Privilege increase, first approved by the Approver; clicks Second Approval and confirms | The status is Approved; the alert Privileged access change stays in the Alert inbox as evidence | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.4 | Business Administrator | badmin | Opens Group Profile Requests › New Group Profile Request, enters the code RENEWAL_ENQUIRY, the name and description, keeps the level Standard, ticks two permissions, adds the approvers Ulysses Access Approver then the New Business Approver, writes the justification and clicks Submit | Toast: AR-yyyy-nnnnnn submitted; the Approvers tab lists the two approvers in order | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.5 | Approver | uamapprover | Approves the group-profile request | The status stays Pending Approval; the request moves to the New Business Approver, who receives the notice | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.6 | Approver (New Business Approver | approver | Opens the request from My Approvals and approves it | The status is For Implementation; the System Administrators receive Access request AR-yyyy-nnnnnn to implement | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.7 | System Administrator | admin | Opens Roles & Permissions, finds the request under Approved Requests to Implement, clicks Implement Request and confirms | Toast: AR-yyyy-nnnnnn implemented; the profile appears in the matrix with its two permissions | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.8 | Requestor | requestor | Opens a New Request of type Deactivate user for a013000196, chooses the reason Resigned, leaves the effective date blank, chooses the approver and clicks Submit | Toast: AR-yyyy-nnnnnn submitted | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.9 | Approver | uamapprover | Approves the deactivation | The status is Approved; the user is Disabled and every open session of the user has ended | Not run
WT-B A change and a revocation under four eyes, and a group-profile change approved in order and implemented | WT-B.10 | System Administrator | admin | Opens Administration › Users with the status Disabled | a013000196 is listed Disabled with the profiles it held; Sessions shows the last session ended by the administrator | Not run
WT-C Refused cases and the messages the user sees | WT-C.1 | Requestor | requestor | Opens New Request, enters the user ID ab and clicks Submit without a full name, profile, approver or justification | Under the fields: Use 3 to 50 letters, digits, dots, dashes or underscores; Enter the full name of the new user; Select at least one role; Select the approver; Enter the justification. Nothing is saved | Not run
WT-C Refused cases and the messages the user sees | WT-C.2 | Requestor | requestor | Enters the user ID a01300019X with the other fields complete and clicks Submit | Under the user ID: The user ID must be a letter followed by nine digits, for example a013000196 | Not run
WT-C Refused cases and the messages the user sees | WT-C.3 | Requestor | requestor | Raises a Modify user request for a013000101, which already has a pending request, and clicks Submit | A request for user a013000101 is already waiting for approval, with its reference | Not run
WT-C Refused cases and the messages the user sees | WT-C.4 | Requestor | requestor | Raises a Modify user request for himself (requestor), ticks an additional profile and clicks Submit | You cannot change your own roles | Not run
WT-C Refused cases and the messages the user sees | WT-C.5 | Requestor | requestor | Enrols a new user with both the User Access Requestor and the User Access Approver profiles and clicks Submit | One user may not hold both User Access Requestor and User Access Approver (separation-of-duties rule SOD-900001): the rule authorised by Information Security | Not run
WT-C Refused cases and the messages the user sees | WT-C.6 | Approver (New Business Approver | approver | Opens AR-2026-900002, assigned to Ulysses Access Approver | The request shows no decision button for this approver; a decision would be refused: Request AR-2026-900002 is assigned to uamapprover for approval | Not run
WT-C Refused cases and the messages the user sees | WT-C.7 | System Administrator | admin | Clicks Implement Request on a group-profile request he raised himself | A request is implemented by someone other than its requester | Not run
WT-C Refused cases and the messages the user sees | WT-C.8 | Subject users of the requests (Marketing AO) | a013000101 | User a013000101 enters a wrong password three times, then the right one | Invalid user name or password each time, also for the right password: a locked account is refused with the same message as a wrong password; Users shows the lock to the System Administrator | Not run
WT-C Refused cases and the messages the user sees | WT-C.9 | System Administrator | admin | Opens Users with the status Locked and clicks Unlock on a013000101 | The user is Active again; the unlock is in the access change log | Not run
WT-C Refused cases and the messages the user sees | WT-C.10 | Subject users of the requests (Marketing AO) | a013000196 | The deactivated user a013000196 tries to sign in | Invalid user name or password, the same message as a wrong password; the attempt does not count towards the lock-out | Not run
WT-C Refused cases and the messages the user sees | WT-C.11 | Requestor | requestor | On My Profile, types a new password that is too short and has no symbol | Still needed: At least 10 characters; A symbol; Change Password stays disabled | Not run
WT-C Refused cases and the messages the user sees | WT-C.12 | Requestor | requestor | Enters the current password as the new password and clicks Change Password | You used this password recently. Choose another one | Not run
WT-D The evidence of access | WT-D.1 | Auditor | auditor | Opens User Access › User Access Matrix, By Action, and searches USER ACCESS | The User Access area by action class, with the permissions each profile holds: the Requestor creates and amends, the Approver approves, the Second Approver gives the second approval | Not run
WT-D The evidence of access | WT-D.2 | Auditor | auditor | Runs the User Group Profile Report for the profile UAM_APPROVER | The modules and tasks of the Approver with With Access, and the dates and actors of its creation and last change | Not run
WT-D The evidence of access | WT-D.3 | Auditor | auditor | Runs Group Profile Membership for MKT_AO as of today | The members of the Marketing Account Officer profile with who added each and when | Not run

## Lists
Result
Not run
Pass
Fail
Blocked