## Cover
INTERNAL COVERAGE
FRS Coverage in BIBS
BRD-11 User Access Maintenance - FRS in BDOI's template v1.3 (internal)
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.0
Date | 11 October 2026
Classification | Internal - iorta TechNXT
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Summary | Coverage of the FRS v1.3 in the BIBS environment, by item count and by acceptance criterion | 14
FR items | Every FR item and sub-item of the FRS v1.3 | 57
Acceptance criteria | Every acceptance criterion of the FRS v1.3 | 117
Legend
Yes | Available in the BIBS environment
Partly | Partly available (reason in the note)
No | Planned for a later release (reason in the note)
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
FRS Coverage in BIBS, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Summary | FR group | FR entry
Summary | FR items
Summary | Yes
Summary | Partly
Summary | No
Summary | % items available
Summary | % items available or partly
Summary | Acceptance criteria
Summary | Yes
Summary | Partly
Summary | No
Summary | % criteria available
Summary | % criteria available or partly
FR items | FR group
FR items | FR item
FR items | Title
FR items | Origin
FR items | BIBS reference FR
FR items | Available |  | Yes, Partly, No
FR items | Evidence
FR items | Note
Acceptance criteria | FR group
Acceptance criteria | FR item
Acceptance criteria | AC
Acceptance criteria | Acceptance criterion
Acceptance criteria | Available |  | Yes, Partly, No
Acceptance criteria | Test case
Acceptance criteria | Note

## Summary
Summary
Coverage of the FRS v1.3 in the BIBS environment, by item count and by acceptance criterion
FR group | FR items | Yes | Partly | No | % items available | % items available or partly | Acceptance criteria | Yes | Partly | No | % criteria available | % criteria available or partly
All FR items | 57 | 57 | 0 | 0 | 100 | 100 | 117 | 117 | 0 | 0 | 100 | 100
FRUM.001 | 6 | 6 | 0 | 0 | 100 | 100 | 17 | 17 | 0 | 0 | 100 | 100
FRUM.002 | 3 | 3 | 0 | 0 | 100 | 100 | 9 | 9 | 0 | 0 | 100 | 100
FRUM.003 | 6 | 6 | 0 | 0 | 100 | 100 | 12 | 12 | 0 | 0 | 100 | 100
FRUM-004 | 3 | 3 | 0 | 0 | 100 | 100 | 6 | 6 | 0 | 0 | 100 | 100
FRUM.005 | 6 | 6 | 0 | 0 | 100 | 100 | 12 | 12 | 0 | 0 | 100 | 100
FRUM.006 | 6 | 6 | 0 | 0 | 100 | 100 | 9 | 9 | 0 | 0 | 100 | 100
FRUM.007 | 3 | 3 | 0 | 0 | 100 | 100 | 6 | 6 | 0 | 0 | 100 | 100
FRUM-008 | 4 | 4 | 0 | 0 | 100 | 100 | 6 | 6 | 0 | 0 | 100 | 100
FRUM.009 | 10 | 10 | 0 | 0 | 100 | 100 | 20 | 20 | 0 | 0 | 100 | 100
FRUM.010 | 5 | 5 | 0 | 0 | 100 | 100 | 10 | 10 | 0 | 0 | 100 | 100
FRUM.011 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRUM.012 | 2 | 2 | 0 | 0 | 100 | 100 | 4 | 4 | 0 | 0 | 100 | 100
FRUM.013 | 2 | 2 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100

## FR items
FR items
Every FR item and sub-item of the FRS v1.3
FR group | FR item | Title | Origin | BIBS reference FR | Available | Evidence | Note
FRUM.001 | FRUM.001.01 | The system shall allow the user to access BDOI-BROKERSYS application using any BDO-issued | BDOI FRS v1.1 | FR-UA-001, FR-UA-002 | Yes | 17 test cases; Conformance register: FR-UA-001 [('Conformant', 4)]; FR-UA-002 [('Conformant', 2)] ¦ Walkthrough WT-A.5, WT-C.10, WT-C.8 | Comparison of BDOI's FRS with the platform: Both: any BDO-issued device and several browser tabs in one session (ours: activity in any tab keeps every tab signed in). The BDO-device rule is enforced by the BDO network and device policy, not by the application (CLR-UA-17).
FRUM.001 | FRUM.001.02 | Login and Role-Based Access | BDOI FRS v1.1 | FR-UA-001, FR-UA-003, FR-UA-051 | Yes | 23 test cases; Conformance register: FR-UA-001 [('Conformant', 4)]; FR-UA-003 [('Conformant', 4)]; FR-UA-051 [('Partly conformant', 2)] ¦ Walkthrough WT-A.5, WT-B.4, WT-B.7, WT-C.10, WT-C.7, WT-C.8, WT-D.1, WT-D.5 | Comparison of BDOI's FRS with the platform: Both sign in through the BDO single sign-on (EIAM) and grant access by role. Ours adds the account match by Windows ID or UPN, the refusal of an unlinked account and the named break-glass administrators with a local password and second factor; BDOI adds the supervisory view of assigned personnel and the denial on document repositories. Lock-out after 3 tries: EIAM's policy for SSO users, the application's for local accounts.
FRUM.001 | FRUM.001.03 | Inactivity Warning | BDOI FRS v1.1 | FR-UA-002 | Yes | 10 test cases; Conformance register: FR-UA-002 [('Conformant', 2)] | Inactivity warning after 15 minutes with BDOI's wording and the buttons Stay Logged In and Log Out (setting), any activity resets it (TC-FRUM.001.03 cases).
FRUM.001 | FRUM.001.04 | Session Timeout Warning | BDOI FRS v1.1 | FR-UA-002, FR-UA-004 | Yes | 15 test cases; Conformance register: FR-UA-002 [('Conformant', 2)]; FR-UA-004 [('Conformant', 3)] ¦ Walkthrough WT-A.7, WT-B.10, WT-C.11, WT-C.12, WT-C.9 | Sign-out after 30 minutes of inactivity with the page 'Your session timed out. Please log in again to continue' and Log In (setting); inactivity and time-out in the audit trail (TC-FRUM.001.04 cases).
FRUM.002 | FRUM.002.01 | New User Creation | BDOI FRS v1.1 | FR-UA-011, FR-UA-031, FR-UA-052 | Yes | 21 test cases; Conformance register: FR-UA-011 [('Partly conformant', 3)]; FR-UA-031 [('Conformant', 2)]; FR-UA-052 [('Partly conformant', 2)] ¦ Walkthrough WT-A.1, WT-A.2, WT-A.3, WT-A.4, WT-B.1, WT-B.10, WT-B.2, WT-B.3 | New users from the Enterprise SSO account and UIDM-ISC events, or by approved request (setting) (TC-FRUM.002.01 cases).
FRUM.002 | FRUM.002.02 | New User details sync to BDOI-BROKERSYS application | BDOI FRS v1.1 | - | Yes | 2 test cases; | Joiner events of UIDM-ISC create the user with the UIDM request number, directory details and last synchronisation; refused events alerted and reprocessed on the Identity Synchronisation screen (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT) (TC-FRUM.002.02 cases).
FRUM.003 | FRUM.003.01 | User Details Update | BDOI FRS v1.1 | FR-UA-012 | Yes | 7 test cases; Conformance register: FR-UA-012 [('Conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | User details updated from the Enterprise SSO directory on each event and with Synchronise Now on the Users screen (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT) (TC-FRUM.003.01 cases).
FRUM.003 | FRUM.003.02 | User Status Update | BDOI FRS v1.1 | - | Yes | 15 test cases; | Deactivation and reactivation of users from the Enterprise SSO status and by approved request (TC-FRUM.003.02 cases).
FRUM.003 | FRUM.003.02.01 | Deactivate User | BDOI FRS v1.1 | FR-UA-013, FR-UA-006 | Yes | 10 test cases; Conformance register: FR-UA-013 [('Partly conformant', 2)]; FR-UA-006 [('Partly conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Access revoked when the Enterprise SSO status is inactive (leaver event), open sessions ended (TC-FRUM.003.02.01 cases).
FRUM.003 | FRUM.003.02.02 | Reactivate User | BDOI FRS v1.1 | FR-UA-014 | Yes | 5 test cases; Conformance register: FR-UA-014 [('Partly conformant', 1)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Roles held before restored when the Enterprise SSO status is active again (TC-FRUM.003.02.02 cases).
FRUM.003 | FRUM.003.03 | User details sync to BDOI-BROKERSYS application | BDOI FRS v1.1 | - | Yes | 2 test cases; | Mover, leaver and status events of UIDM-ISC applied to the user; a disabled Enterprise SSO account cannot sign in (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT) (TC-FRUM.003.03 cases).
FRUM-004 | FRUM-004.01 | Password Expiry | BDOI FRS v1.1 | FR-UA-005, FR-UA-003 | Yes | 21 test cases; Conformance register: FR-UA-005 [('Conformant', 3)]; FR-UA-003 [('Conformant', 4)] ¦ Walkthrough WT-A.5, WT-A.6, WT-A.7, WT-C.10, WT-C.11, WT-C.12, WT-C.8 | Comparison of BDOI's FRS with the platform: Both: the password of SSO users belongs to the SSO platform, with expiry at least every 90 days. Ours keeps a local password policy (expiry 90 days, history, minimum age) for the break-glass administrators only.
FRUM-004 | FRUM-004.02 | Reset Password | BDOI FRS v1.1 | FR-UA-005 | Yes | 13 test cases; Conformance register: FR-UA-005 [('Conformant', 3)] ¦ Walkthrough WT-A.6, WT-A.7, WT-C.11, WT-C.12 | Password reset only by another System Administrator (setting); the last ten passwords cannot be reused (TC-FRUM-004.02 cases).
FRUM-004 | FRUM-004.03 | Forgot Password | BDOI FRS v1.1 | FR-UA-005 | Yes | 11 test cases; Conformance register: FR-UA-005 [('Conformant', 3)] ¦ Walkthrough WT-A.6, WT-A.7, WT-C.11, WT-C.12 | No forgotten-password function on the Login page (setting) (TC-FRUM-004.03 cases).
FRUM.005 | FRUM.005.01 | Role Creation and Permission configuration | BDOI FRS v1.1 | FR-UA-040, FR-UA-044, FR-UA-045, FR-UA-050, FR-UA-051 | Yes | 24 test cases; Conformance register: FR-UA-040 [('Conformant', 2)]; FR-UA-044 [('Conformant', 2)]; FR-UA-045 [('Conformant', 2)]; FR-UA-050 [('Partly conformant', 1)]; FR-UA-051 [('Partly conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.4, WT-B.5, WT-B.6, WT-B.7 | Comparison of BDOI's FRS with the platform: BDOI: authorised users create roles and configure permissions directly in the application (the request is made outside). Ours (BRD 3.002 and p.6): the Business Administrator requests the new group profile, approvers decide in order and the System Administrator implements it; each profile has a privilege level; a direct edit is an audited emergency only. Both: unique names, permissions by module, function and action, audit. BDOI adds record ownership and supervisory access rules.
FRUM.006 | FRUM.006.01 | Role Details Updates | BDOI FRS v1.1 | FR-UA-041, FR-UA-045 | Yes | 12 test cases; Conformance register: FR-UA-041 [('Partly conformant', 2)]; FR-UA-045 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.4, WT-B.5, WT-B.6, WT-B.7 | Comparison of BDOI's FRS with the platform: Same checks (unique name, members shown, the change applies to all members); ours through a change request approved and implemented.
FRUM.006 | FRUM.006.02 | Role Status Updates | BDOI FRS v1.1 | - | Yes | 9 test cases; | Comparison of BDOI's FRS with the platform: Heading of the role deactivation and reactivation items below.
FRUM.006 | FRUM.006.02.01 | Deactivate Role Status Updates | BDOI FRS v1.1 | FR-UA-042 | Yes | 6 test cases; Conformance register: FR-UA-042 [('Partly conformant', 2)] ¦ Walkthrough WT-B.4, WT-D.5 | Comparison of BDOI's FRS with the platform: Same effect: not assignable, history kept, members lose the access. Ours through a request that lists and notifies the members; whether a profile with members may be deactivated is open (UQ16); the System Administrator profile cannot be deactivated.
FRUM.006 | FRUM.006.02.02 | Reactivate Role Status Updates | BDOI FRS v1.1 | FR-UA-043 | Yes | 3 test cases; Conformance register: FR-UA-043 [('Partly conformant', 1)] ¦ Walkthrough WT-B.4, WT-D.5 | Comparison of BDOI's FRS with the platform: Both restore the role with its last permissions; ours through a request.
FRUM.006 | FRUM.006.03 | Permission Updates | BDOI FRS v1.1 | FR-UA-041, FR-UA-053 | Yes | 15 test cases; Conformance register: FR-UA-041 [('Partly conformant', 2)]; FR-UA-053 [('Partly conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.4, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4 | Permissions added and removed by the approved matrix; conflicting permission combinations refused by the rules of Information Security (TC-FRUM.006.03 cases).
FRUM.007 | FRUM.007.01 | View and filter reports | BDOI FRS v1.1 | FR-UA-060, FR-UA-061, FR-UA-062 | Yes | 12 test cases; Conformance register: FR-UA-060 [('Conformant', 2)]; FR-UA-061 [('Conformant', 1)]; FR-UA-062 [('Conformant', 1)] ¦ Walkthrough WT-A.8, WT-D.1, WT-D.2, WT-D.3, WT-D.4 | Comparison of BDOI's FRS with the platform: Same three reports; ours adds the as-of date, the User Access Audit Log and the Access Requests report; BDOI adds sorting and the total count, and refers to "Annex C - Report Templates" while the samples are in Annex B.
FRUM.007 | FRUM.007.02 | Export Reports | BDOI FRS v1.1 | FR-UA-060, FR-UA-061, FR-UA-062 | Yes | 10 test cases; Conformance register: FR-UA-060 [('Conformant', 2)]; FR-UA-061 [('Conformant', 1)]; FR-UA-062 [('Conformant', 1)] ¦ Walkthrough WT-A.8, WT-D.1, WT-D.2, WT-D.3, WT-D.4 | Exports to PDF, Excel and CSV named by BDOI's convention <name>_MMDDYYYY (setting) (TC-FRUM.007.02 cases).
FRUM-008 | FRUM.008.01 | Generate audit logs for compliance, monitoring, security, and audit purposes. | BDOI FRS v1.1 | FR-UA-064, FR-UA-063, FR-UA-004 | Yes | 14 test cases; Conformance register: FR-UA-064 [('Partly conformant', 2)]; FR-UA-063 [('Conformant', 2)]; FR-UA-004 [('Conformant', 3)] ¦ Walkthrough WT-A.2, WT-A.4, WT-A.7, WT-A.8, WT-B.10, WT-B.2, WT-B.3, WT-B.5 | Audit trail with module, Windows ID, role at the time, old and new values and source address (TC-FRUM.008.01 cases).
FRUM-008 | FRUM.008.02 | View audit trail records. | BDOI FRS v1.1 | FR-UA-063 | Yes | 6 test cases; Conformance register: FR-UA-063 [('Conformant', 2)] ¦ Walkthrough WT-A.8, WT-D.2, WT-D.3, WT-D.4 | Audit Trail page with the IP address and role columns, filters by action type and reference number, sortable (TC-FRUM.008.02 cases).
FRUM-008 | FRUM.008.01 (2nd) | Export audit trail records. | BDOI FRS v1.1 | FR-UA-063 | Yes | 5 test cases; Conformance register: FR-UA-063 [('Conformant', 2)] ¦ Walkthrough WT-A.8, WT-D.2, WT-D.3, WT-D.4 | Audit log export in BDOI's audit log template named Audit Logs_MMDDYYYY (TC-FRUM.008.01 cases).
FRUM.001 | FRUM.001.05 | Log Out and Session Log | Added in v1.2 | FR-UA-004 | Yes | 7 test cases; Conformance register: FR-UA-004 [('Conformant', 3)] ¦ Walkthrough WT-A.7, WT-B.10, WT-C.11, WT-C.12, WT-C.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.001 | FRUM.001.06 | Break-glass Administrators | Added in v1.2 | FR-UA-003 | Yes | 12 test cases; Conformance register: FR-UA-003 [('Conformant', 4)] ¦ Walkthrough WT-A.5, WT-C.10, WT-C.8 | Break-glass sign-in with password and second factor; Information Security alerted at each break-glass sign-in (setting of the recipients) (TC-FRUM.001.06 cases).
FRUM.002 | FRUM.002.03 | User Data and User ID Format | Added in v1.2 | FR-UA-052 | Yes | 7 test cases; Conformance register: FR-UA-052 [('Partly conformant', 2)] ¦ Walkthrough WT-B.10, WT-C.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.003 | FRUM.003.04 | Dormant Users | Added in v1.2 | FR-UA-006 | Yes | 6 test cases; Conformance register: FR-UA-006 [('Partly conformant', 2)] | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.005 | FRUM.005.02 | Group-Profile Request | Added in v1.2 | FR-UA-040 | Yes | 8 test cases; Conformance register: FR-UA-040 [('Conformant', 2)] ¦ Walkthrough WT-B.4, WT-D.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.005 | FRUM.005.03 | Approvers in Order | Added in v1.2 | FR-UA-044 | Yes | 7 test cases; Conformance register: FR-UA-044 [('Conformant', 2)] ¦ Walkthrough WT-B.4, WT-D.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.005 | FRUM.005.04 | Implementation by the System Administrator | Added in v1.2 | FR-UA-045 | Yes | 6 test cases; Conformance register: FR-UA-045 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.7, WT-B.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.005 | FRUM.005.05 | Group Profiles of the Access Personas (BRD 4.002.1) | Added in v1.2 | FR-UA-050 | Yes | 4 test cases; Conformance register: FR-UA-050 [('Partly conformant', 1)] ¦ Walkthrough WT-B.7, WT-C.7 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.005 | FRUM.005.06 | Functions Assigned to Group Profiles (BRD 4.002.2) | Added in v1.2 | FR-UA-051 | Yes | 5 test cases; Conformance register: FR-UA-051 [('Partly conformant', 2)] ¦ Walkthrough WT-B.4, WT-B.7, WT-C.7, WT-D.1, WT-D.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.006 | FRUM.006.04 | Group-Profile Change, Deactivation and Reactivation Requests | Added in v1.2 | FR-UA-041, FR-UA-042, FR-UA-043 | Yes | 14 test cases; Conformance register: FR-UA-041 [('Partly conformant', 2)]; FR-UA-042 [('Partly conformant', 2)]; FR-UA-043 [('Partly conformant', 1)] ¦ Walkthrough WT-B.4, WT-D.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.007 | FRUM.007.03 | Access Requests Report and User Access Matrix Export | Added in v1.2 | FR-UA-018, FR-UA-051 | Yes | 10 test cases; Conformance register: FR-UA-018 [('Conformant', 2)]; FR-UA-051 [('Partly conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.3, WT-A.4, WT-B.2, WT-B.3, WT-B.4, WT-B.5, WT-B.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM-008 | FRUM.008.04 | Activities Recorded for User Access | Added in v1.2 | FR-UA-063, FR-UA-064 | Yes | 9 test cases; Conformance register: FR-UA-063 [('Conformant', 2)]; FR-UA-064 [('Partly conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-A.8, WT-B.10, WT-B.2, WT-B.3, WT-B.5, WT-B.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.01 | Draft, Edit, Cancel and Submit a Request | Added in v1.2 | FR-UA-010 | Yes | 12 test cases; Conformance register: FR-UA-010 [('Conformant', 3)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.02 | Enrol a New User | Added in v1.2 | FR-UA-011 | Yes | 11 test cases; Conformance register: FR-UA-011 [('Partly conformant', 3)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.03 | Modify an Existing User | Added in v1.2 | FR-UA-012 | Yes | 7 test cases; Conformance register: FR-UA-012 [('Conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.04 | Deactivate a User | Added in v1.2 | FR-UA-013 | Yes | 5 test cases; Conformance register: FR-UA-013 [('Partly conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.05 | Reactivate a User | Added in v1.2 | FR-UA-014 | Yes | 4 test cases; Conformance register: FR-UA-014 [('Partly conformant', 1)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.06 | Choose the Approver | Added in v1.2 | FR-UA-015 | Yes | 6 test cases; Conformance register: FR-UA-015 [('Conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.07 | Apply Correction on a Returned Request | Added in v1.2 | FR-UA-016 | Yes | 6 test cases; Conformance register: FR-UA-016 [('Conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.08 | Cancel a Submitted Request | Added in v1.2 | FR-UA-017 | Yes | 7 test cases; Conformance register: FR-UA-017 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9, WT-C.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.09 | View Submitted Requests | Added in v1.2 | FR-UA-018 | Yes | 7 test cases; Conformance register: FR-UA-018 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.3, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.009 | FRUM.009.10 | Effective Date | Added in v1.2 | FR-UA-020 | Yes | 6 test cases; Conformance register: FR-UA-020 [('Conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.010 | FRUM.010.01 | Receive, List and Open Requests for Approval | Added in v1.2 | FR-UA-030 | Yes | 5 test cases; Conformance register: FR-UA-030 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.3, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.010 | FRUM.010.02 | Approve a Request | Added in v1.2 | FR-UA-031 | Yes | 6 test cases; Conformance register: FR-UA-031 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.3, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.010 | FRUM.010.03 | Reject a Request | Added in v1.2 | FR-UA-032 | Yes | 5 test cases; Conformance register: FR-UA-032 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9, WT-C.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.010 | FRUM.010.04 | Return a Request to the Requestor | Added in v1.2 | FR-UA-033 | Yes | 3 test cases; Conformance register: FR-UA-033 [('Conformant', 1)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9, WT-C.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.010 | FRUM.010.05 | Second Approval of Privileged and Out-of-Hours Changes | Added in v1.2 | FR-UA-034 | Yes | 8 test cases; Conformance register: FR-UA-034 [('Conformant', 2)] ¦ Walkthrough WT-A.2, WT-A.4, WT-B.2, WT-B.3, WT-B.5, WT-B.6, WT-B.9, WT-C.6 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.011 | FRUM.011.01 | Submit a Bulk Request | Added in v1.2 | FR-UA-019 | Yes | 8 test cases; Conformance register: FR-UA-019 [('Partly conformant', 2)] | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.012 | FRUM.012.01 | Separation-of-Duties Rules | Added in v1.2 | FR-UA-053 | Yes | 9 test cases; Conformance register: FR-UA-053 [('Partly conformant', 2)] ¦ Walkthrough WT-A.1, WT-B.1, WT-B.8, WT-C.1, WT-C.2, WT-C.3, WT-C.4, WT-C.5 | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.012 | FRUM.012.02 | Second Approval of Security Settings | Added in v1.2 | FR-UA-054 | Yes | 7 test cases; Conformance register: FR-UA-054 [('Partly conformant', 2)] | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.
FRUM.013 | FRUM.013.01 | Request and Access-Change Notices | Added in v1.2 | FR-UA-070 | Yes | 5 test cases; Conformance register: FR-UA-070 [('Not testable yet', 2)] | Notices in the system and, by each user's preference, by e-mail (setting) (TC-FRUM.013.01 cases).
FRUM.013 | FRUM.013.02 | Failed Batch Runs | Added in v1.2 | FR-UA-071 | Yes | 4 test cases; Conformance register: FR-UA-071 [('Conformant', 1)] | Shown working in the end-to-end run; criteria without an automated check are confirmed in UAT.

## Acceptance criteria
Acceptance criteria
Every acceptance criterion of the FRS v1.3
FR group | FR item | AC | Acceptance criterion | Available | Test case | Note
FRUM.001 | FRUM.001.01 | 1 | A user signed in on two tabs keeps working in the second tab after working only in the first for 20 minutes. | Yes | TC-FRUM-001.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.01 | 2 | A sign-in from a device that the BDO device policy does not allow is refused by EIAM before the system opens a session. | Yes | TC-FRUM-001.01-AC02 | Shown in TC-FRUM.001.01-AC02: the sign-in from a device outside the device policy is refused at the identity provider (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.001 | FRUM.001.02 | 1 | A user whose Windows ID matches an active user signs in at EIAM and sees only the screens of his or her group profiles; no password of the user is held in the system. | Yes | TC-FRUM-001.02-AC01 | Shown in TC-FRUM.001.02-AC01: single sign-on by Windows ID opens the screens of the user's group profiles, no password held (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.001 | FRUM.001.02 | 2 | An EIAM account that matches no active user is refused with the not-linked message, and the attempt is in the audit trail. | Yes | TC-FRUM-001.02-AC02 | Shown in TC-FRUM.001.02-AC02: an account linked to no active user is refused with the not-linked message and audited (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.001 | FRUM.001.02 | 3 | A user without the permission of an action does not see its button, and the action is refused with "You are not permitted to perform this action". | Yes | TC-FRUM-001.02-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.02 | 4 | The third wrong password of a break-glass account locks it; the next attempt with the right password is refused with "Invalid user name or password", and the Users screen shows the account as locked. | Yes | TC-FRUM-001.02-AC04 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.03 | 1 | After 15 minutes without activity the warning appears with the buttons "Stay Logged In" and "Log Out". | Yes | TC-FRUM-001.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.03 | 2 | Stay Logged In closes the warning and restarts the timer; Log Out ends the session and opens the Login page. | Yes | TC-FRUM-001.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.04 | 1 | After 30 minutes without activity the user is signed out, and the session log shows the reason inactivity. | Yes | TC-FRUM-001.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.04 | 2 | Opening a page of the ended session leads to the Login page and a new sign-in. | Yes | TC-FRUM-001.04-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.04 | 3 | 30 minutes before the fixed end of the session the user sees the session-end warning. | Yes | TC-FRUM-001.04-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.01 | 1 | An enrolment of user a013000196 with the profile Marketing Account Officer, approved by another user, creates the user, who can then sign in. | Yes | TC-FRUM-002.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.01 | 2 | An enrolment with an existing user ID is refused with "User a013000196 already exists". | Yes | TC-FRUM-002.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.01 | 3 | An enrolment with a Windows ID held by another user is refused. | Yes | TC-FRUM-002.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.01 | 4 | An inactive group profile is not offered. | Yes | TC-FRUM-002.01-AC04 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.02 | 1 | A joiner event of UIDM-ISC creates the user, and the user shows the UIDM request number and the time of the event. | Yes | TC-FRUM-002.02-AC01 | Shown in TC-FRUM.002.02-AC01: the joiner event creates the user with the UIDM request number and the event time (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.002 | FRUM.002.02 | 2 | A provisioning event for a Windows ID held by another user is refused, logged and alerted to the System Administrators. | Yes | TC-FRUM-002.02-AC02 | Shown in TC-FRUM.002.02-AC02: an event for a Windows ID of another user is refused, logged and alerted to the System Administrators.
FRUM.003 | FRUM.003.01 | 1 | An approved request moving a user from Marketing Team Lead to Processing Team Lead is applied, and the User Access Audit Log shows "Marketing Team Lead" to "Processing Team Lead". | Yes | TC-FRUM-003.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.01 | 2 | A change of the e-mail only leaves the group profiles unchanged. | Yes | TC-FRUM-003.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.02.01 | 1 | After the approved deactivation the user cannot sign in, and the User Access Report shows the deactivation with the approver. | Yes | TC-FRUM-003.02.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.02.01 | 2 | A deactivation with the effective date 30th is applied on the 30th. | Yes | TC-FRUM-003.02.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.02.01 | 3 | The open session of a deactivated user ends at the user's next action. | Yes | TC-FRUM-003.02.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.02.02 | 1 | After the approved reactivation the user signs in with the group profiles held before the deactivation. | Yes | TC-FRUM-003.02.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.02.02 | 2 | A locked user reactivated with "Also unlock the account" can sign in again. | Yes | TC-FRUM-003.02.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.03 | 1 | A leaver event of UIDM-ISC deactivates the user, and the user's next action is refused. | Yes | TC-FRUM-003.03-AC01 | Shown in TC-FRUM.003.03-AC01: the leaver event deactivates the user and the next action is refused (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.003 | FRUM.003.03 | 2 | A disabled EIAM account cannot sign in to the system. | Yes | TC-FRUM-003.03-AC02 | Shown in TC-FRUM.003.03-AC02: a disabled account cannot sign in (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM-004 | FRUM-004.01 | 1 | A break-glass administrator whose password is 91 days old must set a new one before the home page opens. | Yes | TC-FRUM-004.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM-004 | FRUM-004.01 | 2 | A single sign-on user is never asked for a password by the system. | Yes | TC-FRUM-004.01-AC02 | Shown in TC-FRUM-004.01-AC02: a single sign-on user is never asked for a password (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM-004 | FRUM-004.02 | 1 | A reset password must be changed at the next sign-in. | Yes | TC-FRUM-004.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM-004 | FRUM-004.02 | 2 | A new password equal to one of the last ten is refused. | Yes | TC-FRUM-004.02-AC02 | Shown in TC-FRUM-004.02-AC02: a password equal to one of the last ten is refused.
FRUM-004 | FRUM-004.02 | 3 | A password without a symbol is refused, and the screen lists "A symbol" as still needed. | Yes | TC-FRUM-004.02-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM-004 | FRUM-004.03 | 1 | The Login page shows no forgotten-password function when single sign-on is switched on. | Yes | TC-FRUM-004.03-AC01 | Shown in TC-FRUM-004.03-AC01: the Login page shows no forgotten-password function.
FRUM.005 | FRUM.005.01 | 1 | An approved request for a new role Processing Team Lead creates the role only when the System Administrator implements it. | Yes | TC-FRUM-005.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.01 | 2 | A role code that already exists is refused. | Yes | TC-FRUM-005.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.01 | 3 | A direct change of a role is refused while the emergency role edit is off. | Yes | TC-FRUM-005.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.01 | 1 | A request that adds one permission and removes another is implemented with exactly that difference. | Yes | TC-FRUM-006.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.01 | 2 | A second request for a role with a pending request is refused. | Yes | TC-FRUM-006.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.02.01 | 1 | After the implementation the members of the deactivated role lose its screens at their next action. | Yes | TC-FRUM-006.02.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.02.01 | 2 | The deactivated role is not offered on new requests. | Yes | TC-FRUM-006.02.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.02.02 | 1 | A reactivated role grants its permissions again to its members. | Yes | TC-FRUM-006.02.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.03 | 1 | A request that adds and removes the same permission is refused. | Yes | TC-FRUM-006.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.03 | 2 | A request giving one user both roles of an active separation-of-duties rule is refused with the names of the two roles. | Yes | TC-FRUM-006.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.01 | 1 | The User Access Report shows user a024000000 with the profile Processing Officer, created by the approver of its enrolment and modified by the approver of the later change. | Yes | TC-FRUM-007.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.01 | 2 | For the Marketing Account Officer profile the User Group Profile Report lists the Client Management tasks with With Access or No Access. | Yes | TC-FRUM-007.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.01 | 3 | The membership list shows every member of Marketing Team Lead with who added the member and when. | Yes | TC-FRUM-007.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.02 | 1 | The User Access Report exports to PDF, XLSX and CSV with the header of the report and only the filtered rows. | Yes | TC-FRUM-007.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.01 | 1 | Each attribute of a modified user has one log line with its from and to values and the request number. | Yes | TC-FRUM-008.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.01 | 2 | An attempt to change or delete a log entry is refused. | Yes | TC-FRUM-008.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.02 | 1 | A change of the group profile of a user appears as "Modify User Group Profile" from "Marketing Team Lead" to "Processing Team Lead" with the user who did it. | Yes | TC-FRUM-008.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.02 | 2 | Log-outs appear when the option is selected. | Yes | TC-FRUM-008.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.01 (2nd) | 1 | An export of the audit log for a date range holds only the records of that range and is itself recorded in the audit trail. | Yes | TC-FRUM-008.01-2ND-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.05 | 1 | After Log Out the User Access Audit Log shows the log-out with the user and the time. | Yes | TC-FRUM-001.05-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.05 | 2 | The Users screen shows a signed-in user as Online. | Yes | TC-FRUM-001.05-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.05 | 3 | With single sign-on, after Log Out opening the system again asks for the BDO sign-in. | Yes | TC-FRUM-001.05-AC03 | Shown in TC-FRUM.001.05-AC03: after Log Out the user is signed out at the identity provider and asked to sign in again (Enterprise SSO simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRUM.001 | FRUM.001.06 | 1 | With single sign-on switched on, a break-glass System Administrator signs in with the password and the second factor, and Information Security receives the alert. | Yes | TC-FRUM-001.06-AC01 | Shown in TC-FRUM.001.06-AC01: the break-glass sign-in with password and second factor alerts Information Security.
FRUM.001 | FRUM.001.06 | 2 | Another user cannot sign in with a local password. | Yes | TC-FRUM-001.06-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.001 | FRUM.001.06 | 3 | A wrong second-factor code is refused and counts as a failed attempt. | Yes | TC-FRUM-001.06-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.03 | 1 | The Users screen shows the Windows ID, business unit group, user level and status of each user. | Yes | TC-FRUM-002.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.03 | 2 | An unlock is listed in the User Access Audit Log with the System Administrator who did it. | Yes | TC-FRUM-002.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.002 | FRUM.002.03 | 3 | A System Administrator cannot change his or her own group profiles. | Yes | TC-FRUM-002.03-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.04 | 1 | A user without a sign-in for 91 days is deactivated with the reason "No sign-in for the dormancy period". | Yes | TC-FRUM-003.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.04 | 2 | A user whose deactivation is 7 days away receives the notice and stays active. | Yes | TC-FRUM-003.04-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.003 | FRUM.003.04 | 3 | A System Administrator without a sign-in for 91 days stays active. | Yes | TC-FRUM-003.04-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.02 | 1 | A request for a new profile with its permissions reaches For Implementation after its approvers approve. | Yes | TC-FRUM-005.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.02 | 2 | A request without a permission cannot be submitted. | Yes | TC-FRUM-005.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.03 | 1 | With two approvers, the second is notified only after the first approves. | Yes | TC-FRUM-005.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.03 | 2 | A rejection by the first approver ends the request; the second approver is not asked. | Yes | TC-FRUM-005.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.04 | 1 | An approved new profile exists only after the System Administrator implements it. | Yes | TC-FRUM-005.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.04 | 2 | The requester of a group-profile request cannot implement it. | Yes | TC-FRUM-005.04-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.05 | 1 | The Requestor, Approver and Business Administrator profiles exist with the permissions of Annex M. | Yes | TC-FRUM-005.05-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.06 | 1 | A role without the cancel permission does not show Cancel Request. | Yes | TC-FRUM-005.06-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.005 | FRUM.005.06 | 2 | The User Access Matrix shows the enrol permission under the module User Access, action Create. | Yes | TC-FRUM-005.06-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.04 | 1 | A draft change request is seen and edited only by its creator and is submitted later with the same number. | Yes | TC-FRUM-006.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.006 | FRUM.006.04 | 2 | A deactivation request shows the members of the role. | Yes | TC-FRUM-006.04-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.03 | 1 | The Access Requests report lists the requests of a date range with their status and approver. | Yes | TC-FRUM-007.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.007 | FRUM.007.03 | 2 | The User Access Matrix export lists every role against every permission. | Yes | TC-FRUM-007.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM-008 | FRUM.008.04 | 1 | Each activity of the walkthroughs of Annex O appears in the User Access Audit Log with its actor and time. | Yes | TC-FRUM-008.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.01 | 1 | A draft enrolment saved today, edited the next day and submitted becomes Pending Approval with the same number. | Yes | TC-FRUM-009.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.01 | 2 | A cancelled draft stays in My Requests as Cancelled with its reason. | Yes | TC-FRUM-009.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.01 | 3 | Another Requestor cannot open the draft. | Yes | TC-FRUM-009.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.01 | 4 | A submission without justification is refused with "Enter the justification". | Yes | TC-FRUM-009.01-AC04 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.02 | 1 | A request for a013000196 with the profile Marketing Account Officer, once approved, creates the user. | Yes | TC-FRUM-009.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.02 | 2 | Choosing two profiles of an active separation-of-duties rule shows the warning in the picker, and Submit is refused with "One user may not hold both <profile> and <profile>". | Yes | TC-FRUM-009.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.03 | 1 | The form shows the group profiles the user holds marked Current. | Yes | TC-FRUM-009.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.03 | 2 | A request that changes nothing is refused. | Yes | TC-FRUM-009.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.04 | 1 | The deactivation of a user already deactivated is refused with "User <user> is already deactivated". | Yes | TC-FRUM-009.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.05 | 1 | A reactivation request lists only deactivated or locked users. | Yes | TC-FRUM-009.05-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.06 | 1 | The drop-down lists neither the requester nor the user the request is about. | Yes | TC-FRUM-009.06-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.06 | 2 | Only the chosen approver receives the notice. | Yes | TC-FRUM-009.06-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.07 | 1 | A returned request shows the approver's remarks; after correction and re-submission it is Pending Approval again. | Yes | TC-FRUM-009.07-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.07 | 2 | The history lists both rounds with their remarks. | Yes | TC-FRUM-009.07-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.08 | 1 | A pending request cancelled by its creator disappears from the approver's list and shows Cancelled with the reason. | Yes | TC-FRUM-009.08-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.08 | 2 | An approved and applied request cannot be cancelled. | Yes | TC-FRUM-009.08-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.09 | 1 | A Requestor sees only his or her requests, with the current status. | Yes | TC-FRUM-009.09-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.09 | 2 | The History tab lists the submission, return, re-submission and approval with their remarks. | Yes | TC-FRUM-009.09-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.10 | 1 | A deactivation approved on the 10th with the effective date 15th is applied on the 15th. | Yes | TC-FRUM-009.10-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.009 | FRUM.009.10 | 2 | An effective date in the past is refused with "The effective date cannot be before today". | Yes | TC-FRUM-009.10-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.01 | 1 | The chosen approver receives a notice and finds the request under Assigned to Me. | Yes | TC-FRUM-010.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.01 | 2 | The detail of a role change shows Marketing Team Lead as current and Processing Team Lead as requested. | Yes | TC-FRUM-010.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.02 | 1 | An approved enrolment creates the user and shows the temporary password once. | Yes | TC-FRUM-010.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.02 | 2 | The requester cannot approve his or her own request. | Yes | TC-FRUM-010.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.03 | 1 | A rejection without a reason is refused. | Yes | TC-FRUM-010.03-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.03 | 2 | The requester sees the reason on the rejected request. | Yes | TC-FRUM-010.03-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.04 | 1 | A returned request appears in the requester's list for correction with the approver's remarks. | Yes | TC-FRUM-010.04-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.05 | 1 | A request that adds the System Administrator profile to a user needs a second approval. | Yes | TC-FRUM-010.05-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.05 | 2 | A request submitted at 21:00 on a weekday is flagged out of hours. | Yes | TC-FRUM-010.05-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.010 | FRUM.010.05 | 3 | The first approver cannot give the second approval. | Yes | TC-FRUM-010.05-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.011 | FRUM.011.01 | 1 | A file of three enrolments creates a draft batch of three lines; after approval the three users exist. | Yes | TC-FRUM-011.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.011 | FRUM.011.01 | 2 | A row with an existing user ID is reported before the batch is created. | Yes | TC-FRUM-011.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.011 | FRUM.011.01 | 3 | A file that is not Excel, CSV or TXT is refused. | Yes | TC-FRUM-011.01-AC03 | Available; confirmed with the acceptance test case in UAT.
FRUM.012 | FRUM.012.01 | 1 | A rule on the Requestor and Approver profiles, once authorised, refuses a request that gives one user both. | Yes | TC-FRUM-012.01-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.012 | FRUM.012.01 | 2 | The Business Administrator who created a rule cannot authorise it. | Yes | TC-FRUM-012.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.012 | FRUM.012.02 | 1 | A change of the lock-out attempts by the System Administrator applies only after the Information Security Officer approves it. | Yes | TC-FRUM-012.02-AC01 | Available; confirmed with the acceptance test case in UAT.
FRUM.012 | FRUM.012.02 | 2 | Switching on the emergency role edit needs the same approval. | Yes | TC-FRUM-012.02-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.013 | FRUM.013.01 | 1 | A returned request notifies the requester with the remarks. | Yes | TC-FRUM-013.01-AC01 | Notice in the system with the remarks (NT-05).
FRUM.013 | FRUM.013.01 | 2 | An applied deactivation notifies the affected user by e-mail. | Yes | TC-FRUM-013.01-AC02 | Available; confirmed with the acceptance test case in UAT.
FRUM.013 | FRUM.013.02 | 1 | A failed run of the effective changes sends an e-mail to the recipients with the error. | Yes | TC-FRUM-013.02-AC01 | Available; confirmed with the acceptance test case in UAT.

## Lists
Available
Yes
Partly
No