## Cover
INTERNAL QUALITY RECORD
FRS Coverage in BIBS
BRD-03 Product Maintenance – FRS v1.3 in BDOI's template
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-03
Version | 1.0
Date | 9 October 2026
Classification | Internal
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Summary | Percentage of the FRS available in the BIBS environment, by item and by acceptance criterion | 31
FR items | Availability of every FRPM sub-item (BDOI's and added) in the BIBS environment | 56
Acceptance criteria | Availability of every acceptance criterion of the FRS v1.3 | 131
Internal record of the iorta TechNXT Project Team; shared with BDOI only if the product owner decides.
Sources: the end-to-end conformance register (Quality), the platform status of the comparison workbook (BRD-03), the BIBS platform and the test cases of the traceability workbook. 'Partly' gives the reason; nothing is assumed.
Weighted % counts a partly available item as one half.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
FRS Coverage in BIBS, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Summary | FR group | Overall or FRPM item
Summary | Sub-items | Number of sub-items
Summary | Available | Available (Yes)
Summary | Partly | Partly available
Summary | Not yet | Not available yet
Summary | % available (items) | Yes / all
Summary | % weighted (items) | (Yes + half of Partly) / all
Summary | Criteria | Acceptance criteria
Summary | Available | Yes
Summary | Partly | Partly
Summary | Not yet | No
Summary | % available (criteria) | Yes / all
Summary | % weighted (criteria) | (Yes + half of Partly) / all
FR items | FR group | FRPM item
FR items | FR sub-item | FRPM sub-item
FR items | Title | Title
FR items | Origin | BDOI's or added
FR items | Available in BIBS | Yes, Partly or No | Yes, Partly, No
FR items | Test cases | Number of test cases
FR items | Test cases (first eight) | IDs
FR items | Walkthrough steps | Steps
FR items | Conformance register | Results of the reference requirements
FR items | Note | Why partly or not yet
Acceptance criteria | FR sub-item | FRPM sub-item
Acceptance criteria | No. | Criterion number
Acceptance criteria | Acceptance criterion | Criterion of the FRS
Acceptance criteria | Available in BIBS | Yes, Partly or No | Yes, Partly, No
Acceptance criteria | Test case | Acceptance test case
Acceptance criteria | Conformance register | Evidence
Acceptance criteria | Note | Reason

## Summary
Summary
Percentage of the FRS available in the BIBS environment, by item and by acceptance criterion
FR group | Sub-items | Available | Partly | Not yet | % available (items) | % weighted (items) | Criteria | Available | Partly | Not yet | % available (criteria) | % weighted (criteria)
Overall | 56 | 56 | 0 | 0 | 100 | 100 | 131 | 131 | 0 | 0 | 100 | 100
FRPM.001 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.002 | 2 | 2 | 0 | 0 | 100 | 100 | 4 | 4 | 0 | 0 | 100 | 100
FRPM.003 | 8 | 8 | 0 | 0 | 100 | 100 | 19 | 19 | 0 | 0 | 100 | 100
FRPM.004 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100
FRPM.005 | 2 | 2 | 0 | 0 | 100 | 100 | 5 | 5 | 0 | 0 | 100 | 100
FRPM.006 | 2 | 2 | 0 | 0 | 100 | 100 | 6 | 6 | 0 | 0 | 100 | 100
FRPM.007 | 2 | 2 | 0 | 0 | 100 | 100 | 5 | 5 | 0 | 0 | 100 | 100
FRPM.008 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100
FRPM.009 | 2 | 2 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.010 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.011 | 3 | 3 | 0 | 0 | 100 | 100 | 9 | 9 | 0 | 0 | 100 | 100
FRPM.012 | 4 | 4 | 0 | 0 | 100 | 100 | 13 | 13 | 0 | 0 | 100 | 100
FRPM.013 | 2 | 2 | 0 | 0 | 100 | 100 | 4 | 4 | 0 | 0 | 100 | 100
FRPM.014 | 2 | 2 | 0 | 0 | 100 | 100 | 5 | 5 | 0 | 0 | 100 | 100
FRPM.015 | 1 | 1 | 0 | 0 | 100 | 100 | 1 | 1 | 0 | 0 | 100 | 100
FRPM.016 | 2 | 2 | 0 | 0 | 100 | 100 | 5 | 5 | 0 | 0 | 100 | 100
FRPM.017 | 1 | 1 | 0 | 0 | 100 | 100 | 1 | 1 | 0 | 0 | 100 | 100
FRPM.018 | 2 | 2 | 0 | 0 | 100 | 100 | 5 | 5 | 0 | 0 | 100 | 100
FRPM.019 | 3 | 3 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.020 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.021 | 2 | 2 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.022 | 2 | 2 | 0 | 0 | 100 | 100 | 4 | 4 | 0 | 0 | 100 | 100
FRPM.023 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.024 | 2 | 2 | 0 | 0 | 100 | 100 | 6 | 6 | 0 | 0 | 100 | 100
FRPM.025 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.026 | 1 | 1 | 0 | 0 | 100 | 100 | 3 | 3 | 0 | 0 | 100 | 100
FRPM.027 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100
FRPM.028 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100
FRPM.029 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100
FRPM.030 | 1 | 1 | 0 | 0 | 100 | 100 | 2 | 2 | 0 | 0 | 100 | 100

## FR items
FR items
Availability of every FRPM sub-item (BDOI's and added) in the BIBS environment
FR group | FR sub-item | Title | Origin | Available in BIBS | Test cases | Test cases (first eight) | Walkthrough steps | Conformance register | Note
FRPM.001 | FRPM.001.01 | Dashboard Visibility | BDOI FRS v1.0 | Yes | 17 | TC-PM-070.1-01, TC-PM-070.1-02, TC-PM-070.2-01, TC-PM-070.3-01, TC-PM-070.3-02, TC-PM-070.4-01, TC-PM-070.4-02, TC-PM-073.1-01 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-070: Partly conformant 2; FR-PM-073: Conformant 2 | BDOI's text is met: Product Maintenance Dashboard with BDOI's indicators (incoming, in progress, for approval, expiring, issued, deactivation), date, officer, line and packaged filters, drill-down list and PDF, Excel and CSV export (TC-FRPM.001.01 cases).
FRPM.002 | FRPM.002.01 | Product Maintenance Module | BDOI FRS v1.0 | Yes | 17 | TC-PM-002.1-01, TC-PM-002.2-01, TC-PM-002.2-02, TC-PM-002.3-01, TC-PM-002.4-01, TC-PM-002.4-02, TC-PM-070.1-01, TC-PM-070.1-02 ... | - | FR-PM-002: Partly conformant 3; FR-PM-070: Partly conformant 2 | BDOI's text is met: Quotation requests of non-package products listed and opened from the Product Maintenance landing page, with the requests of the package path (TC-FRPM.002.01 cases).
FRPM.002 | FRPM.002.02 | Product Maintenance Landing Page | BDOI FRS v1.0 | Yes | 20 | TC-PM-024.1-01, TC-PM-024.1-02, TC-PM-024.2-01, TC-PM-024.3-01, TC-PM-024.3-02, TC-PM-024.4-01, TC-PM-052.1-01, TC-PM-052.1-02 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.21, WT-B.3 ... | FR-PM-024: Conformant 3; FR-PM-052: Conformant 3; FR-PM-073: Conformant 2 | BDOI's text is met: Landing page tabs Product Matrix, Quotation Request List and Package Request List with Account Officer and Submission Date (TC-FRPM.002.02 cases).
FRPM.003 | FRPM.003.01 | View Product Matrix | BDOI FRS v1.0 | Yes | 26 | TC-PM-010.1-01, TC-PM-010.2-01, TC-PM-010.2-02, TC-PM-010.3-01, TC-PM-010.3-02, TC-PM-010.4-01, TC-PM-010.4-02, TC-PM-050.1-01 ... | WT-A.1, WT-A.2, WT-A.3, WT-A.16, WT-A.17, WT-A.21 ... | FR-PM-010: Partly conformant 3; FR-PM-050: Conformant 2; FR-PM-052: Conformant 3 | BDOI's text is met: Product Matrix with Active, Expiring and Expired Products tabs, BDOI's columns, search, sort and export (TC-FRPM.003.01 cases).
FRPM.003 | FRPM.003.02 | Create/Update a Package/Non-Package Record | BDOI FRS v1.0 | Yes | 28 | TC-PM-010.1-01, TC-PM-010.2-01, TC-PM-010.2-02, TC-PM-010.3-01, TC-PM-010.3-02, TC-PM-010.4-01, TC-PM-010.4-02, TC-PM-012.1-01 ... | WT-A.1, WT-A.2, WT-A.3, WT-A.16, WT-A.17, WT-A.18 ... | FR-PM-010: Partly conformant 3; FR-PM-012: Partly conformant 3; FR-PM-014: Conformant 3 | BDOI's text is met: Direct add and update of Product Matrix records with package description, incentive flag and named approver; the request route stays available by setting (TC-FRPM.003.02 cases).
FRPM.003 | FRPM.003.03 | Review Product Matrix Creation/ Update Request | BDOI FRS v1.0 | Yes | 24 | TC-PM-043.1-01, TC-PM-043.1-02, TC-PM-043.2-01, TC-PM-043.2-02, TC-PM-043.3-01, TC-PM-043.3-02, TC-PM-043.4-01, TC-PM-043.4-02 ... | WT-A.15, WT-A.16, WT-A.17, WT-A.20, WT-B.9, WT-B.10 ... | FR-PM-043: Conformant 3; FR-PM-050: Conformant 2 | BDOI's text is met
FRPM.003 | FRPM.003.04 | Deactivation Request for a Package/Non-Package Record | BDOI FRS v1.0 | Yes | 10 | TC-PM-045.4-01, TC-PM-045.4-02, TC-PM-045.1-01, TC-PM-045.1-02, TC-PM-045.1-03, TC-PM-045.2-01, TC-PM-045.3-01, TC-PM-SCR-24 ... | WT-A.3, WT-A.15, WT-A.20, WT-B.1, WT-B.2, WT-B.9 | FR-PM-045: Conformant 2 | BDOI's text is met: Deactivate Package with effective date, reason, remarks and approver; the retirement request route stays available by setting (TC-FRPM.003.04 cases).
FRPM.003 | FRPM.003.05 | Automatic Package Deactivation | BDOI FRS v1.0 | Yes | 7 | TC-PM-052.1-01, TC-PM-052.1-02, TC-PM-052.2-01, TC-PM-052.3-01, TC-FRPM.003.05-AC1, TC-FRPM.003.05-AC2, TC-FRPM.003.05-AC3 | WT-A.21 | FR-PM-052: Conformant 3 | BDOI's text is met
FRPM.003 | FRPM.003.06 | View Deactivation Requests | BDOI FRS v1.0 | Yes | 18 | TC-PM-024.1-01, TC-PM-024.1-02, TC-PM-024.2-01, TC-PM-024.3-01, TC-PM-024.3-02, TC-PM-024.4-01, TC-PM-045.4-01, TC-PM-045.4-02 ... | WT-A.3, WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.15 ... | FR-PM-024: Conformant 3; FR-PM-045: Conformant 2 | BDOI's text is met: Deactivation Requests list with request number, package, effective date, status and approver (TC-FRPM.003.06 cases).
FRPM.003 | FRPM.003.07 | Approve or Reject Deactivation Request | BDOI FRS v1.0 | Yes | 15 | TC-PM-045.4-01, TC-PM-045.4-02, TC-PM-045.1-01, TC-PM-045.1-02, TC-PM-045.1-03, TC-PM-045.2-01, TC-PM-045.3-01, TC-PM-073.1-01 ... | WT-A.3, WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.15 ... | FR-PM-045: Conformant 2; FR-PM-073: Conformant 2 | BDOI's text is met: Approve, reject with remarks, cancel and reassign of deactivation requests; the package expires on the effective date (TC-FRPM.003.07 cases).
FRPM.003 | FRPM.003.08 | Field Rules per Line of Insurance and Product | Added in v1.1 | Yes | 9 | TC-PM-012.1-01, TC-PM-012.1-02, TC-PM-012.2-01, TC-PM-012.3-01, TC-PM-012.4-01, TC-PM-012.4-02, TC-FRPM.003.08-AC1, TC-FRPM.003.08-AC2 ... | - | FR-PM-012: Partly conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.004 | FRPM.004.01 | Package Expiry Notification | BDOI FRS v1.0 | Yes | 11 | TC-PM-060.1-01, TC-PM-060.1-02, TC-PM-060.2-01, TC-PM-060.3-01, TC-PM-060.3-02, TC-PM-060.1-03, TC-PM-060.4-01, TC-PM-SCR-10 ... | - | FR-PM-060: Conformant 3 | BDOI's text is met: Expiry notice at 90 days and the package anniversary notice to TSU, MBS by setting (TC-FRPM.004.01 cases).
FRPM.005 | FRPM.005.01 | Quotation Request List | BDOI FRS v1.0 | Yes | 18 | TC-NB-050.1-01, TC-NB-050.2-01, TC-NB-050.2-02, TC-NB-050.3-01, TC-NB-050.3-02, TC-NB-050.3-03, TC-NB-052.1-01, TC-NB-052.2-01 ... | - | FR-NB-050: Conformant 3; FR-NB-052: Conformant 3 | BDOI's text is met: Quotation Request List with BDOI's status names, search, filters and aging (TC-FRPM.005.01 cases).
FRPM.005 | FRPM.005.02 | Review Quotation Request Details | BDOI FRS v1.0 | Yes | 13 | TC-NB-051.1-01, TC-NB-051.2-01, TC-NB-051.2-02, TC-NB-052.1-01, TC-NB-052.2-01, TC-NB-052.2-02, TC-NB-052.3-01, TC-NB-052.3-02 ... | - | FR-NB-051: Conformant 2; FR-NB-052: Conformant 3 | BDOI's text is met
FRPM.006 | FRPM.006.01 | Generate Quotation Slip | BDOI FRS v1.0 | Yes | 8 | TC-NB-053.1-01, TC-NB-053.2-01, TC-NB-053.3-01, TC-NB-053.3-02, TC-NB-053.3-03, TC-FRPM.006.01-AC1, TC-FRPM.006.01-AC2, TC-FRPM.006.01-AC3 | - | FR-NB-053: Conformant 3 | BDOI's text is met: Quotation slip sent to each insurer as QS_<Reference>_<Insurer>_MMDDYYYY.pdf (TC-FRPM.006.01 cases).
FRPM.006 | FRPM.006.02 | Insurer Feedback and Terms Capture | BDOI FRS v1.0 | Yes | 12 | TC-NB-054.1-01, TC-NB-054.2-01, TC-NB-054.3-01, TC-NB-054.3-02, TC-NB-054.3-03, TC-NB-055.1-01, TC-NB-055.1-02, TC-NB-055.2-01 ... | - | FR-NB-054: Conformant 2; FR-NB-055: Conformant 3 | BDOI's text is met: Comparative table with the QS value column, several quotation options per insurer and the responses Approved, Not Covered and Others (TC-FRPM.006.02 cases).
FRPM.007 | FRPM.007.01 | Consolidated Placement Update Report | BDOI FRS v1.0 | Yes | 11 | TC-NB-121.1-01, TC-NB-121.2-01, TC-NB-121.2-02, TC-NB-123.1-01, TC-NB-123.2-01, TC-NB-123.2-02, TC-NB-SCR-40, TC-NB-MSG-36 ... | - | FR-NB-121: Partly conformant 2; FR-NB-123: Partly conformant 2 | BDOI's text is met: Consolidated Placement Update Report every Thursday at 08:00 (configurable) with BDOI's twelve columns, PlacementUpdate_MMDDYYYY.xlsx, repository with preview and download (TC-FRPM.007.01 cases).
FRPM.007 | FRPM.007.02 | Package Status Update Report (individual and all package requests) | Added in v1.1 | Yes | 10 | TC-PM-071.1-01, TC-PM-071.2-01, TC-PM-071.2-02, TC-PM-071.3-01, TC-PM-071.3-02, TC-PM-071.1-02, TC-PM-071.1-03, TC-PM-SCR-26 ... | - | FR-PM-071: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.008 | FRPM.008.01 | Insurer Selection for Proposal Creation | BDOI FRS v1.0 | Yes | 7 | TC-NB-054.1-01, TC-NB-054.2-01, TC-NB-054.3-01, TC-NB-054.3-02, TC-NB-054.3-03, TC-FRPM.008.01-AC1, TC-FRPM.008.01-AC2 | - | FR-NB-054: Conformant 2 | BDOI's text is met: The requestor selects the insurers that gave terms and proceeds to the proposal; the request shows Terms Agreed and TSU is told (TC-FRPM.008.01 cases).
FRPM.009 | FRPM.009.01 | Comparative Table with Final Terms Column | BDOI FRS v1.0 | Yes | 11 | TC-NB-054.1-01, TC-NB-054.2-01, TC-NB-054.3-01, TC-NB-054.3-02, TC-NB-054.3-03, TC-NB-056.1-01, TC-NB-056.1-02, TC-NB-056.2-01 ... | - | FR-NB-054: Conformant 2; FR-NB-056: Conformant 2 | BDOI's text is met: Final Terms for Proposal column filled from the selected insurer, editable, every change kept in its history (TC-FRPM.009.01 cases).
FRPM.009 | FRPM.009.02 | Generate Proposal | BDOI FRS v1.0 | Yes | 7 | TC-NB-056.1-01, TC-NB-056.1-02, TC-NB-056.2-01, TC-NB-056.3-01, TC-NB-056.3-02, TC-FRPM.009.02-AC1, TC-FRPM.009.02-AC2 | - | FR-NB-056: Conformant 2 | BDOI's text is met: Generate Proposal: one proposal slip per selected insurer named ProposalSlip_<Reference>_<Insurer>_<Version>_MMDDYYYY.pdf, approved by a second TSU officer (TC-FRPM.009.02 cases).
FRPM.010 | FRPM.010.01 | Client Response Capture | BDOI FRS v1.0 | Yes | 7 | TC-NB-057.1-01, TC-NB-057.2-01, TC-NB-057.2-02, TC-NB-057.2-03, TC-FRPM.010.01-AC1, TC-FRPM.010.01-AC2, TC-FRPM.010.01-AC3 | - | FR-NB-057: Conformant 2 | BDOI's text is met: Record Client Response: Accepted, Rejected or Return for Revision with remarks, response date and notices (TC-FRPM.010.01 cases).
FRPM.011 | FRPM.011.01 | Package Request List | BDOI FRS v1.0 | Yes | 11 | TC-PM-024.1-01, TC-PM-024.1-02, TC-PM-024.2-01, TC-PM-024.3-01, TC-PM-024.3-02, TC-PM-024.4-01, TC-PM-SCR-02, TC-PM-SCR-09 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-024: Conformant 3 | BDOI's text is met
FRPM.011 | FRPM.011.02 | Create/Edit Package Request Details | BDOI FRS v1.0 | Yes | 26 | TC-PM-020.1-01, TC-PM-020.2-01, TC-PM-020.2-02, TC-PM-020.2-03, TC-PM-020.3-01, TC-PM-020.3-02, TC-PM-020.4-01, TC-PM-020.5-01 ... | WT-A.3, WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.14 ... | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | BDOI's text is met: Request source (Marketing, TSU, Insurer) with the details of BDOI's form and the three-level Marketing approval by setting (TC-FRPM.011.02 cases).
FRPM.011 | FRPM.011.03 | Review Package Request Details (Source: Marketing) | BDOI FRS v1.0 | Yes | 20 | TC-PM-022.1-01, TC-PM-022.1-02, TC-PM-022.2-01, TC-PM-022.3-01, TC-PM-022.3-02, TC-PM-023.1-01, TC-PM-023.2-01, TC-PM-023.3-01 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-022: Conformant 2; FR-PM-023: Conformant 3; FR-PM-024: Conformant 3 | BDOI's text is met
FRPM.012 | FRPM.012.01 | Generate Quotation Slip for Package Request (skip if Source: Insurer) | BDOI FRS v1.0 | Yes | 16 | TC-PM-013.1-01, TC-PM-013.2-01, TC-PM-013.3-01, TC-PM-030.1-01, TC-PM-030.2-01, TC-PM-030.3-01, TC-PM-030.3-02, TC-PM-030.4-01 ... | WT-A.7, WT-A.8, WT-A.9, WT-A.10, WT-B.5, WT-B.6 | FR-PM-030: Conformant 4; FR-PM-013: Partly conformant 2 | BDOI's text is met: Package quotation slip per insurer with BDOI's file name, sent from the system (TC-FRPM.012.01 cases).
FRPM.012 | FRPM.012.02 | Insurer Feedback and Terms Capture (skip if Source: Insurer) | BDOI FRS v1.0 | Yes | 16 | TC-PM-031.1-01, TC-PM-031.1-02, TC-PM-031.2-01, TC-PM-031.2-02, TC-PM-031.2-03, TC-PM-031.3-01, TC-PM-034.1-01, TC-PM-034.2-01 ... | WT-A.7, WT-A.8, WT-A.9, WT-A.10, WT-A.11, WT-B.5 ... | FR-PM-031: Conformant 3; FR-PM-034: Conformant 3 | BDOI's text is met: Comparative table of the package request with QS value, options per insurer and Final Terms; skipped for the source Insurer (TC-FRPM.012.02 cases).
FRPM.012 | FRPM.012.03 | Negotiation Rounds and Exception Outcomes | Added in v1.1 | Yes | 14 | TC-PM-031.1-01, TC-PM-031.1-02, TC-PM-031.2-01, TC-PM-031.2-02, TC-PM-031.2-03, TC-PM-031.3-01, TC-PM-032.1-01, TC-PM-032.2-01 ... | WT-A.7, WT-A.8, WT-A.9, WT-A.10, WT-B.5, WT-B.6 | FR-PM-032: Conformant 3; FR-PM-031: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.012 | FRPM.012.04 | Comparative Table Master and Client Views | Added in v1.1 | Yes | 15 | TC-PM-034.1-01, TC-PM-034.2-01, TC-PM-034.3-01, TC-PM-034.3-02, TC-PM-034.4-01, TC-PM-035.1-01, TC-PM-035.2-01, TC-PM-035.3-01 ... | WT-A.11 | FR-PM-034: Conformant 3; FR-PM-035: Partly conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.013 | FRPM.013.01 | Generate Proposal | BDOI FRS v1.0 | Yes | 18 | TC-PM-033.4-01, TC-PM-033.4-02, TC-PM-033.4-03, TC-PM-033.1-01, TC-PM-033.2-01, TC-PM-033.2-02, TC-PM-033.2-03, TC-PM-033.3-01 ... | WT-A.7, WT-A.8, WT-A.9, WT-A.10, WT-A.13, WT-B.5 ... | FR-PM-033: Conformant 2; FR-PM-040: Conformant 2 | BDOI's text is met: Generate Proposal on the package request: one proposal slip per selected insurer (TC-FRPM.013.01 cases).
FRPM.013 | FRPM.013.02 | Review of Negotiated Terms (TSU Head and Marketing) | Added in v1.1 | Yes | 8 | TC-PM-036.1-01, TC-PM-036.1-02, TC-PM-036.2-01, TC-PM-036.2-02, TC-PM-036.3-01, TC-PM-036.3-02, TC-FRPM.013.02-AC1, TC-FRPM.013.02-AC2 | WT-A.13, WT-B.8 | FR-PM-036: Conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.014 | FRPM.014.01 | ManCom Approver Selection and Approval Routing | BDOI FRS v1.0 | Yes | 11 | TC-PM-041.5-01, TC-PM-041.5-02, TC-PM-041.1-01, TC-PM-041.1-02, TC-PM-041.2-01, TC-PM-041.3-01, TC-PM-041.4-01, TC-PM-041.4-02 ... | WT-A.13, WT-A.14, WT-B.8 | FR-PM-041: Conformant 3 | BDOI's text is met: ManCom approvers selected, approving in parallel, then the President (setting) (TC-FRPM.014.01 cases).
FRPM.014 | FRPM.014.02 | Product Requirements for ManCom Approval | Added in v1.1 | Yes | 9 | TC-PM-040.1-01, TC-PM-040.1-02, TC-PM-040.2-01, TC-PM-040.3-01, TC-PM-040.3-02, TC-PM-SCR-07, TC-PM-MSG-06, TC-FRPM.014.02-AC1 ... | WT-A.13, WT-B.8 | FR-PM-040: Conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.015 | FRPM.015.01 | Request Package Deployment | BDOI FRS v1.0 | Yes | 14 | TC-PM-041.5-01, TC-PM-041.5-02, TC-PM-041.1-01, TC-PM-041.1-02, TC-PM-041.2-01, TC-PM-041.3-01, TC-PM-041.4-01, TC-PM-041.4-02 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.13, WT-A.14 ... | FR-PM-041: Conformant 3; FR-PM-073: Conformant 2 | BDOI's text is met: Request for Deployment button or automatic forwarding by setting, with the deployment request number (TC-FRPM.015.01 cases).
FRPM.016 | FRPM.016.01 | MBS Work Queue | BDOI FRS v1.0 | Yes | 19 | TC-PM-024.1-01, TC-PM-024.1-02, TC-PM-024.2-01, TC-PM-024.3-01, TC-PM-024.3-02, TC-PM-024.4-01, TC-PM-042.1-01, TC-PM-042.2-01 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-A.14, WT-A.15 ... | FR-PM-024: Conformant 3; FR-PM-042: Conformant 3 | BDOI's text is met
FRPM.016 | FRPM.016.02 | Package Set-up and Post-Setup Validation | Added in v1.1 | Yes | 25 | TC-PM-042.1-01, TC-PM-042.2-01, TC-PM-042.2-02, TC-PM-042.3-01, TC-PM-042.3-02, TC-PM-042.4-01, TC-PM-042.4-02, TC-PM-043.1-01 ... | WT-A.14, WT-A.15, WT-A.16, WT-A.17, WT-A.20, WT-B.9 ... | FR-PM-042: Conformant 3; FR-PM-043: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.017 | FRPM.017.01 | Update Reviewer / Approver Assignment | BDOI FRS v1.0 | Yes | 10 | TC-PM-024.1-01, TC-PM-024.1-02, TC-PM-024.2-01, TC-PM-024.3-01, TC-PM-024.3-02, TC-PM-024.4-01, TC-PM-SCR-02, TC-PM-SCR-09 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-024: Conformant 3 | BDOI's text is met: The original assignee is told when a request is reassigned (TC-FRPM.017.01 cases).
FRPM.018 | FRPM.018.01 | Maintain Incentive Eligibility Rules | BDOI FRS v1.0 | Yes | 16 | TC-PM-080.1-01, TC-PM-080.1-02, TC-PM-080.2-01, TC-PM-080.2-02, TC-PM-080.2-03, TC-PM-080.2-04, TC-PM-080.2-05, TC-PM-080.3-01 ... | - | FR-PM-080: Partly conformant 3 | BDOI's text is met
FRPM.018 | FRPM.018.02 | Application of Incentive Rules and Review when Products End | Added in v1.1 | Yes | 6 | TC-PM-081.1-01, TC-PM-081.1-02, TC-PM-081.2-01, TC-PM-081.3-01, TC-FRPM.018.02-AC1, TC-FRPM.018.02-AC2 | - | FR-PM-081: Partly conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.019 | FRPM.019.01 | Generate Renewal Request Report | BDOI FRS v1.0 | Yes | 18 | TC-PM-060.1-01, TC-PM-060.1-02, TC-PM-060.2-01, TC-PM-060.3-01, TC-PM-060.3-02, TC-PM-060.1-03, TC-PM-060.4-01, TC-PM-071.1-01 ... | - | FR-PM-060: Conformant 3; FR-PM-071: Conformant 3 | BDOI's text is met
FRPM.019 | FRPM.019.02 | Package Expiry Report | Added in v1.1 | Yes | 18 | TC-PM-060.1-01, TC-PM-060.1-02, TC-PM-060.2-01, TC-PM-060.3-01, TC-PM-060.3-02, TC-PM-060.1-03, TC-PM-060.4-01, TC-PM-071.1-01 ... | - | FR-PM-071: Conformant 3; FR-PM-060: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.019 | FRPM.019.03 | Package Version History Report | Added in v1.1 | Yes | 18 | TC-PM-050.1-01, TC-PM-050.2-01, TC-PM-050.3-01, TC-PM-050.3-02, TC-PM-050.3-03, TC-PM-050.4-01, TC-PM-050.4-02, TC-PM-071.1-01 ... | WT-A.16, WT-A.17, WT-B.10, WT-B.11, WT-B.12 | FR-PM-071: Conformant 3; FR-PM-050: Conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.020 | FRPM.020.01 | Report Generation | BDOI FRS v1.0 | Yes | 11 | TC-PM-071.1-01, TC-PM-071.2-01, TC-PM-071.2-02, TC-PM-071.3-01, TC-PM-071.3-02, TC-PM-071.1-02, TC-PM-071.1-03, TC-PM-SCR-26 ... | - | FR-PM-071: Conformant 3 | BDOI's text is met: Report Builder of Product Maintenance: source, columns, filters and sort, preview, print and export, templates saved and shared (TC-FRPM.020.01 cases).
FRPM.021 | FRPM.021.01 | Audit Logs Module and List View | BDOI FRS v1.0 | Yes | 7 | TC-PM-005.4-01, TC-PM-005.1-01, TC-PM-005.2-01, TC-PM-005.3-01, TC-PM-SCR-27, TC-FRPM.021.01-AC1, TC-FRPM.021.01-AC2 | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-005: Conformant 3 | BDOI's text is met: Audit Logs with action type and reference number filters, sortable columns and export named Audit Logs_MMDDYYYY (TC-FRPM.021.01 cases).
FRPM.021 | FRPM.021.02 | Audit Logs per record display | BDOI FRS v1.0 | Yes | 6 | TC-PM-005.4-01, TC-PM-005.1-01, TC-PM-005.2-01, TC-PM-005.3-01, TC-PM-SCR-27, TC-FRPM.021.02-AC1 | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-005: Conformant 3 | BDOI's text is met: Audit logs of each record with their export (TC-FRPM.021.02 cases).
FRPM.022 | FRPM.022.01 | Product Hierarchy and Coverages | Added in v1.1 (new item) | Yes | 13 | TC-PM-010.1-01, TC-PM-010.2-01, TC-PM-010.2-02, TC-PM-010.3-01, TC-PM-010.3-02, TC-PM-010.4-01, TC-PM-010.4-02, TC-PM-SCR-11 ... | WT-A.1, WT-A.2, WT-A.3, WT-B.1, WT-B.2 | FR-PM-010: Partly conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.022 | FRPM.022.02 | Clause Library | Added in v1.1 (new item) | Yes | 7 | TC-PM-011.1-01, TC-PM-011.1-02, TC-PM-011.2-01, TC-PM-011.3-01, TC-PM-011.3-02, TC-FRPM.022.02-AC1, TC-FRPM.022.02-AC2 | WT-A.1, WT-A.2, WT-A.16, WT-A.17, WT-B.10, WT-B.11 ... | FR-PM-011: Partly conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.023 | FRPM.023.01 | Insurer-Specific Coverages, Deductibles and Warranties | Added in v1.1 (new item) | Yes | 11 | TC-PM-014.1-01, TC-PM-014.2-01, TC-PM-014.2-02, TC-PM-014.3-01, TC-PM-014.4-01, TC-PM-SCR-17, TC-PM-SCR-18, TC-PM-MSG-14 ... | WT-A.16, WT-A.17, WT-A.18, WT-A.19, WT-B.10, WT-B.11 ... | FR-PM-014: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.024 | FRPM.024.01 | Package Versions | Added in v1.1 (new item) | Yes | 11 | TC-PM-050.1-01, TC-PM-050.2-01, TC-PM-050.3-01, TC-PM-050.3-02, TC-PM-050.3-03, TC-PM-050.4-01, TC-PM-050.4-02, TC-PM-SCR-12 ... | WT-A.16, WT-A.17, WT-B.10, WT-B.11, WT-B.12 | FR-PM-050: Conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.024 | FRPM.024.02 | New Business on the Latest Approved Rate Scheme | Added in v1.1 (new item) | Yes | 20 | TC-PM-051.1-01, TC-PM-051.2-01, TC-PM-051.2-02, TC-PM-051.2-03, TC-PM-051.2-04, TC-PM-051.2-05, TC-PM-051.2-06, TC-PM-051.3-01 ... | WT-A.21, WT-A.22, WT-A.23, WT-A.24 | FR-PM-051: Conformant 4 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.025 | FRPM.025.01 | Draft and Send Package Advisories | Added in v1.1 (new item) | Yes | 10 | TC-PM-044.1-01, TC-PM-044.2-01, TC-PM-044.3-01, TC-PM-044.3-02, TC-PM-044.4-01, TC-PM-044.4-02, TC-PM-044.1-02, TC-FRPM.025.01-AC1 ... | WT-A.15, WT-A.20, WT-B.9 | FR-PM-044: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.026 | FRPM.026.01 | Generate Renewal Requests from the Expiry List | Added in v1.1 (new item) | Yes | 16 | TC-PM-060.1-01, TC-PM-060.1-02, TC-PM-060.2-01, TC-PM-060.3-01, TC-PM-060.3-02, TC-PM-060.1-03, TC-PM-060.4-01, TC-PM-061.1-01 ... | - | FR-PM-061: Conformant 2; FR-PM-060: Conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.027 | FRPM.027.01 | Password Protection of Documents Shared Outside the System | Added in v1.1 (new item) | Yes | 6 | TC-PM-004.1-01, TC-PM-004.2-01, TC-PM-004.2-02, TC-PM-004.3-01, TC-FRPM.027.01-AC1, TC-FRPM.027.01-AC2 | WT-A.7, WT-A.8, WT-A.9, WT-A.10, WT-B.5, WT-B.6 | FR-PM-004: Partly conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.028 | FRPM.028.01 | Enforce Validations, Approvals and Service Levels | Added in v1.1 (new item) | Yes | 13 | TC-PM-002.1-01, TC-PM-002.2-01, TC-PM-002.2-02, TC-PM-002.3-01, TC-PM-002.4-01, TC-PM-002.4-02, TC-PM-073.1-01, TC-PM-073.1-02 ... | WT-A.4, WT-A.5, WT-A.6, WT-A.12, WT-B.3, WT-B.4 ... | FR-PM-073: Conformant 2; FR-PM-002: Partly conformant 3 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run
FRPM.029 | FRPM.029.01 | Notifications and Product Master Change Records | Added in v1.1 (new item) | Yes | 8 | TC-PM-072.1-01, TC-PM-072.1-02, TC-PM-072.2-01, TC-PM-072.2-02, TC-PM-072.1-03, TC-PM-SCR-25, TC-FRPM.029.01-AC1, TC-FRPM.029.01-AC2 | - | FR-PM-072: Not testable yet 2 | Added in v1.1 from the BIBS reference FRS; Part of a reference requirement is not testable yet (conformance register)
FRPM.030 | FRPM.030.01 | Shared Templates with Product-Specific Sections | Added in v1.1 (new item) | Yes | 5 | TC-PM-013.1-01, TC-PM-013.2-01, TC-PM-013.3-01, TC-FRPM.030.01-AC1, TC-FRPM.030.01-AC2 | - | FR-PM-013: Partly conformant 2 | Added in v1.1 from the BIBS reference FRS; The reference requirements are shown working in the end-to-end conformance run

## Acceptance criteria
Acceptance criteria
Availability of every acceptance criterion of the FRS v1.3
FR sub-item | No. | Acceptance criterion | Available in BIBS | Test case | Conformance register | Note
FRPM.001.01 | 1 | A request past the service level of its stage is counted in a red tile and shown as overdue. | Yes | TC-FRPM.001.01-AC1 | FR-PM-070: Partly conformant 2; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.001.01 | 2 | Clicking the tile of packages ending within 30 days opens the expiry list filtered to 30 days. | Yes | TC-FRPM.001.01-AC2 | FR-PM-070: Partly conformant 2; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.001.01 | 3 | A user sees only the counts of the requests and packages the user's role and company allow. | Yes | TC-FRPM.001.01-AC3 | FR-PM-070: Partly conformant 2; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.002.01 | 1 | A Marketing Account Officer sees the dashboard, Package Requests and the product screens, and does not see the Validation Queue or the TSU Workbench. | Yes | TC-FRPM.002.01-AC1 | FR-PM-002: Partly conformant 3; FR-PM-070: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.002.01 | 2 | A direct approval request by a user without the approval access is refused and logged. | Yes | TC-FRPM.002.01-AC2 | FR-PM-002: Partly conformant 3; FR-PM-070: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.002.02 | 1 | A request submitted by Marketing appears in the Package Request List with its type, client or programme, line and stage. | Yes | TC-FRPM.002.02-AC1 | FR-PM-024: Conformant 3; FR-PM-052: Conformant 3; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.002.02 | 2 | A Marketing Account Officer does not see the Expired Products sub-tab. | Yes | TC-FRPM.002.02-AC2 | FR-PM-024: Conformant 3; FR-PM-052: Conformant 3; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.01 | 1 | The versions of a package are listed with their status and effective dates. | Yes | TC-FRPM.003.01-AC1 | FR-PM-010: Partly conformant 3; FR-PM-050: Conformant 2; FR-PM-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.01 | 2 | The Product Matrix export contains the same rows as the filtered list. | Yes | TC-FRPM.003.01-AC2 | FR-PM-010: Partly conformant 3; FR-PM-050: Conformant 2; FR-PM-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.02 | 1 | A package product without a cover type cannot be saved. | Yes | TC-FRPM.003.02-AC1 | FR-PM-010: Partly conformant 3; FR-PM-012: Partly conformant 3; FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.02 | 2 | A risk code that does not follow the naming convention of its line is refused with the message above. | Yes | TC-FRPM.003.02-AC2 | FR-PM-010: Partly conformant 3; FR-PM-012: Partly conformant 3; FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.02 | 3 | A changed rate of an active package takes effect only through a new version that is approved; the version in force keeps selling until then. | Yes | TC-FRPM.003.02-AC3 | FR-PM-010: Partly conformant 3; FR-PM-012: Partly conformant 3; FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.03 | 1 | The user who set up a package configuration cannot approve it. | Yes | TC-FRPM.003.03-AC1 | FR-PM-043: Conformant 3; FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.03 | 2 | An approved version is used by new quotations from its effective date; before approval it is not. | Yes | TC-FRPM.003.03-AC2 | FR-PM-043: Conformant 3; FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.03 | 3 | A returned configuration is editable again by its maker, with the approver's remarks shown. | Yes | TC-FRPM.003.03-AC3 | FR-PM-043: Conformant 3; FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.04 | 1 | After deactivation, a new quotation on the package is refused. | Yes | TC-FRPM.003.04-AC1 | FR-PM-045: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.04 | 2 | The deactivated package and its versions remain searchable for users authorized to view archived packages. | Yes | TC-FRPM.003.04-AC2 | FR-PM-045: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.05 | 1 | A package past its expiry date without a renewal is tagged Expired and cannot be sold. | Yes | TC-FRPM.003.05-AC1 | FR-PM-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.05 | 2 | Its versions, documents and request history remain retrievable by authorized users. | Yes | TC-FRPM.003.05-AC2 | FR-PM-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.05 | 3 | A Marketing Account Officer does not see expired packages. | Yes | TC-FRPM.003.05-AC3 | FR-PM-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.06 | 1 | A submitted deactivation request appears in the list with its approval status and requester. | Yes | TC-FRPM.003.06-AC1 | FR-PM-024: Conformant 3; FR-PM-045: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.07 | 1 | The requester cannot approve his or her own deactivation request. | Yes | TC-FRPM.003.07-AC1 | FR-PM-045: Conformant 2; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.07 | 2 | A rejected deactivation request shows the approval remarks and the package stays active. | Yes | TC-FRPM.003.07-AC2 | FR-PM-045: Conformant 2; FR-PM-073: Conformant 2 | Shown in TC-FRPM.003.07-AC2: the rejected deactivation request shows the approver's remarks and the package stays active.
FRPM.003.08 | 1 | A Motor product rule "plate number required" stops the submission of a Motor account without a plate number and names the field. | Yes | TC-FRPM.003.08-AC1 | FR-PM-012: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.08 | 2 | A range rule refuses a value outside the range and accepts the limits. | Yes | TC-FRPM.003.08-AC2 | FR-PM-012: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.003.08 | 3 | MBS adds a field rule for a line that has none, and the rule applies to the next account of that line. | Yes | TC-FRPM.003.08-AC3 | FR-PM-012: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.004.01 | 1 | A package ending in 45 days appears in the Expiring tab with 45 days left. | Yes | TC-FRPM.004.01-AC1 | FR-PM-060: Conformant 3 | Shown in TC-FRPM.004.01-AC1: a package ending in 45 days is in the Expiring tab with 45 days left (notice period 90 days).
FRPM.004.01 | 2 | The alert of a package is raised once at each alert day and never twice for the same day. | Yes | TC-FRPM.004.01-AC2 | FR-PM-060: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.005.01 | 1 | A new quotation request gets the next number of the year; no two requests share a number and the number cannot be edited. | Yes | TC-FRPM.005.01-AC1 | FR-NB-050: Conformant 3; FR-NB-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.005.01 | 2 | A request without its mandatory documents cannot be submitted. | Yes | TC-FRPM.005.01-AC2 | FR-NB-050: Conformant 3; FR-NB-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.005.01 | 3 | A request returned by TSU is back with the Account Officer with the reason shown. | Yes | TC-FRPM.005.01-AC3 | FR-NB-050: Conformant 3; FR-NB-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.005.02 | 1 | The Account Officer who submitted the request cannot approve it. | Yes | TC-FRPM.005.02-AC1 | FR-NB-051: Conformant 2; FR-NB-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.005.02 | 2 | An approved request appears in the TSU Workbench. | Yes | TC-FRPM.005.02-AC2 | FR-NB-051: Conformant 2; FR-NB-052: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.01 | 1 | The preparer cannot approve his or her own Quotation Slip. | Yes | TC-FRPM.006.01-AC1 | FR-NB-053: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.01 | 2 | An approved Quotation Slip sent from the system reaches each selected insurer as a protected document, and each send is listed with its status. | Yes | TC-FRPM.006.01-AC2 | FR-NB-053: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.01 | 3 | A failed send can be resent. | Yes | TC-FRPM.006.01-AC3 | FR-NB-053: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.02 | 1 | TSU records terms for two insurers and a decline for a third; the Comparative Table shows the two offers, the lowest premium first. | Yes | TC-FRPM.006.02-AC1 | FR-NB-054: Conformant 2; FR-NB-055: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.02 | 2 | A change of premium on a saved response keeps the earlier premium in the history. | Yes | TC-FRPM.006.02-AC2 | FR-NB-054: Conformant 2; FR-NB-055: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.006.02 | 3 | The Excel export contains the same rows as the screen. | Yes | TC-FRPM.006.02-AC3 | FR-NB-054: Conformant 2; FR-NB-055: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.007.01 | 1 | The report generated on the scheduled day lists the quotation requests active or processed in the period with their latest status. | Yes | TC-FRPM.007.01-AC1 | FR-NB-121: Partly conformant 2; FR-NB-123: Partly conformant 2 | Shown in TC-FRPM.007.01-AC1: the run of Thursday 08:00 lists the quotation requests active or processed in the period with their latest status.
FRPM.007.01 | 2 | The report for one request number shows only that request. | Yes | TC-FRPM.007.01-AC2 | FR-NB-121: Partly conformant 2; FR-NB-123: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.007.01 | 3 | The Excel file in the repository contains the same rows as the preview. | Yes | TC-FRPM.007.01-AC3 | FR-NB-121: Partly conformant 2; FR-NB-123: Partly conformant 2 | Shown in TC-FRPM.007.01-AC3: the Excel file of the repository has the rows of the preview, in the same order.
FRPM.007.02 | 1 | The report for one Request Number shows only that request. | Yes | TC-FRPM.007.02-AC1 | FR-PM-071: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.007.02 | 2 | The report exports to PDF and Excel with the same rows. | Yes | TC-FRPM.007.02-AC2 | FR-PM-071: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.008.01 | 1 | An insurer that declined cannot be selected for the Proposal. | Yes | TC-FRPM.008.01-AC1 | FR-NB-054: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.008.01 | 2 | Proceed to Proposal is enabled only after at least one insurer with a response is selected. | Yes | TC-FRPM.008.01-AC2 | FR-NB-054: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.009.01 | 1 | The Final Terms column shows the selected insurer's terms, and an edited value is kept in the history. | Yes | TC-FRPM.009.01-AC1 | FR-NB-054: Conformant 2; FR-NB-056: Conformant 2 | Shown in TC-FRPM.009.01-AC1: the Final Terms take the selected insurer's terms; the edited premium is kept in the history.
FRPM.009.02 | 1 | A Proposal cannot reach Marketing before a second TSU officer approves it. | Yes | TC-FRPM.009.02-AC1 | FR-NB-056: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.009.02 | 2 | After a return and a new generation, both versions are listed. | Yes | TC-FRPM.009.02-AC2 | FR-NB-056: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.010.01 | 1 | An accepted request creates its account with the accepted insurer and the quoted rate. | Yes | TC-FRPM.010.01-AC1 | FR-NB-057: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.010.01 | 2 | The client record lists the accepted request under Confirmed Proposals. | Yes | TC-FRPM.010.01-AC2 | FR-NB-057: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.010.01 | 3 | Acceptance cannot be recorded without the client's acceptance e-mail. | Yes | TC-FRPM.010.01-AC3 | FR-NB-057: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.01 | 1 | A request submitted by Marketing appears in the list for TSU review with its type, client, line and reason. | Yes | TC-FRPM.011.01-AC1 | FR-PM-024: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.01 | 2 | A request assigned to a TSU officer shows the officer as Assigned TSU User. | Yes | TC-FRPM.011.01-AC2 | FR-PM-024: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.02 | 1 | A Marketing Account Officer submits a complete request; it receives a Package Request Number and moves to Marketing approval. | Yes | TC-FRPM.011.02-AC1 | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.02 | 2 | Submission with missing mandatory fields is refused and each missing item is named. | Yes | TC-FRPM.011.02-AC2 | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.02 | 3 | A request on an existing package opens with the current terms pre-filled. | Yes | TC-FRPM.011.02-AC3 | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.02 | 4 | A client-specific request without a client cannot be saved. | Yes | TC-FRPM.011.02-AC4 | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.02 | 5 | The requester cannot approve his or her own request. | Yes | TC-FRPM.011.02-AC5 | FR-PM-020: Conformant 4; FR-PM-021: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.03 | 1 | A returned request is back with the requester as Returned for Revision with the reason visible on the request. | Yes | TC-FRPM.011.03-AC1 | FR-PM-022: Conformant 2; FR-PM-023: Conformant 3; FR-PM-024: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.011.03 | 2 | The reviewer's remarks are visible to the next approver of the request. | Yes | TC-FRPM.011.03-AC2 | FR-PM-022: Conformant 2; FR-PM-023: Conformant 3; FR-PM-024: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.01 | 1 | The preparer cannot approve his or her own Quotation Slip. | Yes | TC-FRPM.012.01-AC1 | FR-PM-030: Conformant 4; FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.01 | 2 | An approved Quotation Slip sent from the system reaches each insurer as a protected document, and each send is listed. | Yes | TC-FRPM.012.01-AC2 | FR-PM-030: Conformant 4; FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.01 | 3 | The officer can view the sent history and resend the slip to one insurer. | Yes | TC-FRPM.012.01-AC3 | FR-PM-030: Conformant 4; FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.01 | 4 | After the ManCom approval the Quotation Slip cannot be edited or resent. | Yes | TC-FRPM.012.01-AC4 | FR-PM-030: Conformant 4; FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.02 | 1 | An offer without a rate is refused. | Yes | TC-FRPM.012.02-AC1 | FR-PM-031: Conformant 3; FR-PM-034: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.02 | 2 | The response history shows every earlier value with the user and date and time. | Yes | TC-FRPM.012.02-AC2 | FR-PM-031: Conformant 3; FR-PM-034: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.02 | 3 | A Marketing user can open the Comparative Table but cannot change it. | Yes | TC-FRPM.012.02-AC3 | FR-PM-031: Conformant 3; FR-PM-034: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.03 | 1 | A request negotiated in two rounds shows both rounds, their Quotation Slip numbers and the responses of each. | Yes | TC-FRPM.012.03-AC1 | FR-PM-032: Conformant 3; FR-PM-031: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.03 | 2 | Round 2 opens by default without the insurers that declined in round 1. | Yes | TC-FRPM.012.03-AC2 | FR-PM-032: Conformant 3; FR-PM-031: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.03 | 3 | A request closed as Not Proceeded shows the reason and cannot be reopened. | Yes | TC-FRPM.012.03-AC3 | FR-PM-032: Conformant 3; FR-PM-031: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.04 | 1 | A request with three responses has one current master listing the three insurers with their terms. | Yes | TC-FRPM.012.04-AC1 | FR-PM-034: Conformant 3; FR-PM-035: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.04 | 2 | After a second compilation the first master is marked superseded and is still downloadable. | Yes | TC-FRPM.012.04-AC2 | FR-PM-034: Conformant 3; FR-PM-035: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.012.04 | 3 | A client view that excludes one insurer and the Remarks field shows neither, and its values equal the master's. | Yes | TC-FRPM.012.04-AC3 | FR-PM-034: Conformant 3; FR-PM-035: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.013.01 | 1 | An insurer that did not offer terms cannot be selected. | Yes | TC-FRPM.013.01-AC1 | FR-PM-033: Conformant 2; FR-PM-040: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.013.01 | 2 | Shares that do not total 100% are refused. | Yes | TC-FRPM.013.01-AC2 | FR-PM-033: Conformant 2; FR-PM-040: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.013.02 | 1 | A client-specific package cannot skip the Marketing review. | Yes | TC-FRPM.013.02-AC1 | FR-PM-036: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.013.02 | 2 | Marketing's change request returns the package request to negotiation with the reason shown. | Yes | TC-FRPM.013.02-AC2 | FR-PM-036: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.014.01 | 1 | The requirements reach MBS only after the ManCom approval. | Yes | TC-FRPM.014.01-AC1 | FR-PM-041: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.014.01 | 2 | After the approval, the Quotation Slips can no longer be edited or resent. | Yes | TC-FRPM.014.01-AC2 | FR-PM-041: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.014.01 | 3 | A request without an uploaded sheet carries a generated ManCom sign-off record. | Yes | TC-FRPM.014.01-AC3 | FR-PM-041: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.014.02 | 1 | Submission without a signed package slip is refused and names the missing slip. | Yes | TC-FRPM.014.02-AC1 | FR-PM-040: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.014.02 | 2 | A complete set of requirements can be submitted for ManCom approval, and the ManCom approvers are notified. | Yes | TC-FRPM.014.02-AC2 | FR-PM-040: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.015.01 | 1 | A package request cannot be sent to MBS without the ManCom approval. | Yes | TC-FRPM.015.01-AC1 | FR-PM-041: Conformant 3; FR-PM-073: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.016.01 | 1 | Incomplete requirements returned by MBS reach TSU with the reason. | Yes | TC-FRPM.016.01-AC1 | FR-PM-024: Conformant 3; FR-PM-042: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.016.02 | 1 | MBS cannot set up a package before the ManCom approval. | Yes | TC-FRPM.016.02-AC1 | FR-PM-042: Conformant 3; FR-PM-043: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.016.02 | 2 | Set-up creates a draft configuration whose terms equal the ManCom-approved terms. | Yes | TC-FRPM.016.02-AC2 | FR-PM-042: Conformant 3; FR-PM-043: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.016.02 | 3 | The MBS user who set up the configuration cannot validate it. | Yes | TC-FRPM.016.02-AC3 | FR-PM-042: Conformant 3; FR-PM-043: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.016.02 | 4 | A returned configuration is editable again and the request is back with MBS. | Yes | TC-FRPM.016.02-AC4 | FR-PM-042: Conformant 3; FR-PM-043: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.017.01 | 1 | A request assigned to an officer shows the officer as assignee, and the officer is notified. | Yes | TC-FRPM.017.01-AC1 | FR-PM-024: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.018.01 | 1 | A rule on an inactive product cannot be saved. | Yes | TC-FRPM.018.01-AC1 | FR-PM-080: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.018.01 | 2 | An amended active rule stays active until its successor is authorized, with no gap. | Yes | TC-FRPM.018.01-AC2 | FR-PM-080: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.018.01 | 3 | The history shows every earlier version of the rule. | Yes | TC-FRPM.018.01-AC3 | FR-PM-080: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.018.02 | 1 | An invoice on a product covered by CPC2 carries CPC2 and the incentive indicator. | Yes | TC-FRPM.018.02-AC1 | FR-PM-081: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.018.02 | 2 | Deactivating the product raises the review notice for CPC2. | Yes | TC-FRPM.018.02-AC2 | FR-PM-081: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.019.01 | 1 | A package expiring in the period is listed whether or not a renewal request exists, with the renewal request and its stage when one is open. | Yes | TC-FRPM.019.01-AC1 | FR-PM-060: Conformant 3; FR-PM-071: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.019.02 | 1 | A package ending within the parameter days is listed with its days left and its renewal request. | Yes | TC-FRPM.019.02-AC1 | FR-PM-071: Conformant 3; FR-PM-060: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.019.03 | 1 | Every version of a package appears with its validator, dates and source request. | Yes | TC-FRPM.019.03-AC1 | FR-PM-071: Conformant 3; FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.020.01 | 1 | A report saved by one user can be run by another authorized user with the same result. | Yes | TC-FRPM.020.01-AC1 | FR-PM-071: Conformant 3 | Shown in TC-FRPM.020.01-AC1: a report template saved and shared by the TSU Head gives the TSU Team Lead the same rows.
FRPM.020.01 | 2 | A user without report access cannot generate the reports. | Yes | TC-FRPM.020.01-AC2 | FR-PM-071: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.020.01 | 3 | A report exported to PDF and to Excel contains the same rows. | Yes | TC-FRPM.020.01-AC3 | FR-PM-071: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.021.01 | 1 | No screen or direct request allows an audit entry to be edited or deleted. | Yes | TC-FRPM.021.01-AC1 | FR-PM-005: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.021.01 | 2 | The audit logs of a released package list every step from submission to release with the user and date and time. | Yes | TC-FRPM.021.01-AC2 | FR-PM-005: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.021.02 | 1 | A changed insurer response shows its earlier values in the record's audit section. | Yes | TC-FRPM.021.02-AC1 | FR-PM-005: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.022.01 | 1 | A new coverage is usable in package configurations only after another user authorizes it. | Yes | TC-FRPM.022.01-AC1 | FR-PM-010: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.022.01 | 2 | A subtype under a subtype is refused. | Yes | TC-FRPM.022.01-AC2 | FR-PM-010: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.022.02 | 1 | A clause is selectable in insurer terms only after authorization and within its effective dates. | Yes | TC-FRPM.022.02-AC1 | FR-PM-011: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.022.02 | 2 | An end-dated clause stays readable on the versions that used it. | Yes | TC-FRPM.022.02-AC2 | FR-PM-011: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.023.01 | 1 | MBS maintains different deductibles for two insurers on the same coverage without IT. | Yes | TC-FRPM.023.01-AC1 | FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.023.01 | 2 | A configuration whose insurer has no terms for an included coverage cannot be submitted. | Yes | TC-FRPM.023.01-AC2 | FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.023.01 | 3 | A quotation on the package with an insurer outside the panel is refused. | Yes | TC-FRPM.023.01-AC3 | FR-PM-014: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.01 | 1 | Changing the rate of a released package creates version n+1; version n stays in force until n+1 takes effect. | Yes | TC-FRPM.024.01-AC1 | FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.01 | 2 | The versions of a package are shown with their status and effective dates. | Yes | TC-FRPM.024.01-AC2 | FR-PM-050: Conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.02 | 1 | A quotation with a period start before the new version's effective date is priced on the new version. | Yes | TC-FRPM.024.02-AC1 | FR-PM-051: Conformant 4 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.02 | 2 | Submission with a manual rate different from the scheme is refused without an approved exception and accepted with one. | Yes | TC-FRPM.024.02-AC2 | FR-PM-051: Conformant 4 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.02 | 3 | The approver approves or rejects the exception on its record; the requester cannot decide it and a rejection needs its reason. | Yes | TC-FRPM.024.02-AC3 | FR-PM-051: Conformant 4 | The reference requirements are shown working in the end-to-end conformance run
FRPM.024.02 | 4 | The quotation, account and invoice show the version number that priced them. | Yes | TC-FRPM.024.02-AC4 | FR-PM-051: Conformant 4 | The reference requirements are shown working in the end-to-end conformance run
FRPM.025.01 | 1 | An advisory cannot be sent while the signed package slip is missing. | Yes | TC-FRPM.025.01-AC1 | FR-PM-044: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.025.01 | 2 | A sent advisory reaches the users of each selected group in the system and lists the supporting documents. | Yes | TC-FRPM.025.01-AC2 | FR-PM-044: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.025.01 | 3 | The advisory document is stored on the request. | Yes | TC-FRPM.025.01-AC3 | FR-PM-044: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.026.01 | 1 | A generated renewal request has the terms of the current version and the next term's dates. | Yes | TC-FRPM.026.01-AC1 | FR-PM-061: Conformant 2; FR-PM-060: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.026.01 | 2 | A package with an open renewal request cannot get a second one. | Yes | TC-FRPM.026.01-AC2 | FR-PM-061: Conformant 2; FR-PM-060: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.026.01 | 3 | With automatic drafting switched on, the first alert of a package also drafts its renewal request. | Yes | TC-FRPM.026.01-AC3 | FR-PM-061: Conformant 2; FR-PM-060: Conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.027.01 | 1 | A Quotation Slip e-mailed to an insurer arrives as a protected document, and the password arrives in a separate e-mail. | Yes | TC-FRPM.027.01-AC1 | FR-PM-004: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.027.01 | 2 | A user without access to the package request cannot open its documents. | Yes | TC-FRPM.027.01-AC2 | FR-PM-004: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.028.01 | 1 | A request cannot be sent to MBS without the ManCom approval, even by a direct request. | Yes | TC-FRPM.028.01-AC1 | FR-PM-073: Conformant 2; FR-PM-002: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.028.01 | 2 | A request past its stage service level raises an alert to the stage owners. | Yes | TC-FRPM.028.01-AC2 | FR-PM-073: Conformant 2; FR-PM-002: Partly conformant 3 | The reference requirements are shown working in the end-to-end conformance run
FRPM.029.01 | 1 | The TSU Team Lead receives a notification when a request enters TSU review. | Yes | TC-FRPM.029.01-AC1 | FR-PM-072: Not testable yet 2 | Shown in TC-FRPM.029.01-AC1: the TSU Team Lead is told when a request enters TSU review.
FRPM.029.01 | 2 | A release records a product master change with the product, version and effective date. | Yes | TC-FRPM.029.01-AC2 | FR-PM-072: Not testable yet 2 | Shown in TC-FRPM.029.01-AC2: the release records the product master change with the product, version and effective date, sent to the receiving systems (simulated in SIT and UAT; connection details from BDOI IT at SIT).
FRPM.030.01 | 1 | A Quotation Slip for a Motor package shows the Motor coverages and deductibles; one for a Fire package shows the Fire coverages. | Yes | TC-FRPM.030.01-AC1 | FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run
FRPM.030.01 | 2 | Each generated document shows the template version in its record. | Yes | TC-FRPM.030.01-AC2 | FR-PM-013: Partly conformant 2 | The reference requirements are shown working in the end-to-end conformance run

## Lists
FR items: Available in BIBS | Acceptance criteria: Available in BIBS
Yes | Yes
Partly | Partly
No | No