## Start here
UX screen register BRD-6 Renewal
The screen images of the set for the BDOI UX Design team
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-6 Renewal (Drop 1)
Version and date |  | Version 2.0, 8 October 2026
For |  | BDOI UX Design team (UXD)
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | Open the sheet UX screen register: one row per screen image of the 07 deck and the 09 image package, with the screen, the personas, the flow and step, the state and the FRS section.
2 | Filter Changed in this issue = Y to see the images that are new or changed in this issue; the change reference names the comment or change request behind the change.
3 | Set the UXD status of each row (Not started, In design, Ready for review, Approved) and write the UXD comments; leave the other columns as issued.
4 | Import the CSV of the image package into the design tool to link each design to its screen image.
5 | Raise questions on the sheet Questions and comments; the project team answers there. At the next issue the UXD status and comments of the unchanged rows are carried over.
The register
Step | ID | Template | What it holds | Kept by | Rows entered | Mandatory cells missing | Status | Open
1 | UXR | UX screen register | 91 screen images of 34 screens; 0 changed in this issue | BDOI UX Design team |  |  | Not started | Open →
Changes in this issue
Change reference |  | What changed |  |  |  |  | Screens
- |  | First issue |  |  |  |  | -
Other sheets
Sheet |  |  | What it holds
Reference lists |  |  | The lists of the drop-downs: states and UXD statuses
Questions and comments |  |  | Questions and comments of the UX Design team, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## UX screen register
UXR UX screen register | [13 empty] | Step 1 of 1
← Back to Start here | Step 1 of 1. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per screen image of BRD-6 Renewal (the 07 deck and the 09 image package): the screen, personas, flow and step, state, FRS section and requirements, the image file, and the UXD status and comments of the UX Design team. Changed in this issue marks the images that are new or changed in this issue, with the change reference.
Provided by | BDOI UX Design team (UXD status and comments); iorta TechNXT project team (the other columns)
Due | With each design review; the rows are re-issued with each version of the set
How it is loaded | Kept by the UX Design team; at a new issue the UXD status and comments of the unchanged rows are carried over and the changed rows are flagged
Source | FRS v2.0 and the screens of the SIT environment (seed data)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (UX Design team lead) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | No | Yes | No | Yes | Conditional: when Changed in this issue is Y
Format | SCR-, NAV- or DO- and a number | Text | Text | Flow ID and title | Whole number | From the list | Section number | FR-... separated by commas | <Screen ID>_<state>.png | Text | From the list | Text | Y or N | Reference
Allowed values | Free entry | Free entry | Free entry | Free entry | A whole number from 1 to 99 | List State of a screen image: 12 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Not started, In design, Ready for review, Approved (list UXD status) | Free entry | Y or N | Free entry
What to enter | The screen of the image, as in the FRS and the deck | The title of the screen | The personas who see the screen in this state | The end-to-end flow that shows the image, if any | The step of the flow | The state of the screen on the image | The section of the FRS (or handbook) that specifies the screen | The functional requirements of the screen | The file of the image package (09) | The caption of the image | The status of the design of this screen state, kept by the UX Design team | Comments of the UX Design team on the screen state | Y when the image is new or changed in this issue of the set | The change reference (comment, change request or issue change) that changed the image
Row | Screen ID * | Screen name * | Persona(s) * | Flow | Step | State * | FRS section * | Requirement IDs | Image file * | What the image shows | UXD status * | UXD comments | Changed in this issue * | Change reference
Example – overwrite or delete | SCR-RN-01 | Renewal Home | Marketing Team Leader |  |  | Default | 13.1.1 | FR-RN-100, FR-RN-102 | SCR-RN-01_home.png | Renewal Home of the Marketing Team Leader: due dates, work queues, renewals by status and classification, workload | Not started |  | N
| SCR-RN-01 | Renewal Home | Marketing Team Leader | - |  | Default | 13.1.1 | FR-RN-100, FR-RN-102 | SCR-RN-01_home.png | Renewal Home of the Marketing Team Leader: due dates, work queues, renewals by status and classification, workload | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | - |  | Default | 13.1.2 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_list.png | Expiry List of the Marketing Team Leader, tab Unassigned Disposition: classification, flags and the actions of the tab | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | - |  | Filled | 13.1.2 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_generate.png | Generate Expiry List dialog with the expiry range | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | - |  | Filled | 13.1.2 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_filters.png | The Filters panel: the expiry range and the multi-select criteria | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | - |  | Filled | 13.1.2 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_assign.png | Assign Disposition dialog: the Account Officer of the unit and the reason of a re-assignment | Not started |  | N
| SCR-RN-03 | Renewal | Marketing Account Officer (Account Broker) | - |  | Read-only or locked | 13.1.3 | FR-RN-002, FR-RN-041, FR-RN-021, FR-RN-026 | SCR-RN-03_record.png | A renewal in review: header, flags, workflow header and the Details tab | Not started |  | N
| SCR-RN-04 | Renewal: Checks, Account History and Computations | Marketing Account Officer (Account Broker) | - |  | Read-only or locked | 13.1.4 | FR-RN-020, FR-RN-022, FR-RN-027, FR-RN-042, FR-RN-064 | SCR-RN-04_checks.png | Checks tab: the result of each check, the classification history and the endorsements | Not started |  | N
| SCR-RN-04 | Renewal: Checks, Account History and Computations | Marketing Account Officer (Account Broker) | - |  | Read-only or locked | 13.1.4 | FR-RN-020, FR-RN-022, FR-RN-027, FR-RN-042, FR-RN-064 | SCR-RN-04_history.png | Account History tab after View Account History: prior renewals, endorsements, payments and claims | Not started |  | N
| SCR-RN-04 | Renewal: Checks, Account History and Computations | Processing Officer (Broker) | - |  | Read-only or locked | 13.1.4 | FR-RN-020, FR-RN-022, FR-RN-027, FR-RN-042, FR-RN-064 | SCR-RN-04_computations.png | Computations tab: the expiring terms and the renewal terms | Not started |  | N
| SCR-RN-05 | Renewal: Insurer, Letters, Documents, Remarks and History | Marketing Team Leader, Marketing Account Officer (Account Broker), Processing Team Leader, Processing Officer (Broker), Contact Center, LAMD (loan status reports), Business Administrator, Auditor | - |  | Read-only or locked | 13.1.5 | FR-RN-004, FR-RN-044, FR-RN-071, FR-RN-080, FR-RN-084 | SCR-RN-05_letters.png | Letters tab: the Renewal Advice sent to the client | Not started |  | N
| SCR-RN-05 | Renewal: Insurer, Letters, Documents, Remarks and History | Marketing Account Officer (Account Broker) | - |  | Read-only or locked | 13.1.5 | FR-RN-004, FR-RN-044, FR-RN-071, FR-RN-080, FR-RN-084 | SCR-RN-05_history.png | History tab: the dispositions, assignments and overrides of the renewal | Not started |  | N
| SCR-RN-06 | My Dispositions | Marketing Account Officer (Account Broker) | - |  | Default | 13.2.1 | FR-RN-040, FR-RN-045, FR-RN-046 | SCR-RN-06_list.png | My Dispositions of the Account Officer with the quick filters | Not started |  | N
| SCR-RN-07 | Set Disposition, Add Remark and Re-open | Marketing Account Officer (Account Broker) | - |  | Filled | 13.2.2 | FR-RN-042, FR-RN-043, FR-RN-044, FR-RN-047, FR-RN-048 | SCR-RN-07_disposition.png | Set Disposition dialog: Not for Renewal with its reason and remarks | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | - |  | Pending approval | 13.2.3 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_list.png | TL Review: the dispositions of the unit waiting for review with the actions of the Team Leader | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | - |  | Filled | 13.2.3 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_override.png | Override dialog: the outstanding balance with the reason and remarks | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | - |  | Filled | 13.2.3 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_return.png | Return to Account Officer dialog with the reason and remarks | Not started |  | N
| SCR-RN-09 | Transfers | Marketing Team Leader, Marketing Account Officer (Account Broker) | - |  | Default | 13.2.4 | FR-RN-031, FR-RN-032 | SCR-RN-09_incoming.png | Transfers, Incoming: the request from another unit with its row action menu | Not started |  | N
| SCR-RN-10 | Processing Worklist | Processing Team Leader | - |  | Default | 13.3.1 | FR-RN-060, FR-RN-061, FR-RN-062, FR-RN-063, FR-RN-065 | SCR-RN-10_list.png | Processing Worklist of the Processing Team Leader with the actions of the tab | Not started |  | N
| SCR-RN-10 | Processing Worklist | Processing Team Leader | - |  | Filled | 13.3.1 | FR-RN-060, FR-RN-061, FR-RN-062, FR-RN-063, FR-RN-065 | SCR-RN-10_assign.png | Assign Processing Officer dialog | Not started |  | N
| SCR-RN-10 | Processing Worklist | Processing Officer (Broker) | - |  | Filled | 13.3.1 | FR-RN-060, FR-RN-061, FR-RN-062, FR-RN-063, FR-RN-065 | SCR-RN-10_return.png | Return to Marketing dialog: to the officer or the Team Leader, with the reason | Not started |  | N
| SCR-RN-11 | Insurer Batches | Processing Officer (Broker) | - |  | Default | 13.3.2 | FR-RN-070, FR-RN-071 | SCR-RN-11_list.png | Insurer Batches with the batch opened: the renewals and the columns of the extract | Not started |  | N
| SCR-RN-11 | Insurer Batches | Processing Officer (Broker) | - |  | Filled | 13.3.2 | FR-RN-070, FR-RN-071 | SCR-RN-11_new.png | New insurer batch dialog: the insurer and the expiry range | Not started |  | N
| SCR-RN-12 | Record Insurer Response | Processing Officer (Broker) | - |  | Filled | 13.3.3 | FR-RN-071 | SCR-RN-12_response.png | Record Insurer Response dialog: renew with revised terms | Not started |  | N
| SCR-RN-13 | Letters | Processing Officer (Broker) | - |  | Default | 13.4.1 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_list.png | Letters, tab RA Ready: the renewals whose Renewal Advice can be generated | Not started |  | N
| SCR-RN-13 | Letters | Processing Officer (Broker) | - |  | Filled | 13.4.1 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_generate.png | Generate Renewal Advice dialog: first or second notice and the confirmation of a late Renewal Advice | Not started |  | N
| SCR-RN-13 | Letters | Marketing Account Officer (Account Broker) | - |  | Default | 13.4.1 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_closing.png | Letters, tab NAL / NFR: the renewals waiting for their closing letter | Not started |  | N
| SCR-RN-14 | Record Acceptance | Marketing Team Leader, Marketing Account Officer (Account Broker), Processing Team Leader, Processing Officer (Broker), Contact Center, LAMD (loan status reports), Business Administrator, Auditor | - |  | Filled | 13.4.2 | FR-RN-084 | SCR-RN-14_accept.png | Record Acceptance dialog: acceptance by payment with its reference | Not started |  | N
| SCR-RN-15 | Follow-ups | Contact Center | - |  | Default | 13.4.3 | FR-RN-083, FR-RN-085 | SCR-RN-15_list.png | Follow-ups of the Contact Center, tab RA Sent | Not started |  | N
| SCR-RN-15 | Follow-ups | Contact Center | - |  | Filled | 13.4.3 | FR-RN-083, FR-RN-085 | SCR-RN-15_followup.png | Add Follow-up dialog: the channel, outcome, next action date and remarks | Not started |  | N
| SCR-RN-16 | LAMD Reports | LAMD (loan status reports) | - |  | Default | 13.4.4 | FR-RN-025 | SCR-RN-16_list.png | LAMD Reports with the upload of a paid-off or past-due loan report | Not started |  | N
| SCR-RN-17 | Renewal Setup: Non-renewable Risk Codes and Checks | Business Administrator | - |  | Default | 13.5.1 | FR-RN-020, FR-RN-024, FR-RN-112 | SCR-RN-17_risk.png | Non-renewable Risk Codes with their row action menu | Not started |  | N
| SCR-RN-17 | Renewal Setup: Non-renewable Risk Codes and Checks | Business Administrator | - |  | Default | 13.5.1 | FR-RN-020, FR-RN-024, FR-RN-112 | SCR-RN-17_checks.png | Checks: the sanitation checks with their severity | Not started |  | N
| SCR-RN-17 | Renewal Setup: Non-renewable Risk Codes and Checks | Business Administrator | - |  | Filled | 13.5.1 | FR-RN-020, FR-RN-024, FR-RN-112 | SCR-RN-17_new.png | New non-renewable risk code dialog | Not started |  | N
| SCR-RN-18 | Renewal Setup: Classification Rules and Decision Matrix | Business Administrator | - |  | Default | 13.5.2 | FR-RN-022, FR-RN-023, FR-RN-112 | SCR-RN-18_matrix.png | Decision Matrix: the versions with their row action menu and the rules of the active version | Not started |  | N
| SCR-RN-18 | Renewal Setup: Classification Rules and Decision Matrix | Business Administrator | - |  | Default | 13.5.2 | FR-RN-022, FR-RN-023, FR-RN-112 | SCR-RN-18_rules.png | Classification Rules: the versions and the rules of the active version | Not started |  | N
| SCR-RN-19 | Renewal Setup: Package Map, Package Choices and Propose Package | Processing Team Leader | - |  | Default | 13.5.3 | FR-RN-028 | SCR-RN-19_map.png | Package Map of the migrated policies with the row action menu | Not started |  | N
| SCR-RN-19 | Renewal Setup: Package Map, Package Choices and Propose Package | Processing Team Leader | - |  | Pending approval | 13.5.3 | FR-RN-028 | SCR-RN-19_choices.png | Package Choices waiting for a second team member | Not started |  | N
| SCR-RN-20 | Renewal Setup: Go-live | Processing Team Leader | - |  | Default | 13.5.4 | FR-RN-016 | SCR-RN-20_golive.png | Go-live tab of the Processing Team Leader: the uploads of the go-live and the corrections to approve | Not started |  | N
| SCR-RN-20 | Renewal Setup: Go-live | Business Administrator | - |  | Default | 13.5.4 | FR-RN-016 | SCR-RN-20_takeover.png | Go-live tab of the Business Administrator: the take-over | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | WT-A An expiring account from the Expiry List to the Team Leader's post | 1 | Success message | 14.1 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_wt-a-step-01.png | WT-A step 1: Opens the Expiry List, tab Unassigned Disposition, ticks the renewal of Pacific Harbor Logistics Inc. and clicks Assign Disposition: Arnel Account Officer, then Assign and Push | Not started |  | N
| SCR-RN-06 | My Dispositions | Marketing Account Officer (Account Broker) | WT-A An expiring account from the Expiry List to the Team Leader's post | 2 | Default | 14.1 | FR-RN-040, FR-RN-045, FR-RN-046 | SCR-RN-06_wt-a-step-02.png | WT-A step 2: Opens My Dispositions | Not started |  | N
| SCR-RN-04 | Renewal: Checks, Account History and Computations | Marketing Account Officer (Account Broker) | WT-A An expiring account from the Expiry List to the Team Leader's post | 3 | Read-only or locked | 14.1 | FR-RN-020, FR-RN-022, FR-RN-027, FR-RN-042, FR-RN-064 | SCR-RN-04_wt-a-step-03.png | WT-A step 3: Opens the renewal, tab Account History, and clicks View Account History | Not started |  | N
| SCR-RN-07 | Set Disposition, Add Remark and Re-open | Marketing Account Officer (Account Broker) | WT-A An expiring account from the Expiry List to the Team Leader's post | 4 | Success message | 14.1 | FR-RN-042, FR-RN-043, FR-RN-044, FR-RN-047, FR-RN-048 | SCR-RN-07_wt-a-step-04.png | WT-A step 4: Clicks Set Disposition: For Renewal with the remarks of the client's call, then Save | Not started |  | N
| SCR-RN-07 | Set Disposition, Add Remark and Re-open | Marketing Account Officer (Account Broker) | WT-A An expiring account from the Expiry List to the Team Leader's post | 5 | Success message | 14.1 | FR-RN-042, FR-RN-043, FR-RN-044, FR-RN-047, FR-RN-048 | SCR-RN-07_wt-a-step-05.png | WT-A step 5: Clicks Push | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | WT-A An expiring account from the Expiry List to the Team Leader's post | 6 | Validation error | 14.1 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_wt-a-step-06.png | WT-A step 6: Opens TL Review, tab For Review, ticks the renewal and clicks Post, then confirms | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | WT-A An expiring account from the Expiry List to the Team Leader's post | 7 | Success message | 14.1 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_wt-a-step-07.png | WT-A step 7: Clicks Override: Outstanding balance, reason Approved by the Team Leader, with remarks (the open claim and the endorsement are overridden the same way) | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | WT-A An expiring account from the Expiry List to the Team Leader's post | 8 | Success message | 14.1 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_wt-a-step-08.png | WT-A step 8: Clicks Post again and confirms | Not started |  | N
| SCR-RN-10 | Processing Worklist | Processing Team Leader | WT-B Processing, the insurer's answer and the Renewal Advice | 1 | Success message | 14.2 | FR-RN-060, FR-RN-061, FR-RN-062, FR-RN-063, FR-RN-065 | SCR-RN-10_wt-b-step-01.png | WT-B step 1: Opens the Processing Worklist, tab For Processing, ticks the renewal and clicks Assign PO: Paolo Processor, then Assign | Not started |  | N
| SCR-RN-11 | Insurer Batches | Processing Officer (Broker) | WT-B Processing, the insurer's answer and the Renewal Advice | 2 | Success message | 14.2 | FR-RN-070, FR-RN-071 | SCR-RN-11_wt-b-step-02.png | WT-B step 2: Opens Insurer Batches, clicks New Batch with Luzon Assurance Co. and the expiry date of the renewal, then Create Batch, and opens the batch | Not started |  | N
| SCR-RN-11 | Insurer Batches | Processing Officer (Broker) | WT-B Processing, the insurer's answer and the Renewal Advice | 3 | Success message | 14.2 | FR-RN-070, FR-RN-071 | SCR-RN-11_wt-b-step-03.png | WT-B step 3: Clicks Send to Insurer and confirms | Not started |  | N
| SCR-RN-12 | Record Insurer Response | Processing Officer (Broker) | WT-B Processing, the insurer's answer and the Renewal Advice | 4 | Success message | 14.2 | FR-RN-071 | SCR-RN-12_wt-b-step-04.png | WT-B step 4: Opens the renewal and clicks Record Insurer Response: Renew as is with the insurer reference, then Record | Not started |  | N
| SCR-RN-13 | Letters | Marketing Account Officer (Account Broker) | WT-B Processing, the insurer's answer and the Renewal Advice | 5 | Success message | 14.2 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_wt-b-step-05.png | WT-B step 5: Opens Letters, tab RA Ready, ticks the renewal, clicks Generate RA: First notice, then Generate | Not started |  | N
| SCR-RN-13 | Letters | Marketing Account Officer (Account Broker) | WT-B Processing, the insurer's answer and the Renewal Advice | 6 | Success message | 14.2 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_wt-b-step-06.png | WT-B step 6: Opens the tab RA Generated, ticks the renewal, clicks Send and confirms | Not started |  | N
| SCR-RN-15 | Follow-ups | Contact Center | WT-C The Contact Center follow-up and the client's acceptance | 1 | Default | 14.3 | FR-RN-083, FR-RN-085 | SCR-RN-15_wt-c-step-01.png | WT-C step 1: Opens Follow-ups, tab RA Sent | Not started |  | N
| SCR-RN-15 | Follow-ups | Contact Center | WT-C The Contact Center follow-up and the client's acceptance | 2 | Success message | 14.3 | FR-RN-083, FR-RN-085 | SCR-RN-15_wt-c-step-02.png | WT-C step 2: Opens the renewal and clicks Add Follow-up: Call, Client will renew, the next action date and the remarks, then Save | Not started |  | N
| SCR-RN-14 | Record Acceptance | Marketing Account Officer (Account Broker) | WT-C The Contact Center follow-up and the client's acceptance | 3 | Success message | 14.3 | FR-RN-084 | SCR-RN-14_wt-c-step-03.png | WT-C step 3: Opens the renewal and clicks Record Acceptance: Payment with the payment reference, then Record | Not started |  | N
| SCR-RN-05 | Renewal: Insurer, Letters, Documents, Remarks and History | Marketing Account Officer (Account Broker) | WT-C The Contact Center follow-up and the client's acceptance | 4 | Read-only or locked | 14.3 | FR-RN-004, FR-RN-044, FR-RN-071, FR-RN-080, FR-RN-084 | SCR-RN-05_wt-c-step-04.png | WT-C step 4: Opens the tab Letters | Not started |  | N
| SCR-RN-07 | Set Disposition, Add Remark and Re-open | Marketing Account Officer (Account Broker) | WT-D Not for Renewal and the closing letter | 1 | Success message | 14.4 | FR-RN-042, FR-RN-043, FR-RN-044, FR-RN-047, FR-RN-048 | SCR-RN-07_wt-d-step-01.png | WT-D step 1: Opens the renewal, views its account history, clicks Set Disposition: Not for Renewal, reason Loan fully paid, with remarks, then Save | Not started |  | N
| SCR-RN-08 | TL Review | Marketing Team Leader | WT-D Not for Renewal and the closing letter | 2 | Success message | 14.4 | FR-RN-050, FR-RN-051, FR-RN-023 | SCR-RN-08_wt-d-step-02.png | WT-D step 2: After the Account Officer's push, ticks the renewal on TL Review, clicks Post and confirms | Not started |  | N
| SCR-RN-13 | Letters | Marketing Account Officer (Account Broker) | WT-D Not for Renewal and the closing letter | 3 | Success message | 14.4 | FR-RN-080, FR-RN-081, FR-RN-082, FR-RN-083, FR-RN-024 | SCR-RN-13_wt-d-step-03.png | WT-D step 3: Opens Letters, tab NAL / NFR, ticks the renewal, clicks Send Letters and confirms | Not started |  | N
| SCR-RN-05 | Renewal: Insurer, Letters, Documents, Remarks and History | Marketing Account Officer (Account Broker) | WT-D Not for Renewal and the closing letter | 4 | Read-only or locked | 14.4 | FR-RN-004, FR-RN-044, FR-RN-071, FR-RN-080, FR-RN-084 | SCR-RN-05_wt-d-step-04.png | WT-D step 4: Opens the renewal, tab Letters | Not started |  | N
| SCR-RN-09 | Transfers | Marketing Team Leader | WT-E A transfer to another unit, and the controls the user sees | 1 | Success message | 14.5 | FR-RN-031, FR-RN-032 | SCR-RN-09_wt-e-step-01.png | WT-E step 1: The Team Leader of Corporate Marketing Team 1 opens Transfers, tab Incoming, chooses Accept in the row action menu and confirms with remarks | Not started |  | N
| SCR-RN-07 | Set Disposition, Add Remark and Re-open | Marketing Account Officer (Account Broker) | WT-E A transfer to another unit, and the controls the user sees | 2 | Validation error | 14.5 | FR-RN-042, FR-RN-043, FR-RN-044, FR-RN-047, FR-RN-048 | SCR-RN-07_wt-e-step-02.png | WT-E step 2: Aileen Account Officer gives a disposition on a renewal without opening its account history | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | WT-E A transfer to another unit, and the controls the user sees | 3 | Validation error | 14.5 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_wt-e-step-03.png | WT-E step 3: Marites Marketing Lead transfers a renewal of her unit to CBG Metro Team 1, her own unit | Not started |  | N
| DO-01 | Renewal Advice (first and second notice) | - | - |  | Document as received | 17.1 | FR-RN-080, FR-RN-081 | DO-01_document.png | Renewal Advice (first and second notice): first page as generated | Not started |  | N
| DO-02 | Not for Renewal Letter and No Advice Letter | - | - |  | Document as received | 17.2 | FR-RN-082, FR-RN-024 | DO-02_document.png | Not for Renewal Letter and No Advice Letter: first page as generated | Not started |  | N
| DO-03 | Insurer extract | - | - |  | Document as received | 17.3 | FR-RN-070 | DO-03_document.png | Insurer extract: first page as generated | Not started |  | N
| DO-04 | Expiry list download | - | - |  | Document as received | 17.4 | FR-RN-014 | DO-04_document.png | Expiry list download: first page as generated | Not started |  | N
| DO-05 | Renewal account details | - | - |  | Document as received | 17.5 | FR-RN-041 | DO-05_document.png | Renewal account details: first page as generated | Not started |  | N
| NAV-RN-01 | Marketing Team Leader: landing page | Marketing Team Leader | - |  | Landing page | 12.3 | - | NAV-RN-01_landing.png | Marketing Team Leader: landing page after sign-in | Not started |  | N
| NAV-RN-01 | Marketing Team Leader: menu | Marketing Team Leader | - |  | Menu | 12.3 | - | NAV-RN-01_menu.png | Marketing Team Leader: menu, every group open | Not started |  | N
| NAV-RN-02 | Marketing Account Officer (Account Broker): landing page | Marketing Account Officer (Account Broker) | - |  | Landing page | 12.3 | - | NAV-RN-02_landing.png | Marketing Account Officer (Account Broker): landing page after sign-in | Not started |  | N
| NAV-RN-02 | Marketing Account Officer (Account Broker): menu | Marketing Account Officer (Account Broker) | - |  | Menu | 12.3 | - | NAV-RN-02_menu.png | Marketing Account Officer (Account Broker): menu, every group open | Not started |  | N
| NAV-RN-03 | Processing Team Leader: landing page | Processing Team Leader | - |  | Landing page | 12.3 | - | NAV-RN-03_landing.png | Processing Team Leader: landing page after sign-in | Not started |  | N
| NAV-RN-03 | Processing Team Leader: menu | Processing Team Leader | - |  | Menu | 12.3 | - | NAV-RN-03_menu.png | Processing Team Leader: menu, every group open | Not started |  | N
| NAV-RN-04 | Processing Officer (Broker): landing page | Processing Officer (Broker) | - |  | Landing page | 12.3 | - | NAV-RN-04_landing.png | Processing Officer (Broker): landing page after sign-in | Not started |  | N
| NAV-RN-04 | Processing Officer (Broker): menu | Processing Officer (Broker) | - |  | Menu | 12.3 | - | NAV-RN-04_menu.png | Processing Officer (Broker): menu, every group open | Not started |  | N
| NAV-RN-05 | Contact Center: landing page | Contact Center | - |  | Landing page | 12.3 | - | NAV-RN-05_landing.png | Contact Center: landing page after sign-in | Not started |  | N
| NAV-RN-05 | Contact Center: menu | Contact Center | - |  | Menu | 12.3 | - | NAV-RN-05_menu.png | Contact Center: menu, every group open | Not started |  | N
| NAV-RN-06 | LAMD (loan status reports): landing page | LAMD (loan status reports) | - |  | Landing page | 12.3 | - | NAV-RN-06_landing.png | LAMD (loan status reports): landing page after sign-in | Not started |  | N
| NAV-RN-06 | LAMD (loan status reports): menu | LAMD (loan status reports) | - |  | Menu | 12.3 | - | NAV-RN-06_menu.png | LAMD (loan status reports): menu, every group open | Not started |  | N
| NAV-RN-07 | Business Administrator: landing page | Business Administrator | - |  | Landing page | 12.3 | - | NAV-RN-07_landing.png | Business Administrator: landing page after sign-in | Not started |  | N
| NAV-RN-07 | Business Administrator: menu | Business Administrator | - |  | Menu | 12.3 | - | NAV-RN-07_menu.png | Business Administrator: menu, every group open | Not started |  | N
| NAV-RN-08 | System Administrator: landing page | System Administrator | - |  | Landing page | 12.3 | - | NAV-RN-08_landing.png | System Administrator: landing page after sign-in | Not started |  | N
| NAV-RN-08 | System Administrator: menu | System Administrator | - |  | Menu | 12.3 | - | NAV-RN-08_menu.png | System Administrator: menu, every group open | Not started |  | N
| NAV-RN-09 | Auditor: landing page | Auditor | - |  | Landing page | 12.3 | - | NAV-RN-09_landing.png | Auditor: landing page after sign-in | Not started |  | N
| NAV-RN-09 | Auditor: menu | Auditor | - |  | Menu | 12.3 | - | NAV-RN-09_menu.png | Auditor: menu, every group open | Not started |  | N
| SCR-RN-02 | Expiry List | Marketing Team Leader | - |  | Empty list | 13.1.2 | FR-RN-010, FR-RN-011, FR-RN-012, FR-RN-013, FR-RN-014, FR-RN-015, FR-RN-030, FR-RN-031 | SCR-RN-02_empty.png | A search that finds no renewal | Not started |  | N
| SCR-RN-03 | Renewal | Auditor | - |  | Read-only or locked | 13.1.3 | FR-RN-002, FR-RN-041, FR-RN-021, FR-RN-026 | SCR-RN-03_auditor.png | The renewal as the Auditor sees it, without the actions | Not started |  | N
| SCR-RN-09 | Transfers | Marketing Team Leader, Marketing Account Officer (Account Broker) | - |  | Default | 13.2.4 | FR-RN-031, FR-RN-032 | SCR-RN-09_actions.png | The row action menu of a transfer request, opened from the more button of its row | Not started |  | N
| SCR-RN-17 | Renewal Setup: Non-renewable Risk Codes and Checks | Business Administrator | - |  | Default | 13.5.1 | FR-RN-020, FR-RN-024, FR-RN-112 | SCR-RN-17_actions.png | The row action menu of a non-renewable risk code | Not started |  | N
Note on B16: Screen ID The screen of the image, as in the FRS and the deck Mandatory: Yes Format: SCR-, NAV- or DO- and a number Allowed values: Free entry Example: SCR-RN-01
Note on C16: Screen name The title of the screen Mandatory: Yes Format: Text Allowed values: Free entry Example: Renewal Home
Note on D16: Persona(s) The personas who see the screen in this state Mandatory: Yes Format: Text Allowed values: Free entry Example: Marketing Team Leader
Note on E16: Flow The end-to-end flow that shows the image, if any Mandatory: No Format: Flow ID and title Allowed values: Free entry
Note on F16: Step The step of the flow Mandatory: No Format: Whole number Allowed values: A whole number from 1 to 99
Note on G16: State The state of the screen on the image Mandatory: Yes Format: From the list Allowed values: List State of a screen image: 12 values, see Reference lists Example: Default
Note on H16: FRS section The section of the FRS (or handbook) that specifies the screen Mandatory: Yes Format: Section number Allowed values: Free entry Example: 13.1.1
Note on I16: Requirement IDs The functional requirements of the screen Mandatory: No Format: FR-... separated by commas Allowed values: Free entry Example: FR-RN-100, FR-RN-102
Note on J16: Image file The file of the image package (09) Mandatory: Yes Format: <Screen ID>_<state>.png Allowed values: Free entry Example: SCR-RN-01_home.png
Note on K16: What the image shows The caption of the image Mandatory: No Format: Text Allowed values: Free entry Example: Renewal Home of the Marketing Team Leader: due dates, work queues, renewals by status and classification, workload
Note on L16: UXD status The status of the design of this screen state, kept by the UX Design team Mandatory: Yes Format: From the list Allowed values: Not started, In design, Ready for review, Approved (list UXD status) Example: Not started
Note on M16: UXD comments Comments of the UX Design team on the screen state Mandatory: No Format: Text Allowed values: Free entry
Note on N16: Changed in this issue Y when the image is new or changed in this issue of the set Mandatory: Yes Format: Y or N Allowed values: Y or N Example: N
Note on O16: Change reference The change reference (comment, change request or issue change) that changed the image Mandatory: Conditional: when Changed in this issue is Y Format: Reference Allowed values: Free entry

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | UX screen register: Changed in this issue | Y | Yes
|  | N | No
State of a screen image (UX_STATE) | UX screen register: State | Default
Filled
Validation error
Confirmation with reason
Success message
Empty list
Read-only or locked
Pending approval
Rejected or returned
Document as received
Landing page
Menu
UXD status (UXD_STATUS) | UX screen register: UXD status | Not started
In design
Ready for review
Approved
Templates of this workbook (TEMPLATES) | Questions and comments: Template | UXR UX screen register
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed
Status (STATUS) | Start here: Status | Not started
In progress
Ready for review
Confirmed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100