## Start here
UX screen register BRD-1 New Business
The screen images of the set for the BDOI UX Design team
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-1 New Business (Drop 1)
Version and date |  | Version 2.1, 8 October 2026
For |  | BDOI UX Design team (UXD)
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | Open the sheet UX screen register: one row per screen image of the 07 deck and the 09 image package, with the screen, the personas, the flow and step, the state and the FRS section.
2 | Filter Changed in this issue = Y to see the images that are new or changed in this issue; the change reference names the comment or change request behind the change.
3 | Set the UXD status of each row (Not started, In design, Ready for review, Approved) and write the UXD comments; leave the other columns as issued.
4 | Import the CSV of the image package into the design tool to link each design to its screen image.
5 | Raise questions on the sheet Questions and comments; the project team answers there. At the next issue the UXD status and comments of the unchanged rows are carried over.
The register
Step | ID | Template | What it holds | Kept by | Rows entered | Mandatory cells missing | Status | Open
1 | UXR | UX screen register | 170 screen images of 67 screens; 27 changed in this issue | BDOI UX Design team |  |  | Not started | Open →
Changes in this issue
Change reference |  | What changed |  |  |  |  | Screens
CHG-NB-2.1-01 |  | Send via Email of quotations: one or more quotations to one or more recipients with the supporting documents ticked in the dialog or sent on their own; a batch sends the valid quotations and lists the others with their reason; each quotation shows the delivery status of its last sending (FR-NB-044, BRNB.042) |  |  |  |  | SCR-NB-05, SCR-NB-07
CHG-NB-2.1-02 |  | Placement slips carry the EOPT details of each client (taxpayer name, TIN, registered address); the Generate Placement Slips dialog shows them or a notice when they are not on record; a slip whose details changed is regenerated before sending (FR-NB-087, BRNB.100) |  |  |  |  | SCR-NB-18, SCR-NB-20
CHG-NB-2.1-03 |  | Insurance Advice register: the sending of each advice shows Manual or Automatic; advices of a mortgagee enrolled in the MIS set-up are sent when they are generated (FR-NB-107, BRNB.060) |  |  |  |  | SCR-NB-26
CHG-NB-2.1-04 |  | Incentive indicator: Pending until the booked invoice is fully paid, then Eligible or Not eligible with the criterion code; evaluated again on endorsement and cancellation (FR-NB-118, BRNB.107) |  |  |  |  | SCR-NB-29, SCR-NB-30
CHG-NB-2.1-05 |  | Service Invoices: the owner is notified of every sending, successful or failed, and the register keeps the status, owner and time (FR-NB-117, BRNB.100.1) |  |  |  |  | SCR-NB-32
Other sheets
Sheet |  |  | What it holds
Reference lists |  |  | The lists of the drop-downs: states and UXD statuses
Questions and comments |  |  | Questions and comments of the UX Design team, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## UX screen register
UXR UX screen register | [13 empty] | Step 1 of 1
← Back to Start here | Step 1 of 1. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per screen image of BRD-1 New Business (the 07 deck and the 09 image package): the screen, personas, flow and step, state, FRS section and requirements, the image file, and the UXD status and comments of the UX Design team. Changed in this issue marks the images that are new or changed in this issue, with the change reference.
Provided by | BDOI UX Design team (UXD status and comments); iorta TechNXT project team (the other columns)
Due | With each design review; the rows are re-issued with each version of the set
How it is loaded | Kept by the UX Design team; at a new issue the UXD status and comments of the unchanged rows are carried over and the changed rows are flagged
Source | FRS v2.1 and the screens of the SIT environment (seed data)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (UX Design team lead) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | No | Yes | No | Yes | Conditional: when Changed in this issue is Y
Format | SCR-, NAV- or DO- and a number | Text | Text | Flow ID and title | Whole number | From the list | Section number | FR-... separated by commas | <Screen ID>_<state>.png | Text | From the list | Text | Y or N | Reference
Allowed values | Free entry | Free entry | Free entry | Free entry | A whole number from 1 to 99 | List State of a screen image: 12 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Not started, In design, Ready for review, Approved (list UXD status) | Free entry | Y or N | Free entry
What to enter | The screen of the image, as in the FRS and the deck | The title of the screen | The personas who see the screen in this state | The end-to-end flow that shows the image, if any | The step of the flow | The state of the screen on the image | The section of the FRS (or handbook) that specifies the screen | The functional requirements of the screen | The file of the image package (09) | The caption of the image | The status of the design of this screen state, kept by the UX Design team | Comments of the UX Design team on the screen state | Y when the image is new or changed in this issue of the set | The change reference (comment, change request or issue change) that changed the image
Row | Screen ID * | Screen name * | Persona(s) * | Flow | Step | State * | FRS section * | Requirement IDs | Image file * | What the image shows | UXD status * | UXD comments | Changed in this issue * | Change reference
Example – overwrite or delete | SCR-NB-01 | Clients | Marketing Account Officer |  |  | Default | 13.1.1 | FR-NB-030, FR-NB-046 | SCR-NB-01_list.png | Clients work list, All Clients tab | Not started |  | N
| SCR-NB-01 | Clients | Marketing Account Officer | - |  | Default | 13.1.1 | FR-NB-030, FR-NB-046 | SCR-NB-01_list.png | Clients work list, All Clients tab | Not started |  | N
| SCR-NB-01 | Clients | Marketing Account Officer | - |  | Default | 13.1.1 | FR-NB-030, FR-NB-046 | SCR-NB-01_filters.png | Clients work list with the advanced filters open | Not started |  | N
| SCR-NB-02 | New Client and Edit Client | Marketing Account Officer | - |  | Empty list | 13.1.2 | FR-NB-031, FR-NB-032, FR-NB-033 | SCR-NB-02_empty.png | New Client form (individual) | Not started |  | N
| SCR-NB-02 | New Client and Edit Client | Marketing Account Officer | - |  | Filled | 13.1.2 | FR-NB-031, FR-NB-032, FR-NB-033 | SCR-NB-02_filled.png | New Client form with the identity, contact and segment entered | Not started |  | N
| SCR-NB-02 | New Client and Edit Client | Marketing Account Officer | - |  | Validation error | 13.1.2 | FR-NB-031, FR-NB-032, FR-NB-033 | SCR-NB-02_error.png | Field messages after Save as prospect with an invalid TIN and mobile | Not started |  | N
| SCR-NB-02 | New Client and Edit Client | Marketing Account Officer | - |  | Validation error | 13.1.2 | FR-NB-031, FR-NB-032, FR-NB-033 | SCR-NB-02_duplicate.png | Duplicate warning: the TIN belongs to an existing client | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | - |  | Default | 13.1.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_record.png | Client record, Details tab, with the onboarding workflow panel | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | - |  | Default | 13.1.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_kyc.png | KYC & Documents tab: checklist and typed upload | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | - |  | Default | 13.1.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_notes.png | Tags & Instructions tab | Not started |  | N
| SCR-NB-03 | Client record | Marketing TL / TH / UH | - |  | Pending approval | 13.1.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_approval.png | Client in KYC review as seen by the verifier (Verify KYC offered) | Not started |  | N
| SCR-NB-04 | KYC Reviews Due | Marketing Account Officer | - |  | Default | 13.1.4 | FR-NB-038 | SCR-NB-04_list.png | KYC Reviews Due with the default filters | Not started |  | N
| SCR-NB-05 | Quotations | Marketing Account Officer | - |  | Default | 13.2.1 | FR-NB-010, FR-NB-042, FR-NB-044 | SCR-NB-05_list.png | Quotations work list, Drafts tab | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-05 | Quotations | Marketing TL / TH / UH | - |  | Default | 13.2.1 | FR-NB-010, FR-NB-042, FR-NB-044 | SCR-NB-05_review.png | For Review tab as seen by the approver | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-06 | New Quotation and Edit Quotation | Marketing Account Officer | - |  | Empty list | 13.2.2 | FR-NB-041, FR-NB-042, FR-NB-047, FR-NB-005, FR-NB-062 | SCR-NB-06_empty.png | New Quotation, step 1 Client | Not started |  | N
| SCR-NB-06 | New Quotation and Edit Quotation | Marketing Account Officer | - |  | Default | 13.2.2 | FR-NB-041, FR-NB-042, FR-NB-047, FR-NB-005, FR-NB-062 | SCR-NB-06_terms.png | Step 2 Product & Terms | Not started |  | N
| SCR-NB-06 | New Quotation and Edit Quotation | Marketing Account Officer | - |  | Default | 13.2.2 | FR-NB-041, FR-NB-042, FR-NB-047, FR-NB-005, FR-NB-062 | SCR-NB-06_items.png | Step 3 Risk Items with the live premium | Not started |  | N
| SCR-NB-06 | New Quotation and Edit Quotation | Marketing Account Officer | - |  | Validation error | 13.2.2 | FR-NB-041, FR-NB-042, FR-NB-047, FR-NB-005, FR-NB-062 | SCR-NB-06_error.png | Message when the user leaves Risk Items without an item | Not started |  | N
| SCR-NB-07 | Quotation record | Marketing Account Officer | - |  | Default | 13.2.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_record.png | Quotation record, Details tab | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing Account Officer | - |  | Default | 13.2.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_items.png | Items & Premium tab | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing TL / TH / UH | - |  | Pending approval | 13.2.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_approval.png | Quotation for review as seen by the approver (Approve, Return To Maker) | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing Account Officer | - |  | Filled | 13.2.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_send.png | Send via Email dialog of an approved quotation | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-08 | Quotation Requests | Marketing Account Officer | - |  | Default | 13.2.4 | FR-NB-040 | SCR-NB-08_list.png | Quotation Requests, To Quote tab | Not started |  | N
| SCR-NB-08 | Quotation Requests | Marketing Account Officer | - |  | Default | 13.2.4 | FR-NB-040 | SCR-NB-08_capture.png | Capture Quotation Request dialog | Not started |  | N
| SCR-NB-08 | Quotation Requests | Marketing Account Officer | - |  | Confirmation with reason | 13.2.4 | FR-NB-040 | SCR-NB-08_close.png | Close dialog with the required Reason for Closing, opened from the row action menu | Not started |  | N
| SCR-NB-09 | Proposal Requests | Marketing Account Officer | - |  | Default | 13.3.1 | FR-NB-050, FR-NB-052 | SCR-NB-09_list.png | Proposal Requests, Drafts tab | Not started |  | N
| SCR-NB-09 | Proposal Requests | Technical Support Unit | - |  | Default | 13.3.1 | FR-NB-050, FR-NB-052 | SCR-NB-09_tsu.png | With TSU tab as seen by the TSU officer | Not started |  | N
| SCR-NB-10 | New Proposal Request and Edit Proposal Request | Marketing Account Officer | - |  | Empty list | 13.3.2 | FR-NB-050, FR-NB-005, FR-NB-017 | SCR-NB-10_empty.png | New Proposal Request form | Not started |  | N
| SCR-NB-10 | New Proposal Request and Edit Proposal Request | Marketing Account Officer | - |  | Filled | 13.3.2 | FR-NB-050, FR-NB-005, FR-NB-017 | SCR-NB-10_filled.png | PRF with risk details, items and requested insurers | Not started |  | N
| SCR-NB-10 | New Proposal Request and Edit Proposal Request | Marketing Account Officer | - |  | Validation error | 13.3.2 | FR-NB-050, FR-NB-005, FR-NB-017 | SCR-NB-10_error.png | Messages when the PRF is submitted without client and product | Not started |  | N
| SCR-NB-11 | Proposal Request record | Marketing Account Officer | - |  | Default | 13.3.3 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_record.png | PRF record, Details tab | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | - |  | Default | 13.3.3 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_qs.png | Quotation Slip tab: insurers approached | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | - |  | Default | 13.3.3 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_responses.png | Insurer Responses tab with the terms received | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | - |  | Default | 13.3.3 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_comparative.png | Comparative Table tab | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | - |  | Filled | 13.3.3 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_terms.png | Terms dialog of one insurer, opened from the row action menu | Not started |  | N
| SCR-NB-12 | TSU Workbench | Technical Support Unit | - |  | Default | 13.3.4 | FR-NB-052, FR-NB-011 | SCR-NB-12_list.png | TSU Workbench | Not started |  | N
| SCR-NB-13 | Accounts | Marketing Account Officer | - |  | Default | 13.4.1 | FR-NB-060, FR-NB-067 | SCR-NB-13_list.png | Accounts work list, All tab | Not started |  | N
| SCR-NB-13 | Accounts | Marketing Account Officer | - |  | Confirmation with reason | 13.4.1 | FR-NB-060, FR-NB-067 | SCR-NB-13_returned.png | Returned to Me tab | Not started |  | N
| SCR-NB-13 | Accounts | Marketing Account Officer | - |  | Default | 13.4.1 | FR-NB-060, FR-NB-067 | SCR-NB-13_filters.png | Accounts with the advanced filters open | Not started |  | N
| SCR-NB-14 | New Account and Edit Account | Marketing Account Officer | - |  | Empty list | 13.4.2 | FR-NB-061, FR-NB-062, FR-NB-063, FR-NB-064, FR-NB-066, FR-NB-068, FR-NB-069 | SCR-NB-14_empty.png | New Account, step 1 Client | Not started |  | N
| SCR-NB-14 | New Account and Edit Account | Marketing Account Officer | - |  | Default | 13.4.2 | FR-NB-061, FR-NB-062, FR-NB-063, FR-NB-064, FR-NB-066, FR-NB-068, FR-NB-069 | SCR-NB-14_period.png | Step 3 Period & payment | Not started |  | N
| SCR-NB-14 | New Account and Edit Account | Marketing Account Officer | - |  | Success message | 13.4.2 | FR-NB-061, FR-NB-062, FR-NB-063, FR-NB-064, FR-NB-066, FR-NB-068, FR-NB-069 | SCR-NB-14_review.png | Step 6 Review & submit with the completeness check | Not started |  | N
| SCR-NB-14 | New Account and Edit Account | Marketing Account Officer | - |  | Validation error | 13.4.2 | FR-NB-061, FR-NB-062, FR-NB-063, FR-NB-064, FR-NB-066, FR-NB-068, FR-NB-069 | SCR-NB-14_duplicate.png | Duplicate risk refused with the existing ARN | Not started |  | N
| SCR-NB-15 | Account record | Marketing Account Officer | - |  | Default | 13.4.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_record.png | Account record, Details tab with the tags | Not started |  | N
| SCR-NB-15 | Account record | Processing | - |  | Pending approval | 13.4.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_processing.png | Submitted account as seen by Processing (Validate, Direct booking, Return To Marketing) | Not started |  | N
| SCR-NB-15 | Account record | Processing | - |  | Confirmation with reason | 13.4.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_return.png | Return To Marketing dialog with the mandatory reason | Not started |  | N
| SCR-NB-16 | FFY Register | Marketing Account Officer | - |  | Default | 13.4.4 | FR-NB-068 | SCR-NB-16_list.png | FFY Register | Not started |  | N
| SCR-NB-17 | Direct Payment | Marketing Account Officer | - |  | Default | 13.4.5 | FR-NB-069 | SCR-NB-17_list.png | Direct Payment Accounts | Not started |  | N
| SCR-NB-18 | Placement Workbench | Processing | - |  | Default | 13.5.1 | FR-NB-080, FR-NB-081, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-087 | SCR-NB-18_list.png | Placement Workbench, For Placement & Booking tab | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-18 | Placement Workbench | Processing | - |  | Validation error | 13.5.1 | FR-NB-080, FR-NB-081, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-087 | SCR-NB-18_generate.png | Generate Placement Slips dialog with the prerequisites of the selected accounts | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-18 | Placement Workbench | Processing | - |  | Empty list | 13.5.1 | FR-NB-080, FR-NB-081, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-087 | SCR-NB-18_cancelled.png | Cancelled Placement tab with Reactivate | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-19 | Account Placement | Processing | - |  | Default | 13.5.2 | FR-NB-080, FR-NB-081, FR-NB-082, FR-NB-083, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-092 | SCR-NB-19_gate.png | Account Placement, Payment Gate tab of an Other Lines account | Not started |  | N
| SCR-NB-19 | Account Placement | Processing | - |  | Default | 13.5.2 | FR-NB-080, FR-NB-081, FR-NB-082, FR-NB-083, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-092 | SCR-NB-19_hold.png | Hold Cover tab | Not started |  | N
| SCR-NB-19 | Account Placement | Processing | - |  | Confirmation with reason | 13.5.2 | FR-NB-080, FR-NB-081, FR-NB-082, FR-NB-083, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-092 | SCR-NB-19_confirm.png | Record Client Confirmation dialog | Not started |  | N
| SCR-NB-20 | Placement Slips | Processing | - |  | Default | 13.5.3 | FR-NB-080, FR-NB-081, FR-NB-087 | SCR-NB-20_list.png | Placement Slips, All Slips tab | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-20 | Placement Slips | Processing | - |  | Filled | 13.5.3 | FR-NB-080, FR-NB-081, FR-NB-087 | SCR-NB-20_send.png | Send placement slip dialog (Resend of a sent slip, from the row action menu) | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-21 | CLPC Billing | Processing | - |  | Default | 13.5.4 | FR-NB-090, FR-NB-091 | SCR-NB-21_list.png | CLPC Billing, Billing Batches tab | Not started |  | N
| SCR-NB-21 | CLPC Billing | Processing | - |  | Default | 13.5.4 | FR-NB-090, FR-NB-091 | SCR-NB-21_upload.png | Upload Payment Report dialog | Not started |  | N
| SCR-NB-22 | Payment Report | Processing | - |  | Pending approval | 13.5.5 | FR-NB-091, FR-NB-092 | SCR-NB-22_review.png | Payment Report match review | Not started |  | N
| SCR-NB-22 | Payment Report | Processing | - |  | Default | 13.5.5 | FR-NB-091, FR-NB-092 | SCR-NB-22_match.png | Match Row dialog, opened from the row action menu | Not started |  | N
| SCR-NB-23 | Issuance Workbench | Processing | - |  | Pending approval | 13.6.1 | FR-NB-100, FR-NB-101, FR-NB-102, FR-NB-103, FR-NB-105 | SCR-NB-23_list.png | Issuance Workbench, Placed – Awaiting Policy tab | Not started |  | N
| SCR-NB-23 | Issuance Workbench | Processing | - |  | Default | 13.6.1 | FR-NB-100, FR-NB-101, FR-NB-102, FR-NB-103, FR-NB-105 | SCR-NB-23_review.png | Policy Received – Review Extraction tab | Not started |  | N
| SCR-NB-24 | E-policy Upload | Processing | - |  | Empty list | 13.6.2 | FR-NB-100, FR-NB-102 | SCR-NB-24_empty.png | E-policy Upload: single and bulk | Not started |  | N
| SCR-NB-24 | E-policy Upload | Processing | - |  | Default | 13.6.2 | FR-NB-100, FR-NB-102 | SCR-NB-24_bulk.png | Bulk upload match review | Not started |  | N
| SCR-NB-25 | Extraction Review | Processing | - |  | Pending approval | 13.6.3 | FR-NB-101, FR-NB-102, FR-NB-114 | SCR-NB-25_review.png | Extraction Review with the differences to check | Not started |  | N
| SCR-NB-26 | Insurance Advice | Processing | - |  | Default | 13.6.4 | FR-NB-103, FR-NB-104, FR-NB-107 | SCR-NB-26_list.png | Insurance Advice register | Not started |  | Y | CHG-NB-2.1-03
| SCR-NB-26 | Insurance Advice | Processing | - |  | Confirmation with reason | 13.6.4 | FR-NB-103, FR-NB-104, FR-NB-107 | SCR-NB-26_send.png | Send Insurance Advice dialog | Not started |  | Y | CHG-NB-2.1-03
| SCR-NB-27 | E-policy Dispatch | E-policy Sender | - |  | Default | 13.6.5 | FR-NB-105, FR-NB-106 | SCR-NB-27_list.png | E-policy Dispatch, Ready to Dispatch tab | Not started |  | N
| SCR-NB-27 | E-policy Dispatch | E-policy Sender | - |  | Default | 13.6.5 | FR-NB-105, FR-NB-106 | SCR-NB-27_report.png | Dispatch Report tab | Not started |  | N
| SCR-NB-28 | Booking Workbench | Processing | - |  | Default | 13.7.1 | FR-NB-110, FR-NB-111, FR-NB-112, FR-NB-114 | SCR-NB-28_list.png | Booking Workbench, Ready to Book tab | Not started |  | N
| SCR-NB-28 | Booking Workbench | Processing | - |  | Default | 13.7.1 | FR-NB-110, FR-NB-111, FR-NB-112, FR-NB-114 | SCR-NB-28_queued.png | Queued for Batch tab with Confirm Batch and Cancel Batch | Not started |  | N
| SCR-NB-28 | Booking Workbench | Processing | - |  | Confirmation with reason | 13.7.1 | FR-NB-110, FR-NB-111, FR-NB-112, FR-NB-114 | SCR-NB-28_booknow.png | Book Now dialog | Not started |  | N
| SCR-NB-29 | Pre-booking Confirmation | Processing | - |  | Default | 13.7.2 | FR-NB-110, FR-NB-113, FR-NB-114, FR-NB-117, FR-NB-118, FR-NB-119 | SCR-NB-29_record.png | Pre-booking Confirmation with the invoice and the journal preview | Not started |  | Y | CHG-NB-2.1-04
| SCR-NB-30 | Booked Invoice | Processing | - |  | Default | 13.7.3 | FR-NB-110, FR-NB-115, FR-NB-116, FR-NB-117, FR-NB-118 | SCR-NB-30_record.png | Booked Invoice, Premium & Commission tab | Not started |  | Y | CHG-NB-2.1-04
| SCR-NB-30 | Booked Invoice | Adjustment | - |  | Confirmation with reason | 13.7.3 | FR-NB-110, FR-NB-115, FR-NB-116, FR-NB-117, FR-NB-118 | SCR-NB-30_cancel.png | Cancel Booking dialog | Not started |  | Y | CHG-NB-2.1-04
| SCR-NB-31 | Endorsements and New Endorsement | Adjustment | - |  | Default | 13.7.4 | FR-NB-115 | SCR-NB-31_list.png | Endorsements list | Not started |  | N
| SCR-NB-31 | Endorsements and New Endorsement | Adjustment | - |  | Default | 13.7.4 | FR-NB-115 | SCR-NB-31_new.png | New Endorsement with the invoice and journal preview | Not started |  | N
| SCR-NB-32 | Service Invoices | Processing | - |  | Default | 13.7.5 | FR-NB-117 | SCR-NB-32_list.png | Service Invoices | Not started |  | Y | CHG-NB-2.1-05
| SCR-NB-32 | Service Invoices | Processing | - |  | Default | 13.7.5 | FR-NB-117 | SCR-NB-32_record.png | Service invoice record | Not started |  | Y | CHG-NB-2.1-05
| SCR-NB-33 | Batch Runs | Processing | - |  | Empty list | 13.7.6 | FR-NB-111 | SCR-NB-33_list.png | Batch Runs | Not started |  | N
| SCR-NB-34 | Booking Setup | Processing | - |  | Default | 13.7.7 | FR-NB-112, FR-NB-117, FR-NB-118 | SCR-NB-34_list.png | Booking Setup, Auto-book Rules tab | Not started |  | N
| SCR-NB-35 | Bulk Uploads | Marketing Account Officer | - |  | Default | 13.8.1 | FR-NB-019 | SCR-NB-35_list.png | Bulk Uploads centre | Not started |  | N
| SCR-NB-36 | Bulk upload wizard | Marketing Account Officer | - |  | Empty list | 13.8.2 | FR-NB-019, FR-NB-035, FR-NB-045, FR-NB-046, FR-NB-065, FR-NB-068, FR-NB-111 | SCR-NB-36_empty.png | Bulk Account Creation: template and upload steps | Not started |  | N
| SCR-NB-36 | Bulk upload wizard | Marketing Account Officer | - |  | Validation error | 13.8.2 | FR-NB-019, FR-NB-035, FR-NB-045, FR-NB-046, FR-NB-065, FR-NB-068, FR-NB-111 | SCR-NB-36_review.png | Review step: the valid rows and the rejected rows with their messages | Not started |  | N
| SCR-NB-36 | Bulk upload wizard | Marketing Account Officer | - |  | Success message | 13.8.2 | FR-NB-019, FR-NB-035, FR-NB-045, FR-NB-046, FR-NB-065, FR-NB-068, FR-NB-111 | SCR-NB-36_processed.png | Valid rows processed; Download Error File and Upload Corrected File are offered for the rejected rows | Not started |  | N
| SCR-NB-36 | Bulk upload wizard | Marketing Account Officer | - |  | Document as received | 13.8.2 | FR-NB-019, FR-NB-035, FR-NB-045, FR-NB-046, FR-NB-065, FR-NB-068, FR-NB-111 | SCR-NB-36_errorfile.png | The error file: the rejected rows with their messages, to correct and upload again | Not started |  | N
| SCR-NB-36 | Bulk upload wizard | Marketing Account Officer | - |  | Success message | 13.8.2 | FR-NB-019, FR-NB-035, FR-NB-045, FR-NB-046, FR-NB-065, FR-NB-068, FR-NB-111 | SCR-NB-36_corrected.png | Upload Corrected File: the corrected rows validated and processed | Not started |  | N
| SCR-NB-37 | NB Dashboard | Marketing TL / TH / UH | - |  | Default | 13.8.3 | FR-NB-120, FR-NB-122 | SCR-NB-37_list.png | New Business Dashboard | Not started |  | N
| SCR-NB-38 | My Work | Marketing Account Officer | - |  | Default | 13.8.4 | FR-NB-011, FR-NB-010 | SCR-NB-38_list.png | My Work, All my queues | Not started |  | N
| SCR-NB-38 | My Work | Marketing TL / TH / UH | - |  | Filled | 13.8.4 | FR-NB-011, FR-NB-010 | SCR-NB-38_assign.png | Assign dialog of a team leader, opened from the row action menu | Not started |  | N
| SCR-NB-39 | My Approvals | New Business Approver | - |  | Default | 13.8.5 | FR-NB-133 | SCR-NB-39_list.png | My Approvals | Not started |  | N
| SCR-NB-40 | New Business Reports | Marketing TL / TH / UH | - |  | Default | 13.8.6 | FR-NB-121, FR-NB-122, FR-NB-123, FR-NB-124, FR-NB-125 | SCR-NB-40_list.png | New Business Reports | Not started |  | N
| SCR-NB-40 | New Business Reports | Marketing TL / TH / UH | - |  | Default | 13.8.6 | FR-NB-121, FR-NB-122, FR-NB-123, FR-NB-124, FR-NB-125 | SCR-NB-40_run.png | Account Status Report run on screen | Not started |  | N
| SCR-NB-41 | Production Targets | Business Administrator | - |  | Default | 13.8.7 | FR-NB-122 | SCR-NB-41_list.png | Production Targets | Not started |  | N
| SCR-NB-42 | Lists of Values | Business Administrator | - |  | Default | 13.8.8 | FR-NB-132 | SCR-NB-42_list.png | Lists of Values | Not started |  | N
| SCR-NB-42 | Lists of Values | Business Administrator | - |  | Default | 13.8.8 | FR-NB-132 | SCR-NB-42_new.png | New value dialog | Not started |  | N
| SCR-NB-43 | Data Retention | New Business Approver | - |  | Default | 13.8.9 | FR-NB-137 | SCR-NB-43_list.png | Data Retention | Not started |  | N
| SCR-NB-44 | Document Templates | New Business Approver | - |  | Default | 13.8.10 | FR-NB-004 | SCR-NB-44_list.png | Document Templates | Not started |  | N
| SCR-NB-45 | Outbound Messages | Business Administrator | - |  | Default | 13.8.11 | FR-NB-013, FR-NB-015 | SCR-NB-45_list.png | Outbound Messages | Not started |  | N
| SCR-NB-46 | Sign in | - | - |  | Empty list | 13.8.12 | FR-NB-130, FR-NB-131 | SCR-NB-46_empty.png | Sign in | Not started |  | N
| SCR-NB-02 | New Client and Edit Client | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 1 | Success message | 14.1 | FR-NB-031, FR-NB-032, FR-NB-033 | SCR-NB-02_wt-a-step-01.png | WT-A step 1: Opens Clients › New Client, enters the individual's identity, contact, address and segment, and clicks Save as prospect | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 2 | Default | 14.1 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_wt-a-step-02.png | WT-A step 2: Opens the client, uploads the KYC form and a valid ID on the KYC & Documents tab and clicks Submit KYC | Not started |  | N
| SCR-NB-03 | Client record | Marketing TL / TH / UH | WT-A Retail package policy from a new client to booking | 3 | Success message | 14.1 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_wt-a-step-03.png | WT-A step 3: Opens the client from My Work and clicks Verify KYC | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 4 | Success message | 14.1 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_wt-a-step-04.png | WT-A step 4: Clicks Confirm client | Not started |  | N
| SCR-NB-06 | New Quotation and Edit Quotation | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 5 | Success message | 14.1 | FR-NB-041, FR-NB-042, FR-NB-047, FR-NB-005, FR-NB-062 | SCR-NB-06_wt-a-step-05.png | WT-A step 5: Clicks Generate Quotation, checks the market segment taken from the client, chooses PAR01, the insurer and its branch, adds the location with its sum insured, reviews the live premium and clicks Submit for Review | Not started |  | N
| SCR-NB-07 | Quotation record | Marketing TL / TH / UH | WT-A Retail package policy from a new client to booking | 6 | Success message | 14.1 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_wt-a-step-06.png | WT-A step 6: Opens the quotation from the For Review tab and clicks Approve | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 7 | Default | 14.1 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_wt-a-step-07.png | WT-A step 7: Clicks Send via Email, keeps the proposed e-mail and clicks Send | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 8 | Default | 14.1 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_wt-a-step-08.png | WT-A step 8: Clicks Record acceptance, uploads the client's reply and clicks Record Acceptance, then Create accounts | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-14 | New Account and Edit Account | Marketing Account Officer | WT-A Retail package policy from a new client to booking | 9 | Success message | 14.1 | FR-NB-061, FR-NB-062, FR-NB-063, FR-NB-064, FR-NB-066, FR-NB-068, FR-NB-069 | SCR-NB-14_wt-a-step-09.png | WT-A step 9: Opens the draft account, completes the mortgagee bank and PN number, reviews the completeness check and clicks Submit to Processing | Not started |  | N
| SCR-NB-15 | Account record | Processing | WT-A Retail package policy from a new client to booking | 10 | Pending approval | 14.1 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_wt-a-step-10.png | WT-A step 10: Opens the account from My Work and clicks Validate | Not started |  | N
| SCR-NB-21 | CLPC Billing | Processing | WT-A Retail package policy from a new client to booking | 11 | Default | 14.1 | FR-NB-090, FR-NB-091 | SCR-NB-21_wt-a-step-11.png | WT-A step 11: Bills the account on CLPC Billing, downloads the file, uploads CLPC's payment report and confirms the matches | Not started |  | N
| SCR-NB-18 | Placement Workbench | Processing | WT-A Retail package policy from a new client to booking | 12 | Default | 14.1 | FR-NB-080, FR-NB-081, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-087 | SCR-NB-18_wt-a-step-12.png | WT-A step 12: Selects the account on the Placement Workbench, clicks For Placement, then Generate Slips, then Send Slips | Not started |  | Y | CHG-NB-2.1-02
| SCR-NB-24 | E-policy Upload | Processing | WT-A Retail package policy from a new client to booking | 13 | Success message | 14.1 | FR-NB-100, FR-NB-102 | SCR-NB-24_wt-a-step-13.png | WT-A step 13: Uploads the insurer's e-policy PDF with the ARN | Not started |  | N
| SCR-NB-25 | Extraction Review | Processing | WT-A Retail package policy from a new client to booking | 14 | Default | 14.1 | FR-NB-101, FR-NB-102, FR-NB-114 | SCR-NB-25_wt-a-step-14.png | WT-A step 14: Checks the extracted policy number against the account and clicks Confirm Policy | Not started |  | N
| SCR-NB-27 | E-policy Dispatch | E-policy Sender | WT-A Retail package policy from a new client to booking | 15 | Success message | 14.1 | FR-NB-105, FR-NB-106 | SCR-NB-27_wt-a-step-15.png | WT-A step 15: Sends the e-policy to the client from Ready to Dispatch | Not started |  | N
| SCR-NB-29 | Pre-booking Confirmation | Processing | WT-A Retail package policy from a new client to booking | 16 | Success message | 14.1 | FR-NB-110, FR-NB-113, FR-NB-114, FR-NB-117, FR-NB-118, FR-NB-119 | SCR-NB-29_wt-a-step-16.png | WT-A step 16: Opens the account from Ready to Book, checks the invoice and the journal preview, and clicks Book Account | Not started |  | Y | CHG-NB-2.1-04
| SCR-NB-30 | Booked Invoice | Processing | WT-A Retail package policy from a new client to booking | 17 | Default | 14.1 | FR-NB-110, FR-NB-115, FR-NB-116, FR-NB-117, FR-NB-118 | SCR-NB-30_wt-a-step-17.png | WT-A step 17: Reviews the Journal and Open Items tabs of the booked invoice | Not started |  | Y | CHG-NB-2.1-04
| SCR-NB-10 | New Proposal Request and Edit Proposal Request | Marketing Account Officer | WT-B Non-package commercial risk through a PRF with insurer quotations | 1 | Success message | 14.2 | FR-NB-050, FR-NB-005, FR-NB-017 | SCR-NB-10_wt-b-step-01.png | WT-B step 1: Opens New Proposal Request, chooses the client and CAR00, describes the risk, adds the item, ticks three insurers, attaches the mandatory documents and clicks Submit for Approval | Not started |  | N
| SCR-NB-11 | Proposal Request record | Marketing TL / TH / UH | WT-B Non-package commercial risk through a PRF with insurer quotations | 2 | Default | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-02.png | WT-B step 2: Opens the PRF and clicks Approve and send to TSU | Not started |  | N
| SCR-NB-12 | TSU Workbench | Technical Support Unit | WT-B Non-package commercial risk through a PRF with insurer quotations | 3 | Success message | 14.2 | FR-NB-052, FR-NB-011 | SCR-NB-12_wt-b-step-03.png | WT-B step 3: Claims the PRF on the TSU Workbench and opens it | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | WT-B Non-package commercial risk through a PRF with insurer quotations | 4 | Pending approval | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-04.png | WT-B step 4: Clicks Accept and Prepare Quotation Slip, confirms the insurers on the Quotation Slip tab and clicks Submit quotation slip with the reply date | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | WT-B Non-package commercial risk through a PRF with insurer quotations | 5 | Pending approval | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-05.png | WT-B step 5: A second TSU officer clicks Approve and send to insurers | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | WT-B Non-package commercial risk through a PRF with insurer quotations | 6 | Default | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-06.png | WT-B step 6: Keys in the terms of each insurer on the Insurer Responses tab (one declines), recommends the lowest premium and clicks Insurer terms complete | Not started |  | N
| SCR-NB-11 | Proposal Request record | Technical Support Unit | WT-B Non-package commercial risk through a PRF with insurer quotations | 7 | Success message | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-07.png | WT-B step 7: Clicks Submit proposal slip for the recommended insurer; a second TSU officer approves and releases it | Not started |  | N
| SCR-NB-11 | Proposal Request record | Marketing Account Officer | WT-B Non-package commercial risk through a PRF with insurer quotations | 8 | Default | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-08.png | WT-B step 8: Clicks Send via Email to send the proposal slip and the comparative table to the client | Not started |  | N
| SCR-NB-11 | Proposal Request record | Marketing Account Officer | WT-B Non-package commercial risk through a PRF with insurer quotations | 9 | Default | 14.2 | FR-NB-051, FR-NB-052, FR-NB-053, FR-NB-054, FR-NB-055, FR-NB-056, FR-NB-057 | SCR-NB-11_wt-b-step-09.png | WT-B step 9: Records the client's acceptance and clicks Create accounts | Not started |  | N
| SCR-NB-03 | Client record | Marketing Account Officer | WT-C Returns for correction and the messages the user sees | 1 | Validation error | 14.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_wt-c-step-01.png | WT-C step 1: Clicks Submit KYC on a prospect without the mandatory documents | Not started |  | N
| SCR-NB-03 | Client record | Marketing TL / TH / UH | WT-C Returns for correction and the messages the user sees | 2 | Rejected or returned | 14.3 | FR-NB-034, FR-NB-036, FR-NB-037, FR-NB-017, FR-NB-018 | SCR-NB-03_wt-c-step-02.png | WT-C step 2: Opens a client in KYC review and clicks Return To Account Officer, selects the reason and writes the comment | Not started |  | N
| SCR-NB-07 | Quotation record | Marketing TL / TH / UH | WT-C Returns for correction and the messages the user sees | 3 | Validation error | 14.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_wt-c-step-03.png | WT-C step 3: Makes a quotation, submits it for review and then tries to approve it himself | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-07 | Quotation record | Marketing TL / TH / UH | WT-C Returns for correction and the messages the user sees | 4 | Rejected or returned | 14.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_wt-c-step-04.png | WT-C step 4: Clicks Return To Maker on the quotation with the reason Rate or terms to be reviewed | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-15 | Account record | Processing | WT-C Returns for correction and the messages the user sees | 5 | Validation error | 14.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_wt-c-step-05.png | WT-C step 5: Clicks Validate on an account whose client is not confirmed (the Account Officer submitted it with the valid ID attached) | Not started |  | N
| SCR-NB-15 | Account record | Processing | WT-C Returns for correction and the messages the user sees | 6 | Rejected or returned | 14.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_wt-c-step-06.png | WT-C step 6: Clicks Return To Marketing with the reason Missing supporting documents | Not started |  | N
| SCR-NB-13 | Accounts | Marketing Account Officer | WT-C Returns for correction and the messages the user sees | 7 | Success message | 14.3 | FR-NB-060, FR-NB-067 | SCR-NB-13_wt-c-step-07.png | WT-C step 7: Opens the Returned to Me tab, opens the account, attaches the document and clicks Resubmit to Processing | Not started |  | N
| SCR-NB-19 | Account Placement | Processing | WT-C Returns for correction and the messages the user sees | 8 | Rejected or returned | 14.3 | FR-NB-080, FR-NB-081, FR-NB-082, FR-NB-083, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-092 | SCR-NB-19_wt-c-step-08.png | WT-C step 8: Records an insurer return on a placed account with the reason Additional insurer requirements | Not started |  | N
| SCR-NB-19 | Account Placement | Processing | WT-C Returns for correction and the messages the user sees | 9 | Default | 14.3 | FR-NB-080, FR-NB-081, FR-NB-082, FR-NB-083, FR-NB-084, FR-NB-085, FR-NB-086, FR-NB-092 | SCR-NB-19_wt-c-step-09.png | WT-C step 9: Clicks Resubmit for Placement, then Generate Placement Slip, and sends the new slip from the Placement Slips tab | Not started |  | N
| DO-01 | Insurance quotation (quotation letter) | - | - |  | Document as received | 17.1 | FR-NB-004, FR-NB-044 | DO-01_document.png | Insurance quotation (quotation letter): first page as generated | Not started |  | N
| DO-02 | Quotation slip | - | - |  | Document as received | 17.2 | FR-NB-053 | DO-02_document.png | Quotation slip: first page as generated | Not started |  | N
| DO-03 | Comparative table | - | - |  | Document as received | 17.3 | FR-NB-055 | DO-03_document.png | Comparative table: first page as generated | Not started |  | N
| DO-04 | Proposal slip | - | - |  | Document as received | 17.4 | FR-NB-056 | DO-04_document.png | Proposal slip: first page as generated | Not started |  | N
| DO-05 | Placement slip | - | - |  | Document as received | 17.5 | FR-NB-080, FR-NB-081 | DO-05_document.png | Placement slip: first page as generated | Not started |  | N
| DO-06 | Hold cover request | - | - |  | Document as received | 17.6 | FR-NB-082 | DO-06_document.png | Hold cover request: first page as generated | Not started |  | N
| DO-07 | Insurance Advice | - | - |  | Document as received | 17.7 | FR-NB-103, FR-NB-104 | DO-07_document.png | Insurance Advice: first page as generated | Not started |  | N
| DO-08 | Service invoice and service invoice credit | - | - |  | Document as received | 17.8 | FR-NB-117 | DO-08_document.png | Service invoice and service invoice credit: first page as generated | Not started |  | N
| DO-09 | CLPC billing file | - | - |  | Document as received | 17.9 | FR-NB-090 | DO-09_document.png | CLPC billing file: first page as generated, with six of its nine columns | Not started |  | N
| DO-10 | Reports (New Business Reports) | - | - |  | Document as received | 17.10 | FR-NB-124, FR-NB-125 | DO-10_document.png | Reports (New Business Reports): first page as generated | Not started |  | N
| NAV-NB-01 | Marketing Account Officer: landing page | Marketing Account Officer | - |  | Landing page | 12.3 | - | NAV-NB-01_landing.png | Marketing Account Officer: landing page after sign-in | Not started |  | N
| NAV-NB-01 | Marketing Account Officer: menu | Marketing Account Officer | - |  | Menu | 12.3 | - | NAV-NB-01_menu.png | Marketing Account Officer: menu, every group open | Not started |  | N
| NAV-NB-02 | Marketing TL / TH / UH: landing page | Marketing TL / TH / UH | - |  | Landing page | 12.3 | - | NAV-NB-02_landing.png | Marketing TL / TH / UH: landing page after sign-in | Not started |  | N
| NAV-NB-02 | Marketing TL / TH / UH: menu | Marketing TL / TH / UH | - |  | Menu | 12.3 | - | NAV-NB-02_menu.png | Marketing TL / TH / UH: menu, every group open | Not started |  | N
| NAV-NB-03 | Technical Support Unit: landing page | Technical Support Unit | - |  | Landing page | 12.3 | - | NAV-NB-03_landing.png | Technical Support Unit: landing page after sign-in | Not started |  | N
| NAV-NB-03 | Technical Support Unit: menu | Technical Support Unit | - |  | Menu | 12.3 | - | NAV-NB-03_menu.png | Technical Support Unit: menu, every group open | Not started |  | N
| NAV-NB-04 | Processing: landing page | Processing | - |  | Landing page | 12.3 | - | NAV-NB-04_landing.png | Processing: landing page after sign-in | Not started |  | N
| NAV-NB-04 | Processing: menu | Processing | - |  | Menu | 12.3 | - | NAV-NB-04_menu.png | Processing: menu, every group open | Not started |  | N
| NAV-NB-05 | Processing Team Leader: landing page | Processing Team Leader | - |  | Landing page | 12.3 | - | NAV-NB-05_landing.png | Processing Team Leader: landing page after sign-in | Not started |  | N
| NAV-NB-05 | Processing Team Leader: menu | Processing Team Leader | - |  | Menu | 12.3 | - | NAV-NB-05_menu.png | Processing Team Leader: menu, every group open | Not started |  | N
| NAV-NB-06 | New Business Approver: landing page | New Business Approver | - |  | Landing page | 12.3 | - | NAV-NB-06_landing.png | New Business Approver: landing page after sign-in | Not started |  | N
| NAV-NB-06 | New Business Approver: menu | New Business Approver | - |  | Menu | 12.3 | - | NAV-NB-06_menu.png | New Business Approver: menu, every group open | Not started |  | N
| NAV-NB-07 | E-policy Sender: landing page | E-policy Sender | - |  | Landing page | 12.3 | - | NAV-NB-07_landing.png | E-policy Sender: landing page after sign-in | Not started |  | N
| NAV-NB-07 | E-policy Sender: menu | E-policy Sender | - |  | Menu | 12.3 | - | NAV-NB-07_menu.png | E-policy Sender: menu, every group open | Not started |  | N
| NAV-NB-08 | Adjustment: landing page | Adjustment | - |  | Landing page | 12.3 | - | NAV-NB-08_landing.png | Adjustment: landing page after sign-in | Not started |  | N
| NAV-NB-08 | Adjustment: menu | Adjustment | - |  | Menu | 12.3 | - | NAV-NB-08_menu.png | Adjustment: menu, every group open | Not started |  | N
| NAV-NB-09 | Business Administrator: landing page | Business Administrator | - |  | Landing page | 12.3 | - | NAV-NB-09_landing.png | Business Administrator: landing page after sign-in | Not started |  | N
| NAV-NB-09 | Business Administrator: menu | Business Administrator | - |  | Menu | 12.3 | - | NAV-NB-09_menu.png | Business Administrator: menu, every group open | Not started |  | N
| NAV-NB-10 | System Administrator: landing page | System Administrator | - |  | Landing page | 12.3 | - | NAV-NB-10_landing.png | System Administrator: landing page after sign-in | Not started |  | N
| NAV-NB-10 | System Administrator: menu | System Administrator | - |  | Menu | 12.3 | - | NAV-NB-10_menu.png | System Administrator: menu, every group open | Not started |  | N
| NAV-NB-11 | Auditor: landing page | Auditor | - |  | Landing page | 12.3 | - | NAV-NB-11_landing.png | Auditor: landing page after sign-in | Not started |  | N
| NAV-NB-11 | Auditor: menu | Auditor | - |  | Menu | 12.3 | - | NAV-NB-11_menu.png | Auditor: menu, every group open | Not started |  | N
| SCR-NB-01 | Clients | Marketing Account Officer | - |  | Empty list | 13.1.1 | FR-NB-030, FR-NB-046 | SCR-NB-01_empty.png | A search that finds no client | Not started |  | N
| SCR-NB-07 | Quotation record | Auditor | - |  | Read-only or locked | 13.2.3 | FR-NB-042, FR-NB-043, FR-NB-044, FR-NB-045, FR-NB-012, FR-NB-013, FR-NB-014 | SCR-NB-07_auditor.png | A quotation as the Auditor sees it, without the actions | Not started |  | Y | CHG-NB-2.1-01
| SCR-NB-08 | Quotation Requests | Marketing Account Officer | - |  | Default | 13.2.4 | FR-NB-040 | SCR-NB-08_actions.png | The row action menu of a request, opened from the more button of its row | Not started |  | N
| SCR-NB-15 | Account record | Auditor | - |  | Read-only or locked | 13.4.3 | FR-NB-060, FR-NB-064, FR-NB-067, FR-NB-068, FR-NB-069, FR-NB-113, FR-NB-012 | SCR-NB-15_auditor.png | An account as the Auditor sees it, without the actions | Not started |  | N
Note on B16: Screen ID The screen of the image, as in the FRS and the deck Mandatory: Yes Format: SCR-, NAV- or DO- and a number Allowed values: Free entry Example: SCR-NB-01
Note on C16: Screen name The title of the screen Mandatory: Yes Format: Text Allowed values: Free entry Example: Clients
Note on D16: Persona(s) The personas who see the screen in this state Mandatory: Yes Format: Text Allowed values: Free entry Example: Marketing Account Officer
Note on E16: Flow The end-to-end flow that shows the image, if any Mandatory: No Format: Flow ID and title Allowed values: Free entry
Note on F16: Step The step of the flow Mandatory: No Format: Whole number Allowed values: A whole number from 1 to 99
Note on G16: State The state of the screen on the image Mandatory: Yes Format: From the list Allowed values: List State of a screen image: 12 values, see Reference lists Example: Default
Note on H16: FRS section The section of the FRS (or handbook) that specifies the screen Mandatory: Yes Format: Section number Allowed values: Free entry Example: 13.1.1
Note on I16: Requirement IDs The functional requirements of the screen Mandatory: No Format: FR-... separated by commas Allowed values: Free entry Example: FR-NB-030, FR-NB-046
Note on J16: Image file The file of the image package (09) Mandatory: Yes Format: <Screen ID>_<state>.png Allowed values: Free entry Example: SCR-NB-01_list.png
Note on K16: What the image shows The caption of the image Mandatory: No Format: Text Allowed values: Free entry Example: Clients work list, All Clients tab
Note on L16: UXD status The status of the design of this screen state, kept by the UX Design team Mandatory: Yes Format: From the list Allowed values: Not started, In design, Ready for review, Approved (list UXD status) Example: Not started
Note on M16: UXD comments Comments of the UX Design team on the screen state Mandatory: No Format: Text Allowed values: Free entry
Note on N16: Changed in this issue Y when the image is new or changed in this issue of the set Mandatory: Yes Format: Y or N Allowed values: Y or N Example: N
Note on O16: Change reference The change reference (comment, change request or issue change) that changed the image Mandatory: Conditional: when Changed in this issue is Y Format: Reference Allowed values: Free entry

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | UX screen register: Changed in this issue | Y | Yes
|  | N | No
State of a screen image (UX_STATE) | UX screen register: State | Default
Filled
Validation error
Confirmation with reason
Success message
Empty list
Read-only or locked
Pending approval
Rejected or returned
Document as received
Landing page
Menu
UXD status (UXD_STATUS) | UX screen register: UXD status | Not started
In design
Ready for review
Approved
Templates of this workbook (TEMPLATES) | Questions and comments: Template | UXR UX screen register
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed
Status (STATUS) | Start here: Status | Not started
In progress
Ready for review
Confirmed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100