## Cover
CHANGE CONTROL
CR Effort Estimate
Operations Cashiering; goes with the FRS Operations Cashiering v3.4
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Effort | Man-days of 8 hours, plus or minus 20 percent, for the open change requests only. | 3
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
CR Effort Estimate, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Effort | CR
Effort | Title
Effort | Analysis and design
Effort | Backend
Effort | Frontend
Effort | Testing
Effort | Documentation and UAT
Effort | Total

## Effort
Effort
Man-days of 8 hours, plus or minus 20 percent, for the open change requests only.
CR | Title | Analysis and design | Backend | Frontend | Testing | Documentation and UAT | Total
CR-CSH-101 | Time rules of the Cashiering stages: overdue marker and reminder | 1 | 2.5 | 1 | 1.5 | 0.5 | 6.5
CR-CSH-102 | Each user chooses an e-mail copy of the Cashiering notices | 0.5 | 1 | 1 | 0.5 | 0.5 | 3.5
Total | Open change requests | 1.5 | 3.5 | 2 | 2 | 1 | 10