## Cover
CHANGE CONTROL
Change Request Register
Renewal; goes with the FRS Renewal v1.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | Change requests of BRD-06 Renewal. | 4
Decision Log | Decision Log | 2
Legend
Open
Closed
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | CR
Register | Title
Register | Status v1.1 |  | Open, Withdrawn, Closed, Approved, Rejected
Register | Reference
Register | Man-days
Register | Note
Decision Log | Date
Decision Log | Item
Decision Log | Decision

## Register
Register
Change requests of BRD-06 Renewal.
CR | Title | Status v1.1 | Reference | Man-days | Note
CR-RN-005 | Annual renewal budget maintenance, upload, inquiry and history | Open | FRRN.042 | 11 | Not in the BRD; delivered; BDOI approves or asks for removal.
CR-RN-008 | CBG Motor rules of Annexes D and E: depreciation, BI / PD tiers, Auto Promo to Regular | Open | FRRN.009.02 | 6.5 | Not in the BRD; delivered; BDOI approves or asks for removal.
CR-RN-015 | Placement turnaround time in business days with With Issue and resolution date | Open | FRRN.029.05 | 8 | Not in the BRD; delivered; BDOI approves or asks for removal.
CR-RN-024 | Accessibility of the Renewal screens (WCAG 2.2 level AA) | Open | NFR-ACC-01 | 20 | Not in the BRD; OOTB partial; not delivered.

## Decision Log
Decision Log
Change Request Register – BIBS – BDOI Broker System
Date | Item | Decision
11 Oct 2026 | Register v1.0 | 24 candidate changes after the product owner review (green, orange and BRD gaps).
16 Oct 2026 | Register v1.1 | Aligned with the FRS v1.3: the green point and the BRD gaps are delivered and leave the register; integration points are Integration scope; four change requests stay open (CR-RN-005, 008 and 015 delivered; CR-RN-024 not delivered).

## Lists
Status v1.1
Open
Withdrawn
Closed
Approved
Rejected