## Cover
CHANGE CONTROL
CR Effort Estimate
Renewal; goes with the FRS Renewal v1.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Effort | Man-days of 8 hours, plus or minus 20 percent, for the open change requests only. | 5
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
CR Effort Estimate, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Effort | CR
Effort | Title
Effort | Analysis and design
Effort | Backend
Effort | Frontend
Effort | Testing
Effort | Documentation and UAT
Effort | Total

## Effort
Effort
Man-days of 8 hours, plus or minus 20 percent, for the open change requests only.
CR | Title | Analysis and design | Backend | Frontend | Testing | Documentation and UAT | Total
CR-RN-005 | Annual renewal budget maintenance, upload, inquiry and history | 1.5 | 4 | 3 | 2 | 0.5 | 11
CR-RN-008 | CBG Motor rules of Annexes D and E: depreciation, BI / PD tiers, Auto Promo to Regular | 1 | 3 | 0.5 | 1.5 | 0.5 | 6.5
CR-RN-015 | Placement turnaround time in business days with With Issue and resolution date | 1 | 3 | 1.5 | 2 | 0.5 | 8
CR-RN-024 | Accessibility of the Renewal screens (WCAG 2.2 level AA) | 2 | 0 | 12 | 4 | 2 | 20
Total | Open change requests | 5.5 | 10 | 17 | 9.5 | 3.5 | 45.5