## Cover
CHANGE CONTROL
Change Request Register
Claims; goes with the FRS Claims v1.0
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-07
Version | 1.0
Date | 17 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | Change requests of BRD-07 Claims. | 12
Decision Log | Decision Log | 1
Legend
Open
Closed
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | CR
Register | Title
Register | Status v1.0 |  | Open, Withdrawn, Closed, Approved, Rejected
Register | Reference
Register | Man-days
Register | Note
Decision Log | Date
Decision Log | Item
Decision Log | Decision

## Register
Register
Change requests of BRD-07 Claims.
CR | Title | Status v1.0 | Reference | Man-days | Note
CR-CLM-101 | Claims Reporting Form by the Marketing Account Officer: draft, CRF reference, submit, accept or return, conversion to a claim | Open | FRCLM.008.01, 002.03 | 13 | BDOI's FRS; not in the BRD; not offered.
CR-CLM-102 | Approval of follow-ups and record changes by the Team Leader and Team Head, with return comments and approval queues | Open | FRCLM.010, 003.04 | 14.5 | BDOI's FRS; not in the BRD.
CR-CLM-103 | Dashboards of the Claims Handler, Team Leader and Team Head: team measures, lead measures, SLA/TAT, workload, groupings | Open | FRCLM.001.02 to .04 | 17 | BDOI's FRS; not in the BRD.
CR-CLM-104 | Visibility of claims by hierarchy: handler own, Team Leader team, Team Head all | Open | FRCLM.009.02 | 8.5 | BDOI's FRS; BRD gives view access to all covers (Q-CL-07).
CR-CLM-105 | Claim types by risk code, claim categories and claim severity masters with filtering | Open | FRCLM.005.02 to .04 | 9.5 | BDOI's FRS; not in the BRD.
CR-CLM-106 | Adjuster and appraiser master with contact details | Open | FRCLM.004.02 | 5 | BDOI's FRS; the BRD asks for the list only.
CR-CLM-107 | Formal Loss Advice templates with versions, effectivity dates and the consolidated letter | Open | FRCLM.007.01 | 9.5 | BDOI's FRS; the BRD asks for the loss advice only.
CR-CLM-108 | Risk-code blocks of the claim (Motor, Health with hospital list, Mortgage Redemption) and the Total Loss tag | Open | FRCLM.008.10, 017.02 | 12 | BDOI's FRS (Annex P).
CR-CLM-109 | Turnaround dates on the follow-up and the Insurers' Scorecard (A to F, acceptance rate, average TAT) | Open | FRCLM.020, 009.04 | 11.5 | BDOI's FRS (Annex AB).
CR-CLM-110 | Claims KRA report (Annex AC) | Open | FRCLM.019 | 7 | BDOI's FRS; Annex AC not received.
CR-CLM-111 | Sustainability report, claims input | Open | FRCLM.018 | 5.5 | BDOI's FRS; content to confirm.
CR-CLM-112 | Settlement fields, settlement check registry and certificate of no claim (Annexes R, S, T) | Open | FRCLM.023.03 | 10 | BDOI's FRS; annexes empty; effort indicative (Q-CL-05).

## Decision Log
Decision Log
Change Request Register – BIBS – BDOI Broker System
Date | Item | Decision
17 Oct 2026 | Register v1.0 | Register v1.0: twelve change requests from BDOI's FRS v1.0 for points not in the Claims BRD and not offered by the OOTB platform; four green points offered by the OOTB platform at no cost. BDOI approves or rejects each change request.

## Lists
Status v1.0
Open
Withdrawn
Closed
Approved
Rejected