## Cover
CHANGE CONTROL
CR Effort Estimate
Claims; goes with the FRS Claims v1.0
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-07
Version | 1.0
Date | 17 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Effort | Man-days of 8 hours, plus or minus 20 percent, for the open change requests only. | 13
Delivery Work | Partial and gap requirements of the BRD scope: delivery work of the programme, not change requests; indicative man-days for planning. | 13
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
CR Effort Estimate, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Effort | CR
Effort | Title
Effort | Analysis and design
Effort | Backend
Effort | Frontend
Effort | Testing
Effort | Documentation and UAT
Effort | Total
Delivery Work | No.
Delivery Work | Delivery work in the BRD scope
Delivery Work | Requirements
Delivery Work | Man-days

## Effort
Effort
Man-days of 8 hours, plus or minus 20 percent, for the open change requests only.
CR | Title | Analysis and design | Backend | Frontend | Testing | Documentation and UAT | Total
CR-CLM-101 | Claims Reporting Form by the Marketing Account Officer: draft, CRF reference, submit, accept or return, conversion to a claim | 1.5 | 4 | 4 | 2.5 | 1 | 13
CR-CLM-102 | Approval of follow-ups and record changes by the Team Leader and Team Head, with return comments and approval queues | 1.5 | 5 | 4 | 3 | 1 | 14.5
CR-CLM-103 | Dashboards of the Claims Handler, Team Leader and Team Head: team measures, lead measures, SLA/TAT, workload, groupings | 2 | 5 | 6 | 3 | 1 | 17
CR-CLM-104 | Visibility of claims by hierarchy: handler own, Team Leader team, Team Head all | 1 | 3 | 2 | 2 | 0.5 | 8.5
CR-CLM-105 | Claim types by risk code, claim categories and claim severity masters with filtering | 1 | 3 | 3 | 2 | 0.5 | 9.5
CR-CLM-106 | Adjuster and appraiser master with contact details | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 5
CR-CLM-107 | Formal Loss Advice templates with versions, effectivity dates and the consolidated letter | 1 | 3 | 3 | 2 | 0.5 | 9.5
CR-CLM-108 | Risk-code blocks of the claim (Motor, Health with hospital list, Mortgage Redemption) and the Total Loss tag | 1.5 | 4 | 4 | 2 | 0.5 | 12
CR-CLM-109 | Turnaround dates on the follow-up and the Insurers' Scorecard (A to F, acceptance rate, average TAT) | 1.5 | 4 | 3 | 2.5 | 0.5 | 11.5
CR-CLM-110 | Claims KRA report (Annex AC) | 1 | 3 | 1 | 1.5 | 0.5 | 7
CR-CLM-111 | Sustainability report, claims input | 1 | 2 | 1 | 1 | 0.5 | 5.5
CR-CLM-112 | Settlement fields, settlement check registry and certificate of no claim (Annexes R, S, T) | 1.5 | 3 | 3 | 2 | 0.5 | 10
Total | Open change requests | 15 | 40.5 | 35.5 | 24.5 | 7.5 | 123

## Delivery Work
Delivery Work
Partial and gap requirements of the BRD scope: delivery work of the programme, not change requests; indicative man-days for planning.
No. | Delivery work in the BRD scope | Requirements | Man-days
DW-CLM-01 | Handler dashboard: ageing trend | FRCLM.001.01 | 2
DW-CLM-02 | Read access of Marketing to the claim record | FRCLM.002.02 | 2
DW-CLM-03 | Supervising Team Lead and Team Head in the handler register | FRCLM.002.06 | 2
DW-CLM-04 | Annex F status list, status types and alphabetical order | FRCLM.003.02 | 2
DW-CLM-05 | Claim type values of Annex M | FRCLM.005.01 | 1
DW-CLM-06 | Claim logging fields of Annex P in the BRD scope | FRCLM.008.02 | 4
DW-CLM-07 | Return of the claim of an unpaid policy to the Account Officer | FRCLM.008.04 | 2
DW-CLM-08 | Preview of the loss advice before sending | FRCLM.008.08 | 1
DW-CLM-09 | Follow-up list: follow-up count, plate number, aging since last follow-up | FRCLM.009.01 | 3
DW-CLM-10 | Quick view and Annex Q follow-up fields in the BRD scope | FRCLM.009.03, 009.04 | 3
DW-CLM-11 | BDOI report heading, filter set, detailed and summary presentation of the claims reports | FRCLM.011 to 017 | 10
DW-CLM-12 | Barangay level and several locations in the claims-prone report | FRCLM.017.01 | 2
DW-CLM-13 | Enable the OOTB document checklist, repair shops and list export | FRCLM.006, 007.02, 009.08 | 4