## Cover
USER STORIES
User Stories
Claims: epics and user stories with acceptance criteria
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-07
Version | 1.0
Date | 17 Oct 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Stories | One row per epic, then its stories. Issue ID and Parent link a story to its epic on import; the columns match the import file of the programme backlog. | 29
Epics | Epics with their number of stories and points (first estimate). | 5
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
User Stories, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Stories | Issue Type |  | Epic, Story
Stories | Issue ID
Stories | Parent
Stories | Story ID
Stories | Summary
Stories | Epic Name
Stories | Persona
Stories | User story
Stories | Description
Stories | Priority |  | Highest, High, Medium, Low
Stories | Labels
Stories | Component
Stories | Fix Version
Stories | Story Points
Stories | BRD IDs
Stories | FR IDs
Stories | Rule IDs
Stories | Screen
Stories | Acceptance Criteria
Epics | Epic ID
Epics | Epic
Epics | Stories
Epics | Story points

## Stories
Stories
One row per epic, then its stories. Issue ID and Parent link a story to its epic on import; the columns match the import file of the programme backlog.
Issue Type | Issue ID | Parent | Story ID | Summary | Epic Name | Persona | User story | Description | Priority | Labels | Component | Fix Version | Story Points | BRD IDs | FR IDs | Rule IDs | Screen | Acceptance Criteria
Epic | 1001 |  | EP-CLM-01 | Claims - Dashboards and access | Claims - Dashboards and access | - | - | Dashboards and access of Claims (BRD-07). Stories: 2; story points: 13. | High | BRD-07 Drop-2 | Claims | Drop 2 |  | BRD-07 | FRCLM.001.01, FRCLM.001.02, FRCLM.001.03, FRCLM.001.04, FRCLM.002.01, FRCLM.002.02, FRCLM.002.03, FRCLM.002.04, FRCLM.002.05, FRCLM.002.06 | - | - | -
Epic | 1002 |  | EP-CLM-02 | Claims - Claims masters | Claims - Claims masters | - | - | Claims masters of Claims (BRD-07). Stories: 5; story points: 26. | High | BRD-07 Drop-2 | Claims | Drop 2 |  | BRD-07 | FRCLM.003.01, FRCLM.003.02, FRCLM.003.03, FRCLM.003.04, FRCLM.004.01, FRCLM.004.02, FRCLM.004.03, FRCLM.005.01, FRCLM.005.02, FRCLM.005.03, FRCLM.005.04, FRCLM.006.01, FRCLM.006.02, FRCLM.006.03, FRCLM.007.01, FRCLM.007.02, FRCLM.007.03, FRCLM.007.04, FRCLM.007.05 | - | - | -
Epic | 1003 |  | EP-CLM-03 | Claims - Claim record and insurers | Claims - Claim record and insurers | - | - | Claim record and insurers of Claims (BRD-07). Stories: 3; story points: 23. | High | BRD-07 Drop-2 | Claims | Drop 2 |  | BRD-07 | FRCLM.008.01, FRCLM.008.02, FRCLM.008.03, FRCLM.008.04, FRCLM.008.05, FRCLM.008.06, FRCLM.008.07, FRCLM.008.08, FRCLM.008.09, FRCLM.008.10, FRCLM.021.01, FRCLM.021.02, FRCLM.022.01, FRCLM.022.02 | - | - | -
Epic | 1004 |  | EP-CLM-04 | Claims - Follow-up, approval and settlement | Claims - Follow-up, approval and settlement | - | - | Follow-up, approval and settlement of Claims (BRD-07). Stories: 4; story points: 29. | High | BRD-07 Drop-2 | Claims | Drop 2 |  | BRD-07 | FRCLM.009.01, FRCLM.009.02, FRCLM.009.03, FRCLM.009.04, FRCLM.009.05, FRCLM.009.06, FRCLM.009.07, FRCLM.009.08, FRCLM.010.01, FRCLM.010.02, FRCLM.023.01, FRCLM.023.02, FRCLM.023.03, FRCLM.024.01 | - | - | -
Epic | 1005 |  | EP-CLM-05 | Claims - Claims reports and scorecard | Claims - Claims reports and scorecard | - | - | Claims reports and scorecard of Claims (BRD-07). Stories: 10; story points: 28. | High | BRD-07 Drop-2 | Claims | Drop 2 |  | BRD-07 | FRCLM.011.01, FRCLM.011.02, FRCLM.012.01, FRCLM.012.02, FRCLM.013.01, FRCLM.013.02, FRCLM.014.01, FRCLM.014.02, FRCLM.015.01, FRCLM.015.02, FRCLM.016.01, FRCLM.016.02, FRCLM.017.01, FRCLM.017.02, FRCLM.018.01, FRCLM.019.01, FRCLM.020.01, FRCLM.020.02 | - | - | -
Story | 1101 | 1001 | US-CLM-001 | A dashboard of my claims, follow-ups and ageing | Claims - Dashboards and access | Claims Handler | As a Claims Handler, I want a dashboard of my claims, follow-ups and ageing, so that I see what to do first. | As a Claims Handler, I want a dashboard of my claims, follow-ups and ageing, so that I see what to do first. Screen: SCR-CLM-01 Claims Home. Requirements: FRCLM.001.01, FRCLM.001.02, FRCLM.001.03, FRCLM.001.04. Rules: BR-CLM-08. | High | BRD-07 Drop-2 | Claims | Drop 2 | 8 | BRD-07 | FRCLM.001.01, FRCLM.001.02, FRCLM.001.03, FRCLM.001.04 | BR-CLM-08 | SCR-CLM-01 Claims Home | (AC1) Given three of my claims due for follow-up today, when I open Claims Home, then the tile Due today shows 3. (AC2) Given a Team Leader, when I open Claims Home, then I see the totals of my team and the approvals waiting.
Story | 1102 | 1001 | US-CLM-002 | Each claims profile to have its own access | Claims - Dashboards and access | Claims Unit Head | As a Claims Unit Head, I want each claims profile to have its own access, so that claims data is seen and changed only by the right people. | As a Claims Unit Head, I want each claims profile to have its own access, so that claims data is seen and changed only by the right people. Screen: SCR-CLM-09 Claims Setup. Requirements: FRCLM.002.01, FRCLM.002.02, FRCLM.002.03, FRCLM.002.04, FRCLM.002.05, FRCLM.002.06. Rules: BR-CLM-01, BR-CLM-04. | High | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.002.01, FRCLM.002.02, FRCLM.002.03, FRCLM.002.04, FRCLM.002.05, FRCLM.002.06 | BR-CLM-01, BR-CLM-04 | SCR-CLM-09 Claims Setup | (AC1) Given a Marketing Account Officer, when I open the Claims Reports, then I see the loss reports of the accounts. (AC2) Given a handler group with its Team Lead, when a follow-up needs approval, then it goes to that Team Lead.
Story | 1103 | 1002 | US-CLM-003 | To keep the claim statuses with the roles allowed to set them | Claims - Claims masters | Claims Unit Head | As a Claims Unit Head, I want to keep the claim statuses with the roles allowed to set them, so that statuses mean the same for everybody. | As a Claims Unit Head, I want to keep the claim statuses with the roles allowed to set them, so that statuses mean the same for everybody. Screen: SCR-CLM-09 Claims Setup. Requirements: FRCLM.003.01, FRCLM.003.02, FRCLM.003.03, FRCLM.003.04. Rules: BR-CLM-01, BR-CLM-05. | High | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.003.01, FRCLM.003.02, FRCLM.003.03, FRCLM.003.04 | BR-CLM-01, BR-CLM-05 | SCR-CLM-09 Claims Setup | (AC1) Given the status list, when a handler opens Change Status, then only the statuses of his role and unit show, in alphabetical order. (AC2) Given a status that needs approval, when a handler sets it, then the change waits for the Team Leader.
Story | 1104 | 1002 | US-CLM-004 | To keep the adjusters and appraisers with their contacts | Claims - Claims masters | Claims Unit Head | As a Claims Unit Head, I want to keep the adjusters and appraisers with their contacts, so that handlers reach them quickly. | As a Claims Unit Head, I want to keep the adjusters and appraisers with their contacts, so that handlers reach them quickly. Screen: SCR-CLM-09 Claims Setup. Requirements: FRCLM.004.01, FRCLM.004.02, FRCLM.004.03. Rules: BR-CLM-01, BR-CLM-05. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.004.01, FRCLM.004.02, FRCLM.004.03 | BR-CLM-01, BR-CLM-05 | SCR-CLM-09 Claims Setup | (AC1) Given a new adjuster, when I add it with its contact, then it is selectable on the claims.
Story | 1105 | 1002 | US-CLM-005 | Claim types, categories and severities by risk code | Claims - Claims masters | Claims Unit Head | As a Claims Unit Head, I want claim types, categories and severities by risk code, so that claims are classified the same way. | As a Claims Unit Head, I want claim types, categories and severities by risk code, so that claims are classified the same way. Screen: SCR-CLM-12 Claims Masters. Requirements: FRCLM.005.01, FRCLM.005.02, FRCLM.005.03, FRCLM.005.04. Rules: BR-CLM-05. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.005.01, FRCLM.005.02, FRCLM.005.03, FRCLM.005.04 | BR-CLM-05 | SCR-CLM-12 Claims Masters | (AC1) Given a Motor policy, when the handler records a claim, then only the Motor claim types and categories are offered.
Story | 1106 | 1002 | US-CLM-006 | The documents required for each claim type to be listed and checked | Claims - Claims masters | Claims Handler | As a Claims Handler, I want the documents required for each claim type to be listed and checked, so that the insurer receives a complete file. | As a Claims Handler, I want the documents required for each claim type to be listed and checked, so that the insurer receives a complete file. Screen: SCR-CLM-04 Claim. Requirements: FRCLM.006.01, FRCLM.006.02, FRCLM.006.03. Rules: BR-CLM-09. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.006.01, FRCLM.006.02, FRCLM.006.03 | BR-CLM-09 | SCR-CLM-04 Claim | (AC1) Given a Motor claim, when I open Documents, then the required documents of Annex J for Motor are listed. (AC2) Given a required document missing, when I submit the claim to the insurer, then I am told which document is missing.
Story | 1107 | 1002 | US-CLM-007 | To keep the loss advice letter and the claims lists | Claims - Claims masters | Claims Unit Head | As a Claims Unit Head, I want to keep the loss advice letter and the claims lists, so that letters and lists follow BDOI's standards. | As a Claims Unit Head, I want to keep the loss advice letter and the claims lists, so that letters and lists follow BDOI's standards. Screen: SCR-CLM-12 Claims Masters. Requirements: FRCLM.007.01, FRCLM.007.02, FRCLM.007.03, FRCLM.007.04, FRCLM.007.05. Rules: -. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 8 | BRD-07 | FRCLM.007.01, FRCLM.007.02, FRCLM.007.03, FRCLM.007.04, FRCLM.007.05 | - | SCR-CLM-12 Claims Masters | (AC1) Given a new letter version effective 1-Jan, when a letter is generated on 2-Jan, then the new version is used.
Story | 1108 | 1003 | US-CLM-008 | To complete the claim from the reporting form and send the loss advice | Claims - Claim record and insurers | Claims Handler | As a Claims Handler, I want to complete the claim from the reporting form and send the loss advice, so that the insurer is told of the loss with complete data. | As a Claims Handler, I want to complete the claim from the reporting form and send the loss advice, so that the insurer is told of the loss with complete data. Screen: SCR-CLM-03 Record Claim. Requirements: FRCLM.008.01, FRCLM.008.02, FRCLM.008.03, FRCLM.008.04, FRCLM.008.05, FRCLM.008.06, FRCLM.008.07, FRCLM.008.08, FRCLM.008.09, FRCLM.008.10. Rules: BR-CLM-01, BR-CLM-02, BR-CLM-03, BR-CLM-06. | Highest | BRD-07 Drop-2 | Claims | Drop 2 | 13 | BRD-07 | FRCLM.008.01, FRCLM.008.02, FRCLM.008.03, FRCLM.008.04, FRCLM.008.05, FRCLM.008.06, FRCLM.008.07, FRCLM.008.08, FRCLM.008.09, FRCLM.008.10 | BR-CLM-01, BR-CLM-02, BR-CLM-03, BR-CLM-06 | SCR-CLM-03 Record Claim | (AC1) Given a fully paid policy, when I record the claim, then it gets its claim number and the loss advice can be sent. (AC2) Given an unpaid policy, when I record the claim, then it is flagged unpaid and the authorization code stays disabled.
Story | 1109 | 1004 | US-CLM-009 | A follow-up list with the ages and a quick view of each claim | Claims - Follow-up, approval and settlement | Claims Handler | As a Claims Handler, I want a follow-up list with the ages and a quick view of each claim, so that I follow up every claim on time. | As a Claims Handler, I want a follow-up list with the ages and a quick view of each claim, so that I follow up every claim on time. Screen: SCR-CLM-02 Claims Worklist. Requirements: FRCLM.009.01, FRCLM.009.02, FRCLM.009.03, FRCLM.009.04, FRCLM.009.05, FRCLM.009.06, FRCLM.009.07, FRCLM.009.08. Rules: BR-CLM-01, BR-CLM-07, BR-CLM-08. | Highest | BRD-07 Drop-2 | Claims | Drop 2 | 13 | BRD-07 | FRCLM.009.01, FRCLM.009.02, FRCLM.009.03, FRCLM.009.04, FRCLM.009.05, FRCLM.009.06, FRCLM.009.07, FRCLM.009.08 | BR-CLM-01, BR-CLM-07, BR-CLM-08 | SCR-CLM-02 Claims Worklist | (AC1) Given my claims, when I open the worklist, then each shows its last follow-up, its ages and the next follow-up date. (AC2) Given a follow-up recorded, when I save it, then the next follow-up date is set and the action plan kept.
Story | 1110 | 1004 | US-CLM-010 | To approve or return the follow-ups that need my approval | Claims - Follow-up, approval and settlement | Claims Team Leader | As a Claims Team Leader, I want to approve or return the follow-ups that need my approval, so that status changes are validated. | As a Claims Team Leader, I want to approve or return the follow-ups that need my approval, so that status changes are validated. Screen: SCR-CLM-11 Approvals. Requirements: FRCLM.010.01, FRCLM.010.02. Rules: -. | High | BRD-07 Drop-2 | Claims | Drop 2 | 8 | BRD-07 | FRCLM.010.01, FRCLM.010.02 | - | SCR-CLM-11 Approvals | (AC1) Given a follow-up with status Closed - Denied, when I approve it, then it goes to the Team Head. (AC2) Given a follow-up I deny with a comment, when I save, then it returns to the handler with my comment.
Story | 1111 | 1005 | US-CLM-011 | The Outstanding Claims report in BDOI's layout | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the Outstanding Claims report in BDOI's layout, so that management sees the open claims by insurer or type. | As a Claims / Risk user, I want the Outstanding Claims report in BDOI's layout, so that management sees the open claims by insurer or type. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.011.01, FRCLM.011.02. Rules: BR-CLM-10. | High | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.011.01, FRCLM.011.02 | BR-CLM-10 | SCR-CLM-08 Claims Reports | (AC1) Given the as-of date 30-Sep, when I run it grouped by insurer, detailed, then the claims are listed per insurer with the BDOI heading.
Story | 1112 | 1005 | US-CLM-012 | The Settled Claims report in BDOI's layout | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the Settled Claims report in BDOI's layout, so that management sees the settlements of a period. | As a Claims / Risk user, I want the Settled Claims report in BDOI's layout, so that management sees the settlements of a period. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.012.01, FRCLM.012.02. Rules: BR-CLM-10. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 2 | BRD-07 | FRCLM.012.01, FRCLM.012.02 | BR-CLM-10 | SCR-CLM-08 Claims Reports | (AC1) Given July, when I run it grouped by risk code, then the claims settled in July are listed per risk code.
Story | 1113 | 1005 | US-CLM-013 | The claims past due report | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the claims past due report, so that old claims are pursued. | As a Claims / Risk user, I want the claims past due report, so that old claims are pursued. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.013.01, FRCLM.013.02. Rules: BR-CLM-10. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 2 | BRD-07 | FRCLM.013.01, FRCLM.013.02 | BR-CLM-10 | SCR-CLM-08 Claims Reports | (AC1) Given N = 90, when I run the report, then only the claims aged more than 90 days are listed.
Story | 1114 | 1005 | US-CLM-014 | The ageing report per status | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the ageing report per status, so that bottlenecks show. | As a Claims / Risk user, I want the ageing report per status, so that bottlenecks show. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.014.01, FRCLM.014.02. Rules: BR-CLM-08, BR-CLM-10. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 2 | BRD-07 | FRCLM.014.01, FRCLM.014.02 | BR-CLM-08, BR-CLM-10 | SCR-CLM-08 Claims Reports | (AC1) Given the as-of date, when I run it, then each status shows its claims with the age in the status and overall.
Story | 1115 | 1005 | US-CLM-015 | The loss experience report with my own title | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the loss experience report with my own title, so that accounts are discussed on facts. | As a Claims / Risk user, I want the loss experience report with my own title, so that accounts are discussed on facts. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.015.01, FRCLM.015.02. Rules: BR-CLM-10. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.015.01, FRCLM.015.02 | BR-CLM-10 | SCR-CLM-08 Claims Reports | (AC1) Given a title and a loss date range, when I run it, then the report carries my title and the paid, outstanding and total per claim.
Story | 1116 | 1005 | US-CLM-016 | The loss ratio report | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the loss ratio report, so that renewal and pricing use the losses. | As a Claims / Risk user, I want the loss ratio report, so that renewal and pricing use the losses. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.016.01, FRCLM.016.02. Rules: BR-CLM-10, BR-CLM-11. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.016.01, FRCLM.016.02 | BR-CLM-10, BR-CLM-11 | SCR-CLM-08 Claims Reports | (AC1) Given a client with premium 100,000.00 and losses 40,000.00, when I run it, then the loss ratio is 40%.
Story | 1117 | 1005 | US-CLM-017 | To see the locations with frequent claims and the total losses | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want to see the locations with frequent claims and the total losses, so that risks are analysed. | As a Claims / Risk user, I want to see the locations with frequent claims and the total losses, so that risks are analysed. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.017.01, FRCLM.017.02. Rules: -. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.017.01, FRCLM.017.02 | - | SCR-CLM-08 Claims Reports | (AC1) Given three claims at one barangay in three years, when I run the report, then the location is flagged claims-prone.
Story | 1118 | 1005 | US-CLM-018 | The claims input of the sustainability report | Claims - Claims reports and scorecard | Claims / Risk user | As a Claims / Risk user, I want the claims input of the sustainability report, so that BDOI reports on climate-related losses. | As a Claims / Risk user, I want the claims input of the sustainability report, so that BDOI reports on climate-related losses. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.018.01. Rules: -. | Low | BRD-07 Drop-2 | Claims | Drop 2 | 2 | BRD-07 | FRCLM.018.01 | - | SCR-CLM-08 Claims Reports | (AC1) Given the as-of date, when I run it, then the claims with their location and catastrophe code are listed.
Story | 1119 | 1005 | US-CLM-019 | The KRA report of the claims staff | Claims - Claims reports and scorecard | Claims Team Head | As a Claims Team Head, I want the KRA report of the claims staff, so that performance is measured the same way. | As a Claims Team Head, I want the KRA report of the claims staff, so that performance is measured the same way. Screen: SCR-CLM-08 Claims Reports. Requirements: FRCLM.019.01. Rules: -. | Low | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.019.01 | - | SCR-CLM-08 Claims Reports | (AC1) Given a period and a Claims Officer, when I run the KRA, then the KRA criteria of Annex AC are scored.
Story | 1120 | 1005 | US-CLM-020 | An insurer scorecard on turnaround times | Claims - Claims reports and scorecard | Claims Team Head | As a Claims Team Head, I want an insurer scorecard on turnaround times, so that insurers are compared on service. | As a Claims Team Head, I want an insurer scorecard on turnaround times, so that insurers are compared on service. Screen: SCR-CLM-13 Insurers' Scorecard. Requirements: FRCLM.020.01, FRCLM.020.02. Rules: -. | Medium | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.020.01, FRCLM.020.02 | - | SCR-CLM-13 Insurers' Scorecard | (AC1) Given an insurer approving 96% of claims within TAT, when the scorecard runs, then its approval TAT rating is A.
Story | 1121 | 1003 | US-CLM-021 | The premium of the cover checked on every claim | Claims - Claim record and insurers | Claims Handler | As a Claims Handler, I want the premium of the cover checked on every claim, so that no claim proceeds on unpaid premium. | As a Claims Handler, I want the premium of the cover checked on every claim, so that no claim proceeds on unpaid premium. Screen: SCR-CLM-04 Claim. Requirements: FRCLM.021.01, FRCLM.021.02. Rules: BR-CLM-03. | Highest | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.021.01, FRCLM.021.02 | BR-CLM-03 | SCR-CLM-04 Claim | (AC1) Given an unpaid invoice, when the premium is paid, then the claim flag clears and the code can be generated.
Story | 1122 | 1003 | US-CLM-022 | To record what the insurers report and their location references | Claims - Claim record and insurers | Claims Handler | As a Claims Handler, I want to record what the insurers report and their location references, so that insurer communications are auditable. | As a Claims Handler, I want to record what the insurers report and their location references, so that insurer communications are auditable. Screen: SCR-CLM-04 Claim. Requirements: FRCLM.022.01, FRCLM.022.02. Rules: BR-CLM-06. | High | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.022.01, FRCLM.022.02 | BR-CLM-06 | SCR-CLM-04 Claim | (AC1) Given an e-mail from the insurer, when I record the update, then it is in the claim history with date, source and remarks.
Story | 1123 | 1004 | US-CLM-023 | To record the settlement and close or reopen claims | Claims - Follow-up, approval and settlement | Claims Team Leader | As a Claims Team Leader, I want to record the settlement and close or reopen claims, so that the claim ends with the right outcome. | As a Claims Team Leader, I want to record the settlement and close or reopen claims, so that the claim ends with the right outcome. Screen: SCR-CLM-04 Claim. Requirements: FRCLM.023.01, FRCLM.023.02, FRCLM.023.03. Rules: BR-CLM-05. | High | BRD-07 Drop-2 | Claims | Drop 2 | 5 | BRD-07 | FRCLM.023.01, FRCLM.023.02, FRCLM.023.03 | BR-CLM-05 | SCR-CLM-04 Claim | (AC1) Given a settlement type that closes the claim, when I set it with the amount and date, then the claim is closed permanently. (AC2) Given a closed claim, when the Team Head reopens it with a reason, then it is In Progress again.
Story | 1124 | 1004 | US-CLM-024 | To ask for the premium remittance a claim waits for | Claims - Follow-up, approval and settlement | Claims Handler | As a Claims Handler, I want to ask for the premium remittance a claim waits for, so that the insurer releases the claim. | As a Claims Handler, I want to ask for the premium remittance a claim waits for, so that the insurer releases the claim. Screen: SCR-CLM-04 Claim. Requirements: FRCLM.024.01. Rules: -. | High | BRD-07 Drop-2 | Claims | Drop 2 | 3 | BRD-07 | FRCLM.024.01 | - | SCR-CLM-04 Claim | (AC1) Given a claim in With BDOI - For Premium Remittance, when the batch is fully remitted, then I am told and the claim flag clears.

## Epics
Epics
Epics with their number of stories and points (first estimate).
Epic ID | Epic | Stories | Story points
EP-CLM-01 | Dashboards and access | 2 | 13
EP-CLM-02 | Claims masters | 5 | 26
EP-CLM-03 | Claim record and insurers | 3 | 23
EP-CLM-04 | Follow-up, approval and settlement | 4 | 29
EP-CLM-05 | Claims reports and scorecard | 10 | 28

## Lists
Issue Type | Priority
Epic | Highest
Story | High
Medium
Low