## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
User Access Maintenance; goes with the FRS User Access Maintenance v1.6
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.3
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Inputs | Open questions, dependencies and settings of the FRS v1.6. | 29
Legend
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.3. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Inputs | No.
Inputs | What BDOI provides or decides
Inputs | Owner
Inputs | Needed by
Inputs | Status |  | Open, Received, Confirmed
Inputs | Answer

## Inputs
Inputs
Open questions, dependencies and settings of the FRS v1.6.
No. | What BDOI provides or decides | Owner | Needed by | Status | Answer
Q-UA-01 | Working hours for the out-of-hours second approval (today every hour of every day, so no change is out of hours)? | Information Security | 01 Dec 2026 | Open
Q-UA-02 | Dormancy period and notice: keep 90 and 7 days? | Business Administration | 01 Dec 2026 | Open
Q-UA-03 | Apply an approved group-profile change at approval, or after implementation by the System Administrator? | Information Security | 01 Dec 2026 | Open
Q-UA-04 | Certification frequency and the reviewers who receive the extract? | Internal Audit | 01 Dec 2026 | Open
Q-UA-05 | Approve change request CR-UA-007 (data access by company and branch)? | Business Administration | 01 Dec 2026 | Open
Q-UA-06 | Approve change request CR-UA-016 (emergency direct edit of group profiles)? | Information Security | 01 Dec 2026 | Open
D-UA-01 | BDOI IT registers BIBS in Entra ID for each environment (client, redirect address). | BDOI IT | Before SIT | Open
D-UA-02 | BDOI IT connects UIDM-ISC to the BIBS SCIM service through the API gateway, with test events in SIT and UAT. | BDOI IT | Before SIT | Open
D-UA-03 | BDOI provides the target User Access Matrix (group profiles and permissions) before SIT. | BDOI IT | Before SIT | Open
D-UA-04 | The users and group profiles at go-live are loaded by Data Migration (BRD-13). | BDOI | Before SIT | Open
P-01 | Confirm the value of: Session timeout (default 30 minutes) | Information Security | 01 Dec 2026 | Open
P-02 | Confirm the value of: Inactivity warning before sign-out (default 15 minutes) | Information Security | 01 Dec 2026 | Open
P-03 | Confirm the value of: Warning before the session ends (default 30 minutes) | Information Security | 01 Dec 2026 | Open
P-04 | Confirm the value of: Bank's inactivity warning wording (default Yes) | Information Security | 01 Dec 2026 | Open
P-05 | Confirm the value of: Session timed-out page (default Yes) | Information Security | 01 Dec 2026 | Open
P-06 | Confirm the value of: Dormant after (default 90 days) | Information Security | 01 Dec 2026 | Open
P-07 | Confirm the value of: Dormancy notice before (default 7 days) | Information Security | 01 Dec 2026 | Open
P-08 | Confirm the value of: Failed sign-ins before lock-out (default 3) | Information Security | 01 Dec 2026 | Open
P-09 | Confirm the value of: Password expires after (default 90 days) | Information Security | 01 Dec 2026 | Open
P-10 | Confirm the value of: Minimum password age (default 1 day) | Information Security | 01 Dec 2026 | Open
P-11 | Confirm the value of: Previous passwords not reused (default 10) | Information Security | 01 Dec 2026 | Open
P-12 | Confirm the value of: Password expiry notice (default 7 days) | Information Security | 01 Dec 2026 | Open
P-13 | Confirm the value of: Password reset by another administrator only (default Yes) | Information Security | 01 Dec 2026 | Open
P-14 | Confirm the value of: Provisioning from UIDM-ISC (default Yes) | Information Security | 01 Dec 2026 | Open
P-15 | Confirm the value of: Group profiles from UIDM-ISC events (default Yes) | Information Security | 01 Dec 2026 | Open
P-16 | Confirm the value of: Reconciliation every (default 1 day) | Information Security | 01 Dec 2026 | Open
P-17 | Confirm the value of: Apply a group-profile change at approval (default No (System Administrator implements)) | Information Security | 01 Dec 2026 | Open
P-18 | Confirm the value of: Working hours (default 00:00-24:00, MON-SUN (BDOI to set, Q-UA-01)) | Information Security | 01 Dec 2026 | Open
P-19 | Confirm the value of: Emergency direct edit of group profiles (default No) | Information Security | 01 Dec 2026 | Open

## Lists
Status
Open
Received
Confirmed