## Cover
USER ACCEPTANCE
Business Unit Walkthrough Users
User Access Maintenance; goes with the FRS User Access Maintenance v1.6
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.3
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | One walkthrough account per persona of the FRS v1.6. | 5
Script | The storyboards of the Process and Storyboards v1.6, step by step. | 27
Legend
Pass
Fail
Blocked
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.3. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona
Users | Walkthrough account
Users | Does
Users | Screens
Users | Sign-in
Script | Storyboard
Script | Step
Script | Who
Script | Screen
Script | Does
Script | Sees
Script | Result |  | Not run, Pass, Fail, Blocked

## Users
Users
One walkthrough account per persona of the FRS v1.6.
Persona | Walkthrough account | Does | Screens | Sign-in
User Access Administrator | Ursula Access Administrator | Looks after the users received from UIDM-ISC: data access, unlock, end of sessions; watches Identity Sync and resolves refused events and reconciliation mismatches; proposes UAM settings. | Users, Group Profiles (read), Identity Sync, Separation of Duties (read), Access Matrix, Reports & Certification, Audit Log, UAM Settings | Issued separately by the iorta TechNXT Project Team; sign-in through Microsoft Entra ID where the tenant is connected
Group Profile Maker | Rhea Access Requestor | Proposes new group profiles and changes, deactivations and reactivations of group profiles; corrects a returned change; withdraws an own change. | Group Profiles, Access Matrix, Reports & Certification | Issued separately by the iorta TechNXT Project Team; sign-in through Microsoft Entra ID where the tenant is connected
Group Profile Checker | Ulysses Access Approver | Approves, returns or rejects a group-profile change made by someone else. A second checker gives the second approval of a High or Admin profile or of a change outside the working hours. | Group Profiles, Access Matrix, Reports & Certification | Issued separately by the iorta TechNXT Project Team; sign-in through Microsoft Entra ID where the tenant is connected
Information Security | Ingrid Security Officer | Authorises separation-of-duties rules, follows the violations, approves UAM settings, receives the alerts and oversees certification. | Group Profiles (read), Separation of Duties, Access Matrix, Reports & Certification, Audit Log, UAM Settings | Issued separately by the iorta TechNXT Project Team; sign-in through Microsoft Entra ID where the tenant is connected
Auditor | Audrey Access Auditor | Reads every User Access screen, runs the reports and takes the certification extract. Changes nothing. | Users, Group Profiles, Separation of Duties, Access Matrix, Reports & Certification, Audit Log | Issued separately by the iorta TechNXT Project Team; sign-in through Microsoft Entra ID where the tenant is connected

## Script
Script
The storyboards of the Process and Storyboards v1.6, step by step.
Storyboard | Step | Who | Screen | Does | Sees | Result
SB-1 Joiner to first sign-in | 1 | UIDM-ISC | Identity Sync › Events | Sends the joiner and the group-profile event of UIDM-2026-005196. | Two events for BDO\inavarro, both Applied. | Not run
SB-1 Joiner to first sign-in | 2 | User Access Administrator | Users | Searches a01300019. | Isabel Navarro is Active with Marketing Account Officer. | Not run
SB-1 Joiner to first sign-in | 3 | User Access Administrator | User › Profile | Opens the user. | Account data and the data sent by UIDM-ISC, with the request number. | Not run
SB-1 Joiner to first sign-in | 4 | User Access Administrator | User › Group Profiles | Opens Group Profiles. | Marketing Account Officer, source UIDM-ISC, with the date and request number. | Not run
SB-1 Joiner to first sign-in | 5 | Isabel Navarro | Sign in | Opens BIBS and clicks Sign in with Microsoft Entra ID. | Entra ID asks for her password and second factor. | Not run
SB-1 Joiner to first sign-in | 6 | Isabel Navarro | Home | Is signed in. | The New Business Dashboard and only the menus of a Marketing Account Officer. | Not run
SB-1 Joiner to first sign-in | 7 | User Access Administrator | User › Sessions | Checks the first session. | One open session with the sign-in time. | Not run
SB-2 Mover and leaver | 1 | UIDM-ISC | Identity Sync › Events | Sends the mover and group-profile events of UIDM-2026-005240. | Mover and Group profiles events Applied. | Not run
SB-2 Mover and leaver | 2 | User Access Administrator | User › Group Profiles | Opens Isabel's group profiles. | Marketing Team Leader active; Marketing Account Officer removed. | Not run
SB-2 Mover and leaver | 3 | User Access Administrator | User › Access History | Opens the history. | Each attribute with its from and to value and the UIDM request number. | Not run
SB-2 Mover and leaver | 4 | UIDM-ISC | User › Profile | Sends the leaver of UIDM-2026-005251 for Carlo Mendoza. | Carlo is Inactive; his sessions are ended. | Not run
SB-2 Mover and leaver | 5 | Auditor | User › Access History | Reads Carlo's history. | Deactivation with the UIDM request number. | Not run
SB-3 Group-profile change under maker-checker | 1 | Group Profile Maker | Group Profile › Definition | Opens Marketing Account Officer. | Definition, members and the Propose Change button. | Not run
SB-3 Group-profile change under maker-checker | 2 | Group Profile Maker | Propose Change | Adds the permission, enters the reason, clicks Submit for Approval. | The permission picker by area and the reason field. | Not run
SB-3 Group-profile change under maker-checker | 3 | Group Profile Maker | Pending Change | Reads the submitted change. | AR-2026-000001 Pending, maker Rhea, permission added. | Not run
SB-3 Group-profile change under maker-checker | 4 | Group Profile Checker | Pending Change | Opens the change from the notice. | Approve, Return for Correction and Reject. | Not run
SB-3 Group-profile change under maker-checker | 5 | Group Profile Checker | Approve | Enters a remark and confirms. | The change goes to implementation. | Not run
SB-3 Group-profile change under maker-checker | 6 | System Administrator | Pending Change | Implements the approved change. | For Implementation with the Implement button; then Implemented. | Not run
SB-3 Group-profile change under maker-checker | 7 | Auditor | Group Profile › History | Reads the history. | Change number, maker, checker, date and status. | Not run
SB-4 Refused event and reconciliation | 1 | User Access Administrator | Identity Sync › Refused | Opens the alert. | Event refused: no group profile MKT_SUPERVISOR. | Not run
SB-4 Refused event and reconciliation | 2 | User Access Administrator | Dismiss | Enters the remark after UIDM-ISC corrected the request. | The event is closed with the remark. | Not run
SB-4 Refused event and reconciliation | 3 | User Access Administrator | Identity Sync › Reconciliation | Clicks Synchronise Now. | Mismatch: status differs for a013000196. | Not run
SB-4 Refused event and reconciliation | 4 | User Access Administrator | Identity Sync › Status | Checks the connection. | Last call, last success, errors, refused events and open mismatches. | Not run
SB-5 Evidence for the auditor and certification | 1 | Auditor | Reports & Certification | Opens the reports. | Five reports and the certification extract. | Not run
SB-5 Evidence for the auditor and certification | 2 | Auditor | Take Extract | Chooses XLSX and confirms. | The extract is logged with rows and SHA-256; Information Security is told. | Not run
SB-5 Evidence for the auditor and certification | 3 | Auditor | Audit Log | Reads the user access events. | Every event with from and to values, who and when. | Not run
SB-5 Evidence for the auditor and certification | 4 | Auditor | Access Matrix | Checks the group profiles against the permissions. | The matrix, exportable to Excel. | Not run

## Lists
Result
Not run
Pass
Fail
Blocked