CHANGE REGISTER

Change Management Register - Summary

Deviations from the BRDs that go through change control, with effort in man-days

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-CMR-BRD-00-S |
| Version | 1.0 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 26 Sep 2026 | iorta TechNXT Business Analyst lead | iorta TechNXT Solution Architect | BIBS Product Owner (pending) | First issue with the register v1.0 (status as of 26 September 2026) |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| BIBS Product Owner | Approver | BDOI | Chair of the Change Control Board |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Plan, drops and effort |
| Owners of BRD-1 to BRD-13 | Reviewers | BDOI | Decision owners of the CRs of their BRD |
| BDOI IT (integration owners) | Reviewer | BDOI | Interface and infrastructure CRs |
| Project team | Delivery | iorta TechNXT | Impact analysis, scheduling, FRS revisions |

Contents

1 Purpose and scope	4

1.1 Purpose	4

1.2 What the register contains	4

1.3 Sources	4

1.4 What is not in the register	5

2 The change-control process	5

2.1 Steps and roles	5

2.2 Change Control Board	6

2.3 How the statuses are used in this issue	6

3 Headline figures	7

3.1 Totals	7

3.2 By drop	7

3.3 By deviation type	7

3.4 By CR status	8

3.5 By BRD	8

4 Top 20 deviations by effort and impact	8

5 Decisions needed from BDOI	9

6 Estimation basis	10

7 Sign-off	11

# 1 Purpose and scope

## 1.1 Purpose

Status of this document. For documentation and change control; does not change the platform or the FRS baseline. The register records where BIBS differs from the BRDs and what it takes to close each difference. An approved change reaches the FRS only through an FRS revision that cites the CR ID.

The BRDs were written before BIBS and, in several places, for the legacy systems (EBIX, QPS, ISYS) that BIBS replaces. The FRS of each BRD records, in its chapter of proposed business rules and clarifications, where the proposed behaviour differs from the BRD text. BDOI's decisions of 26 September 2026 (single go-live, no Employee Benefits portal, documents in S3, reinsurance through Remittance, package remapping at sanitation, January to May 2028 renewals in BIBS, year-end option A) add more. This document and its workbook bring all of these into one master list, so that each deviation is decided once by the Change Control Board (CCB), with its effort known.

## 1.2 What the register contains

The workbook BIBS_Change_Register_BRD-00_Change_Management_v1.0.xlsx has one row per deviation: 178 change requests (CR-0001 to CR-0178 in the workbook), each with the drop, the BRD and its requirement IDs and pages, the FRS FR IDs, the deviation type, the BRD requirement, the proposed behaviour, the reason, the business impact, the affected departments, the effort in man-days (Analysis, Development, Test, Documentation), the priority, the CR status, the BDOI decision owner, the register and question references, and the target drop or release.

Table 1: Sheets of the workbook

| Sheet | Content |
| --- | --- |
| Cover, Document control | Title, version, the statement above, baseline, version history, review and approval, distribution |
| How to read | Reading guide, the nine deviation types, CR statuses, priorities, size classes and every column |
| Register | The 178 CRs; filters, drop-down lists, frozen headers; printed on A3 landscape, two pages across |
| Summary | Counts and man-days by drop, BRD, type, status and priority, recalculated from the Register |
| Effort basis | Team roles, the man-day, what is included and excluded, size classes, man-days by activity |
| Change control | The eight-step process with roles and times; the proposed CCB membership and its rules |
| CR form | The change request form to fill, sign and file for each CR |

## 1.3 Sources

Deviations were taken from these sources and merged where two sources record the same point; the Source column of the register keeps every reference.

•	The FRS of each BRD: the chapter "Proposed business rules and clarifications for confirmation", the scope exclusions of every FRS and the out-of-scope IDs of FRS BRD-6, and chapter 5 of the umbrella FRS BRD-00.

•	The requirements baselines of the BRDs.

•	The BRD discrepancy and clarification register v1.2 (conflicts between BRDs, BRD against platform, NFR items, DCR-210 to DCR-243).

•	The programme alignment pack (drop and integration mismatches, IER), the architecture option and document storage decisions, and the cross-BRD decisions D1 to D10.

•	BDOI's answers of 26 September 2026 (A1 to A6 and DMQ36 to DMQ39).

## 1.4 What is not in the register

•	Open questions that do not change a requirement (they stay in the discrepancy register until answered).

•	The delivery of what the FRS specify (Renewal, Employee Benefits, Customer Servicing Facility, Submitted Policies, Data Migration, Claims) is not a change. Only the delta caused by a deviation is estimated.

•	Document-quality items of the BRD pack (typing, numbering, names).

•	Scope that a BRD itself puts out (for example New Business OOS-1 and OOS-2), except where a BDOI addendum removed a requirement that the main BRD still carries.

# 2 The change-control process

## 2.1 Steps and roles

Every deviation in the register, and every new change request, follows the same eight steps. The register is the log; the CR form is the record of each decision.

Table 2: Change-control process

| Step | What happens | Who | Output | Time |
| --- | --- | --- | --- | --- |
| 1. Request | Anyone in BDOI or the project team raises a change request on the CR form, or the project team raises a CR from a recorded deviation (FRS clarifications, register, alignment pack). | Requester; Project Manager (iorta TechNXT) logs it | CR row in this register, status Draft | Same day |
| 2. Impact analysis | The business analyst and solution architect assess scope, BRD and FRS references, affected modules, data, interfaces, tests, documents and drop; estimate effort in man-days (Analysis, Development, Test, Documentation). | Business analyst, Solution architect; BDOI owner of the BRD for business impact | Impact analysis on the CR form; status For CCB review | 5 working days (10 for L / XL) |
| 3. CCB review | The Change Control Board reviews the CR at its fortnightly meeting (or ad hoc for High priority items): accept, reject, defer, or ask for more analysis. | Change Control Board | Minutes with the decision per CR | Fortnightly |
| 4. Approval | Approved CRs are signed on the CR form by the BDOI decision owner and the BIBS Product Owner. A CR above 25 man-days, or one that moves a drop date, also needs the Program Manager. | Decision owner; BIBS Product Owner; Program Manager (L / XL, date change) | Status Approved or Rejected; signed CR form | Within 5 working days of the CCB |
| 5. Schedule | The Project Manager places the CR in a drop or release and updates the plan, the FRS change list and the test plan scope. | Project Manager (iorta TechNXT); BDOI Program Manager | Target drop / release set; plan updated | Next planning cycle |
| 6. Implement | The team delivers and documents the change: configuration, FRS revision, test cases, user and configuration guides. | Delivery team | Delivered change, FRS revision, test cases | As scheduled |
| 7. Verify | QA runs the SIT cases and regression; the BDOI owner checks the behaviour in SIT or UAT against the CR. | QA engineer; BDOI owner of the BRD | Test evidence; acceptance by the owner | Within the drop SIT / UAT window |
| 8. Close | The Project Manager records the result, the FRS version that carries it and the closing date; the CR is reported in the release notes. | Project Manager; BIBS Product Owner | Status Implemented; release note entry | At release |

## 2.2 Change Control Board

The CCB decides every CR. The owner of the BRD concerned is the decision owner and attends for the CRs of that BRD.

Table 3: Change Control Board (proposed)

| Member | Organisation | Role on the board |
| --- | --- | --- |
| BIBS Product Owner | BDOI | Chair; casting vote on scope and priority |
| Program Manager, Business Project Services | BDO Unibank ESG | Plan, drops and budget; approves L / XL items and date changes |
| Owner of the BRD concerned (department head or product owner) | BDOI | Decision owner of the CR; attends for the CRs of the BRD |
| Head, Comptrollership | BDOI | Member for any CR that touches posting, GL, tax or BIR reports |
| Chief Compliance Officer (or delegate) | BDOI | Member for any CR that touches screening, KYC, access control or retention |
| BDOI IT (integration owner) | BDOI | Member for interfaces and infrastructure items |
| Project Manager | iorta TechNXT | Secretary: agenda, register, minutes, schedule |
| Solution Architect | iorta TechNXT | Presents impact analysis and effort |
| Business Analyst lead | iorta TechNXT | Presents BRD / FRS references and test impact |

Rules of the board:

•	Quorum: the chair (or a named delegate), the Program Manager and the decision owner of each CR on the agenda.

•	The CCB meets every two weeks from October 2026 to go-live, and ad hoc for High priority items that block a drop.

•	A CR above 25 man-days, or one that moves a drop or the go-live date, needs the Program Manager's approval.

•	Rejected CRs keep their row with the reason; the BRD text stands.

## 2.3 How the statuses are used in this issue

•	For acceptance - 56 CRs. The proposed behaviour is decided and documented and differs from the BRD text. No work remains; the CCB records the acceptance, or raises a new CR if it wants the BRD text delivered instead (the "BRD as written" column gives the indicative effort).

•	For CCB review - 43 CRs. Impact analysis is complete and the item can be decided now, most of them on a proposal or a BDOI decision already given.

•	Draft - 79 CRs. The impact analysis is done but the item needs a BDOI answer (values, layouts, interfaces or a yes / no on scope) before the CCB can decide.

No row is Approved or Rejected yet: the CCB has not met. BDOI's decisions of 26 September 2026 are recorded as "For CCB review" so that the board records them formally.

# 3 Headline figures

## 3.1 Totals

Table 4: Headline figures

| Figure | Value |
| --- | --- |
| Change requests in the register | 178 |
| Open (Draft or For CCB review) | 122 |
| For acceptance | 56 |
| High priority (all / open) | 29 / 27 |
| CRs with no remaining effort (0 man-days) | 71 |
| CRs of size L (11-25 man-days) / XL (over 25) | 31 / 4 |
| Man-days to close all open deviations | 936 |
| of which Analysis / Development / Test / Documentation | 154 / 424 / 258 / 100 |

The 936 man-days are the work still needed to close the deviations as proposed. Not all of it is additional to the BRD scope: part of it (for example the umbrella gaps, the S3 store and the EIAM sign-in) is work the programme needs anyway; the register makes it visible and puts it under change control. Integration dependencies (269 man-days) and items deferred pending a BDOI answer (287 man-days) make up 59 percent of the total, so most of the effort is released only by BDOI answers and interface specifications. Drop 1 carries the most effort (422 man-days).

## 3.2 By drop

Table 5: Deviations and man-days by drop

| Drop | Scope | CRs | High | Open | Analysis | Dev. | Test | Doc. | Total md |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Drop 0 | Setup and Data Migration | 30 | 7 | 27 | 33 | 98 | 63 | 21 | 215 |
| Drop 1 | Transactional (upstream and downstream) | 100 | 14 | 58 | 71 | 191 | 122 | 38 | 422 |
| Drop 2 | Independent | 18 | 2 | 14 | 24 | 52 | 33 | 14 | 123 |
| Programme | Programme (cross-drop) | 29 | 6 | 22 | 26 | 83 | 40 | 26 | 175 |
| Phase 2 | Reinsurance module | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 |
| Total |  | 178 | 29 | 122 | 154 | 424 | 258 | 100 | 936 |

## 3.3 By deviation type

Table 6: Deviations and man-days by type

| Deviation type | CRs | High | Open | Analysis | Dev. | Test | Doc. | Total md |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope addition — beyond BRD | 15 | 1 | 8 | 17 | 53 | 28 | 9 | 107 |
| Scope reduction / descoped | 14 | 2 | 7 | 2 | 3 | 3 | 5 | 13 |
| Behaviour differs from BRD | 45 | 2 | 12 | 8 | 22 | 13 | 3 | 46 |
| Deferred pending BDOI answer | 37 | 5 | 37 | 51 | 124 | 85 | 27 | 287 |
| Deferred to Phase 2 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 |
| BRD conflict resolved by decision | 21 | 4 | 12 | 6 | 7 | 8 | 4 | 25 |
| Integration dependency | 21 | 5 | 21 | 43 | 129 | 74 | 23 | 269 |
| NFR / infrastructure change | 13 | 5 | 13 | 18 | 58 | 27 | 21 | 124 |
| Data migration | 11 | 5 | 11 | 9 | 28 | 20 | 7 | 64 |
| Total | 178 | 29 | 122 | 154 | 424 | 258 | 100 | 936 |

## 3.4 By CR status

Table 7: Deviations and man-days by CR status

| CR status | CRs | High | Open | Analysis | Dev. | Test | Doc. | Total md |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Draft | 79 | 12 | 79 | 124 | 348 | 212 | 65 | 749 |
| For CCB review | 43 | 15 | 43 | 30 | 76 | 46 | 35 | 187 |
| For acceptance | 56 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total | 178 | 29 | 122 | 154 | 424 | 258 | 100 | 936 |

## 3.5 By BRD

Table 8: Deviations and man-days by BRD

| BRD | Name | CRs | High | Open | Analysis | Dev. | Test | Doc. | Total md |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BRD-00 | Core Replacement (umbrella) and programme | 42 | 6 | 36 | 49 | 145 | 76 | 42 | 312 |
| BRD-01 | New Business | 27 | 1 | 12 | 20 | 61 | 36 | 12 | 129 |
| BRD-02 | Operations | 21 | 4 | 6 | 11 | 25 | 15 | 5 | 56 |
| BRD-03 | Product Maintenance | 4 | 1 | 3 | 3 | 5 | 5 | 3 | 16 |
| BRD-04 | Collections | 15 | 0 | 9 | 11 | 30 | 18 | 5 | 64 |
| BRD-05 | Accounting, Disbursement and ACSL | 20 | 6 | 14 | 18 | 47 | 32 | 7 | 104 |
| BRD-06 | Renewal | 10 | 3 | 9 | 5 | 16 | 12 | 5 | 38 |
| BRD-07 | Claims | 5 | 1 | 3 | 5 | 8 | 7 | 2 | 22 |
| BRD-08 | Employee Benefits | 5 | 1 | 4 | 5 | 10 | 7 | 4 | 26 |
| BRD-09 | Customer Servicing Facility | 3 | 0 | 3 | 0 | 2 | 1 | 0 | 3 |
| BRD-10 | Sanction Screening | 6 | 1 | 6 | 9 | 23 | 16 | 5 | 53 |
| BRD-11 | User Access Maintenance | 7 | 1 | 4 | 6 | 23 | 13 | 5 | 47 |
| BRD-12 | Submitted Policies | 4 | 2 | 4 | 5 | 13 | 8 | 2 | 28 |
| BRD-13 | Data Migration | 9 | 2 | 9 | 7 | 16 | 12 | 3 | 38 |
| Total |  | 178 | 29 | 122 | 154 | 424 | 258 | 100 | 936 |

# 4 Top 20 deviations by effort and impact

Table 9: Open CRs ranked by man-days x priority weight (High 3, Medium 2, Low 1); full text in the Register

| CR | BRD | BRD asks | Proposed | Man-days | Priority | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CR-0028 | BRD-00 | Documents and attachments are stored in an S3 bucket only. | Proposed: every file in S3 with its metadata in PostgreSQL. | 36 (XL) | High | For CCB review |
| CR-0117 | BRD-05 | The 138 reports and schedules of Appendix A. | 28 schedule definitions and 58 report-pack entries with draft layouts. | 29 (XL) | High | For CCB review |
| CR-0027 | BRD-00 | The IER sizes ten microservices, three tenants, Aurora and MongoDB per tenant, Istio and ... | BIBS stays a modular monolith on one PostgreSQL database, deployed on EKS as four workloads (web, jobs, integration ... | 28 (XL) | High | For CCB review |
| CR-0161 | BRD-11 | BRD-11 makes an approved request in BIBS the only way to change a user or a group profile. | Proposed: UIDM-ISC provisions users and group-profile assignments through an API (SCIM 2.0 or its connector) with the ... | 27 (XL) | High | Draft |
| CR-0002 | BRD-02 | The Operations BRD specifies remittance to insurers only. | Proposed: the named reinsurance transactions run in Remittance as remittance types with reinsurer counterparties and ... | 24 (L) | High | Draft |
| CR-0073 | BRD-01 | Sign-in with the BDO profile: Windows ID through BDO EUA, LDAP / AD or SSO. | BIBS sign-in with user ID and password. | 23 (L) | High | Draft |
| CR-0131 | BRD-05 | BDOI accounting is delivered to the BDO Enterprise General Ledger. | No GL interface. | 21 (L) | High | Draft |
| CR-0081 | BRD-02 | Payment files are encrypted and cannot be edited. | Operations users upload the files. | 20 (L) | High | Draft |
| CR-0166 | BRD-12 | Receive submitted-policy details from the approved sources. | Excel uploads per source layout. | 17 (L) | High | Draft |
| CR-0021 | BRD-00 | Retain, archive and purge per the BRD values, which differ by BRD. | Retention rules per record type with review counts (default 5 years online, 15 years archive. | 16 (L) | High | Draft |
| CR-0043 | BRD-00 | Insurer files are received and sent automatically: production feedback, remittance ORs ... | Users upload and download the files on the screens. | 23 (L) | Medium | Draft |
| CR-0108 | BRD-04 | Draft requirements on commission receivables and incentives (drop plan item 1.D7). | Proposed in FRS BRD-4 section 4.10 for confirmation of the draft addendum. | 23 (L) | Medium | Draft |
| CR-0044 | BRD-00 | BIBS data is ingested by the BDO Enterprise Data Platform. | Integration events (9 topics) and report exports. | 20 (L) | Medium | Draft |
| CR-0146 | BRD-07 | BRD-7 assumes open and historical claims are migrated. | Open claims are migrated only if BDOI puts the object in scope. | 13 (L) | High | Draft |
| CR-0159 | BRD-10 | Production values, lists and the AMLC STR format. | Documented defaults apply. | 17 (L) | Medium | Draft |
| CR-0020 | BRD-00 | Recovery objectives and backup frequency differ by BRD. | RPO 15 minutes (continuous WAL archiving) and RTO 4 hours for the whole platform, as in the IER. | 11 (L) | High | For CCB review |
| CR-0147 | BRD-08 | Insurers and client HR use a secure portal or API: sign-in, uploads, downloads, requests ... | No portal: insurers and client HR send files by e-mail or an agreed channel and EB users upload and validate them. | 11 (L) | High | For CCB review |
| CR-0014 | BRD-00 | Centralised, real-time dashboards for all roles, with drill-down. | Each module has its home page. | 16 (L) | Medium | Draft |
| CR-0071 | BRD-01 | Extraction from uploaded documents, including scanned submitted policies. | Text PDFs are extracted. | 16 (L) | Medium | Draft |
| CR-0012 | BRD-00 | Dynamic report customisation: data fields, charts and summaries. | BIBS has fixed report columns and saved parameter variants. | 15 (L) | Medium | Draft |

# 5 Decisions needed from BDOI

The CRs below cannot be closed without a BDOI decision. The dates are the latest that keep the drop plan: scope-shaping items by 16 October 2026 (the date of the programme alignment), the rest before FRS sign-off on 30 November 2026, and the interface specifications by 31 January 2027 for Drop 2.

Table 10: Decisions needed from BDOI

| Topic | CRs | Decision needed | Decision owner | By |
| --- | --- | --- | --- | --- |
| Identity and access | CR-0073, CR-0161 | Confirm OpenID Connect with Entra ID and the user claim; decide whether UIDM-ISC provisions users only (proposal) or owns all access requests | UAM Product Owner with ITIO; BDOI IT | 16 Oct 2026 |
| Reinsurance in Remittance | CR-0002, CR-0003 | Name the reinsurance transactions and their accounting; send the Cashiering and Remittance addenda | Head of Operations; Head, Comptrollership | 16 Oct 2026 |
| Employee Benefits without portal | CR-0147, CR-0074 | Confirm that insurers and client HR send files by e-mail and EB users upload them; confirm EB placement through the NB placement screens | Product Owner, Employee Benefits | 16 Oct 2026 |
| Documents in S3 and DR | CR-0028, CR-0046, CR-0020 | Confirm the five storage decisions (presigned links, malware scanning, Object Lock, KMS keys, ECM copies) and the DR region | BDOI IT; Chief Compliance Officer | 16 Oct 2026 |
| Money rules | CR-0084, CR-0092, CR-0125 | Choose EXCLUDE or CAP; give incentive targets, amounts and the CPC2 base; confirm the 2% withholding entries | Head of Operations; Head, Comptrollership; Head, MBS | 30 Oct 2026 |
| Sanctions match | CR-0155 | Decide block or warn on an open sanctions match at quotation, placement, booking and renewal | Chief Compliance Officer | 30 Oct 2026 |
| Interfaces | CR-0081, CR-0131, CR-0044, CR-0043, CR-0062, CR-0053, CR-0166, CR-0047 | Give layouts, transport, frequency and owners of each interface | BDOI IT | 31 Jan 2027 |
| NFR set | CR-0019, CR-0021, CR-0022, CR-0023 | Approve one BIBS-wide NFR set and the retention per record type | BIBS Product Owner; BDOI IT; Chief Compliance Officer | 30 Nov 2026 |
| FRBS report pack | CR-0117, CR-0118 | Give the final layouts of the report pack and confirm that BIR books stay worksheets | Head, Comptrollership | 30 Nov 2026 |
| Renewal and migration | CR-0134, CR-0146, CR-0139 | Decide one LAMD intake; decide whether open claims migrate; confirm the go-live transition as recorded | Product Owner, Renewal; Product Owner, Claims; Program Manager | 30 Nov 2026 |

# 6 Estimation basis

Table 11: Team roles in the estimates

| Role | Work counted in the estimate |
| --- | --- |
| Business analyst | Analysis: impact analysis, BDOI workshops, rules and layouts, FRS and test plan updates (with the technical writer) |
| Solution architect | Analysis of interfaces, data and infrastructure items |
| Backend developer | Development: services, data changes, jobs, interfaces, reports |
| Frontend developer | Development: screens, forms and lists |
| QA engineer | Test: SIT test cases written and run, regression |
| Technical writer | Documentation: FRS, test plan, user and configuration guides, release notes |

•	A man-day is 8 working hours of one team member. Figures are rounded to whole days.

•	Effort is the work still needed to close the deviation as proposed in the "Proposed behaviour" column. It is 0 when the behaviour is decided and documented and only needs acceptance.

•	For an item deferred pending a BDOI answer, the effort is the work to complete it once BDOI answers as proposed (interface, values, layouts, screens). A different answer is re-estimated at impact analysis.

•	The optional column "BRD as written" gives the indicative effort to deliver the BRD text instead of the proposed behaviour, for the CCB to compare.

•	Development includes configuration. Test covers SIT test cases (writing and running) and regression. Documentation covers the FRS, test plan and guides.

•	Excluded: UAT support, BDOI staff time, infrastructure provisioning by BDO IT (buckets, keys, network routes, certificates), licences and third-party services, and the Phase 2 Reinsurance module.

•	Excluded: the delivery of what the FRS specify (BRD-6, BRD-8, BRD-9, BRD-12, BRD-13, BRD-7). Only the delta caused by the deviation is estimated.

•	Estimates are at the accuracy of an impact analysis (about plus or minus 30 percent). The CCB re-estimates an item when BDOI's answer differs from the proposal.

•	Status and counts are as of the date on the cover and are refreshed with each issue of the register.

Size classes: S 1 to 3 man-days, M 4 to 10, L 11 to 25, XL over 25; 0 means acceptance only. The Register shows the class and the chosen number, for example "L (13)".

# 7 Sign-off

By signing, BDOI accepts this register as the list of deviations under change control as of 26 September 2026, the change-control process and the CCB membership proposed in chapter 2. It does not approve any single CR: each CR is decided by the CCB. The FRS baseline and the platform are not changed by this document.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | BIBS Product Owner (chair of the CCB) | BDOI |  |  |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Chief Compliance Officer | BDOI |  |  |
|  | BDOI IT (integration owner) | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |