## Cover
RISK REGISTER
BIBS Risk Register (RAID log)
Programme risks, assumptions, issues and dependencies with owner, mitigation and status
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 08 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Summary | Open risks by category and rating; 15 assumptions, 8 issues, 26 dependencies | 10
Risks | Programme risks with probability, impact, owner, mitigation and status | 25
Assumptions | Planning assumptions to validate with BDOI | 15
Issues | Current issues of the programme | 8
Dependencies | Dependencies on BDOI (same list as the Project Plan) | 26
Legend
OPEN | Not yet mitigated or resolved
IN PROGRESS | Mitigation or action under way
CLOSED | Closed
Probability and impact 1 (very low) to 5 (very high); score = probability x impact; rating High from 15, Medium 8 to 14, Low up to 7. High items go to the steering committee; the log is reviewed at the weekly programme meeting. Status as of 08-Oct-2026.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
BIBS Risk Register (RAID log), version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Summary | Category | Risk category
Summary | High | Open High risks
Summary | Medium | Open Medium risks
Summary | Low | Open Low risks
Summary | Open total | Open risks of the category
Summary | Highest scores | Risks with the highest score
Risks | ID | Risk identifier
Risks | Category | Category | Scope, Schedule, Data, Integration, Technology, Security, Environment, People, Adoption, Finance
Risks | Risk | Short name of the risk
Risks | Cause | What causes the risk
Risks | Effect | What happens if it occurs
Risks | P | Probability 1-5
Risks | I | Impact 1-5
Risks | Score | Probability x impact
Risks | Rating | High, Medium or Low | High, Medium, Low
Risks | Owner | Owner of the mitigation
Risks | Mitigation | Actions that reduce probability or impact
Risks | Contingency | What we do if it occurs
Risks | Review / trigger date | Date of the next decision or trigger
Risks | Status | Status | Open, In progress, Closed
Risks | Source | Where the risk comes from
Assumptions | ID | Assumption identifier
Assumptions | Assumption | What the plan assumes
Assumptions | Basis | BDOI answer or document behind it
Assumptions | Effect if false | What changes if the assumption is wrong
Assumptions | Owner | Who validates it
Assumptions | Validate by | Date
Assumptions | Status | Status | Open, In progress, Closed
Issues | ID | Issue identifier
Issues | Issue | What has happened
Issues | Effect | Effect on the programme
Issues | Owner | Owner of the action
Issues | Priority | High, Medium or Low | High, Medium, Low
Issues | Action | Action to resolve it
Issues | Due | Date
Issues | Status | Status | Open, In progress, Closed
Dependencies | ID | Dependency identifier (same as the Project Plan)
Dependencies | Type | Decision, data, environment, integration or resource
Dependencies | Dependency | What BDOI provides or decides
Dependencies | Provided by | Owner
Dependencies | Needed by | Date
Dependencies | Needed for | Activity that waits for it
Dependencies | Effect if late | Effect
Dependencies | State | On track, At risk, Late or Delivered | On track, At risk, Late, Delivered

## Summary
Summary
Open risks by category and rating; 15 assumptions, 8 issues, 26 dependencies
Category | High | Medium | Low | Open total | Highest scores
Scope | 2 | 1 | 1 | 4 | R-02, R-01, R-14
Schedule | 1 | 1 | 0 | 2 | R-16, R-25
Data | 1 | 2 | 0 | 3 | R-03, R-10, R-13
Integration | 0 | 3 | 0 | 3 | R-04, R-20, R-21
Technology | 0 | 3 | 0 | 3 | R-06, R-09, R-19
Security | 0 | 2 | 0 | 2 | R-05, R-18
Environment | 1 | 1 | 0 | 2 | R-08, R-22
People | 1 | 1 | 0 | 2 | R-17, R-23
Adoption | 0 | 2 | 0 | 2 | R-24, R-07
Finance | 0 | 2 | 0 | 2 | R-11, R-12

## Risks
Risks
Programme risks with probability, impact, owner, mitigation and status
ID | Category | Risk | Cause | Effect | P | I | Score | Rating | Owner | Mitigation | Contingency | Review / trigger date | Status | Source
R-01 | Scope | New BRD versions of 8-Oct-2026 to absorb | BDOI issued new versions of ten documents on 8-Oct-2026 (New Business, Operations re-issue v1.01 and topic annexes, Collections, Accounting, Renewal addendum, Claims, CSF with Case Management, Submitted Policies, Data Migration V0.03, report list of 13-May-2026) | FRS, traceability, test cases and sign-off sets cite superseded pages and miss restated requirements; Drop 1 sign-off on 30-Nov-2026 at risk | 5 | 3 | 15 | High | iorta Business Analyst lead | Comparison of every old and new version done; FRS re-based to v2.1 or the next minor version with a user-story view and storyboard index; restated requirements raised as clarifications; re-issue by 23-Oct-2026 (proposed) | Sign the unchanged chapters first and re-sign the changed pages only (delta sign-off) | 2026-10-23 | In progress | Source-document comparison of 8-Oct-2026
R-02 | Scope | Customer Servicing Case Management enters scope | The signed CSF Addendum - Case Management (11 requirements BRCSFCM.001-.012; case types with turnaround times, 125 natures of transaction, 51 product types, 33 market segments, 53 fulfilment units; a new Fulfilment Unit persona) replaces SharePoint tracking; FRS BRD-09 v1.0 had case management out of scope (CR-0005, DCR-163) | New module (case record, routing, SLA and escalation, reports, dashboards) with effort not in the plan; Drop 1 or Drop 2 dates at risk | 5 | 4 | 20 | High | Product Owner, CSF; Program Manager | Change request to the CCB by 30-Oct-2026 with the impact analysis; proposed delivery with Drop 2 (requirements to 26-Feb-2027, development Mar-Apr 2027, SIT Jul-Sep 2027) | Deliver case logging and the supervisor queue for go-live and the dashboards in the first release after hypercare | 2026-10-30 | Open | CSF BRD with the Case Management addendum (8-Oct-2026)
R-03 | Data | Data Migration BRD V0.03 conflicts with earlier BDOI answers | The signed V0.03 brings into scope objects held as conditional or excluded (claims, submitted policies, payees, in-progress renewals, e-policy linking) and asks to migrate the renewals in progress, against the answer of 26-Sep-2026 (DMQ37); it also drops the '(legacy)' qualifier of the sub-ledgers (DMQ18) | Data object register, layouts and the Handbook v2.0 are not aligned; new layouts after the M2 freeze; Trial migration scope changes | 4 | 4 | 16 | High | Data Migration Lead; Program Manager | Position paper per conflict with our proposal; decision at M2 (30-Oct-2026); Handbook and test plan re-based on V0.03 | Objects not decided by M2 are completed in legacy before the freeze | 2026-10-30 | Open | Data Migration BRD V0.03; Handbook; DEC-03
R-04 | Integration | EIAM and UIDM-ISC decisions late | EIAM sign-in (tenant, claims, session life, OIDC or SAML 2.0) and the UIDM-ISC option (accounts only, accounts and roles, aggregation only; SCIM provisioning) are not yet specified (DEC-05, IQ04, IQ05) | Sign-in stays local in SIT; directory sign-in, single sign-on, provisioning and MFA tested late; user loading at go-live becomes manual | 3 | 4 | 12 | Medium | BDOI IT; BDO IT EIAM and IGA teams | Local sign-in with the Windows ID captured on every user; directory mode switched on when specified; decision workshop with the EIAM and IGA teams in November 2026; specifications by 31-Jan-2027 | Go-live with EIAM sign-in and bulk user loading through access requests; UIDM-ISC provisioning in the first release after hypercare | 2027-01-31 | Open | Drop 0 closure RSK-04; alignment pack IQ04, IQ05
R-05 | Security | Spring Framework 6.2 security advisories | The Spring project publishes security advisories for the Spring Framework 6.2 and Spring Security lines used by Spring Boot 3.5; new advisories will appear during SIT, UAT and production | The dependency gate fails (CVSS 7.0 or higher); unplanned patch releases during test windows; exposure in production if a patch is late | 4 | 3 | 12 | Medium | iorta Solution Architect; BDOI Information Security | Dependency, container and secret scans on every change; monthly patch release; critical findings patched within 7 days and high within 30 days; SBOM kept with every release; regression run on every patch | Temporary compensating control at the Gateway API or Apigee X layer, approved by Information Security, with a dated acceptance at most six months | 2026-11-30 | In progress | Quality gates; component baseline of 8-Oct-2026
R-06 | Technology | Spring Boot 4 upgrade path | The client baseline of 8-Oct-2026 is Spring Boot 3.5; its open-source support window ends before the first years of production are over; Spring Boot 4 brings Spring Framework 7 and Jakarta EE 11 changes | A late upgrade lands in UAT or hypercare; or production runs on a line without open-source patches | 3 | 4 | 12 | Medium | iorta Solution Architect; BDOI IT | Compatibility assessment Jan-Mar 2027; CCB decision by 31-Mar-2027; if approved, upgrade release in May-Jun 2027 before Trial migration 2 so that the full SIT regression, UAT and the performance test run on the upgraded stack | Stay on Spring Boot 3.5 with extended support through go-live; upgrade in the first release after hypercare (Q2 2028) | 2027-03-31 | Open | Component baseline of 8-Oct-2026
R-07 | Adoption | Screenshots and training material out of date after screen changes | The BRD versions of 8-Oct-2026, Case Management, the UX points and change requests change screens after the sign-off sets, UX decks, user guides and training material were captured | Users trained on screens that differ from production; sign-off sets show superseded screens; re-capture effort | 4 | 2 | 8 | Medium | iorta change and training lead | Screen register with a change flag per screen; re-capture of the changed screens with every release; user guides refer to screen IDs; content freeze for training at Drop 1 UAT mid-point (29-Oct-2027) and delta notes after it | Release notes per persona and a 30-minute delta session before go-live | 2027-10-29 | Open | UX screen register per sign-off set
R-08 | Environment | Environment provisioning late | SIT (4-Jan-2027), UAT (19-Jul-2027), Pre-Prod (1-Oct-2027), production and DR (1-Nov-2027) depend on BDOI IT; the IER has no Pre-Prod and DR cluster sheets and does not cost the declared components (IQ33) | SIT, UAT, performance test or dress rehearsal start late; go-live date at risk | 3 | 5 | 15 | High | BDOI IT | Environment checklist per environment agreed by 30-Nov-2026; restated IER sizing; monthly environment review at the steering committee; acceptance test of each environment one week before its date | Run Drop 1 SIT on a temporary cluster managed by iorta TechNXT with masked data, if Information Security approves | 2026-11-30 | Open | Alignment pack 6.2, 6.6; IQ27, IQ33
R-09 | Technology | IER and the component baseline differ | The IER describes ten microservices, Redis 7 and ingress-nginx; the baseline of 8-Oct-2026 is one application on managed Kubernetes with Valkey 8, Kafka 3.9 and the Gateway API | Environments ordered with the wrong components; re-work and delay | 3 | 3 | 9 | Medium | BDOI IT; iorta Solution Architect | IER restated with the baseline and the Kubernetes sizing of the alignment pack by 30-Nov-2026 (IQ25) | Component substitutions recorded in the environment acceptance | 2026-11-30 | Open | Alignment pack IQ25; client decisions of 8-Oct-2026
R-10 | Data | Configuration inputs late | Configuration items of the Drop 0 workbook arrive after their due dates D1-D7 | Drop 1 SIT or a trial migration runs on seed values; results do not hold for production | 3 | 4 | 12 | Medium | Program Manager | Owner and due date per item; status reviewed weekly from December 2026 | Retest the affected cases on the production values in UAT | 2027-01-04 | Open | Drop 0 closure RSK-01
R-11 | Finance | Chart of accounts and accounting rules not final before Drop 1 SIT | The production chart and the accounting rules are not final by D2 | Postings tested against a draft chart; GL opening and Migration Clearing not reconcilable | 3 | 4 | 12 | Medium | Head, Comptrollership | Chart and rules due at D2 (4-Jan-2027); legacy accounts and GL map at D3 and D4 | Posting retest cycle in UAT before Trial migration 3 | 2027-01-04 | Open | Drop 0 closure RSK-02
R-12 | Finance | Year-end option A not confirmed by M6 | Comptrollership has not confirmed go-live at the year-end boundary with a provisional opening and true-ups | Cut-over calendar, GL opening and true-ups change | 2 | 5 | 10 | Medium | Head, Comptrollership | Confirmation asked with the Drop 0 closure (DEC-01); decision by 1-Oct-2027 at the latest | January interim period in legacy and a later go-live date in January 2028 | 2027-10-01 | Open | Drop 0 closure RSK-03
R-13 | Data | Conditional migration objects decided late | F04, F06, F07, P04, P05 and R09 are not decided at M1 and M2 | Layouts, trials and reconciliation of those objects added late | 3 | 3 | 9 | Medium | Program Manager | Decisions at M1 and M2 (DEC-03) | Objects not decided are completed in legacy before the freeze | 2026-10-30 | Open | Drop 0 closure RSK-05
R-14 | Scope | Changes to signed content during later reviews | Drop 1 reviews ask to change signed Drop 0 screens, rules or templates | Re-work of signed sets and their tests | 3 | 3 | 9 | Medium | Program Manager | Change control: every change is a CR with its effect on the other BRDs and a delta sign-off | Defer non-critical changes to the first release after hypercare | 2026-12-09 | Open | Drop 0 closure RSK-07
R-15 | Scope | Insurer-company functions visible to BDOI users | BIBS is broker-only; the insurer-company modules (insurer underwriting, insurer claims, treaty and cession accounting, actuarial reserves, group consolidation, insurer taxes) are being removed from the BIBS release | A residual menu, report or posting option confuses users or auditors | 2 | 3 | 6 | Low | iorta Solution Architect | Removal completed and verified in SIT; menu check per persona in every regression; UAT test case per BRD that the insurer suite is absent | Hide through the module switches and remove in the next release | 2026-12-18 | In progress | Client instruction (broker-only scope)
R-16 | Schedule | Short lead time of the January 2028 renewals | Expiries of January 2028 get days to four weeks instead of 140 days for insurer requests and Renewal Advices | Late renewals, hold covers, client complaints in the first weeks | 4 | 4 | 16 | High | Head of the Renewal processing team | Day-1 priority queue (go-live extraction at 04:00, January expiries flagged urgent); January staffing plan signed; Renewal team trained and practised on Trial migration 4 and dress-rehearsal data by 14-Dec-2027 | Overtime and back-up handlers from Processing; daily review at the hypercare triage | 2027-12-14 | Open | Handbook risk 16; cut-over CT-013
R-17 | People | Business user capacity in Q4 2027 | Drop 1 UAT (Aug-Dec), Drop 2 UAT (Oct-Nov), Trial migrations 3 and 4, the dress rehearsal and end-user training (Oct-Dec) need the same business users while they run daily operations and the year-end close | UAT coverage falls; training attendance falls; sign-off slips | 4 | 4 | 16 | High | BIBS Product Owner; business owners | Named UAT testers per BRD by 16-Jul-2027; UAT calendar per unit; key users trained in July so they test and coach; end-user training in short persona sessions of 3 to 4 hours | Back-fill from other branches; extend end-user training into the first week of hypercare for low-volume personas | 2027-07-16 | Open | BDOI programme timeline
R-18 | Security | Security test findings arrive in December 2027 | Performance and penetration tests run Nov-Dec 2027, two to six weeks before go-live | Fixes and retests compete with the cut-over | 3 | 4 | 12 | Medium | BDOI Information Security | Early security scan in SIT in June 2027 (IQ35); scans on every change; provider named by 31-May-2027 | Risk acceptance by Information Security for medium findings with a fix date after go-live | 2027-05-31 | Open | Alignment pack IQ35
R-19 | Technology | Sizing basis for the peak load not agreed | The IER uses 1,200 internal users; the umbrella BRD gives 1,344 named and 429 concurrent users (IQ32) | Production under-sized or over-sized; performance test target disputed | 2 | 4 | 8 | Medium | BDOI IT | Agree 1,344 named and 429 concurrent users as the test target by 31-Dec-2026 | Horizontal scaling headroom kept in the production cluster | 2026-12-31 | Open | Alignment pack IQ32
R-20 | Integration | Drop 2 interfaces not specified | EDP (SD 11), EGL and CARMS are not yet explained (IQ15-IQ17); the insurer exchanges are not listed (IQ18) | Drop 2 development (Mar-Apr 2027) without specifications | 4 | 3 | 12 | Medium | BDOI IT | Specifications by 31-Jan-2027; interface contract per system signed by BDOI IT | Report exports in place of the EGL and EDP feeds at go-live | 2027-01-31 | Open | Alignment pack IQ15-IQ18
R-21 | Integration | Bank channel layouts not known | Layouts and transport of CMS / New BOB, OBPCS, Old BOB, PMS are not confirmed; the purpose of AFTS is unknown (IQ09, IQ10) | Cashiering and Disbursement channels tested late | 3 | 3 | 9 | Medium | BDOI IT | Layouts by 26-Feb-2027; configurable payment-file layouts | User upload of the bank files at go-live | 2027-02-26 | Open | Alignment pack IQ09, IQ10
R-22 | Environment | Non-production hours too short for batch and migration cycles | Non-production runs 12 x 5 (IER assumption); month-end cycles, weekend trial migrations and the dress rehearsal need extended hours (IQ27) | Trial migrations and batch tests cannot run as planned | 3 | 3 | 9 | Medium | BDOI IT | Extended-hours calendar agreed per trial migration and month-end cycle by 31-Mar-2027 | Run the cycles on Pre-Prod | 2027-03-31 | Open | Alignment pack IQ27
R-23 | People | Key person dependency | Few BDOI subject-matter experts per BRD and few iorta TechNXT specialists per area | Decisions and knowledge stall when a person leaves or is absent | 3 | 3 | 9 | Medium | iorta Project Manager; BIBS Product Owner | Back-up named per role in the RACI; decisions and knowledge recorded in the FRS, registers and the knowledge base; knowledge transfer from June 2027 | Replacement within 10 working days with a hand-over | 2026-12-09 | Open | Programme governance
R-24 | Adoption | Users keep Excel trackers and SharePoint after go-live | Renewal trackers, collection lists and CSF SharePoint tracking are familiar; parallel records feel safer | Data outside BIBS; adoption KPIs missed; audit trail incomplete | 3 | 3 | 9 | Medium | BIBS Product Owner; business owners | Trackers retired by unit on go-live (the RA-sent tracker loaded once); adoption KPIs reviewed weekly in hypercare; supervisors use BIBS dashboards in team meetings | Targeted coaching by the key users of the unit | 2028-02-02 | Open | OCM and training framework
R-25 | Schedule | Operations BRD re-issue v1.01 changes signed scope | Operations re-issued its BRD as v1.01 with five signed topic annexes (37 changes, 15 of high priority), for example Cashiering removed from BIR 2307 processing | FRS BRD-02 v2.0 and its sign-off set re-work; Drop 1 downstream development scope grows | 4 | 3 | 12 | Medium | Head of Operations; iorta Business Analyst lead | FRS BRD-02 re-based in v2.1; CRs for the changes beyond the earlier baseline | Phase the lower-priority changes into the second development wave | 2026-11-13 | In progress | Operations BRD v1.01 comparison

## Assumptions
Assumptions
Planning assumptions to validate with BDOI
ID | Assumption | Basis | Effect if false | Owner | Validate by | Status
A-01 | All modules go live together on Monday 3-Jan-2028 (T); there is no early go-live | BDOI answer A1 (26-Sep-2026) | Re-plan of the cut-over and the migration calendar | Steering committee | 2027-10-01 | Open
A-02 | Reinsurance is phase 2; Remittance handles the reinsurance transactions in Drop 1 | BDOI answer A3 | Reinsurance scope added to Drop 1 | BIBS Product Owner | 2026-11-30 | Open
A-03 | BIBS is broker-only; insurer-company modules are not part of the release | Client instruction | Scope and test effort grow | BIBS Product Owner | 2026-11-30 | Open
A-04 | Documents and attachments are stored in the S3 document store only | BDOI answer A4 | ECM integration needed | BDOI IT | 2026-11-30 | Open
A-05 | The drops split requirements, test and sign-off workload; the platform goes to UAT complete | BDOI answer A5 | Partial UAT per drop; more regression | Program Manager | 2026-11-30 | Open
A-06 | BDOI IT owns every external touch-point; integrations run through Apigee X | BDOI integration list (26-Sep-2026) | Interface ownership disputes | BDOI IT | 2027-01-31 | Open
A-07 | Component baseline of 8-Oct-2026: PostgreSQL 16, Valkey 8, Kafka 3.9, OpenJDK 21, Spring Boot 3.5, React, Node 22 LTS (packaging only), nginx, managed Kubernetes, Gateway API | Client decisions of 8-Oct-2026 | Re-platforming effort | BDOI IT | 2026-11-30 | Open
A-08 | Sign-in by OIDC or SAML 2.0 single sign-on with EIAM (Entra ID); TOTP MFA; a break-glass administrator is allowed | Drop 0 BRD-11 set; IQ04 | Local sign-in remains; MFA design changes | BDOI Information Security | 2027-01-31 | Open
A-09 | Four trial migrations and a dress rehearsal run on masked extracts | Handbook PR-DM-15 (DMQ31) | Fewer rehearsals; higher cut-over risk | Program Manager; Compliance | 2026-10-30 | Open
A-10 | Platform sized for 1,344 named and 429 concurrent users | Umbrella BRD p.42 (IQ32) | Re-sizing and new performance test | BDOI IT | 2026-12-31 | Open
A-11 | Non-production runs 12 x 5 with extended hours on request for batch cycles, trial migrations and the dress rehearsal | IER assumptions (IQ27) | Cycles cannot run | BDOI IT | 2027-03-31 | Open
A-12 | A training environment with training users and seed data is provided on the UAT cluster from 19-Jul-2027 | Proposed | Training on SIT or UAT data; conflicts with testing | BDOI IT | 2027-07-19 | Open
A-13 | BDOI names trainers who deliver end-user training after train-the-trainer | Proposed | iorta trainers needed for 1,344 users | Business owners | 2027-07-30 | Open
A-14 | BDOI application support (L1, L2) and BDO IT operations take over at hypercare exit (2-Feb-2028); iorta TechNXT provides L3 product support | Proposed | Hypercare extended | BDOI IT | 2027-05-31 | Open
A-15 | The screen language is English; dates dd-MMM-yyyy and amounts formatted in PHP unless the currency says otherwise | BDO UX guidelines | Translation and re-capture of material | BIBS Product Owner | 2026-11-30 | Open

## Issues
Issues
Current issues of the programme
ID | Issue | Effect | Owner | Priority | Action | Due | Status
I-01 | Ten source documents re-issued on 8-Oct-2026; FRS, test plans and sign-off sets cite superseded pages | Sign-off on superseded references | iorta Business Analyst lead | High | Re-base every affected FRS and set (v2.1 or next minor); delta sign-off | 2026-10-23 | In progress
I-02 | FRS BRD-09 not aligned with the signed CSF Case Management addendum | Case Management not specified | Product Owner, CSF | High | CR to the CCB with the impact analysis and the proposed drop | 2026-10-30 | Open
I-03 | Data Migration Handbook v2.0 written on the unsigned draft V0.01 | Traceability to the signed V0.03 missing | Data Migration Lead | High | Re-base the Handbook, test plan and test cases on V0.03 | 2026-10-30 | In progress
I-04 | Operations BRD v1.01 and topic annexes not in FRS BRD-02 v2.0 | Operations scope out of date | Head of Operations | High | FRS BRD-02 v2.1 with the 37 changes | 2026-11-13 | In progress
I-05 | Submitted Policies BRD renumbered (BRIDSP references moved); four new requirements | Traceability broken | Product Owner, Submitted Policies | Medium | Renumber traceability, test plan and set; specify the new requirements | 2026-11-13 | In progress
I-06 | Component baseline changes of 8-Oct-2026 (Valkey 8, Gateway API) being implemented | Deployment configuration and IER to update | iorta Solution Architect | Medium | Release on the new baseline; IER restated | 2026-11-30 | In progress
I-07 | Screens changed by the re-based FRS need re-capture in the sign-off sets and UX decks | Sets show superseded screens | iorta change and training lead | Medium | Re-capture changed screens per release from the screen register | 2026-11-30 | Open
I-08 | IER describes a different architecture and lacks Pre-Prod and DR sheets | Environment ordering risk | BDOI IT | High | Restate the IER (IQ25, IQ33) | 2026-11-30 | Open

## Dependencies
Dependencies
Dependencies on BDOI (same list as the Project Plan)
ID | Type | Dependency | Provided by | Needed by | Needed for | Effect if late | State
DEP-01 | Decision | Answers to the M1 and M2 decisions of the Data Migration set (DEC-02, DEC-03, DEC-11, DEC-12) | BDOI business owners | 2026-10-16 | Migration layouts and object scope | Layouts frozen late; Trial migration 1 scope reduced | On track
DEP-02 | Decision | Position on the Data Migration BRD V0.03 conflicts: renewals in progress (BRID_MIG 12.1 against DMQ37), claims, submitted policies, payees and e-policy linking in scope | Program Manager; Head of the Renewal processing team; Head, Comptrollership | 2026-10-30 | Data object register and Handbook v2.1 | New layouts after M2; migration effort and trial scope change | On track
DEP-03 | Decision | Scope and drop of Customer Servicing Case Management (CSF addendum, BRCSFCM.001-.012) | Product Owner, CSF; Change Control Board | 2026-10-30 | FRS BRD-09 extension and the Drop 2 plan | Case Management cannot be delivered for go-live | On track
DEP-04 | Decision | Sign-off of the Drop 0 sets (BRD-13, BRD-03, BRD-11) and of the Drop 1 FRS | Product owners | 2026-11-30 | Freeze of the Drop 1 development scope | Development starts on unsigned scope; rework | On track
DEP-05 | Data | Organisation, chart of accounts, accounting rules and bank accounts for Drop 1 SIT (D2) | Head, Comptrollership | 2027-01-04 | Drop 1 SIT postings | SIT runs on seed values; postings retested | On track
DEP-06 | Environment | SIT environment on managed Kubernetes with PostgreSQL 16, Valkey 8, Kafka 3.9, document store and Gateway API | BDOI IT | 2027-01-04 | Drop 1 SIT | SIT start slips day for day | On track
DEP-07 | Integration | EIAM sign-in specification (tenant, claims, session life, OIDC or SAML 2.0) and application registration | BDO IT EIAM team | 2027-01-31 | Directory sign-in in SIT | Sign-in stays local in SIT; directory sign-in tested late | On track
DEP-08 | Integration | UIDM-ISC option (accounts only, accounts and roles, or aggregation only) and SCIM provisioning connector | BDO IT IGA team | 2027-01-31 | Provisioning in SIT | User provisioning tested late; manual user loading at go-live | On track
DEP-09 | Data | First full extracts with control files and volumes (M3) | BDOI IT | 2027-01-29 | Profiling and load sizing | Trial migration 1 on partial data | On track
DEP-10 | Integration | Drop 2 integration specifications: EGL, EDP (SD 11), CARMS, insurer exchanges | BDOI IT | 2027-01-31 | Drop 2 development (Mar-Apr 2027) | Drop 2 interfaces descoped or delivered after go-live | On track
DEP-11 | Integration | Bank channel layouts and transport: CMS / New BOB, OBPCS, Old BOB, AFTS, PMS | BDOI IT | 2027-02-26 | Cashiering and Disbursement channels in SIT | Manual uploads at go-live | On track
DEP-12 | Integration | CCM sending mode, sender addresses and attachment limits | BDOI IT | 2027-02-26 | Renewal Advices, e-policies and notifications | E-mail tested late | On track
DEP-13 | Integration | Apigee X proxies, products and credentials for the BIBS integrations in SIT, UAT and production | BDO IT API team | 2027-03-31 | Integration test | Integration test slips into UAT | On track
DEP-14 | Decision | Spring Boot 4 upgrade before go-live or after hypercare | BDOI IT; Change Control Board | 2027-03-31 | Upgrade window May-Jun 2027 | Upgrade forced late or carried into production support | On track
DEP-15 | Decision | DR region and data residency (IQ26) | BDOI IT; BDOI Information Security | 2027-03-31 | Production and DR set-up | DR not ready at go-live | On track
DEP-16 | Data | Role-to-permission matrix and the users of the SIT and UAT testers (D3) | Business Administration; BDOI Information Security | 2027-04-09 | Access in SIT and UAT | Testers without access; UAT starts late | On track
DEP-17 | Data | Code maps approved, including the package code map (M5) | Data owners; TSU | 2027-06-18 | Trial migration 2 | Trial migration 2 incomplete | On track
DEP-18 | Resource | Named application support team (L1 and L2) and BDO IT operations staff for knowledge transfer | BDOI IT; BDO IT operations | 2027-05-31 | Knowledge transfer from 7-Jun-2027 | Hand-over at hypercare exit at risk | On track
DEP-19 | Resource | Penetration test provider named; early SIT scan approved (IQ35) | BDOI Information Security | 2027-05-31 | Security tests | Findings arrive in December 2027 | On track
DEP-20 | Resource | UAT testers named per BRD (at least two per business unit) and released for the UAT windows | Business owners | 2027-07-16 | UAT | UAT coverage reduced | On track
DEP-21 | Environment | UAT environment and training environment with training users | BDOI IT | 2027-07-19 | Key user training and UAT | Training and UAT start late | On track
DEP-22 | Resource | BDOI trainers named for train-the-trainer (one per business unit and persona group) | Business owners | 2027-07-30 | Train-the-trainer from 6-Sep-2027 | End-user training delivered by iorta only; capacity limit | On track
DEP-23 | Environment | Pre-Prod at production size | BDOI IT | 2027-10-01 | Performance test and dress rehearsal | Dress rehearsal not production-sized | On track
DEP-24 | Decision | Year-end option A confirmed; point of no return confirmed (DEC-01, DEC-13) | Head, Comptrollership; Program Manager | 2027-10-01 | Cut-over calendar and GL opening | Cut-over calendar changes | On track
DEP-25 | Environment | Production and DR environments | BDOI IT | 2027-11-01 | Production values, ORR and cut-over | Go-live date at risk | On track
DEP-26 | Data | Production values of every configuration item (D6) | Configuration owners | 2027-11-01 | Dress rehearsal | Dress rehearsal on non-production values | On track

## _lists (hidden)
Scope | High | Open | Open | High | Open | On track
Schedule | Medium | In progress | In progress | Medium | In progress | At risk
Data | Low | Closed | Closed | Low | Closed | Late
Integration | [5 empty] | Delivered
Technology
Security
Environment
People
Adoption
Finance