CLOSURE SUMMARY FOR THE STEERING COMMITTEE

Drop 0 Closure Summary

Setup and Data Migration: sign-off sets, decisions, configuration inputs and the move to Drop 1

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-CS-DROP-0 |
| Version | 2.0 |
| Date | 5 October 2026 |
| Status | Issued for the BDOI steering committee |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 2.0 | 5 Oct 2026 | iorta TechNXT Project Manager | iorta TechNXT Business Analysis |  | First issue with the three Drop 0 sign-off sets v2.0 and the Drop 0 configuration inputs workbook |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Chair and approver | BDO Unibank ESG | Steering committee decision |
| Product Owner, Marketing Business System | Business owner of BRD-03 and BRD-11 | BDOI | Decisions and sign-off |
| Head, Comptrollership | Owner of the finance set-up and the year-end option | BDOI | Decisions and configuration inputs |
| Head, BDOI Information Security | Owner of the security settings | BDOI | Decisions and configuration inputs |
| Head, BDOI IT | Owner of extracts, sign-in and integrations | BDOI | Decisions and configuration inputs |
| Data Migration Lead | Owner of the migration objects | BDOI | Decisions |
| Project team | Delivery | iorta TechNXT | Sessions, answers, revisions, change requests |

Contents

1 Purpose of this summary	4

2 Scope of Drop 0	5

3 The three sign-off sets	6

4 Proposed rules and clarifications for confirmation	7

5 Consolidated decisions BDOI takes	8

6 Configuration inputs	10

6.1 Timeline	11

7 Entry and exit criteria	13

7.1 Entry criteria for closing Drop 0	13

7.2 Exit criteria: Drop 0 is closed when	13

7.3 Entry criteria for Drop 1	13

8 Risks and dependencies	14

9 Change control	15

10 Closure sign-off	16

# 1 Purpose of this summary

This summary asks the BDOI steering committee to close Drop 0 (Setup and Data Migration) and to open Drop 1. It brings together, in one place, what the three Drop 0 sign-off sets ask the business to confirm, the number of proposed rules and clarifications that are still open in each set, the decisions BDOI takes to close the drop, the configuration inputs BDOI provides before go-live and when, the entry and exit criteria, the risks and dependencies, and the change control that applies once the sets are signed.

The companion workbook 01_BIBS_Drop-0_Configuration_Inputs_v2.0.xlsx lists every configuration input with its BDOI owner, its due date relative to go-live and its one route into BIBS. Go-live is proposed for Monday 3 January 2028 (T), at the year-end boundary, subject to the confirmation of the year-end option by Comptrollership (decision DEC-01).

# 2 Scope of Drop 0

Drop 0 prepares the platform on which every other drop runs and moves the legacy data into it. In the BDOI drop plan it covers:

•	0.1 Accessibility and Login, 0.2 Authorization and 0.3 User Maintenance: BRD-11 User Access Maintenance;

•	0.4 Data Management: the GL accounts and reference tables of Comptrollership (the finance set-up of BRD-5 used by Drop 1);

•	0.5 Workflow: the approval stages of the Drop 0 functions;

•	0.6 Product Maintenance: BRD-03 Product Maintenance;

•	the Data Migration stream: BRD-13 Data Migration;

•	the Drop 0 integrations: EIAM, UIDM-ISC, LMS, HL-LOAS, PMS, CMS / New BOB, OBPCS, AFTS, Old BOB, ECM, CCM, M365 and TFS.

Requirements and mapping run from September to November 2026; the migration is prepared from November 2026 to March 2027, tested in SIT from April to July 2027 and in UAT from August to October 2027; the full migration and the cut-over run from November 2027 to January 2028.

# 3 The three sign-off sets

Each set is issued as one release set in its own folder of Drop 0 and is signed as one unit by its business owner. Signing a set freezes its screens, fields, rules, messages, notifications and interface contract as specified.

Table 1: The three sign-off sets of Drop 0

| Sign-off set | Files (v2.0) | What the business confirms | Signed by | Sign-off |
| --- | --- | --- | --- | --- |
| BRD-03 Product Maintenance | • 00_BIBS_StartHere_BRD-03_Product_Maintenance_v2.0.docx • 01_BIBS_GuideDeck_BRD-03_Product_Maintenance_v2.0.pptx • 02_BIBS_FRS_BRD-03_Product_Maintenance_v2.0.docx • 03_BIBS_Signoff_BRD-03_Product_Maintenance_v2.0.xlsx • 04_BIBS_TestPlan_BRD-03_Product_Maintenance_v2.0.xlsx • 05_BIBS_TestPlan_BRD-03_Product_Maintenance_Summary_v2.0.docx • 06_BIBS_Templates_BRD-03_Configuration_Inputs_v2.0.xlsx | • The package request, negotiation, ManCom sign-off, set-up and release of packages, the package versions and rate schemes, expiry, monitoring and incentive criteria, as specified screen by screen • The masters of Product Maintenance: product catalogue, coverages and clauses, rates and taxes, insurers and sales organisation • The configuration inputs of templates CI-01 to CI-10 and who provides each | Product Owner, Marketing Business System | 30-Nov-2026 |
| BRD-11 User Access Maintenance | • 00_BIBS_StartHere_BRD-11_User_Access_Maintenance_v2.0.docx • 01_BIBS_GuideDeck_BRD-11_User_Access_Maintenance_v2.0.pptx • 02_BIBS_FRS_BRD-11_User_Access_Maintenance_v2.0.docx • 03_BIBS_Signoff_BRD-11_User_Access_Maintenance_v2.0.xlsx • 04_BIBS_TestPlan_BRD-11_User_Access_Maintenance_v2.0.xlsx • 05_BIBS_TestPlan_BRD-11_User_Access_Maintenance_Summary_v2.0.docx • 06_BIBS_Templates_BRD-11_Configuration_Inputs_v2.0.xlsx | • Sign-in, session and password rules; the access requests, approvals and group-profile requests under four eyes; the System Administrator functions and the access reports • The menus of every persona and the role-to-permission matrix • The security parameters and the configuration inputs of templates CI-01 to CI-06 | Product Owner, Marketing Business System; Business Administration; BDOI Information Security; BDOI IT | 1-Dec-2026 |
| BRD-13 Data Migration | • 00_BIBS_StartHere_BRD-13_Data_Migration_v2.0.docx • 01_BIBS_GuideDeck_BRD-13_Data_Migration_v2.0.pptx • 02_BIBS_Handbook_BRD-13_Data_Migration_v2.0.docx • 03_BIBS_Workbook_BRD-13_Data_Migration_v2.0.xlsx • 04_BIBS_TestPlan_BRD-13_Data_Migration_v2.0.xlsx • 05_BIBS_TestPlan_BRD-13_Data_Migration_Summary_v2.0.docx | • The decision per data object (migrate, carry forward, conditional, archive, excluded), the owners and stewards, and the load templates and code maps • The Migration Console screens, the reconciliation levels and the sign-off gates G1 to G6 • The cut-over runbook, the year-end cut-over option, the run-off of the legacy items and the decommissioning criteria | Program Manager, Business Project Services; Data Migration Lead; data owners; Comptrollership; BDOI IT | 30-Oct-2026 |

# 4 Proposed rules and clarifications for confirmation

Each set closes with a chapter of proposed business rules and clarifications for confirmation: the points where the proposed rule differs from the BRD text or where BIBS needs a BDOI decision to complete the rule. The FRS of BRD-03 and BRD-11 also carry their open questions; the Data Migration Handbook carries its open decisions with the date each is needed by. The counts below are taken from those chapters.

Table 2: Items for confirmation per sign-off set

| Sign-off set | Proposed rules and clarifications for confirmation | Open questions and decisions | Open or partly answered | Recommended, to confirm | Answered |
| --- | --- | --- | --- | --- | --- |
| BRD-03 Product Maintenance | 20 | 17 | 16 | 0 | 1 |
| BRD-11 User Access Maintenance | 20 | 21 | 21 | 0 | 0 |
| BRD-13 Data Migration | 28 | 42 | 37 | 1 | 4 |
| Total | 68 | 80 | 74 | 1 | 5 |

Every proposed rule is decided with the review of its set (Agree, Agree with change, Disagree, Need more information), or accepted as the working assumption with its decision date. A decision that only sets a value (a list, a parameter, a template) is applied as configuration through the workbook; a decision that changes a screen, field, rule or message is applied in version 2.1 of the set.

# 5 Consolidated decisions BDOI takes

The decisions below gather the items of the three clarification chapters that shape the other drops, the cut-over or the configuration. The column From names the items of the sets they answer.

Table 3: Consolidated decisions BDOI takes to close Drop 0

| ID | Topic | Decision BDOI takes | From | BDOI owner | Needed by |
| --- | --- | --- | --- | --- | --- |
| DEC-01 | Year-end cut-over: option A | Confirm go-live on Monday 3 January 2028 at the year-end boundary, with legacy closing FY2027 and BIBS opening from a provisional balance-sheet opening, trued up after the legacy close and the audited statements. | PR-DM-01, DMQ39, DMQ25 | Head, Comptrollership; Program Manager | M6 (1-Oct-2027); confirmation asked with the Drop 0 closure |
| DEC-02 | Legacy account codes and Migration Clearing | Confirm the separate legacy control accounts and Migration Clearing, and assign their codes in the production chart (template D0-09). | PR-DM-02, DMQ18 | Head, Comptrollership | M1 (16-Oct-2026) |
| DEC-03 | Conditional migration objects | Decide for remittances in flight (F04), PDCs and pick-ups (F06), open claims (F07), submitted-policy masterlists (P04), Employee Benefits programmes (P05) and payees (R09) whether each is completed in legacy, carried or brought into scope. | PR-DM-05, PR-DM-26, DMQ30, DMQ21, DMQ33 | Program Manager; Head, Operations | M1 (16-Oct-2026) and M2 (30-Oct-2026) |
| DEC-04 | Access request stages | Confirm the stage list of an access request (Draft, Pending approval, Second approval where needed, Approved; For implementation and Implemented for a group-profile request) and that the System Administrator implements every approved group-profile change. | CLR-UA-18, CLR-UA-19, CLR-UA-12 | Business Administration; BDOI Information Security | Sign-off of BRD-11 (1-Dec-2026) |
| DEC-05 | Directory sign-in and provisioning | Specify the EIAM sign-in (tenant, claims, session life) and choose the UIDM-ISC option: accounts only, accounts and roles, or aggregation only. | CLR-UA-01, CLR-UA-03, IQ04, IQ05 | BDOI IT | Before SIT of the sign-in (Q1 2027) |
| DEC-06 | Security values: passwords, sessions, dormancy, working hours | Confirm or change the security parameters of template CI-05, the dormancy period and notice, and whether public holidays count as out of hours. | CLR-UA-08, CLR-UA-14, UQ07, UQ08 | BDOI Information Security | D5 (16-Jul-2027) |
| DEC-07 | Business unit groups and user levels | Give the values of the two lists before the users are loaded. | CLR-UA-05, UQ05 | Business Administration | D3 (9-Apr-2027) |
| DEC-08 | Package approval chain and ManCom quorum | Confirm one Marketing approval by the TL, TH or UH (or give the chain by segment or amount) and that one ManCom member's sign-off completes the step (or give the quorum). | CLR-PM-03, CLR-PM-05, PQ07, PQ08 | Product Owner, Marketing Business System | Sign-off of BRD-03 (30-Nov-2026) |
| DEC-09 | Package documents and risk-code naming | Provide the layouts of the package documents and the risk-code naming convention of each product line. | CLR-PM-01, CLR-PM-02, PQ02 | Product Owner, Marketing Business System; TSU | D5 (16-Jul-2027) |
| DEC-10 | Package remapping at Renewal sanitation | Confirm the answer of 26-Sep-2026 and name the TSU preparer of the package code map (template CI-07, object R06). | CLR-PM-14, PR-DM-24, DMQ36 | Product Owner, Marketing Business System; TSU | M2 (30-Oct-2026) |
| DEC-11 | Client scope and matching | Confirm the clients migrated (from 2020 to present, plus older clients with in-force business), the daily batches up to the freeze, and the matching keys and thresholds. | PR-DM-08, PR-DM-09, DMQ04, DMQ05, DCR-173 | Product Owner, Marketing Business System | M1 (16-Oct-2026) |
| DEC-12 | In-force policy headers and legacy invoices | Confirm the header scope and the treatment of a legacy invoice (not re-booked; processed like a BIBS invoice on the legacy control accounts). | PR-DM-11, PR-DM-23, DMQ09, DMQ10 | Head, Operations; Head, Comptrollership | M1 (16-Oct-2026) |
| DEC-13 | Point of no return | Confirm the end of the first business day as the point of no return and who decides a rollback. | PR-DM-16, DMQ32 | Program Manager | M6 (1-Oct-2027) |
| DEC-14 | Advisory recipients and alert channel | Name the recipient units of package advisories and confirm in-app notices to TSU and MBS for the expiry and incentive alerts (sheet Notifications). | CLR-PM-06, CLR-PM-07, PQ12 | Product Owner, Marketing Business System | D5 (16-Jul-2027) |
| DEC-15 | Full status labels | Confirm full stage and status labels on the screens, with the short forms of the labels above 21 characters. | CLR-PM-20, CLR-UA-20 | Business owners of BRD-03 and BRD-11 | Sign-off of each set |

# 6 Configuration inputs

The workbook has one register row per configuration input, grouped in twelve areas: organisation; chart of accounts and accounting; banks and bank accounts; document numbering; lists of values; system and security parameters; notifications and documents; products and packages; insurers and partners; users, roles and approvals; module rules and set-up; data migration reference data. Each row has one route:

•	Template: the owner fills the template sheet named in the row; the rows are entered or uploaded on the named screen and authorised by a second user. The workbook holds the templates CI-01 to CI-10 of BRD-03 and CI-01 to CI-06 of BRD-11, taken from the same sources as their sets, and the fifteen Drop 0 templates D0-01 to D0-15 for the company, branches, holidays, dimensions, employees, chart of accounts, categories and numbering, accounting rules, legacy accounts, tax codes, bank accounts, check books, petty cash, statement layouts and approval limits.

•	Screen: the owner enters the item directly on the named screen and records the decision in the register.

•	Migration object: the item is extracted from the legacy systems and loaded by the named object of the Migration Workbook of BRD-13. It is not typed in the configuration workbook; the sheet Migration cross-reference names the object of every such item, so that no item reaches BIBS twice.

Table 4: Register items per area and route

| Area | Template | Screen | Migration object | Items |
| --- | --- | --- | --- | --- |
| Organisation | 5 | 5 | 1 | 11 |
| Chart of accounts and accounting | 5 | 6 | 1 | 12 |
| Banks and bank accounts | 5 | 1 | 0 | 6 |
| Document numbering | 2 | 0 | 1 | 3 |
| Lists of values | 1 | 0 | 1 | 2 |
| System and security parameters | 2 | 4 | 0 | 6 |
| Notifications and documents | 3 | 1 | 0 | 4 |
| Products and packages | 7 | 0 | 2 | 9 |
| Insurers and partners | 0 | 2 | 3 | 5 |
| Users, roles and approvals | 5 | 1 | 0 | 6 |
| Module rules and set-up | 0 | 12 | 0 | 12 |
| Data migration reference data | 0 | 0 | 2 | 2 |
| Total | 35 | 32 | 11 | 78 |

Table 5: Lists of the workbook with one row per value

| List | Rows | Of which loaded by the migration (R01) |
| --- | --- | --- |
| Lists of values | 133 | 8 |
| System parameters | 208 | 0 |
| Numbered document prefixes | 11 | 0 |
| Notification events | 88 | 0 |
| Document templates | 62 | 0 |
| Accounting events (rules of D0-08) | 87 | 0 |

## 6.1 Timeline

The due dates are set against the programme milestones and counted back from go-live. The platform set-up that Drop 1 SIT uses is due first; the production values are due before the dress rehearsal, and the reference values freeze with the code maps seven days before go-live.

Table 6: Configuration inputs timeline (go-live T = 3-Jan-2028)

| Due | Milestone | Date | Before go-live | Configuration inputs due |
| --- | --- | --- | --- | --- |
| D1 | Drafts with the Drop 0 sign-off | 1-Dec-2026 | T-56 weeks | • Legacy control accounts and Migration Clearing • Directory sign-in and provisioning (EIAM, UIDM-ISC) |
| D2 | Platform set-up for Drop 1 SIT | 4-Jan-2027 | T-52 weeks | • Company • Branches and invoicing branches • Holiday calendar • Cost centres and business lines • Chart of accounts • Account categories and numbering scheme • Accounting rules per event • Company bank accounts • Account numbering scheme |
| D3 | Reference data for Trial migration 1 (M4) | 9-Apr-2027 | T-38 weeks | • Sales organisation (regions, departments, teams, unit heads, account officers) • Bank list (mortgagee banks) • Lists of values (every list of the platform) • Product catalogue • Insurers and insurer branches • Commission rates by insurer and product • Payees • Role-to-permission matrix |
| D4 | Code maps approved (M5) | 18-Jun-2027 | T-28 weeks | • Chart of accounts mapping (legacy GL account to BIBS account) • Values of the lists used by migrated records • Package map (legacy package to BIBS package version) • Code maps of the reference data • Branch code map |
| D5 | Values for UAT | 16-Jul-2027 | T-24 weeks | • Employees • Cost-centre rules • Production targets • Currencies and exchange rates • Group, subsidiaries and inter-company relationships • Tax codes and forms • Financial statement formats and account schedules • Asset categories • Investment portfolios • GL-SL reconciliation controls (ACSL) • Service fee rates • Bank statement layouts • Payment file layouts of the collection channels • Document number prefixes • System parameters (every parameter of the platform) • Sign-in, password, session and access-request parameters • Exception codes and alert thresholds • Scheduled job times • Data retention rules • Notification events and recipients • Fixed recipients and sender address • Document templates (letters, slips, advices, e-mails) • Screening forms and STR layout • Coverages, perils and field rules • Clause library • Rate tables • Incentive criteria • Lists and parameters of Product Maintenance • Package document templates • Business partners other than insurers (suppliers, service providers) • Insurer location references (claims) • Approvers, approval rules and authorisation limits • Separation-of-duties rules • Approval limits and matrices of the modules • User scope of Submitted Policies • Booking rules and incentive rules • Remittance incentive rules • Commission incentive schemes • Collections assignment and escalation rules • Renewal buckets and decision matrix • Submitted Policies rules, limits and letters • Screening configuration • Watchlist sources and entries • Employee Benefits set-up • Claims handlers and set-up • Production reconciliation extract schedules • New Business report variants |
| D6 | Production values before the dress rehearsal | 1-Nov-2027 | T-9 weeks | • Financial year and periods • Recurring journals • Check books • Petty cash funds • Packages in force at go-live • Users at go-live |
| D7 | Map freeze (T-7) | 27-Dec-2027 | T-1 weeks | • Receipt series in use (AR and OR) |

# 7 Entry and exit criteria

## 7.1 Entry criteria for closing Drop 0

•	The three sign-off sets v2.0 of Drop 0 are issued: BRD-03 Product Maintenance, BRD-11 User Access Maintenance and BRD-13 Data Migration, each with its test plan.

•	The configuration inputs workbook of Drop 0 is issued and each owner has received the sheets of the items it owns.

•	The walkthrough sessions of each set are held on the SIT environment with seed data.

## 7.2 Exit criteria: Drop 0 is closed when

•	The sign-off certificate of each of the three sets is signed (BRD-13 by 30-Oct-2026, BRD-03 by 30-Nov-2026, BRD-11 by 1-Dec-2026).

•	Every proposed rule and clarification of the three sets is decided, or accepted as the working assumption with its decision date.

•	Every consolidated decision of this summary has an owner and a date; those due at M1 and M2 are taken.

•	Every configuration item of the workbook has an owner, a due date and one route; the items due at D1 are Provided or In progress.

•	The comments logs of the three sets are closed: answered, corrected in v2.1, or raised as change requests.

## 7.3 Entry criteria for Drop 1

•	Drop 0 is closed: the three sets are signed and the decisions of this summary are recorded.

•	The BRD-1 New Business sign-off set v2.0 is issued (folder Drop-1_Transactional); its review and sign-off follow the same steps.

•	The platform set-up that Drop 1 SIT uses is provided by D2 (4-Jan-2027): company, branches, holidays, dimensions, chart of accounts and numbering, accounting rules, bank accounts.

•	The users and group profiles of the SIT and UAT reviewers are created through access requests.

•	The lists of values and parameters of New Business are confirmed on the sheets Lists of values and System parameters.

# 8 Risks and dependencies

Table 7: Risks

| ID | Risk | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| RSK-01 | Configuration inputs arrive after their due date, so Drop 1 SIT or a trial migration runs on seed values | SIT results do not hold for production; trial migrations are repeated | Owner per item and due date in the workbook; status reviewed at the weekly programme meeting from December 2026 | Program Manager |
| RSK-02 | The production chart of accounts and the accounting rules are not final before Drop 1 SIT | Postings of Drop 1 are tested against a draft chart; the GL opening (G01) and Migration Clearing cannot be reconciled | Chart and rules due at D2; legacy accounts (D0-09) and the GL map (R08) due at D3 and D4 | Head, Comptrollership |
| RSK-03 | Year-end option A is not confirmed by M6 | The cut-over calendar, the GL opening and the true-ups change | Confirmation asked with the Drop 0 closure (DEC-01) | Head, Comptrollership |
| RSK-04 | EIAM and UIDM-ISC specifications are late | Sign-in stays local for SIT; the directory sign-in is tested late | Local sign-in with the Windows ID captured on every user; directory mode switched on when specified (DEC-05) | BDOI IT |
| RSK-05 | Conditional migration objects are decided late | Layouts, trial migrations and reconciliation of those objects are added late | Decisions at M1 and M2 (DEC-03); objects not decided are completed in legacy before the freeze | Program Manager |
| RSK-06 | An item reaches BIBS by two routes (keyed on a screen and loaded by the migration) | Duplicate or conflicting reference values at go-live | One route per item in the workbook; the Migration cross-reference sheet names the object of every migrated item | Data Migration Lead |
| RSK-07 | Changes to signed Drop 0 content during Drop 1 reviews | Rework of screens and templates of a signed set | Change control: every change is a change request with its effect on the other BRDs and a delta sign-off | Program Manager |

Table 8: Dependencies

| ID | Dependency | From | Needed by |
| --- | --- | --- | --- |
| DEP-01 | BDOI answers to the M1 and M2 decisions of the Data Migration set | BDOI business owners | 16-Oct-2026 and 30-Oct-2026 |
| DEP-02 | Organisation, chart of accounts, accounting rules and bank accounts for Drop 1 SIT | Comptrollership | 4-Jan-2027 (D2) |
| DEP-03 | First full extracts with control files and volumes | BDOI IT | 29-Jan-2027 (M3) |
| DEP-04 | EIAM and UIDM-ISC specifications | BDOI IT | Q1 2027 |
| DEP-05 | Role-to-permission matrix and users of the SIT and UAT reviewers | Business Administration; Information Security | 9-Apr-2027 (D3) |
| DEP-06 | Code maps approved, including the package code map | Data owners; TSU | 18-Jun-2027 (M5) |
| DEP-07 | Production values of every configuration item | Owners in the workbook | 1-Nov-2027 (D6), dress rehearsal |

# 9 Change control

•	Before signature. A question on a set is answered in the comments log of its sign-off workbook without changing the text; a correction is made once, in version 2.1 of the set, with the changed rows marked.

•	After signature. Nothing in a signed set changes without a change request in the Change Management Register. The request states its effect on the other BRDs through the cross-BRD interface contract of the set and its mandays, is approved by the owners of every BRD it touches, and is delivered as a new version of the set (2.1, 2.2) in which only the changed pages are signed again.

•	Configuration inputs. A value in the workbook is changed by the owner of the row until the due date, and after it by a change request. The reference values and code maps freeze seven days before go-live (D7); a change after the freeze is a change request with a new code map version.

•	Open items. A question still open at signature stays open on its stated working assumption until BDOI answers it; the answer is applied as configuration or through a change request.

# 10 Closure sign-off

By signing, the steering committee closes Drop 0 on the basis of the three signed sets, records the decisions of chapter 5 with their owners and dates, accepts the configuration inputs timeline of chapter 6 and opens Drop 1.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Product Owner, Marketing Business System | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Head, BDOI Information Security | BDOI |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Data Migration Lead | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |