START HERE GUIDE

Start Here

Guide to the BRD-01 New Business Sign-off Pack, release set v2.0

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-SH-BRD-01 |
| Version | 2.0 |
| Date | 27 September 2026 |
| Status | Issued for BDOI business sign-off |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 2.0 | 27 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Business Analysis |  | First issue with the BRD-1 New Business business sign-off pack (replaces the release note of the set) |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Product Owner, BDOI | Approver | BDOI | Sign-off |
| Marketing Business Services and System Support (MBS) | Business owner | BDOI | Review and sign-off |
| Marketing, TSU, Processing, Comptrollership | Reviewers | BDOI | Review of their screens and rows |
| Compliance and BDOI IT | Reviewers | BDOI | KYC and screening; interfaces and access |
| Business Project Services | BRD owner | BDO Unibank ESG | Traceability and sign-off coordination |
| Project team | Delivery | iorta TechNXT | Sessions, answers, revisions, change requests |

Contents

1 What this pack is for	4

2 The pack at a glance	4

3 Where to start	4

4 Steps up to closure	5

5 Change control after sign-off	6

# 1 What this pack is for

This pack shows BRD-1 New Business as built in BIBS on 27-Sep-2026, screen by screen, so that each BDOI business unit can confirm what it will get and sign it off. Signing freezes the content, the screens and the navigation of New Business; a later change goes through the Change Management Register with its mandays. The screenshots use fictitious seed data only.

# 2 The pack at a glance

The files are numbered so that they sort in reading order in the folder BRD-01_New_Business of Drop 1.

Table 1: The documents of the set, in reading order

| File | What it is for | Who reads it | When |
| --- | --- | --- | --- |
| 00_BIBS_StartHere_BRD-01_New_Business_v2.0.docx | Start Here: the map of the pack, who reads what, the steps and the dates | Everyone | First, on issue |
| 01_BIBS_GuideDeck_BRD-01_New_Business_v2.0.pptx | Sign-off Pack Guide: purpose, approach, the module at a glance, caveats, entry and exit criteria, change control | Business owner, unit heads; presented at the kick-off | Kick-off session |
| 02_BIBS_FRS_BRD-01_New_Business_v2.0.docx | Functional Requirements Specification v2.0: requirements, navigation, 46 screen specifications with screenshots, walkthroughs, messages, notifications, documents, uploads, cross-BRD contract | Business users of each area; Finance, Compliance and BDOI IT for their chapters | During the review, with the SIT walkthroughs |
| 03_BIBS_Signoff_BRD-01_New_Business_v2.0.xlsx | Sign-off workbook: one row per screen, field, rule and message with the BU review columns; comments log, meeting minutes, version history, sign-off certificate | Every reviewer; the business owner signs it | During the review and at sign-off |
| 04_BIBS_TestPlan_BRD-01_New_Business_v2.0.xlsx | Test plan workbook: the test cases traced to the FRs and to the screens, including one screen case and one message case per screen | Business users who will run UAT; BDOI IT | After the screens; used again in SIT and UAT |
| 05_BIBS_TestPlan_BRD-01_New_Business_Summary_v2.0.docx | Test plan summary: scope, approach, coverage and the cases by area | Business owner, BDOI IT | Before sign-off |

# 3 Where to start

Table 2: Reading order per role

| Role | Where to start |
| --- | --- |
| Business owner (Product Owner, Head of MBS) | 00 Start Here; 01 Guide deck; FRS chapters 1-3 (context and personas), 14 (walkthroughs) and 20 (sign-off); workbook Sign-off certificate |
| Business users (Marketing, TSU, Processing) | FRS chapter 12 (navigation) and the screens of your area in chapter 13; walkthroughs in chapter 14; messages in chapter 15; workbook Screen standards, Screen catalogue, Field register, Business rules and Messages |
| Finance (Comptrollership) | FRS Booking requirements (chapter 4) and generated documents (chapter 17: service invoice); walkthrough A steps 16-17; cross-BRD contract with Operations, Collections and Accounting (chapter 19); workbook Business rules of the booking screens |
| Compliance | Client onboarding and KYC screens (SCR-NB-01 to 04); sanction screening lines of the contract (chapter 19); retention rules; messages of the client screens |
| BDOI IT | Interfaces and integration (chapter 7), non-functional requirements (chapter 8), menu by persona (chapter 12), cross-BRD contract (chapter 19); integrations pending specifications (Guide deck, caveats) |
| iorta TechNXT project team | All documents; keeps the comments log, the meeting minutes and the version history of the workbook, answers every comment and keeps the traceability to SIT and UAT |

SIT users of the seed data for the review: ao and mkttl (Marketing), tsu (TSU), proc, proctl and epol (Processing), badmin (Business Administration). The passwords are sent separately to the named reviewers.

# 4 Steps up to closure

Table 3: From issue to closure

| No. | Step | Who (R, A, C, I) | Output | When / duration |
| --- | --- | --- | --- | --- |
| 1 | Pack issued | R: iorta TechNXT Project Manager; A: iorta TechNXT delivery lead; I: all reviewers | Release set v2.0 in the BRD-01 folder; invitations to the sessions | Day 0 (Mon 28-Sep-2026) |
| 2 | Kick-off and screen walkthrough on SIT | R: iorta TechNXT Business Analysis; A: BDOI Product Owner; C: unit heads; I: BDOI IT | Screens shown live; first questions logged in the comments log; minutes | 4 sessions, 1 to 6-Oct-2026 |
| 3 | Review with the workbook | R: business users of each unit; A: unit heads; C: iorta TechNXT (questions) | Every row marked Accept, Change requested or Comment; comments log entries | 10 working days after the walkthroughs, until Fri 16-Oct-2026 |
| 4 | Comments consolidated and a Q&A session | R: iorta TechNXT Project Manager and Business Analysis; A: BDOI Product Owner; C: reviewers | One consolidated comments log, each item typed (clarification, defect, change request) and answered; Q&A minutes | 3 working days, Q&A on Wed 21-Oct-2026 |
| 5 | One revision cycle (v2.1) | R: iorta TechNXT Business Analysis; A: iorta TechNXT delivery lead; C: reviewers who raised the items | Release set v2.1 with the changed rows marked; change requests raised for the rest | 2 working days, v2.1 on Fri 23-Oct-2026; check by the reviewers until Wed 28-Oct-2026 |
| 6 | Sign-off meeting and signature | R: iorta TechNXT Project Manager; A: BDOI Product Owner; C: unit heads, Finance, Compliance, BDOI IT | Signed sign-off certificate; minutes; open items accepted as assumptions or change requests | Fri 30-Oct-2026 |
| 7 | Handover to development or build freeze | R: iorta TechNXT delivery lead; A: BDOI Product Owner; I: BDOI IT, other BRD owners | Build frozen as signed; approved deltas scheduled in the Change Management Register | From Mon 2-Nov-2026 |
| 8 | Traceability into SIT and UAT | R: iorta TechNXT test lead; A: BDOI Product Owner; C: business users | SIT and UAT runs traced to the signed screens, rules and messages; results against each row | SIT Jan - Jul 2027; UAT Aug - Dec 2027 |

How to review. Open the FRS chapters of your area or the same screens on SIT. In the sign-off workbook, set BU review to Accept, Change requested or Comment on each row you review (sheets Screen standards, Screen catalogue, Field register, Business rules, Messages), write the change in BU comment, and add your name and the date. Questions go to the Comments log sheet. One workbook per unit is enough.

Table 4: SIT walkthrough sessions

| Date | Time | Session | Units |
| --- | --- | --- | --- |
| Thu 1-Oct-2026 | 09:30-12:00 | Kick-off; client onboarding, KYC and package quotation (walkthrough A steps 1-9) | Marketing, MBS |
| Fri 2-Oct-2026 | 09:30-12:00 | Non-package placement: PRF, quotation slip, insurer responses, proposal slip (walkthrough B) | TSU, Marketing |
| Mon 5-Oct-2026 | 09:30-12:30 | Validation, payment, placement, issuance and booking; returns and messages (walkthrough A steps 10-17, walkthrough C) | Processing, Comptrollership |
| Tue 6-Oct-2026 | 09:30-11:30 | Bulk uploads with the error file, reports and dashboard, administration screens | MBS, Business Administration, Compliance, BDOI IT |

# 5 Change control after sign-off

Signing freezes the New Business screens, fields, navigation, actions, business rules, messages, notifications, documents, upload templates and the cross-BRD contract as specified. Configuration values marked "default" (SLA hours, thresholds, list entries, templates) are not frozen. A change to anything frozen is raised in the Change Management Register with the screen, field, rule or message concerned, assessed with its mandays and its effect on the other BRDs, approved by the owners of every BRD it touches, and delivered as a new version of the set; only the affected pages are signed again.