## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
Renewal; goes with the FRS Renewal v1.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Inputs | Open questions, dependencies and settings of the FRS Renewal v1.3. | 50
Legend
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Inputs | No.
Inputs | What BDOI provides or decides
Inputs | Owner
Inputs | Needed by
Inputs | Status |  | Open, Received, Confirmed
Inputs | Answer

## Inputs
Inputs
Open questions, dependencies and settings of the FRS Renewal v1.3.
No. | What BDOI provides or decides | Owner | Needed by | Status | Answer
Q-RN-01 | Third panel: Non-Renewable (BDOI's FRS, setting default) or Exception (BRD BRRN.023)? | Product Owner, Renewal | 30 Nov 2026 | Open
Q-RN-02 | Transfer: referral, transfer of the account, or both (setting RNW_TRANSFER_MODE = BOTH)? | Marketing Heads | 30 Nov 2026 | Open
Q-RN-03 | Second approval after the client's acceptance (RNW_SECOND_APPROVAL, off by default)? | Product Owner, Renewal; Processing | 30 Nov 2026 | Open
Q-RN-04 | Lock point: at the Renewal Advice (BRD 2.004.9) or at placement (RNW_LOCK_POINT)? | Product Owner, Renewal | 30 Nov 2026 | Open
Q-RN-05 | Status names on the lists: BDOI's names (default) or the stages of the system (RNW_STATUS_NAMES)? | Product Owner, Renewal | 30 Nov 2026 | Open
Q-RN-06 | Effect of a BDOFC or BDOSOLD match on the renewal (flag only, or route to Review)? | Product Owner, Renewal; CBG | 30 Nov 2026 | Open
Q-RN-07 | What makes a structural change, and is the routing to New Business automatic? | Marketing; TSU | 30 Nov 2026 | Open
Q-RN-08 | Confirm the CCM and MFT go-live dates; e-mail stays the fall-back (RNW_DELIVERY_CHANNEL). | BDO ITG | 30 Nov 2026 | Open
Q-RN-09 | Confirm the password convention of protected files for individual and corporate clients. | Product Owner, Renewal; Compliance | 30 Nov 2026 | Open
Q-RN-10 | Confirm the incentive criteria for renewals (BRRN.041). | Product Owner, Renewal | 30 Nov 2026 | Open
Q-RN-11 | Approve or remove the change requests CR-RN-005, CR-RN-008 and CR-RN-015, which are delivered. | Product Owner, Renewal | 30 Nov 2026 | Open
D-RN-01 | BDOI IT gives the CCM address, client identifier and access key (ICD IF-RN-01). | BDOI IT | Before SIT | Open
D-RN-02 | BDOI IT gives the MFT server, folders, key and the list of enrolled insurers (ICD IF-RN-02). | BDOI IT | Before SIT | Open
D-RN-03 | BDOI IT gives the LMS directory and the billing file recipients (ICD IF-RN-05). | BDOI IT | Before SIT | Open
D-RN-04 | LAMD gives the monthly loan reports in the agreed layout (ICD IF-RN-06). | BDOI | Before SIT | Open
D-RN-05 | Data Migration loads the policies in force and the package code map before the go-live take-over. | BDOI | Before SIT | Open
D-RN-06 | BDOI gives the final wording of the Renewal Advice, letters and e-mails. | BDOI | Before SIT | Open
P-01 | Confirm the value of: RNW_EXTRACTION_LEAD_DAYS: days before expiry of the daily extraction (default 140) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-02 | Confirm the value of: RNW_EXTRACTION_LEAD_DAYS_BY_SEGMENT: lead days per segment (default (none)) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-03 | Confirm the value of: RNW_EXCLUDED_LINES: lines never extracted (default HMO, GLI, GPA) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-04 | Confirm the value of: RNW_BULK_INITIATION_SEGMENTS: segments initiated in bulk (default CLG) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-05 | Confirm the value of: RNW_REFERENCE_PREFIX: prefix of the renewal reference (default RNW) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-06 | Confirm the value of: RNW_DUPLICATE_CRITERIA / RNW_DUPLICATE_MIN_MATCH (default Expiring policy and PN / 1) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-07 | Confirm the value of: RNW_OUTSTANDING_THRESHOLD / RNW_FIN_IMPACT_TOLERANCE (default 0.00 / 0.00) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-08 | Confirm the value of: RNW_TSI_ABOVE_ROUTE: TSI above the threshold (default QUOTATION) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-09 | Confirm the value of: RNW_ENDORSEMENT_ROUTE: endorsements that route to Review (default ANY) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-10 | Confirm the value of: RNW_THIRD_BUCKET: third panel (default NON_RENEWABLE) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-11 | Confirm the value of: RNW_CLEAN_AUTO_RENEWAL / RNW_STP_SKIP_TL_REVIEW (default Yes / Yes) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-12 | Confirm the value of: RNW_AUTO_ASSIGN_SEGMENTS / RNW_AUTO_ASSIGN_PROCESSING (default (none) / No) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-13 | Confirm the value of: RNW_TRANSFER_MODE (default BOTH) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-14 | Confirm the value of: RNW_POSTING_APPROVER (default OPTIONAL) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-15 | Confirm the value of: RNW_LOCK_POINT (default RA_GENERATION) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-16 | Confirm the value of: RNW_REOPEN_DAYS: days after expiry to re-open (default 30) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-17 | Confirm the value of: RNW_INSURER_REPLY_DAYS (default 10) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-18 | Confirm the value of: RNW_RA_NOTICE_MODE / FIRST / LAST / SECOND / MIN notice days (default AUTOMATIC / 75 / 45 / 15 / 30) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-19 | Confirm the value of: RNW_NRNS_REMINDER_DAYS / RNW_NRNS_WAITING_DAYS (default 90 / 0) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-20 | Confirm the value of: RNW_NAL_OFFSET_DAYS / RNW_NRL_OFFSET_DAYS_CBG / _NON_CBG / RNW_NON_ACCEPTANCE_DAYS (default 1 / 1 / 3 / 0) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-21 | Confirm the value of: RNW_NAL_REASONS: reasons answered with a No Advice Letter (default Direct to insurer, with submitted policy, booked to new invoice, unit sold, cancelled policy) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-22 | Confirm the value of: RNW_PASSWORD_CONVENTION / RNW_FILE_NAMES (default CLIENT / CLIENT) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-23 | Confirm the value of: RNW_DELIVERY_CHANNEL (default CCM) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-24 | Confirm the value of: RNW_SECOND_APPROVAL: approval after acceptance (default No) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-25 | Confirm the value of: RNW_AUTO_PLACEMENT / RNW_BOOK_ON_PLACEMENT_APPROVAL (default No / No) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-26 | Confirm the value of: RNW_PLACEMENT_SLA_PACKAGED / _NON_PACKAGE / RNW_PLACEMENT_CUTOFF_HOUR (default 3 / 10 / 15) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-27 | Confirm the value of: RNW_HOLD_COVER_DAYS_NON_CBG / _CBG / _CBG_HOME_TRANSFER / _CBG_MOTOR_TRANSFER (default 30 / 90 / 30 / 60) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-28 | Confirm the value of: RNW_HOLD_COVER_CBG_DAYS_BEFORE / EXTENSION_WINDOW / EXTENSION_DAYS (default 75 / 7 / 15, 30) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-29 | Confirm the value of: RNW_CLPC_BILLING_DAYS_BEFORE / RNW_CLPC_FFY_DAYS (default 10 / 10th and 25th) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-30 | Confirm the value of: RNW_KYC_UPCOMING_DAYS / RNW_KYC_CLIENT_TYPES (default 60 / Bank, Non-bank) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-31 | Confirm the value of: RNW_ESCALATION_DAYS: days to expiry of the ageing flag (default IBG 60, Leasing 60, others 30) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-32 | Confirm the value of: RNW_CBG_MOTOR_AUTO_UPDATE / BI and PD tiers / RNW_PROMO_TO_REGULAR (default Yes / tables / Yes) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open
P-33 | Confirm the value of: RNW_MFT_ENROLLED_INSURERS / RNW_CCM_MODE / RNW_MFT_MODE / RNW_LMS_MODE (default (none) / LIVE at BDOI) | BDOI Product Owner, Renewal | 30 Nov 2026 | Open

## Lists
Status
Open
Received
Confirmed