## Cover
USER ACCEPTANCE
Business Unit Walkthrough Users
Renewal; goes with the FRS Renewal v1.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | One walkthrough account per persona of the FRS Renewal v1.3; the people are fictitious. | 10
Script | The storyboards of the Process and Storyboards v1.3, step by step. | 25
Legend
Pass
Fail
Blocked
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona
Users | Walkthrough account
Users | Does
Users | Screens
Users | Sign-in
Script | Storyboard
Script | Step
Script | Who
Script | Screen
Script | Does
Script | Sees
Script | Result |  | Not run, Pass, Fail, Blocked

## Users
Users
One walkthrough account per persona of the FRS Renewal v1.3; the people are fictitious.
Persona | Walkthrough account | Does | Screens | Sign-in
Marketing Team Lead | Marites Marketing Lead; Rosario Renewal Team Lead | Generates and initiates the expiry list, assigns and transfers renewals, reviews, returns, overrides and posts dispositions, decides transfers and TSU requests. | Renewal Home, Dashboard, Expiry List, TL Review, Transfers, Letters, KYC Monitoring | Issued separately by the iorta TechNXT Project Team
Marketing Account Officer | Aileen Account Officer; Arnel Account Officer | Gives the disposition of assigned renewals, sends the Renewal Advice and letters, records the client's acceptance, raises transfers and TSU requests. | My Dispositions, Renewal, Letters, Transfer Requests, KYC Monitoring | Issued separately by the iorta TechNXT Project Team
Processing Team Lead | Patricia Processing Lead | Assigns posted renewals to Processing Officers, uploads files, approves package choices, follows placement and billing. | Processing Dashboard, Processing Worklist, Renewal Setup (package choices), Submitted for Placement | Issued separately by the iorta TechNXT Project Team
Processing Officer | Paolo Processor | Sends renewals to the insurers, records the insurer's answer, places, books, sends e-policies and billing files. | Processing Worklist, Insurer Batches, Submitted for Placement, E-Policies, CLPC Billing Files | Issued separately by the iorta TechNXT Project Team
Contact Center | Cecilia Contact Center | Follows up clients who have not answered the Renewal Advice; sees no premium or commission. | Follow-ups, Renewal | Issued separately by the iorta TechNXT Project Team
LAMD | Leonardo Loan Monitoring | Uploads the LAMD loan reports and reads the matching results. | LAMD Reports, RMU Account Maintenance | Issued separately by the iorta TechNXT Project Team
TSU Officer | Teodoro TSU Analyst | Works the quotation requests raised from renewals. | TSU Requests | Issued separately by the iorta TechNXT Project Team
Business Administrator | Bea Business Admin | Keeps Renewal Setup, risk codes, lists of values, letter templates, RMU codes and the budget. | Renewal Setup, Risk Code Maintenance, Renewal Annual Budget, Channel Monitor, Audit Logs | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | Keeps the group profiles and the channel connections. | Channel Monitor; User Access screens (BRD-11) | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | Reads renewals, their history, the reports and the audit logs. Changes nothing. | Renewal Dashboard, Renewal Accounts, Audit Logs, reports | Issued separately by the iorta TechNXT Project Team

## Script
Script
The storyboards of the Process and Storyboards v1.3, step by step.
Storyboard | Step | Who | Screen | Does | Sees | Result
SB-01 An expiring account from the Expiry List to the Team Leader's post | 1 | Marketing Team Lead | Expiry List | Opens the Expiry List, tab Unassigned Disposition, ticks the renewal of Pacific Harbor Logistics Inc. and clicks Assign Disposition: Arnel Account Officer, then Assign and Push | Message: 1 assigned; the renewal leaves the tab | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 2 | Account Officer | My Dispositions | Opens My Dispositions | The renewal assigned to him with its expiry, the Review classification and the flags Outstanding and Claims | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 3 | Account Officer | Renewal | Opens the renewal, tab Account History, and clicks View Account History | The payments of the expiring invoice and the open claim; the viewing is recorded | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 4 | Account Officer | Set Disposition, Add Remark and Re-open | Clicks Set Disposition: For Renewal with the remarks of the client's call, then Save | Message: Saved; the disposition For Renewal on the renewal | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 5 | Account Officer | Set Disposition, Add Remark and Re-open | Clicks Push | Message: Pushed to the Team Leader; the status Review in Progress | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 6 | Marketing Team Lead | TL Review | Opens TL Review, tab For Review, ticks the renewal and clicks Post, then confirms | The outcome: 1 refused, the renewal cannot be posted while the claims, endorsement and outstanding premium checks fail | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 7 | Marketing Team Lead | TL Review | Clicks Override: Outstanding balance, reason Approved by the Team Leader, with remarks (the open claim and the endorsement are overridden the same way) | Message: 1 overridden; the override kept in the History tab of the renewal | Not run
SB-01 An expiring account from the Expiry List to the Team Leader's post | 8 | Marketing Team Lead | TL Review | Clicks Post again and confirms | Message: 1 posted; the renewal moves to Processing | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 1 | Processing Team Lead | Processing Worklist | Opens the Processing Worklist, tab For Processing, ticks the renewal and clicks Assign PO: Paolo Processor, then Assign | Message: 1 assigned; the renewal In Processing | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 2 | Processing Officer | Insurer Batches | Opens Insurer Batches, clicks New Batch with Luzon Assurance Co. and the expiry date of the renewal, then Create Batch, and opens the batch | The batch Draft with the renewal and the columns of the insurer extract | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 3 | Processing Officer | Insurer Batches | Clicks Send to Insurer and confirms | Message: Batch sent to the insurer; the batch Sent with its reply date | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 4 | Processing Officer | Record Insurer Response | Opens the renewal and clicks Record Insurer Response: Renew as is with the insurer reference, then Record | Message: Saved; the renewal RA Ready | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 5 | Account Officer | Letters | Opens Letters, tab RA Ready, ticks the renewal, clicks Generate RA: First notice, then Generate | Message: 1 generated; the renewal in RA Generated, locked on the Marketing side | Not run
SB-02 Processing, the insurer's answer and the Renewal Advice | 6 | Account Officer | Letters | Opens the tab RA Generated, ticks the renewal, clicks Send and confirms | Message: 1 sent; the Renewal Advice e-mailed protected to the client | Not run
SB-03 The Contact Center follow-up and the client's acceptance | 1 | Contact Center | Follow-ups | Opens Follow-ups, tab RA Sent | The renewal waiting for the client's reply | Not run
SB-03 The Contact Center follow-up and the client's acceptance | 2 | Contact Center | Follow-ups | Opens the renewal and clicks Add Follow-up: Call, Client will renew, the next action date and the remarks, then Save | Message: Saved; the follow-up on the Remarks & Follow-ups tab | Not run
SB-03 The Contact Center follow-up and the client's acceptance | 3 | Account Officer | Record Acceptance | Opens the renewal and clicks Record Acceptance: Payment with the payment reference, then Record | Message: Saved; the renewal For Placement and Booking | Not run
SB-03 The Contact Center follow-up and the client's acceptance | 4 | Account Officer | Renewal | Opens the tab Letters | The Renewal Advice in the e-mail queue to the client and the acceptance by payment | Not run
SB-04 Not for Renewal and the closing letter | 1 | Account Officer | Set Disposition, Add Remark and Re-open | Opens the renewal, views its account history, clicks Set Disposition: Not for Renewal, reason Loan fully paid, with remarks, then Save | Message: Saved; the disposition Not for Renewal with its reason | Not run
SB-04 Not for Renewal and the closing letter | 2 | Marketing Team Lead | TL Review | After the Account Officer's push, ticks the renewal on TL Review, clicks Post and confirms | Message: 1 posted; the renewal goes to the closing letters | Not run
SB-04 Not for Renewal and the closing letter | 3 | Account Officer | Letters | Opens Letters, tab NAL / NFR, ticks the renewal, clicks Send Letters and confirms | Message: 1 sent; the renewal is closed | Not run
SB-04 Not for Renewal and the closing letter | 4 | Account Officer | Renewal | Opens the renewal, tab Letters | The Not for Renewal Letter in the e-mail queue to the client | Not run
SB-05 A transfer to another unit, and the controls the user sees | 1 | Marketing Team Lead | Transfers | The Team Leader of Corporate Marketing Team 1 opens Transfers, tab Incoming, chooses Accept in the row action menu and confirms with remarks | Message: Transfer accepted; the renewal joins the Unassigned tab of the unit | Not run
SB-05 A transfer to another unit, and the controls the user sees | 2 | Account Officer | Set Disposition, Add Remark and Re-open | Aileen Account Officer gives a disposition on a renewal without opening its account history | Open the Account History before you give the disposition | Not run
SB-05 A transfer to another unit, and the controls the user sees | 3 | Marketing Team Lead | Expiry List | Marites Marketing Lead transfers a renewal of her unit to CBG Metro Team 1, her own unit | The receiving unit must be another unit | Not run

## Lists
Result
Not run
Pass
Fail
Blocked