RUNBOOK

Cutover Runbook

BRD-13 Data Migration - production cutover from T-30 to hypercare exit

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-DMC-BRD-13 |
| Version | 1.2 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | First issue; dates are relative to T until BDOI confirms the go-live date (DMQ25); re-issued after the dress rehearsal with named people and measured timings |
| 1.1 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | Calendar of the BDOI timeline (go-live January 2028, proposed Monday 3 January 2028) with the relative days mapped to dates; tasks moved off the year-end holidays (GNG-2 and the last business day to T-5, completion drives to T-12, client load to T-11); carried RMEL cohorts of January-May 2028 with the completeness check and the catch-up extraction; default names of the decommissioning criteria. Named people and measured durations follow in version 1.2 after the dress rehearsal |
| 1.2 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | BDOI answers of 26-Sep-2026. Year-end cut-over option A (DMQ39, recommended, awaiting Comptrollership confirmation) - December soft close, provisional GL opening, legacy GL restricted to FY2027 adjustments, true-up 1 (T+15 to T+18) and the final true-up with the legacy GL lock and the closure (T+60 to T+120, new phase H). January-May 2028 expiries processed in BIBS after go-live (DMQ37) - Renewal team readiness, RA-sent file with maker-checker review of rejects (DMQ38), go-live extraction at T 04:00 and the day-1 priority queue; the carried cohorts are removed. Tasks renumbered CT-001 to CT-095. Named people and measured durations follow in version 1.3 after the dress rehearsal |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Owner of the cutover; chair of the go / no-go board |
| Go / no-go board members | Approver | BDOI | Checkpoints GNG-1, GNG-2, GNG-3 |
| BDOI IT (legacy EBIX, QPS, ISYS, CMS) | Task owner | BDOI | Freeze, extracts, read-only, rollback |
| Comptrollership; Operations; Marketing; Compliance | Task owner | BDOI | Accounts, reconciliation, verification, communication |
| Project team | Task owner | iorta TechNXT | Loads, reconciliation, environment, hypercare |

Contents

1 Purpose and use	5

2 Cutover organisation	5

2.1 Command centre	5

2.2 Roles	6

3 Timeline	6

3.1 Calendar	7

3.2 Freeze windows	8

4 Go / no-go checkpoints	9

5 Task list	11

5.1 Phase A - Readiness	11

5.2 Phase B - Pre-load and daily deltas	12

5.3 Phase C - Legacy freeze and final extracts	13

5.4 Phase D - Production load	14

5.5 Phase E - Reconciliation, verification and go / no-go	15

5.6 Phase F - Go-live	16

5.7 Phase G - Hypercare	16

5.8 Phase H - Final true-up and legacy GL close	18

6 Rollback	19

7 Year-end cut-over and FY2027 true-ups	19

8 Communication plan	20

9 Hypercare	21

9.1 Roster	21

9.2 Exit criteria	21

10 Decommissioning checklists	22

Sign-off	23

# 1 Purpose and use

This runbook is the plan of the production cutover of BIBS: from 30 days before go-live (T) to the end of hypercare. It lists every task with its owner, start, duration, predecessors and the evidence that proves it is done; the go / no-go checkpoints with their criteria; the freeze windows; the rollback procedure; the communication plan; the hypercare roster and exit criteria; and the decommissioning checklists of the legacy systems.

•	T is the go-live date. The BDOI timeline sets it in January 2028 (DMQ25). The recommendation, awaiting Comptrollership confirmation, is Monday 3 January 2028 at the year-end boundary (DMQ39 option A, register DCR-242): legacy processes to 31 December 2027 and closes FY2027, and BIBS opens with the open items at 31 December and a provisional GL opening. Days are calendar days; times are Philippine time (PHT). Section 3.1 maps the relative days to dates; tasks that would fall on the year-end holidays are placed on the nearest working day.

•	The same tasks are in the Cutover Task Plan workbook (BIBS_Migration_BRD-13_Cutover_Task_Plan_v1.2.xlsx), where names, actual times and status are recorded, and in the Migration Console as the plan of kind PRODUCTION (FR-DM-120). The console is the record during the cutover; the workbook is the planning and review copy.

•	The plan is rehearsed in four trial migrations (April, July, August and October 2027) and a dress rehearsal (November 2027) (Strategy chapter 10). This version gives planned durations; version 1.3, issued after the dress rehearsal, gives the measured durations and the named people.

•	The early renewal release of the concept paper of 6 September 2026 is superseded by the single January 2028 go-live (register DCR-240). The renewals of the January-May 2028 expiries are processed in BIBS after go-live (DMQ37): no renewal is carried from legacy. The Renewal processing team is made ready for the January expiries (CT-013), compiles the renewal advices already sent from its Excel trackers (CT-033) and reviews the rejected rows with a maker and a checker (CT-055); BIBS extracts every expiry to 31 May 2028 at T 04:00 (CT-062), and the team works the day-1 priority queue, January expiries first (CT-066).

•	The FY2027 closing and audit adjustments that Comptrollership posts in the legacy GL after the freeze reach BIBS as true-ups: true-up 1 after the legacy year-end close (CT-080 to CT-084) and the final true-up after the audited financial statements, followed by the legacy GL lock and the closure (phase H, CT-087 to CT-095).

# 2 Cutover organisation

## 2.1 Command centre

•	Location and channels. A command centre room at BDOI head office, a standing bridge line and a chat channel for the cutover team, open from T-3 17:00 to T+5.

•	Status calls. T-3 to T: every 4 hours and at each checkpoint. T+1 to T+5: 08:00 and 17:00. Afterwards daily at 17:00 until hypercare exit.

•	Decisions. Task owners report completion with the evidence in the console. The Data Migration Lead decides within the plan; anything that changes the plan, the scope or a checkpoint goes to the go / no-go board.

•	Escalation. Task owner to the Data Migration Lead (15 minutes), to the iorta Project Manager and the Program Manager (30 minutes), to the go / no-go board (1 hour, or immediately for a stop condition).

Stop conditions (the board meets at once): a rejected final extract that cannot be re-sent within 2 hours; a load failure that leaves a financial object incomplete; Migration Clearing not 0.00 after the reconciliation window; a legacy posting after the freeze; loss of the production environment or of the snapshot.

## 2.2 Roles

Table 1: Roles used in the task plan

| Code | Role | Organisation |
| --- | --- | --- |
| PM | BDOI Program Manager (ESG - Business Project Services) | BDOI |
| DML | BDOI Data Migration Lead | BDOI |
| OWN | Data owners (department heads of each object) | BDOI |
| STW | Data stewards | BDOI |
| COMP | Comptrollership (reconciliation approver for financial objects) | BDOI |
| OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI |
| MKT | Marketing (Retail and Corporate) | BDOI |
| RNW | Renewal processing team (makers and checkers; Head of the Renewal processing team) | BDOI |
| CMP | Compliance and Audit | BDOI |
| BIT | BDOI IT (legacy systems, extracts, network, SFTP) | BDOI |
| GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT |
| IPM | iorta TechNXT Project Manager | iorta TechNXT |
| IML | iorta TechNXT Migration Lead (loaders, reconciliation, console) | iorta TechNXT |
| IOP | iorta TechNXT Migration Operator (intake, validation, loads) | iorta TechNXT |
| IDO | iorta TechNXT DevOps (AWS environment, snapshots, access, monitoring) | iorta TechNXT |
| IQA | iorta TechNXT QA (smoke tests, issue triage) | iorta TechNXT |

# 3 Timeline

Table 2: Cutover phases

| Phase | Name | When | Tasks | IDs |
| --- | --- | --- | --- | --- |
| A | Readiness | T-30 to T-15 (4 to 19 Dec 2027) | 15 | CT-001 to CT-015 |
| B | Pre-load and daily deltas | T-14 to T-4 (20 to 30 Dec 2027) | 19 | CT-016 to CT-034 |
| C | Legacy freeze and final extracts | T-3 (Friday 31 Dec 2027) | 5 | CT-035 to CT-039 |
| D | Production load | T-2 (Saturday 1 Jan 2028) | 13 | CT-040 to CT-052 |
| E | Reconciliation, verification and go / no-go | T-1 (Sunday 2 Jan 2028) | 9 | CT-053 to CT-061 |
| F | Go-live | T (Monday 3 Jan 2028) | 9 | CT-062 to CT-070 |
| G | Hypercare and true-up 1 | T+1 to T+30 (4 Jan to 2 Feb 2028) | 16 | CT-071 to CT-086 |
| H | Final true-up and legacy GL close | T+31 to T+120 (Feb to 2 May 2028) | 9 | CT-087 to CT-095 |

## 3.1 Calendar

Table 3: Relative days on the calendar of the recommended go-live

| Day | Date (T = 3-Jan-2028) | Note |
| --- | --- | --- |
| T-30 | Sat 4 Dec 2027 | Dress rehearsal (15-26 Nov 2027) already done; reserve slot 6-10 Dec 2027 if its exit criteria were missed |
| T-26 | Wed 8 Dec 2027 | Feast of the Immaculate Conception (special non-working day) - the Comptrollership set-up (CT-007) is planned from T-25 |
| T-21 | Mon 13 Dec 2027 | Communications to branches, insurers and bank channels; legacy December soft close under way |
| T-20 | Tue 14 Dec 2027 | Renewal processing team readiness - January staffing plan, training, day-1 queue rehearsed |
| T-15 | Sun 19 Dec 2027 | GNG-1 (board meets on Friday 17 December if preferred) |
| T-14 | Mon 20 Dec 2027 | December soft close complete; production pre-load of reference data starts |
| T-12 | Wed 22 Dec 2027 | Client extract; completion drives for remittance batches and in-flight items (moved from T-9, Christmas Day) |
| T-11 | Thu 23 Dec 2027 | Client load and sign-off; daily client deltas start (moved from T-10, Christmas Eve) |
| T-10 | Fri 24 Dec 2027 | Christmas Eve (special non-working day) - no task planned |
| T-9 | Sat 25 Dec 2027 | Christmas Day - no task planned |
| T-7 | Mon 27 Dec 2027 | Code map freeze; legacy reference-data change freeze |
| T-5 | Wed 29 Dec 2027 | Last legacy business day; GNG-2 (moved from T-4, Rizal Day); freeze announcement; final RA-sent file; legacy GL access list for FY2027 adjustments |
| T-4 | Thu 30 Dec 2027 | Rizal Day (regular holiday) - no task planned |
| T-3 | Fri 31 Dec 2027 | Last day of the year (special non-working day) - last legacy EOD; preliminary December TB; business freeze 22:00; legacy GL restricted to FY2027 adjustments; final extracts |
| T-2 | Sat 1 Jan 2028 | New Year's Day - production load, provisional GL opening (cut-over team on duty) |
| T-1 | Sun 2 Jan 2028 | Reconciliation, verification, P03 resubmissions until 12:00, GNG-3 at 18:00 |
| T | Mon 3 Jan 2028 | Renewal go-live extraction 04:00; go-live 08:00; day-1 renewal priority queue; point of no return 18:00 |
| T+10 | Thu 13 Jan 2028 | First daily Renewal extraction of new expiries (1 June 2028) |
| T+15 | Tue 18 Jan 2028 | Legacy FY2027 year-end close complete |
| T+18 | Fri 21 Jan 2028 | True-up 1 posted, reconciled and signed |
| T+30 | Wed 2 Feb 2028 | First month-end close (January 2028) completed; hypercare exit decision |
| T+60 | Fri 3 Mar 2028 | Interim true-up 2, only when needed |
| T+85 | Tue 28 Mar 2028 | Audited FY2027 financial statements (about March-April 2028; follows the audit timetable) |
| T+99 | Tue 11 Apr 2028 | Final true-up posted; FY2027 BIR annual returns filed from legacy |
| T+106 | Tue 18 Apr 2028 | Legacy GL locked |
| T+120 | Tue 2 May 2028 | True-ups closed |

Figure 1: The cutover weekend (T = Monday 3 January 2028, recommended; times PHT)

## 3.2 Freeze windows

Table 4: Freeze windows

| Freeze | From | Until | Scope | Exception route |
| --- | --- | --- | --- | --- |
| Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects |
| Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live |
| Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings of the business modules of EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements; GL journals other than the FY2027 adjustments | None; an urgent item is recorded on paper and keyed in BIBS on T |
| Legacy GL (FY2027 adjustments) | T-3 22:00 | Legacy GL lock (T+106) | Only FY2027 closing and audit adjustments, by the Comptrollership users on the signed access list; FY2028 periods never opened in legacy; no new business | Each journal in the FY2027 adjustment register; it reaches BIBS in the next true-up |
| BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board |
| BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical issue approved by the go / no-go board |

# 4 Go / no-go checkpoints

Each checkpoint is recorded in the Migration Console with the value of every criterion at the time of the decision (FR-DM-121). A criterion that is not met blocks GO unless the board records a waiver with its reason (only for criteria marked as waivable in the console; the financial and clearing criteria of GNG-3 are never waived).

Table 5: GNG-1 at T-15 - Start the production pre-load

| # | Criterion |
| --- | --- |
| 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed |
| 2 | Production environment, roles and PH-only access ready; masking off only in production |
| 3 | Legacy control accounts, Migration Clearing and LG_ rule lines approved in production (DMQ18) |
| 4 | Code map versions for production approved |
| 5 | Transfer path (SFTP or console) tested |
| 6 | December soft close on track for 20 December 2027 |
| 7 | Renewal processing team ready - January staffing plan signed, training done, day-1 queue rehearsed |
| 8 | No open Critical issue of the migration or of a Day-1 module |

Table 6: GNG-2 at T-5 - Enter the legacy freeze on T-3

| # | Criterion |
| --- | --- |
| 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running |
| 2 | Client review queue empty |
| 3 | Final extract jobs timed within the window (dry run) |
| 4 | In-flight items and remittance batches closed or listed for carry-forward |
| 5 | P01 dry run covers every expiry to 31 May 2028 and every renewal term booked in legacy starting on or after T |
| 6 | Draft RA-sent file validated; its rejects reviewed by the Renewal processing team |
| 7 | Comptrollership access list for the legacy GL after the freeze named |
| 8 | Communications sent; branches and insurers informed |

Table 7: GNG-3 at T-1 18:00 - Go live on T

| # | Criterion |
| --- | --- |
| 1 | Every Day-1 object at G6 (100 percent) |
| 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object |
| 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan |
| 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency |
| 5 | Migration Clearing - 0.00 per branch and currency |
| 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00 |
| 7 | Client review queue empty; screening run complete |
| 8 | Business smoke test passed |
| 9 | Rollback point (snapshot) taken and verified |
| 10 | Hypercare roster and support channels in place |
| 11 | Preliminary December TB signed as the provisional opening; legacy GL restricted to the named FY2027 adjustment users |
| 12 | Headers of every expiry to 31 May 2028 loaded; RA-sent file loaded; Renewal January staffing plan confirmed |

Table 8: POINT OF NO RETURN at T 18:00 - Continue in BIBS; fallback to legacy no longer offered (DMQ32)

| # | Criterion |
| --- | --- |
| 1 | No Critical issue that stops receipts, payment application, remittance or booking |
| 2 | Migration Clearing still 0.00; no posting in legacy since the freeze |
| 3 | Every branch has transacted in BIBS |

Table 9: TRUE-UP CLOSED at T+120 - Close the FY2027 true-ups

| # | Criterion |
| --- | --- |
| 1 | Final true-up reconciled to the audited FY2027 TB and signed by the Head of Comptrollership |
| 2 | Legacy GL locked for all users; FY2027 adjustment register closed |
| 3 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers after the final true-up |
| 4 | Opening journals no longer marked PROVISIONAL |

# 5 Task list

Columns: When is the day relative to T and the planned start time; Owner is the accountable role (codes in section 2.2); Hours is the planned elapsed time; After lists the tasks that must be complete first; Verification is the evidence recorded in the console.

## 5.1 Phase A - Readiness

Table 10: Phase A - Readiness

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-001 | T-30 | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed, go-live renewal extraction run) | DML | 4 | - | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |
| CT-002 | T-30 | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25) with Comptrollership's confirmation of the year-end option A (DMQ39); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated; option A confirmed in writing by the Head of Comptrollership |
| CT-003 | T-29 | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |
| CT-004 | T-28 | Freeze the production cutover plan in the Migration Console (plan kind PRODUCTION, tasks and owners from this list) | IML | 4 | CT-002 | MIG-CUTOVER-STATUS shows the plan with every task owned |
| CT-005 | T-28 | Production environment ready - BIBS release of the go-live release deployed, MIG_ENVIRONMENT_CLASS = PRODUCTION, MIG_CUTOVER_DATE = T, MIG_OPENING_VALUE_DATE = 1-Jan-2028, MIG_GOLIVE_RENEWAL_TO = 31-May-2028, MIG_RENEWAL_URGENT_TO = 31-Jan-2028, jobs scheduled | IDO | 8 | - | Deployment record; parameter screen; job list |
| CT-006 | T-27 | Grant the migration roles in production (DATA_MIGRATION_LEAD, DATA_STEWARD, DATA_OWNER, MIGRATION_OPERATOR, MIGRATION_RECON_APPROVER, MIGRATION_GONOGO), the true-up permissions (MIG_TRUEUP_PREPARE, MIG_TRUEUP_APPROVE) and the P03 permissions of the Renewal processing team (MIG_DQ_RESOLVE, MIG_RESUBMIT_APPROVE) through User Access requests; check PH-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |
| CT-007 | T-25 | Comptrollership sets up in production the legacy control accounts, Migration Clearing, the LG_ accounting rule lines (DMQ18) and the retained earnings account of the opening, through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |
| CT-008 | T-25 | Approve the final code map versions for production (all sets, including the PACKAGE map loaded for Renewal); record versions in the plan | OWN | 16 | - | MIG-MAP-VERSIONS lists one APPROVED version per set |
| CT-009 | T-24 | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |
| CT-010 | T-21 | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-6) |
| CT-011 | T-21 | Legacy December soft close - accruals and cut-offs, bank reconciliations, sub-ledger to GL reconciliations, known year-end adjustments posted - completed by 20 December 2027 (T-14) | COMP | 56 | - | Soft-close checklist signed by the Head of Comptrollership on 20 Dec 2027 |
| CT-012 | T-20 | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Trial migration 3, unmapped codes | STW | 80 | - | Clean-up tracker; counts reduced against Trial migration 3 profiling |
| CT-013 | T-20 | Renewal processing team ready for the January expiries - staffing plan for January (handlers, overtime, back-up) signed; BIBS Renewal training completed; day-1 priority queue worked on the Trial migration 4 and dress-rehearsal data; draft RA-sent file from the Excel trackers validated and its rejects reviewed (maker-checker) | RNW | 16 | CT-009 | Staffing plan signed by the Head of the Renewal processing team; draft P03 validated; rejects corrected and approved |
| CT-014 | T-18 | SFTP drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |
| CT-015 | T-15 | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-013, CT-014 | Decision recorded in the console with the GNG-1 criteria |

## 5.2 Phase B - Pre-load and daily deltas

Table 11: Phase B - Pre-load and daily deltas

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-016 | T-14 08:00 | Take a production database snapshot before the pre-load | IDO | 1 | CT-015 | Snapshot ID recorded in the plan |
| CT-017 | T-14 09:00 | Extract and send R01-R08 and R11 (current values; R06 is the PACKAGE map prepared by TSU) with control files | BIT | 6 | CT-016 | Files received; intake checks passed (extract status CHECKED) |
| CT-018 | T-14 15:00 | Validate and load reference data R01-R08 (R06 into the Renewal package map); authorise CREATE values in each master | IOP | 8 | CT-017 | Batches LOADED; MIG-UNMAPPED-CODES empty for R objects |
| CT-019 | T-13 | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-018 | MIG-SIGNOFF-STATUS shows G6 for R01-R08 |
| CT-020 | T-13 | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-019 | Batch SIGNED_OFF |
| CT-021 | T-12 | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-019 | Files CHECKED; counts against the Trial migration 4 volumes within 5 percent |
| CT-022 | T-12 | Validate clients; run matching; clear the review queue | STW | 24 | CT-021 | Review queue empty; MIG-CLIENT-MATCH reviewed |
| CT-023 | T-11 | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-022 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED; G6 signed |
| CT-024 | T-11 | Daily client delta (new and changed clients of the day) from T-11 to T-5 - extract 23:00, load 00:30 (job MIG_CLIENT_DELTA) | BIT | 1 | CT-023 | Delta batch SIGNED_OFF each morning by 07:00 |
| CT-025 | T-12 | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 | - | List of carried items for F04 agreed by Operations - Remittance |
| CT-026 | T-12 | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, renewals placed or bound in legacy and not yet booked (booked before the freeze so that the new term migrates as a header), check pick-ups, refunds (DMQ33) | OPS | 40 | - | In-flight list reduced; the rest listed for carry-forward or re-keying |
| CT-027 | T-7 | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-019 | Freeze notice sent; change log opened |
| CT-028 | T-7 | Legacy reference-data change freeze in EBIX and QPS (insurers, products, packages, AOs, branches) | BIT | 1 | CT-027 | Maintenance screens locked or change log reviewed daily |
| CT-029 | T-7 | Dry run of the final extract jobs on the current day's data (timing and control files; P01 covers every expiry to 31-May-2028 and every booked renewal term starting on or after T) | BIT | 6 | CT-017 | Extract timings within the plan; control files correct; P01 dry run checked against the legacy in-force list |
| CT-030 | T-5 | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-013, CT-023, CT-024, CT-025, CT-026, CT-029 | Decision recorded with the GNG-2 criteria |
| CT-031 | T-5 | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-030 | Communication plan item 7 sent |
| CT-032 | T-5 17:00 | Last legacy business day - last business transactions; cashiers deposit and close; UPP of the day recorded (30 and 31 December are holidays, DMQ39) | OPS | 3 | CT-030 | Branch close checklist from every branch |
| CT-033 | T-5 18:00 | Final RA-sent file (P03) compiled from the Excel trackers with the RAs sent up to the last business day (maker); the checker compares it with the trackers and releases it; trackers closed for new RAs | RNW | 3 | CT-032 | File and control file ready; checker's release recorded |
| CT-034 | T-5 18:00 | Name the Comptrollership users who may post FY2027 closing and audit adjustments in the legacy GL after the freeze; open the FY2027 adjustment register | COMP | 2 | CT-030 | Access list signed by the Head of Comptrollership; register opened |

## 5.3 Phase C - Legacy freeze and final extracts

Table 12: Phase C - Legacy freeze and final extracts

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-035 | T-3 20:00 | Last legacy EOD (EBIX, QPS, ISYS, CMS); preliminary December 2027 trial balance run | BIT | 2 | CT-032 | EOD logs complete without error; preliminary TB printed per branch and currency |
| CT-036 | T-3 22:00 | Legacy business freeze - EBIX, QPS, CMS business modules set to read-only; batch jobs that post are disabled; legacy GL restricted to the named Comptrollership users and to FY2027 periods (FY2028 periods are not opened in legacy) | BIT | 1 | CT-035, CT-034 | Test posting refused in each business module and by a GL user not on the list; job list shows disabled jobs |
| CT-037 | T-3 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-036 | Last delta batch SIGNED_OFF |
| CT-038 | T-3 22:30 | Final extracts after the EOD - P01, P01S, P03 (the RA-sent file of the Renewal processing team), F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 preliminary December TB (version PROVISIONAL) | BIT | 5 | CT-036, CT-033 | Every file and control file in the intake; SHA-256 recorded |
| CT-039 | T-3 23:30 | Comptrollership signs the preliminary December trial balance as the provisional opening - balanced per branch and currency, with the FY2027 result per branch and currency | COMP | 2 | CT-035 | Signed TB totals and FY2027 result per branch and currency |

## 5.4 Phase D - Production load

Table 13: Phase D - Production load

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-040 | T-2 02:00 | Take the production database snapshot - the rollback point | IDO | 1 | CT-037, CT-038 | Snapshot ID and restore test of the snapshot metadata recorded |
| CT-041 | T-2 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-040 | Every extract CHECKED; rejected files re-sent within 1 hour |
| CT-042 | T-2 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-041 | Error rate within the master threshold; every expiry to 31-May-2028 present against the legacy in-force list; G4 signed by the Data Migration Lead |
| CT-043 | T-2 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-042 | MIG-RECON-SUMMARY for P01 MATCHED |
| CT-044 | T-2 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-041 | 0 financial errors or owner-approved exclusions with manual-entry plan |
| CT-045 | T-2 09:00 | Load open legacy invoices F01 with opening entries MIG_LEGACY_INVOICE_OPENING | IOP | 5 | CT-043, CT-044 | Batch LOADED without rejects |
| CT-046 | T-2 09:00 | Validate and load UPP F02 with opening entries MIG_UPP_OPENING | IOP | 3 | CT-041, CT-023 | Batch LOADED without rejects |
| CT-047 | T-2 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-045 | Batches LOADED |
| CT-048 | T-2 15:00 | Load the provisional GL opening G01 - OPENING journals per branch and currency, value date 1-Jan-2028; balance-sheet lines; FY2027 result to retained earnings; legacy control-account lines to Migration Clearing | IOP | 2 | CT-039, CT-045, CT-046 | Journals posted and flagged PROVISIONAL; balance sheet in BIBS equals the preliminary TB; P&L accounts 0.00 |
| CT-049 | T-2 16:00 | Validate and load the RA-sent file P03; send MIG-REJECTS of P03 to the Renewal processing team (maker and checker) | IOP | 2 | CT-043 | Batch LOADED or LOADED_WITH_REJECTS; rejection report with correction columns sent |
| CT-050 | T-2 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-041 | Next AR / OR numbers = legacy last used + 1 per branch |
| CT-051 | T-2 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-047, CT-048 | MIG-GL-CLEARING shows 0.00 per branch and currency |
| CT-052 | T-2 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-051 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED with approval |

## 5.5 Phase E - Reconciliation, verification and go / no-go

Table 14: Phase E - Reconciliation, verification and go / no-go

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-053 | T-1 06:00 | Start the full sanction screening run of migrated clients (SCR_PERIODIC_SCREENING, full rescreen) | IOP | 6 | CT-023 | Run completed; hits in the screening queue for Compliance |
| CT-054 | T-1 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-052 | Sample checklists signed; G6 for every Day-1 object |
| CT-055 | T-1 08:00 | P03 rejects - the maker corrects each row and prepares the resubmission; the checker approves it by 12:00 (MIG_RESUBMIT_DEADLINE); the operator loads the rerun batch; rows still rejected are listed for the day-1 queue | RNW | 4 | CT-049 | Resubmission approved by a checker other than the maker; rerun reconciled; list of rows still rejected |
| CT-056 | T-1 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-052 | Smoke test checklist passed; no posting left open |
| CT-057 | T-1 13:00 | Check jobs, alerts and integrations for Monday (Renewal go-live extraction at T 04:00, PAYMENT_AUTOMATCH hourly, payment file handlers, daily Renewal extraction, e-mail) | IDO | 2 | CT-056 | Job schedule and alert routing checked |
| CT-058 | T-1 15:00 | Prepare the go / no-go pack - MIG-GONOGO with measured criteria, open issues, sign-off status | IML | 2 | CT-053, CT-054, CT-055, CT-056, CT-057 | Pack circulated to the board by 17:00 |
| CT-059 | T-1 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-058 | Decision recorded in the console with every criterion value |
| CT-060 | T-1 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-059 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |
| CT-061 | T-1 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-059 | Communication plan item 8 sent |

## 5.6 Phase F - Go-live

Table 15: Phase F - Go-live

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-062 | T 04:00 | Renewal go-live extraction - a candidate for every migrated header expiring 3-Jan to 31-May-2028 that was not renewed in legacy; priority by expiry date, January expiries flagged URGENT; RAs already sent recorded from P03; extraction check MIG-RENEWAL-GOLIVE | IOP | 2 | CT-061 | MIG-RENEWAL-GOLIVE balances for every month January-May 2028; URGENT count = January headers |
| CT-063 | T 06:00 | Enable business logins; confirm legacy business modules stay read-only; legacy links shown in BIBS | IDO | 1 | CT-061 | Log-in test per persona; legacy posting refused |
| CT-064 | T 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-063 | Attendance on the bridge |
| CT-065 | T 08:00 | BIBS open for business | PM | 0 | CT-064 | First transactions observed in each branch |
| CT-066 | T 08:00 | Renewal processing team works the day-1 priority queue - URGENT January expiries first, earliest expiry first; insurer requests and RAs for the expiries without an RA; the tracker is checked first for rows still rejected in P03 | RNW | 10 | CT-062, CT-065 | End-of-day count of URGENT candidates with an RA sent or an insurer request made |
| CT-067 | T 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-065 | Run summary; legacy and new postings in the right accounts |
| CT-068 | T 12:00 | Midday check - issues, queues, Migration Clearing still 0.00, no legacy business posting | IML | 1 | CT-065 | Midday report to the board |
| CT-069 | T 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-068 | Decision recorded |
| CT-070 | T 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-069 | Job run log; CRB lists the day's receipts |

## 5.7 Phase G - Hypercare

Table 16: Phase G - Hypercare and true-up 1

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-071 | T+1 | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, URGENT January renewals without an RA or insurer request, failed jobs (daily until exit) | IML | 1 | CT-070 | Daily hypercare report |
| CT-072 | T+1 | Issue triage twice a day (10:00 and 16:00) with Operations, Comptrollership, Renewal and iorta QA | IQA | 1 | CT-070 | Issue log updated; severity agreed |
| CT-073 | T+2 | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-070 | Schedules show legacy invoice numbers; OPS_REMITTANCE posts to DTIP legacy |
| CT-074 | T+3 | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-070 | Worklist counts agree with F03 |
| CT-075 | T+5 | Staging purge - payloads and intake files of the signed-off production batches deleted within 5 days (MIG_STAGING_PURGE) | IDO | 1 | CT-059 | No staging payload older than 5 days after sign-off; purge log |
| CT-076 | T+7 | Week-1 review with the board - issues, volumes, performance, renewal queue, user feedback | GNG | 2 | CT-071 | Minutes; actions |
| CT-077 | T+10 | First daily Renewal extraction that creates new candidates - expiry 1-Jun-2028 on 13-Jan-2028; headers already extracted at go-live are skipped | RNW | 1 | CT-062 | Candidates of 1-Jun-2028 created; no duplicate of a go-live candidate |
| CT-078 | T+10 | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-070 | Run report; legacy sub-ledgers reduced by the batch total |
| CT-079 | T+14 | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-076 | Criteria status recorded |
| CT-080 | T+15 | Legacy FY2027 year-end close completed by Comptrollership - closing adjustments posted in legacy, each entered in the FY2027 adjustment register | COMP | 8 | CT-036 | Register complete for the close; legacy post-close TB run |
| CT-081 | T+16 | Extract for true-up 1 - legacy TB after the close (G01, version TU1), adjustment journal lines since the freeze (G03), open-item detail of the lines on legacy control accounts (G03D), legacy journal listing since the freeze from the audit trail; control files | BIT | 4 | CT-080 | Every file and control file CHECKED |
| CT-082 | T+17 | Validate true-up 1 (cut-off, FY2027 dates, register, balance, mapping, open-item detail); the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-081 | Validation without error; true-up 1 submitted |
| CT-083 | T+18 | Head of Comptrollership approves true-up 1; BIBS posts the opening-balance adjustment journals MIG-TU-1 (type OPENING, value date 1-Jan-2028) and the open-item adjustments | COMP | 2 | CT-082 | Journals posted; approver is not the preparer |
| CT-084 | T+18 | Reconcile true-up 1 (MIG-TRUEUP-RECON) - cut-off; movement = legacy TB change = register; BIBS opening = legacy post-close TB; Migration Clearing 0.00; legacy control accounts = sub-ledgers; the Head of Comptrollership signs | COMP | 4 | CT-083 | All checks met; true-up 1 signed |
| CT-085 | T+30 | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-079, CT-084 | ACSL reconciliation without difference; FRBS schedules include legacy balances; opening balances include true-up 1 |
| CT-086 | T+30 | Hypercare exit decision | GNG | 2 | CT-085 | Exit criteria met; hand-over to production support (L1 / L2 / L3) |

## 5.8 Phase H - Final true-up and legacy GL close

Table 17: Phase H - Final true-up and legacy GL close

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-087 | T+60 | Interim true-up 2 when Comptrollership has posted material FY2027 adjustments since true-up 1 - same steps as true-up 1; skipped when there are none | COMP | 16 | CT-084 | True-up 2 signed, or 'none' recorded by the Head of Comptrollership |
| CT-088 | T+85 | Auditor's adjustments agreed and posted in legacy; audited FY2027 financial statements signed (about March-April 2028; the date follows the audit timetable) | COMP | 16 | CT-080 | Audited FS; register complete with the AUDIT adjustments |
| CT-089 | T+92 | Extract for the final true-up - legacy audited TB (G01, version FINAL), adjustment lines since the previous true-up (G03), their open-item detail (G03D), legacy journal listing since the freeze; control files | BIT | 4 | CT-087, CT-088 | Every file and control file CHECKED |
| CT-090 | T+95 | Validate the final true-up; the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-089 | Validation without error; final true-up submitted |
| CT-091 | T+99 | Head of Comptrollership approves the final true-up; January 2028 is reopened for the posting when closed; BIBS posts MIG-TU-F; January is closed again the same day | COMP | 4 | CT-090 | Journals posted; period reopen and close logged with the reason |
| CT-092 | T+99 | FY2027 BIR annual returns and the audited FS filed from legacy data by Comptrollership (not a BIBS task; BIBS is the source from FY2028) | COMP | 8 | CT-088 | Filing evidence recorded |
| CT-093 | T+100 | Reconcile the final true-up to the audited FY2027 TB (MIG-TRUEUP-RECON); re-run the February and March 2028 balance-sheet reports it changed; the Head of Comptrollership signs and shares the reconciliation with the external auditor | COMP | 8 | CT-091 | All checks met; final true-up signed; reports re-filed |
| CT-094 | T+106 | Lock the legacy GL for all users (FY2027 closed in legacy); close the FY2027 adjustment register | BIT | 2 | CT-093 | Test posting refused in the legacy GL; register closed |
| CT-095 | T+120 | Close the true-ups - final opening statement signed by the Head of Comptrollership and the Program Manager; opening journals no longer PROVISIONAL; a later FY2027 finding is a prior-period adjustment in BIBS outside the migration | PM | 2 | CT-094 | Closure recorded in the console |

# 6 Rollback

The rollback returns BDOI to legacy with no loss of data. It is available until the point of no return, the end-of-day review on T at 18:00 (DMQ32). The rollback point is the production database snapshot taken at T-2 02:00 (task CT-040), before any open item, header or trial balance is loaded; reference data and clients pre-loaded before it stay loaded and are harmless because legacy stays the system of record until go-live.

Table 18: Rollback procedure

| Step | Name | Action | Owner |
| --- | --- | --- | --- |
| RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG |
| RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (PAYMENT_AUTOMATCH, payment file handlers, Renewal extraction, e-mail dispatch). | IDO |
| RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with MIG-CUTOVER-STATUS and the Operations reports for re-keying in legacy. | IML |
| RB-4 | Restore | Restore the production database to the rollback-point snapshot (CT-037); restore the object store for attachments of the same time; verify the restore (row counts of key tables, application start). | IDO |
| RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; lift the GL restriction; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT |
| RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS |
| RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM |
| RB-8 | Review | Within 2 business days - root cause, new go-live date, which trial migrations to repeat; purge the production staging of the failed cutover within 5 days. | PM |

After the point of no return, there is no technical rollback. An issue is corrected forward in BIBS through the normal business functions (correction, reversal, adjustment), with the change visible in the Prod Recon legacy change report where it touches a legacy invoice. The true-ups come after the point of no return; a true-up that is wrong is corrected by the next true-up, never by editing a posted journal.

# 7 Year-end cut-over and FY2027 true-ups

The cut-over sits on the year-end boundary (DMQ39, option A; recommended, awaiting Comptrollership confirmation at M6). It changes three things in the plan:

•	Before the freeze. Comptrollership completes a December soft close by 20 December 2027 (CT-011), so the preliminary December trial balance is close to final, and names the users who may post FY2027 adjustments in the legacy GL after the freeze (CT-034).

•	At the freeze. The legacy business modules become read-only, and the legacy GL stays open only for FY2027 closing and audit adjustments by those users, in FY2027 periods (CT-036). The preliminary December trial balance is signed as the provisional opening (CT-039) and loaded as balance-sheet opening journals dated 1 January 2028, with the FY2027 result in retained earnings (CT-048). FY2028 P&L starts at zero in BIBS.

•	After go-live. Each FY2027 adjustment reaches BIBS as an opening-balance adjustment journal (type OPENING, value date 1 January 2028) in a true-up, prepared by the Comptrollership GL lead and approved by the Head of Comptrollership: true-up 1 after the legacy year-end close (CT-080 to CT-084, before the January close) and the final true-up after the audited financial statements (CT-088 to CT-093). Each true-up is reconciled to the legacy trial balance with the cut-off checks of the Reconciliation Approach before it is signed. The legacy GL is then locked (CT-094) and the true-ups are closed (CT-095). The FY2027 BIR annual returns and the FY2027 audit use legacy (CT-092); FY2028 uses BIBS.

Options B (go-live after the first-quarter close in April 2028, with a year-to-date P&L migration) and C (two books in parallel for the first quarter of 2028) were considered and are not recommended (Strategy section 11.1). If BDOI wants more assurance in January, Comptrollership compares the key BIBS reports with the opening position instead of keeping two books.

# 8 Communication plan

Table 19: Communication plan

| # | Message | Audience | Channel | When | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM |
| 2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS |
| 3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML |
| 4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM |
| 5 | Renewals of the January-May 2028 expiries are processed in BIBS from go-live, January expiries first; RAs already sent are not sent again; RAs sent up to 29 December go in the trackers | Renewal processing team, Retail and Corporate Marketing, branches | E-mail from the Head of the Renewal processing team; team briefing | T-21 | RNW |
| 6 | Legacy GL after the freeze - FY2027 closing and audit adjustments only, by named users; true-up timetable to April 2028 | Comptrollership, external auditor, BDOI IT | Memo from the Head of Comptrollership | T-21 | COMP |
| 7 | Last legacy business day T-5 (29 December); legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items over the holidays | All users, branches, insurers | E-mail; branch notice | T-5 | PM |
| 8 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM |
| 9 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM |
| 10 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM |
| 11 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM |
| 12 | True-ups closed; legacy GL locked | Comptrollership, external auditor, Program Manager | Memo | T+120 | COMP |

# 9 Hypercare

Hypercare runs from go-live to the first month-end close with the legacy control accounts (about T+30). The command centre stays open to T+5, then the daily 17:00 call continues until exit.

Daily checks (task CT-071): Migration Clearing 0.00 per branch and currency; legacy control accounts against their sub-ledgers (ACSL, context LEGACY); automatch runs and the unapplied items they left; URGENT January renewals without an RA sent or an insurer request; payment file results; exception queues (rejected receipts, remittance exclusions, failed postings); failed jobs and alerts; open issues by severity; user tickets by department.

## 9.1 Roster

Table 20: Hypercare roster (names in the task plan, sheet Hypercare Roster)

| Function | Who | Coverage | Escalates to |
| --- | --- | --- | --- |
| Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager |
| Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager |
| Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager |
| Infrastructure | iorta DevOps | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager |
| Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead |
| Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end; true-ups T+15 to T+120 | Head, Comptrollership |
| Renewal processing team | Head of the Renewal processing team; makers and checkers | 08:00-20:00 T to T+10 on the day-1 queue; P03 resubmissions on T-2 and T-1 | Program Manager |
| Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head |
| Service desk (L1) | BDOI service desk | Service hours | BDOI IT head |

## 9.2 Exit criteria

Table 21: Hypercare exit criteria

| # | Exit criterion |
| --- | --- |
| 1 | No open Critical or High issue; Medium issues have an agreed fix date |
| 2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days |
| 3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference |
| 4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident |
| 5 | Staging and extract files of production purged within 5 days of sign-off (purge log) |
| 6 | True-up 1 posted, reconciled and signed |
| 7 | Every URGENT January renewal has an RA sent or an insurer request made |
| 8 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted |

# 10 Decommissioning checklists

A legacy system is decommissioned only when every item of its checklist is met and signed (FR-DM-123; DMQ27). The legacy context in BIBS closes separately, when the legacy positions have run off. The words before the dash are the default criterion names that the Migration Console and its messages use.

Table 22: Decommissioning checklist - EBIX

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - F01, F02, F03, F04, F06, G01 and C01 signed off |
| 2 | Final true-up reconciled - final true-up signed against the audited FY2027 TB; legacy GL locked |
| 3 | Archive reconciled - archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |
| 4 | Legacy Inquiry verified - by Audit / Compliance on samples of each record type |
| 5 | No open item needs the system - no open legacy invoice or legacy UPP needs an EBIX document; the legacy context in BIBS may still be open |
| 6 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |
| 7 | Access logs archived - read-only access logs exported to the archive |
| 8 | Retention covered - database backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |
| 9 | Owners signed - EBIX system owner, Compliance and Comptrollership |

Table 23: Decommissioning checklist - QPS

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - C01, P01, P03 and the R objects signed off |
| 2 | No open item needs the system - last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |
| 3 | Archive reconciled - archive objects of QPS loaded and reconciled |
| 4 | Legacy Inquiry verified - by Audit / Compliance |
| 5 | Access logs archived - read-only access logs exported to the archive |
| 6 | Retention covered - database backup retained per DMQ27 |
| 7 | Owners signed - QPS system owner, Compliance and the Heads of Marketing |

Table 24: Decommissioning checklist - ISYS

| # | Criterion |
| --- | --- |
| 1 | No open item needs the system - claims and ACSL reports and the Marketing Diary replaced by BIBS reports |
| 2 | Archive reconciled - GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |
| 3 | Final true-up reconciled - ISYS GL lines of the final true-up signed; ISYS GL locked |
| 4 | Owners signed - ISYS system owner, Claims and Comptrollership |

Table 25: Decommissioning checklist - CMS

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - collection state F03 and UPP F02 reconciled and signed off |
| 2 | Archive reconciled - disposition history archived (H01) if required by DMQ34 |
| 3 | Owners signed - Head of Operations (Collections) and BDOI IT |

Table 26: Decommissioning checklist - Excel masterlists and file shares

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - submitted-policy masterlists migrated (P04) or archived |
| 2 | Archive reconciled - KYC documents and legacy documents (C04, H02) archived with checksums |
| 3 | Retention covered - folders set to read-only, then removed per the retention decision |
| 4 | Owners signed - owning department and Compliance |

Table 27: Decommissioning checklist - Legacy context in BIBS

| # | Criterion |
| --- | --- |
| 1 | No open legacy invoice - every legacy invoice paid, reversed, written off or reclassified |
| 2 | No legacy UPP balance - every legacy UPP applied, refunded or reclassified |
| 3 | Legacy accounts at zero - legacy control accounts and Migration Clearing at 0.00 |
| 4 | Chart decision recorded - Comptrollership decides whether the legacy accounts are closed in the chart |

# Sign-off

By signing, BDOI approves this runbook as the plan of the production cutover. The confirmed go-live date and the Comptrollership confirmation of the year-end option A (M6), the named people and the measured durations are added in version 1.3 after the dress rehearsal.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services (chair, go / no-go board) | BDO Unibank ESG |  |  |
|  | Data Migration Lead | BDOI |  |  |
|  | Head, Operations | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |