## Cover
CUTOVER RUNBOOK - TASK PLAN
Cutover Task Plan
BRD-13 Data Migration - production cutover from T-30 to hypercare exit
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-13
Version | 1.0
Date | 26 September 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Tasks | Cutover tasks with owner, duration, predecessors and verification | 75
Roles | Owner roles | 15
Phases | Cutover phases | 7
Checkpoints | Go / no-go checkpoints and their criteria | 25
Freeze Windows | Freeze windows | 5
Rollback | Rollback procedure (only on NO-GO or before the point of no return) | 8
Communication | Communication plan | 9
Hypercare Roster | Hypercare roster | 8
Hypercare Exit | Hypercare exit criteria | 6
Decommissioning | Decommissioning checklist per legacy system (BRID 12.1; DMQ27) | 28
Legend
DONE | Task completed and verified
IN PROGRESS | Task running
BLOCKED | Task cannot start or finish
N/A | Not needed in this cutover
T = go-live, the first business day (Monday) of a month after a legacy month-end close. Days are calendar days; times are Philippine time.
The same plan is loaded in the Migration Console (plan kind PRODUCTION); the console records actual times and evidence (FR-DM-120).
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Cutover Task Plan, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Tasks | Task | Task ID
Tasks | Phase | Phase of the cutover
Tasks | Day | Day relative to go-live (T)
Tasks | Start (PHT) | Planned start time
Tasks | Task | What is done
Tasks | Owner | Accountable role (sheet Roles)
Tasks | Hours | Planned elapsed hours
Tasks | Predecessors | Tasks that must be complete first
Tasks | Verification / evidence | How completion is proven
Tasks | Checkpoint | Go / no-go checkpoint or milestone
Tasks | Assignee (name) | Named person
Tasks | Actual start | Date and time
Tasks | Actual end | Date and time
Tasks | Status | Task status | NOT STARTED, IN PROGRESS, DONE, BLOCKED, N/A
Roles | Code | Role code used in the Owner column
Roles | Role | Role
Roles | Organisation | Organisation
Roles | Name (to fill) | Named person and phone
Phases | Phase | Phase code
Phases | Name | Phase
Phases | When | Days
Checkpoints | Checkpoint | Checkpoint
Checkpoints | When | Day and time
Checkpoints | Decision | What is decided
Checkpoints | # | Criterion no.
Checkpoints | Criterion | Criterion that must be met
Checkpoints | Measured value | Value at the decision
Checkpoints | Met | Y / N | Y, N
Freeze Windows | Freeze | What is frozen
Freeze Windows | From | Start
Freeze Windows | Until | End
Freeze Windows | Scope | What may not change
Freeze Windows | Exception route | How an urgent change is handled
Rollback | Step | Step
Rollback | Name | Step name
Rollback | Action | What is done
Rollback | Owner | Role
Rollback | Done at | Date and time
Communication | # | Item
Communication | Message | What is said
Communication | Audience | Who receives it
Communication | Channel | How
Communication | When | Day
Communication | Owner | Role
Communication | Sent on | Date
Hypercare Roster | Function | Support function
Hypercare Roster | Who | Team
Hypercare Roster | Coverage | Hours
Hypercare Roster | Escalates to | Escalation
Hypercare Roster | Names and phone (to fill) | Named people
Hypercare Exit | # | Criterion
Hypercare Exit | Exit criterion | Criterion
Hypercare Exit | Met | Y / N | Y, N
Hypercare Exit | Evidence | Report or sign-off
Decommissioning | Legacy system | System or context
Decommissioning | # | Criterion
Decommissioning | Criterion | Criterion
Decommissioning | Evidence | Report, log or sign-off
Decommissioning | Signed by / date | Signer
Decommissioning | Status | Status | OPEN, DONE, N/A

## Tasks
Tasks
Cutover tasks with owner, duration, predecessors and verification
Task | Phase | Day | Start (PHT) | Task | Owner | Hours | Predecessors | Verification / evidence | Checkpoint | Assignee (name) | Actual start | Actual end | Status
CT-001 | A Readiness | T-30 |  | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed) | DML | 4 |  | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |  |  |  |  | NOT STARTED
CT-002 | A Readiness | T-30 |  | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated |  |  |  |  | NOT STARTED
CT-003 | A Readiness | T-29 |  | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |  |  |  |  | NOT STARTED
CT-004 | A Readiness | T-28 |  | Freeze the production cutover plan in the Migration Console (plan kind PRODUCTION, tasks and owners from this list) | IML | 4 | CT-002 | MIG-CUTOVER-STATUS shows the plan with every task owned |  |  |  |  | NOT STARTED
CT-005 | A Readiness | T-28 |  | Production environment ready - BIBS release of the go-live build deployed, MIG_ENVIRONMENT_CLASS = PRODUCTION, MIG_CUTOVER_DATE = T, jobs scheduled | IDO | 8 |  | Deployment record; parameter screen; job list |  |  |  |  | NOT STARTED
CT-006 | A Readiness | T-27 |  | Grant the migration roles in production (DATA_MIGRATION_LEAD, DATA_STEWARD, DATA_OWNER, MIGRATION_OPERATOR, MIGRATION_RECON_APPROVER, MIGRATION_GONOGO) through User Access requests; check PH-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |  |  |  |  | NOT STARTED
CT-007 | A Readiness | T-26 |  | Comptrollership sets up in production the legacy control accounts, Migration Clearing and the LG_ accounting rule lines (DMQ18), through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |  |  |  |  | NOT STARTED
CT-008 | A Readiness | T-25 |  | Approve the final code map versions for production (all sets); record versions in the plan | OWN | 16 |  | MIG-MAP-VERSIONS lists one APPROVED version per set |  |  |  |  | NOT STARTED
CT-009 | A Readiness | T-24 |  | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |  |  |  |  | NOT STARTED
CT-010 | A Readiness | T-21 |  | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-4) |  |  |  |  | NOT STARTED
CT-011 | A Readiness | T-20 |  | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Mock 3, unmapped codes | STW | 80 |  | Clean-up tracker; counts reduced against Mock 3 profiling |  |  |  |  | NOT STARTED
CT-012 | A Readiness | T-18 |  | SFTP drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |  |  |  |  | NOT STARTED
CT-013 | A Readiness | T-15 |  | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-012 | Decision recorded in the console with the GNG-1 criteria | GNG-1 |  |  |  | NOT STARTED
CT-014 | B Pre-load and daily deltas | T-14 | 08:00 | Take a production database snapshot before the pre-load | IDO | 1 | CT-013 | Snapshot ID recorded in the plan |  |  |  |  | NOT STARTED
CT-015 | B Pre-load and daily deltas | T-14 | 09:00 | Extract and send R01-R08 and R11 (current values) with control files | BIT | 6 | CT-014 | Files received; intake checks passed (extract status CHECKED) |  |  |  |  | NOT STARTED
CT-016 | B Pre-load and daily deltas | T-14 | 15:00 | Validate and load reference data R01-R08; authorise CREATE values in each master | IOP | 8 | CT-015 | Batches LOADED; MIG-UNMAPPED-CODES empty for R objects |  |  |  |  | NOT STARTED
CT-017 | B Pre-load and daily deltas | T-13 |  | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-016 | MIG-SIGNOFF-STATUS shows G6 for R01-R08 |  |  |  |  | NOT STARTED
CT-018 | B Pre-load and daily deltas | T-13 |  | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-017 | Batch SIGNED_OFF |  |  |  |  | NOT STARTED
CT-019 | B Pre-load and daily deltas | T-12 |  | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-017 | Files CHECKED; counts against the Mock 3 volumes within 5 percent |  |  |  |  | NOT STARTED
CT-020 | B Pre-load and daily deltas | T-12 |  | Validate clients; run matching; clear the review queue | STW | 24 | CT-019 | Review queue empty; MIG-CLIENT-MATCH reviewed |  |  |  |  | NOT STARTED
CT-021 | B Pre-load and daily deltas | T-10 |  | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-020 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED; G6 signed |  |  |  |  | NOT STARTED
CT-022 | B Pre-load and daily deltas | T-10 |  | Daily client delta (new and changed clients of the day) from T-10 to T-4 - extract 23:00, load 00:30 (job MIG_CLIENT_DELTA) | BIT | 1 | CT-021 | Delta batch SIGNED_OFF each morning by 07:00 |  |  |  |  | NOT STARTED
CT-023 | B Pre-load and daily deltas | T-9 |  | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 |  | List of carried items for F04 agreed by Operations - Remittance |  |  |  |  | NOT STARTED
CT-024 | B Pre-load and daily deltas | T-9 |  | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, check pick-ups, refunds (DMQ33) | OPS | 40 |  | In-flight list reduced; the rest listed for carry-forward or re-keying |  |  |  |  | NOT STARTED
CT-025 | B Pre-load and daily deltas | T-7 |  | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-017 | Freeze notice sent; change log opened |  |  |  |  | NOT STARTED
CT-026 | B Pre-load and daily deltas | T-7 |  | Legacy reference-data change freeze in EBIX and QPS (insurers, products, AOs, branches) | BIT | 1 | CT-025 | Maintenance screens locked or change log reviewed daily |  |  |  |  | NOT STARTED
CT-027 | B Pre-load and daily deltas | T-7 |  | Dry run of the final extract jobs on the current day's data (timing and control files) | BIT | 6 | CT-015 | Extract timings within the plan; control files correct |  |  |  |  | NOT STARTED
CT-028 | B Pre-load and daily deltas | T-5 |  | Confirm the RMEL cohorts to carry (expiry T to T+140) with Marketing; freeze new legacy RMEL extractions | MKT | 4 |  | Cohort list and counts per month agreed |  |  |  |  | NOT STARTED
CT-029 | B Pre-load and daily deltas | T-4 |  | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-021, CT-022, CT-023, CT-024, CT-027, CT-028 | Decision recorded with the GNG-2 criteria | GNG-2 |  |  |  | NOT STARTED
CT-030 | B Pre-load and daily deltas | T-4 |  | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-029 | Communication plan item 5 sent |  |  |  |  | NOT STARTED
CT-031 | C Legacy freeze and final extracts | T-3 | 17:00 | Last legacy business transactions; cashiers deposit and close; UPP of the day recorded | OPS | 3 | CT-029 | Branch close checklist from every branch |  |  |  |  | NOT STARTED
CT-032 | C Legacy freeze and final extracts | T-3 | 20:00 | Last legacy EOD and month-end close (EBIX, QPS, ISYS, CMS) | BIT | 2 | CT-031 | EOD logs complete without error |  |  |  |  | NOT STARTED
CT-033 | C Legacy freeze and final extracts | T-3 | 22:00 | Legacy business freeze - EBIX, QPS, CMS set to read-only for business users; batch jobs that post are disabled | BIT | 1 | CT-032 | Test posting refused in each legacy system; job list shows disabled jobs | FREEZE |  |  |  | NOT STARTED
CT-034 | C Legacy freeze and final extracts | T-3 | 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-033 | Last delta batch SIGNED_OFF |  |  |  |  | NOT STARTED
CT-035 | C Legacy freeze and final extracts | T-3 | 22:30 | Final extracts after the EOD - P01, P01S, P03, F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 trial balance | BIT | 5 | CT-033 | Every file and control file in the intake; SHA-256 recorded |  |  |  |  | NOT STARTED
CT-036 | C Legacy freeze and final extracts | T-3 | 23:30 | Comptrollership confirms the legacy trial balance is final and balanced per branch and currency | COMP | 2 | CT-032 | Signed TB total per branch and currency |  |  |  |  | NOT STARTED
CT-037 | D Production load | T-2 | 02:00 | Take the production database snapshot - the rollback point | IDO | 1 | CT-034, CT-035 | Snapshot ID and restore test of the snapshot metadata recorded | ROLLBACK POINT |  |  |  | NOT STARTED
CT-038 | D Production load | T-2 | 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-037 | Every extract CHECKED; rejected files re-sent within 1 hour |  |  |  |  | NOT STARTED
CT-039 | D Production load | T-2 | 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-038 | Error rate within the master threshold; G4 signed by the Data Migration Lead |  |  |  |  | NOT STARTED
CT-040 | D Production load | T-2 | 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-039 | MIG-RECON-SUMMARY for P01 MATCHED |  |  |  |  | NOT STARTED
CT-041 | D Production load | T-2 | 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-038 | 0 financial errors or owner-approved exclusions with manual-entry plan |  |  |  |  | NOT STARTED
CT-042 | D Production load | T-2 | 09:00 | Load open legacy invoices F01 with opening entries MIG_LEGACY_INVOICE_OPENING | IOP | 5 | CT-040, CT-041 | Batch LOADED without rejects |  |  |  |  | NOT STARTED
CT-043 | D Production load | T-2 | 09:00 | Validate and load UPP F02 with opening entries MIG_UPP_OPENING | IOP | 3 | CT-038, CT-021 | Batch LOADED without rejects |  |  |  |  | NOT STARTED
CT-044 | D Production load | T-2 | 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-042 | Batches LOADED |  |  |  |  | NOT STARTED
CT-045 | D Production load | T-2 | 15:00 | Load the GL opening trial balance G01 (OPENING journals per branch and currency) | IOP | 2 | CT-036, CT-042, CT-043 | Journals posted; TB in BIBS equals the legacy TB |  |  |  |  | NOT STARTED
CT-046 | D Production load | T-2 | 16:00 | Load RMEL cohorts P03 and make them available to Renewal | IOP | 2 | CT-040 | Candidates visible in Renewal with source LEGACY |  |  |  |  | NOT STARTED
CT-047 | D Production load | T-2 | 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-038 | Next AR / OR numbers = legacy last used + 1 per branch |  |  |  |  | NOT STARTED
CT-048 | D Production load | T-2 | 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-044, CT-045 | MIG-GL-CLEARING shows 0.00 per branch and currency |  |  |  |  | NOT STARTED
CT-049 | D Production load | T-2 | 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-048 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED with approval |  |  |  |  | NOT STARTED
CT-050 | E Reconciliation, verification and go / no-go | T-1 | 06:00 | Start the full sanction screening run of migrated clients (SCR_PERIODIC_SCREENING, full rescreen) | IOP | 6 | CT-021 | Run completed; hits in the screening queue for Compliance |  |  |  |  | NOT STARTED
CT-051 | E Reconciliation, verification and go / no-go | T-1 | 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-049 | Sample checklists signed; G6 for every Day-1 object |  |  |  |  | NOT STARTED
CT-052 | E Reconciliation, verification and go / no-go | T-1 | 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-049 | Smoke test checklist passed; no posting left open |  |  |  |  | NOT STARTED
CT-053 | E Reconciliation, verification and go / no-go | T-1 | 13:00 | Check jobs, alerts and integrations for Monday (PAYMENT_AUTOMATCH hourly, payment file handlers, Renewal extraction, e-mail) | IDO | 2 | CT-052 | Job schedule and alert routing checked |  |  |  |  | NOT STARTED
CT-054 | E Reconciliation, verification and go / no-go | T-1 | 15:00 | Prepare the go / no-go pack - MIG-GONOGO with measured criteria, open defects, sign-off status | IML | 2 | CT-050, CT-051, CT-052, CT-053 | Pack circulated to the board by 17:00 |  |  |  |  | NOT STARTED
CT-055 | E Reconciliation, verification and go / no-go | T-1 | 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-054 | Decision recorded in the console with every criterion value | GNG-3 |  |  |  | NOT STARTED
CT-056 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-055 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |  |  |  |  | NOT STARTED
CT-057 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-055 | Communication plan item 6 sent |  |  |  |  | NOT STARTED
CT-058 | F Go-live | T | 06:00 | Enable business logins; confirm legacy stays read-only; legacy links shown in BIBS | IDO | 1 | CT-057 | Log-in test per persona; legacy posting refused |  |  |  |  | NOT STARTED
CT-059 | F Go-live | T | 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-058 | Attendance on the bridge |  |  |  |  | NOT STARTED
CT-060 | F Go-live | T | 08:00 | BIBS open for business | PM | 0 | CT-059 | First transactions observed in each branch | GO-LIVE |  |  |  | NOT STARTED
CT-061 | F Go-live | T | 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-060 | Run summary; legacy and new postings in the right accounts |  |  |  |  | NOT STARTED
CT-062 | F Go-live | T | 12:00 | Midday check - defects, queues, Migration Clearing still 0.00, no legacy posting | IML | 1 | CT-060 | Midday report to the board |  |  |  |  | NOT STARTED
CT-063 | F Go-live | T | 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-062 | Decision recorded | POINT OF NO RETURN |  |  |  | NOT STARTED
CT-064 | F Go-live | T | 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-063 | Job run log; CRB lists the day's receipts |  |  |  |  | NOT STARTED
CT-065 | G Hypercare | T+1 |  | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, failed jobs (daily until exit) | IML | 1 | CT-064 | Daily hypercare report |  |  |  |  | NOT STARTED
CT-066 | G Hypercare | T+1 |  | Defect triage twice a day (10:00 and 16:00) with Operations, Comptrollership and iorta QA | IQA | 1 | CT-064 | Defect log updated; severity agreed |  |  |  |  | NOT STARTED
CT-067 | G Hypercare | T+2 |  | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-064 | Schedules show legacy invoice numbers; OPS_REMITTANCE posts to DTIP legacy |  |  |  |  | NOT STARTED
CT-068 | G Hypercare | T+3 |  | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-064 | Worklist counts agree with F03 |  |  |  |  | NOT STARTED
CT-069 | G Hypercare | T+5 |  | Staging purge - payloads and intake files of the signed-off production batches deleted within 5 days (MIG_STAGING_PURGE) | IDO | 1 | CT-055 | No staging payload older than 5 days after sign-off; purge log |  |  |  |  | NOT STARTED
CT-070 | G Hypercare | T+5 |  | Check the daily Renewal extraction from the migrated headers (policies expiring at business date + 140 days) - first runs | MKT | 2 | CT-046 | Candidates created with source LEGACY |  |  |  |  | NOT STARTED
CT-071 | G Hypercare | T+7 |  | Week-1 review with the board - defects, volumes, performance, user feedback | GNG | 2 | CT-065 | Minutes; actions |  |  |  |  | NOT STARTED
CT-072 | G Hypercare | T+10 |  | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-064 | Run report; legacy sub-ledgers reduced by the batch total |  |  |  |  | NOT STARTED
CT-073 | G Hypercare | T+14 |  | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-071 | Criteria status recorded | CHECKPOINT |  |  |  | NOT STARTED
CT-074 | G Hypercare | T+30 |  | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-073 | ACSL reconciliation without difference; FRBS schedules include legacy balances |  |  |  |  | NOT STARTED
CT-075 | G Hypercare | T+30 |  | Hypercare exit decision | GNG | 2 | CT-074 | Exit criteria met; hand-over to production support (L1 / L2 / L3) | HYPERCARE EXIT |  |  |  | NOT STARTED

## Roles
Roles
Owner roles
Code | Role | Organisation | Name (to fill)
PM | BDOI Program Manager (ESG - Business Project Services) | BDOI
DML | BDOI Data Migration Lead | BDOI
OWN | Data owners (department heads of each object) | BDOI
STW | Data stewards | BDOI
COMP | Comptrollership (reconciliation approver for financial objects) | BDOI
OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI
MKT | Marketing (Retail and Corporate) and Renewal handlers | BDOI
CMP | Compliance and Audit | BDOI
BIT | BDOI IT (legacy systems, extracts, network, SFTP) | BDOI
GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT
IPM | iorta TechNXT Project Manager | iorta TechNXT
IML | iorta TechNXT Migration Lead (loaders, reconciliation, console) | iorta TechNXT
IOP | iorta TechNXT Migration Operator (intake, validation, loads) | iorta TechNXT
IDO | iorta TechNXT DevOps (AWS environment, snapshots, access, monitoring) | iorta TechNXT
IQA | iorta TechNXT QA (smoke tests, defect triage) | iorta TechNXT

## Phases
Phases
Cutover phases
Phase | Name | When
A | Readiness | T-30 to T-15
B | Pre-load and daily deltas | T-14 to T-4
C | Legacy freeze and final extracts | T-3 (Friday)
D | Production load | T-2 (Saturday)
E | Reconciliation, verification and go / no-go | T-1 (Sunday)
F | Go-live | T (Monday)
G | Hypercare | T+1 to the first month-end close

## Checkpoints
Checkpoints
Go / no-go checkpoints and their criteria
Checkpoint | When | Decision | # | Criterion | Measured value | Met
GNG-1 | T-15 | Start the production pre-load | 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed
GNG-1 | T-15 | Start the production pre-load | 2 | Production environment, roles and PH-only access ready; masking off only in production
GNG-1 | T-15 | Start the production pre-load | 3 | Legacy control accounts, Migration Clearing and LG_ rule lines approved in production (DMQ18)
GNG-1 | T-15 | Start the production pre-load | 4 | Code map versions for production approved
GNG-1 | T-15 | Start the production pre-load | 5 | Transfer path (SFTP or console) tested
GNG-1 | T-15 | Start the production pre-load | 6 | No open Critical defect of the migration or of a Day-1 module
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 2 | Client review queue empty
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 3 | Final extract jobs timed within the window (dry run)
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 4 | In-flight items and remittance batches closed or listed for carry-forward
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 5 | RMEL cohorts to carry confirmed
GNG-2 | T-4 | Enter the legacy freeze on T-3 | 6 | Communications sent; branches and insurers informed
GNG-3 | T-1 18:00 | Go live on T | 1 | Every Day-1 object at G6 (100 percent)
GNG-3 | T-1 18:00 | Go live on T | 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object
GNG-3 | T-1 18:00 | Go live on T | 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan
GNG-3 | T-1 18:00 | Go live on T | 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency
GNG-3 | T-1 18:00 | Go live on T | 5 | Migration Clearing - 0.00 per branch and currency
GNG-3 | T-1 18:00 | Go live on T | 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00
GNG-3 | T-1 18:00 | Go live on T | 7 | Client review queue empty; screening run complete
GNG-3 | T-1 18:00 | Go live on T | 8 | Business smoke test passed
GNG-3 | T-1 18:00 | Go live on T | 9 | Rollback point (snapshot) taken and verified
GNG-3 | T-1 18:00 | Go live on T | 10 | Hypercare roster and support channels in place
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 1 | No Critical defect that stops receipts, payment application, remittance or booking
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 2 | Migration Clearing still 0.00; no posting in legacy since the freeze
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 3 | Every branch has transacted in BIBS

## Freeze Windows
Freeze Windows
Freeze windows
Freeze | From | Until | Scope | Exception route
Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects
Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live
Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings in EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements, GL journals | None; an urgent item is recorded on paper and keyed in BIBS on T
BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board
BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical defect approved by the go / no-go board

## Rollback
Rollback
Rollback procedure (only on NO-GO or before the point of no return)
Step | Name | Action | Owner | Done at
RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG
RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (PAYMENT_AUTOMATCH, payment file handlers, Renewal extraction, e-mail dispatch). | IDO
RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with MIG-CUTOVER-STATUS and the Operations reports for re-keying in legacy. | IML
RB-4 | Restore | Restore the production database to the rollback-point snapshot (CT-037); restore the object store for attachments of the same time; verify the restore (row counts of key tables, application start). | IDO
RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT
RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS
RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM
RB-8 | Review | Within 2 business days - root cause, new go-live date, which mocks to repeat; purge the production staging of the failed cutover within 5 days. | PM

## Communication
Communication
Communication plan
# | Message | Audience | Channel | When | Owner | Sent on
1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM
2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS
3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML
4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM
5 | Legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items during the weekend | All users, branches, insurers | E-mail; branch notice | T-4 | PM
6 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM
7 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM
8 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM
9 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM

## Hypercare Roster
Hypercare Roster
Hypercare roster
Function | Who | Coverage | Escalates to | Names and phone (to fill)
Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager
Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager
Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager
Infrastructure | iorta DevOps | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager
Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead
Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end | Head, Comptrollership
Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head
Service desk (L1) | BDOI service desk | Service hours | BDOI IT head

## Hypercare Exit
Hypercare Exit
Hypercare exit criteria
# | Exit criterion | Met | Evidence
1 | No open Critical or High defect; Medium defects have an agreed fix date
2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days
3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference
4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident
5 | Staging and extract files of production purged within 5 days of sign-off (purge log)
6 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted

## Decommissioning
Decommissioning
Decommissioning checklist per legacy system (BRID 12.1; DMQ27)
Legacy system | # | Criterion | Evidence | Signed by / date | Status
EBIX | 1 | Final extracts reconciled and signed off (F01, F02, F03, F04, F06, G01, C01) |  |  | OPEN
EBIX | 2 | Archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |  |  | OPEN
EBIX | 3 | Legacy Inquiry verified by Audit / Compliance on samples of each record type |  |  | OPEN
EBIX | 4 | No open legacy invoice or legacy UPP that needs an EBIX document; the legacy context in BIBS may still be open |  |  | OPEN
EBIX | 5 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |  |  | OPEN
EBIX | 6 | Read-only access logs exported to the archive |  |  | OPEN
EBIX | 7 | Database backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |  |  | OPEN
EBIX | 8 | Sign-off by the EBIX system owner, Compliance and Comptrollership |  |  | OPEN
QPS | 1 | Final extracts reconciled and signed off (C01, P01, P03, R objects) |  |  | OPEN
QPS | 2 | Last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |  |  | OPEN
QPS | 3 | Archive objects of QPS loaded and reconciled |  |  | OPEN
QPS | 4 | Legacy Inquiry verified by Audit / Compliance |  |  | OPEN
QPS | 5 | Read-only access logs exported; database backup retained per DMQ27 |  |  | OPEN
QPS | 6 | Sign-off by the QPS system owner, Compliance and the Heads of Marketing |  |  | OPEN
ISYS | 1 | Claims and ACSL reports and the Marketing Diary no longer needed (replaced by BIBS reports) |  |  | OPEN
ISYS | 2 | GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |  |  | OPEN
ISYS | 3 | Sign-off by the ISYS system owner, Claims and Comptrollership |  |  | OPEN
CMS | 1 | Collection state F03 and UPP F02 reconciled and signed off |  |  | OPEN
CMS | 2 | Disposition history archived (H01) if required by DMQ34 |  |  | OPEN
CMS | 3 | Sign-off by the Head of Operations (Collections) and BDOI IT |  |  | OPEN
Excel masterlists and file shares | 1 | Submitted-policy masterlists migrated (P04) or archived |  |  | OPEN
Excel masterlists and file shares | 2 | KYC documents and legacy documents (C04, H02) archived with checksums |  |  | OPEN
Excel masterlists and file shares | 3 | Folders set to read-only, then removed per the retention decision |  |  | OPEN
Excel masterlists and file shares | 4 | Sign-off by the owning department and Compliance |  |  | OPEN
Legacy context in BIBS | 1 | No open legacy invoice (paid, reversed, written off or reclassified) |  |  | OPEN
Legacy context in BIBS | 2 | No legacy UPP with a balance |  |  | OPEN
Legacy context in BIBS | 3 | Legacy control accounts and Migration Clearing at 0.00 |  |  | OPEN
Legacy context in BIBS | 4 | Comptrollership decides whether the legacy accounts are closed in the chart |  |  | OPEN

## _lists (hidden)
NOT STARTED | Y | Y | OPEN
IN PROGRESS | N | N | DONE
DONE |  |  | N/A
BLOCKED
N/A