## Cover
CHANGE CONTROL
Change Request Register
Product Maintenance; goes with the FRS Product Maintenance v1.7
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-03
Version | 1.4
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | Change requests of BRD-03 Product Maintenance. | 1
Decision Log | Decision Log | 4
Legend
Open
Closed
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.4. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | CR
Register | Title
Register | Status v1.4 |  | Open, Withdrawn, Closed, Approved, Rejected
Register | Reference
Register | Man-days
Register | Note
Decision Log | Date
Decision Log | Item
Decision Log | Decision

## Register
Register
Change requests of BRD-03 Product Maintenance.
CR | Title | Status v1.4 | Reference | Man-days | Note
CR-PM-101 | Accessibility of the Product Maintenance screens (WCAG 2.2 level AA) | Open | NFR-ACC-01 | 11.5 | Not in the BRD; OOTB partial.

## Decision Log
Decision Log
Change Request Register – BIBS – BDOI Broker System
Date | Item | Decision
11 Oct 2026 | Register v1.0 | One change request (CR-PM-101) after the product owner review.
16 Oct 2026 | Register v1.1 | No change; aligned with the FRS v1.4.
16 Oct 2026 | Register v1.2 | No change request: the insurer page (FRPM.023.02) and the change history (FRPM.021.03) are delivered as best practice; aligned with the FRS v1.5.
17 Oct 2026 | Register v1.3 | No change request: the Ledger Accounts tab of the insurer page and the Master Data Change Log screen are delivered as best practice; aligned with the FRS v1.6.

## Lists
Status v1.4
Open
Withdrawn
Closed
Approved
Rejected