STRATEGY AND APPROACH

Data Migration Strategy and Approach

BRD-13 Data Migration - what is migrated, how it gets into BIBS, and how cutover is run and proven

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-DMS-BRD-13 |
| Version | 1.1 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 0.9 | 25 Sep 2026 | iorta TechNXT Solution Architect | iorta TechNXT Business Analysis |  | Internal draft from the BRD-13 baseline, the build design and FRS BRD-13 v1.0 |
| 1.0 | 26 Sep 2026 | iorta TechNXT Solution Architect | iorta TechNXT Project Manager | BDOI Program Manager (pending) | First issue for BDOI review, with the Data Requirements Workbook, the extract templates, the Cutover Runbook and the Reconciliation Approach of the same version |
| 1.1 | 26 Sep 2026 | iorta TechNXT Solution Architect | iorta TechNXT Project Manager | BDOI Program Manager (pending) | Re-based on the BDOI programme timeline (go-live January 2028; mocks in the SIT and UAT migration windows; BDOI input dates inside requirements and mapping, Sep-Oct 2026); early-renewal concept paper recorded as superseded by the single January 2028 go-live; mock-load order; carried RMEL cohorts of January-May 2028 (layout P03); package remapping options and recommendation; decisions DMQ36-DMQ39 |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Review and sign-off; owner of the cutover |
| Head, Comptrollership; Product Owners FRBS / ACSL and Disbursement | Approver | BDOI | Open items, GL opening, legacy sub-ledgers, reconciliation |
| Head, Operations; Operations - Financial Transactions and Processing | Approver | BDOI | Legacy invoices, UPP, remittance, collections |
| Product Owner, Marketing Business System; Heads of Retail and Corporate Marketing | Approver | BDOI | Client master, reference data, renewal transition |
| Compliance; Unit Head, Analytics and Risk Management | Reviewer | BDOI | Data protection, archive, access logging |
| BDOI IT (legacy EBIX, QPS, ISYS, CMS) | Reviewer | BDOI | Extracts, transfer, legacy read-only and decommissioning |
| Project team | Delivery | iorta TechNXT | Build, rehearsals, cutover, hypercare |

Contents

1 Introduction	7

1.1 Purpose	7

1.2 Scope and basis	7

1.3 The Data Migration document set	8

1.4 References	8

2 Objectives and principles	9

2.1 Objectives	9

2.2 Principles	9

2.3 What this migration does not do	10

3 Scope and decisions per data object	11

3.1 The decision gate	11

3.2 Data object register	11

3.3 Depth, delta and due dates	13

3.4 Business owners and data stewards	14

3.5 Client migration "2020 to present" and daily client batches	15

4 Source systems	17

4.1 Legacy systems in scope	17

4.2 Source per object	17

5 Target in BIBS	19

5.1 Target per object and load order	19

5.2 How migrated records are marked	20

6 Migration approach	21

6.1 End-to-end process	21

6.2 Extract templates	22

6.3 Secure transfer and staging	25

6.4 Profiling	25

6.5 Cleansing: who fixes what	25

6.6 Mapping and code maps	26

6.6.1 Package remapping	27

6.7 Validation	28

6.8 Client matching and survivorship	28

6.9 Load through the BIBS services	29

6.10 Reconciliation and sign-off	29

7 Legacy invoices after go-live	30

7.1 What a legacy invoice is	30

7.2 Legacy sub-ledgers	31

7.3 Worked example: one legacy invoice from load to remittance	31

7.4 Unapplied premium payments (UPP)	32

7.5 Payments, reversals, remittance, endorsements and Prod Recon	33

7.6 When the legacy context closes	33

8 In-force policies and the renewal-driven transition	34

8.1 In-force policy headers	34

8.2 Renewal by RMEL cohort	34

9 History, archive and read-only access	36

10 Migration cycles	37

10.1 Mocks, dress rehearsal and production	37

10.2 Test data and masking	38

11 Cutover strategy	39

11.1 Approach	39

11.2 Freeze windows	39

11.3 Parallel run	39

11.4 Go / no-go	40

11.5 Rollback	40

11.6 Hypercare	40

11.7 In-flight items at the freeze	40

11.8 Decommissioning	41

12 Data security	42

13 Roles and responsibilities	43

13.1 Migration organisation	43

13.2 RACI	43

14 Risks and mitigations	45

15 Dependencies and open decisions	46

15.1 Dependencies	46

15.2 Open decisions and the date each is needed by	46

16 Timeline	49

16.1 Alignment with the BDOI timeline	49

Glossary	51

Sign-off	52

# 1 Introduction

## 1.1 Purpose

This document sets out how BDO Insurance and Reinsurance Brokers, Inc. (BDOI) moves from its legacy systems to BIBS (BDOI Broker System, on iNXT BrokerVerse). It answers four questions for the BDOI departments and BDOI IT:

1.	What data moves, object by object, and what stays behind (Migrate, Carry forward, Archive, Excluded).

2.	What BDOI provides, in which form and by when (the Data Requirements Workbook and the extract templates).

3.	How the data gets into BIBS: transfer, staging, cleansing, code mapping, validation, load and reconciliation, and who does each step.

4.	How the cutover is run and proven: rehearsals, freeze, go / no-go, rollback, hypercare and decommissioning of the legacy systems.

It also explains, for business readers, how legacy invoices and unapplied payments that are still open at cutover are processed in BIBS after go-live.

## 1.2 Scope and basis

The basis is the Data Migration BRD (R1), a draft v0.01 of 14-Apr-2026 that is not signed (p.2, p.15-16; register DCR-189). The BRD asks for a selective, continuity-focused migration (p.3): migrate clean master and reference data for Day 1, carry forward only the open operational financial positions, keep history in read-only legacy or an archive, and let renewals recreate clean records in BIBS (p.5). This document follows that approach and fills the gaps the BRD leaves with proposals, each tied to an open decision (DMQ##) that BDOI confirms.

Data Migration is designed and not yet built in BIBS. The mechanisms named here (Migration Console, loaders, reconciliation, legacy invoice processing) are those of the build design (R3) and the FRS (R4).

Programme calendar and the early-renewal concept paper. This version follows the BDOI drop plan and timeline (R9): data migration is part of Drop 0, requirements and mapping run in September-October 2026, the build from November 2026 to March 2027, SIT migration from April to July 2027, UAT migration from August to October 2027, full migration and cut-over from November 2027 to January 2028, and go-live is in January 2028. The concept paper on an early renewal release (R10), signed on 6 September 2026, proposed to take renewal processing live by 15 August 2027 with the client master and reference data migrated ahead of it. BDOI decided on 26 September 2026 that everything goes live together in January 2028; the concept paper is therefore superseded and there is one production cut-over (register DCR-240). Three of its points still apply and are part of this approach: reference data and clients are loaded first in every mock (section 10.1), the renewals of the January-May 2028 expiries are carried into BIBS at cut-over (section 8.2), and legacy packages are remapped to the BIBS package names with an agreed owner (section 6.6.1).

## 1.3 The Data Migration document set

Table 1: Documents of this set (version 1.1)

| Document | Format | Use |
| --- | --- | --- |
| Data Migration Strategy and Approach (this document) | Word | Decisions, approach, responsibilities, timeline; for approval |
| BDOI Data Requirements Workbook | Excel | One sheet per extract layout (fields, formats, rules, BIBS target), object register, code map templates, control totals, data-quality rules, open decisions; for BDOI IT and data stewards |
| Extract templates (templates/) | CSV + README | One header-only CSV per layout and the control-file template (deliverable 20) |
| Reconciliation Approach and Sign-off | Word | Reconciliation per object, sampling, evidence and the sign-off forms |
| Cutover Runbook | Word | Cutover organisation, T-30 to hypercare exit, checkpoints, rollback, communication, decommissioning |
| Cutover Task Plan | Excel | The runbook tasks with owner, duration, predecessors and verification, for execution |
| Migration Test Plan BRD-13 | Excel + Word | Test conditions and cases of every Data Migration FR (deliverable 3) |

## 1.4 References

Table 2: Reference documents

| Ref. | Document | Version | Location |
| --- | --- | --- | --- |
| R1 | BDO Insure Core Modernization - Data Migration BRD | draft v0.01, 14-Apr-2026 | docs/source-documents/BRD - Data Migration - draft V0.01.pdf |
| R2 | Data Migration (BRD-13) requirements baseline and fit/gap | current | docs/requirements/BDOI_DM_BRD_SPEC.md |
| R3 | Data Migration build design | current | docs/architecture/DATA_MIGRATION_DESIGN.md |
| R4 | Functional Requirements Specification BRD-13 Data Migration | 1.1 | BIBS_FRS_BRD-13_Data_Migration_v1.1.docx |
| R5 | BRD BDOI Core Replacement (umbrella BRD) and its analysis | v01 | docs/source-documents/00 - BRD BDOI Core Replacement v01.pdf; BDOI_CORE_BRD_SPEC.md |
| R6 | BRD discrepancy and clarification register | 1.1 | BIBS_Register_BRD-00_Discrepancies_and_Clarifications_v1.1.xlsx |
| R7 | Deliverables plan, UAT readiness programme and hosting appendix | current | docs/deliverables/README.md |
| R8 | Operations, Collections, Accounting / ACSL and Renewal designs | current | docs/architecture/ |
| R9 | BDOI drop plan and programme timeline | received 26-Sep-2026 | docs/source-documents/BDOI_DROP_PLAN.md; BDOI Programme Timeline.webp |
| R10 | Concept Paper - Advance Implementation of Renewal Processing | V1.0, signed 06-Sep-2026; superseded 26-Sep-2026 | docs/source-documents/Concept Paper - Advance Implementation of Renewal Processing V1.0 (signed).pdf |

# 2 Objectives and principles

## 2.1 Objectives

The BRD states the objective as "a stable Core go-live by ensuring Day-1 operational continuity for marketing, operations, and accounting while establishing a clean and trusted data foundation" (p.3). In measurable terms, at go-live:

Table 3: Migration objectives and how they are measured

| # | Objective | Measure at go-live |
| --- | --- | --- |
| 1 | Marketing finds every in-scope client and uses it without re-encoding (BRID 2.1) | Every in-scope legacy client number resolves to one BIBS client; client review queue empty |
| 2 | Every code used by a migrated record exists in BIBS (BRID 3.1) | Unmapped-code report empty for all Day-1 objects |
| 3 | Every open receivable, payable and unapplied payment continues in BIBS (BRID 5.1-8.1) | Open balances in BIBS equal the legacy extract per currency; Migration Clearing 0.00 per branch and currency |
| 4 | Legacy invoices are processed with the normal BIBS screens (BRID 5.2-10.1) | Smoke test on production passed (payment, automatch, remittance, Invoice 360) |
| 5 | Every migrated object is reconcilable from source to target (BRID 1.1b) | Reconciliation L1-L5 signed per object (gate G5) |
| 6 | History remains retrievable with logged access (BRID 11.1) | Legacy read-only link or archive inquiry available per legacy system |
| 7 | Renewals move to BIBS by expiry month (BRID 12.1) | Every renewal of the January-May 2028 expiries not booked in legacy is a candidate in BIBS Renewal (carried or caught up); later cohorts extracted by BIBS |

## 2.2 Principles

1.	Selective, not a conversion. Every data object gets one class through a decision gate (BRID 1.1a). History is never loaded into business tables; it stays in read-only legacy or goes to the archive.

2.	Continuity first. Anything BDOI must act on after go-live (a receivable, a payable, an unapplied payment, a renewal in progress, a promise to pay) is carried forward, so no business process depends on legacy after the freeze.

3.	Clean start. Master data is cleansed and deduplicated before it is loaded. Data that fails the rules is fixed at source or excluded by its owner; it is not loaded "as is".

4.	One processing system per item. From the freeze, a legacy open item is processed only in BIBS. Legacy becomes read-only (BRD p.5). There is no two-way synchronisation.

5.	Load through the BIBS services. Records are created by the same services the screens use, so every BIBS rule, audit entry and accounting entry applies. Nothing is written directly into a business table.

6.	Reconcile everything, and keep the evidence. Every extract carries control totals; every object is reconciled by counts, amounts, hash totals, fields and GL; a break is fixed or explained and approved before sign-off.

7.	Rehearse before production. Four mocks and a dress rehearsal run the full cutover with masked data and measured timings, in the SIT and UAT migration windows of the BDOI timeline. Production follows the rehearsed plan.

8.	Protect personal data. Masked data outside production, staging purged within 5 days of sign-off, access only for migration roles and only from the Philippines (hosting appendix, R7).

## 2.3 What this migration does not do

•	It does not convert closed transactions, GL history or expired policies into BIBS business tables (BRD p.3).

•	It does not re-book legacy invoices. A legacy invoice keeps its legacy number and is processed as a legacy invoice until it is settled.

•	It does not create users from legacy. Users are created through User Access requests (BRD-11); legacy user IDs are only mapped so that AO, handler and collector fields resolve.

•	It does not run legacy and BIBS in parallel for the same items (section 11.3).

•	It does not write back to QPS or EBIX after the freeze (register DCR-202).

# 3 Scope and decisions per data object

## 3.1 The decision gate

BRID 1.1a asks that each data object is classed Migrate, Carry forward (open items), Archive or Excluded once the business owners have assessed four criteria: Day-1 need, compliance need, read-only / archival option and data trust (p.7). The BRD does not give the rule that turns the criteria into a class (DMQ02, DCR-192). The proposal:

Table 4: Proposed decision rule (DMQ02)

| Class | When | Examples |
| --- | --- | --- |
| Migrate | Day-1 need = Yes and the data is master or reference data; data trust High or Medium after cleansing | Clients, LOVs, insurers, products, GL opening balances |
| Carry forward | Day-1 need = Yes and the record is an open operational or financial position that BDOI must still act on | Open legacy invoices, UPP, open promises to pay, RMEL renewals in progress |
| Conditional | Day-1 need depends on a business condition that BDOI states (BRID 4.1 "when operationally required") | In-force policy headers; objects not named in the BRD (claims, EB, submitted policies, payees) |
| Archive | Day-1 need = No and compliance need = Yes, or the read-only / archival option is required | Closed invoices, receipts, remittances, expired policies, GL history, documents |
| Excluded | Day-1 need = No and compliance need = No, or the data is rebuilt in BIBS | Users and roles, screening results |

The Data Migration Lead records the four criteria and the proposed class per object in the Migration Console; the business owner of the object approves it (gate G1, FR-DM-002). A later change of class needs a new approval, and an object whose data is loaded cannot be moved to Archive or Excluded until the load is rolled back.

## 3.2 Data object register

The register below is the proposal for gate G1 (R3 section 2; DMQ01, DCR-195). The workbook sheet "Object Register" holds the same rows with the columns BDOI fills in (volumes, named owners and stewards, status).

Table 5: Data objects and proposed decisions (BDOI confirms at gate G1)

| Object | Data object | Decision | Rationale |
| --- | --- | --- | --- |
| R01 | Lists of values and MIS values | Migrate | Every coded field of clients, policies and open items needs its BIBS value on Day 1 (BRID 3.1). Legacy values are mapped to BIBS values; missing values are created through the LOV master with maker-checker. |
| R02 | Branches and invoicing branches | Migrate | Branch codes are mapped only; BIBS branches are configured by Comptrollership before the load. |
| R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Migrate | Clients, policies and open items carry the AO and unit; MIS reporting and Collections assignment need them on Day 1. |
| R04 | Insurers and insurer branches | Migrate | Every open invoice, header and remittance position is owed to or by an insurer. |
| R05 | Product lines, cover types, products and risk codes | Migrate | The risk code decides the premium components, taxes and commission of every open invoice and header. |
| R06 | Packages (active package versions) | Migrate | Renewals of packaged policies need the active package version (BRD-3). Legacy packages are remapped to the package names TSU maintains in BIBS through the PACKAGE code map at upload (recommendation, DMQ36). |
| R07 | Commission rates by insurer and product | Migrate | Endorsements and renewals of legacy policies compute commission from the rate table. |
| R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Migrate | The GL opening trial balance (G01) is loaded through this map; legacy control accounts are mapped to Migration Clearing. |
| R09 | Payees | Conditional | The payee migration handler exists (DISB_PAYEE_MIGRATION); in scope if BDOI confirms (AQ11, DMQ30). |
| R10 | Users and roles | Excluded | Users are created through User Access requests and approvals (BRD-11); legacy user IDs are only mapped (map set USER) so AO, handler and collector fields resolve. |
| R11 | Receipt series in use (AR and OR, ATP and next number) | Carry forward | Receipts issued in BIBS after go-live must continue the BIR-authorised series without gap or overlap. |
| C01 | Client master (individual and corporate) | Migrate | Marketing, Operations and Renewal must find and use clients on Day 1 without re-encoding (BRID 2.1); clients are deduplicated before load. Umbrella BRD p.43 asks for clients "2020 to present" and daily client batches (DCR-173). |
| C03 | Client payout accounts (for refunds) | Migrate | Refunds of legacy UPP (BRID 5.4) need the client's payout account. |
| C04 | KYC documents and IDs | Archive | Documents stay retrievable for audit; BIBS keeps the KYC status and review date on the client (DMQ07 may change this to MIGRATE). |
| C05 | Screening results and risk ratings | Excluded | One full screening run after the client load gives current results (BRD-10); legacy results are archived with the client history. |
| P01 | In-force policy headers | Conditional | Needed to locate active coverage, to endorse legacy invoices (BRID 9) and to renew in BIBS (BRID 12.1); the scope condition is decided by BDOI (DMQ09). |
| P02 | Expired policies and policy history | Archive | History is not converted (BRD p.3); kept for inquiry. |
| P03 | RMEL cohorts January to May 2028 (renewals prepared in legacy, not booked at the freeze) | Carry forward | Policies expiring from T to T + 140 days (January to May 2028 for a January 2028 go-live) are in their renewal cycle in legacy at the freeze; the renewals not yet booked continue in BIBS Renewal with their disposition and are placed and booked in BIBS (BRID 12.1; DMQ26, DMQ37). The early renewal release of the concept paper is superseded by the single January 2028 go-live. |
| P04 | Submitted-policy masterlists | Conditional | Loaded through the Submitted Policies migration handler (SBM_MIGRATION) if BDOI confirms (SP SQ16, DMQ30); layout issued with that module. |
| P05 | Employee Benefits programmes | Conditional | Loaded through EB_PROGRAMME_LOAD if BDOI confirms (DMQ30); layout issued with the EB module. |
| F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Carry forward | Receivables and payables open at cutover must be collected, remitted, reversed and endorsed in BIBS (BRID 5.1-10.1). |
| F02 | Unapplied premium payments (UPP) with disposition in progress | Carry forward | Unapplied cash must not be lost after cutover (BRID 5.1); it is applied, refunded or reclassified in BIBS. |
| F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | Carry forward | Collectors continue their follow-up without re-keying (CQ07); only the open state is carried, history is archived (DMQ34). |
| F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Conditional | Proposal - complete legacy batches before the freeze; carry only holds and special remittances that cannot complete (DMQ21). |
| F05 | DP billing in process and DP commission receivable | Carry forward | Carried inside F01 (dp_flag and the COMMISSION components of direct-payment invoices); no separate file. |
| F06 | PDCs in the warehouse, check pick-ups and refunds in process | Conditional | Proposal - carry PDCs in the warehouse; complete pick-ups and refunds in legacy before the freeze where possible (DMQ33). |
| F07 | Open claims | Conditional | Loaded through the Claims migration (BCL_CLAIM_MIGRATION, V1025 held) if BDOI decides (CLQ14, DMQ30); closed claims are archived. |
| G01 | GL opening trial balance per account, branch and currency | Migrate | The BIBS GL starts from the legacy closing balances; the legacy control-account lines go to Migration Clearing, which the F01 and F02 opening entries clear to 0.00. |
| G02 | GL history (journals and balances before cutover) | Archive | Kept for audit; BIBS starts from the opening trial balance. |
| H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | Archive | History stays in read-only legacy or the BIBS archive with logged access (BRID 11.1). |
| H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | Archive | Documents are kept with their archive record and a checksum. |

## 3.3 Depth, delta and due dates

Table 6: Depth, delta frequency, format and due dates per object

| Object | History depth | Delta after the first full extract | Format | Due |
| --- | --- | --- | --- | --- |
| R01 | Current values and values used by any migrated record | None after the map freeze (T-7 days); changes by change request and a new map version | CSV | M3 (29 Jan 2027) |
| R02 | Current | None | CSV | M3 (29 Jan 2027) |
| R03 | Current, plus inactive AOs referenced by open items | Weekly until the freeze | CSV | M3 (29 Jan 2027) |
| R04 | Active insurers, and inactive insurers with open items | None | CSV | M3 (29 Jan 2027) |
| R05 | Current, plus codes used by in-force policies and open items | None | CSV | M3 (29 Jan 2027) |
| R06 | Active versions only | None | XLSX or CSV | M3 (29 Jan 2027) |
| R07 | Rates effective at cutover and later | None | CSV | M3 (29 Jan 2027) |
| R08 | Current chart | None | XLSX or CSV | M3 (29 Jan 2027) |
| R09 | Active payees | None | CSV | M3 (29 Jan 2027) |
| R11 | Series in use at the freeze | Final values at the freeze (T-3) | CSV | M3 (29 Jan 2027); final at T-3 |
| C01 | Clients from 2020 to present (umbrella p.43); filter per DMQ05 | Daily new and changed clients from T-14 days until the freeze | CSV | M3 (29 Jan 2027); deltas daily from T-14 days |
| C03 | Active accounts | None | CSV | M3 (29 Jan 2027) |
| C04 | Per retention | None | CSV index plus files | Before decommissioning |
| P01 | Policies in force at T (DMQ09) | Single load after the freeze | CSV | M3 (29 Jan 2027); final at T-2 |
| P02 | Per retention (5 years online, 15 years archive, umbrella p.45) | None | CSV | Before decommissioning |
| P03 | Expiries from T to T + 140 days (3-Jan to 22-May-2028 for T = 3-Jan-2028) | One file per cohort month in the mocks; single final load after the freeze | CSV or XLSX | M3 (29 Jan 2027); final at T-2 |
| P04 | All active records | None | XLSX | M3 (29 Jan 2027) if in scope |
| P05 | Active programmes | None | XLSX | M3 (29 Jan 2027) if in scope |
| F01 | Every invoice with any open component at T (DMQ10) | Single load after the freeze | CSV with control file | M3 (29 Jan 2027); final at T-2 |
| F02 | Every UPP item with a balance at T | Single load after the freeze | CSV with control file | M3 (29 Jan 2027); final at T-2 |
| F03 | Open items only | Single load after the freeze | CSV | M3 (29 Jan 2027); final at T-2 |
| F04 | Open at T | Single load after the freeze | CSV | M3 (29 Jan 2027); final at T-2 |
| F05 | Open at T | - | In F01 | With F01 |
| F06 | Open at T | Single load after the freeze | CSV | M3 (29 Jan 2027); final at T-2 |
| F07 | Open at T | Single load after the freeze | CSV | M3 (29 Jan 2027) if in scope |
| G01 | Balances at the last legacy EOD before T (after month-end close) | Single load after the freeze | XLSX or CSV with control file | M3 (29 Jan 2027); final at T-2 |
| G02 | Per retention | None | CSV | Before decommissioning |
| H01 | Per retention (5 years online, 15 years archive, umbrella p.45) | None | CSV | Before decommissioning |
| H02 | Per retention | None | CSV index plus files | Before decommissioning |

The milestones in the Due column are:

Table 7: Milestones of BDOI inputs

| Milestone | What is due | When |
| --- | --- | --- |
| M0 | Pack issued to BDOI (v1.1 on the BDOI programme calendar) | 26 Sep 2026 |
| M1 | Build-shaping decisions (answers that change what is built) | 16 Oct 2026 |
| M2 | Owners, stewards, keys and remaining business rules; object decisions signed (gate G1); layouts frozen, version 1 (G2 part 1) - end of requirements and mapping | 30 Oct 2026 |
| M3 | First full extracts in the templates, with control files and volumes (profiling, performance sizing) | 29 Jan 2027 |
| M4 | Extracts for Mock 1 (SIT migration starts); reference data and clients first | 9 Apr 2027 |
| M5 | Code maps approved for Mock 2 (G2), including the PACKAGE map | 18 Jun 2027 |
| M6 | Cut-over date and window, fallback and decommissioning criteria agreed | 1 Oct 2027 |

## 3.4 Business owners and data stewards

Each object has a business owner who signs its decision (G1), its code maps (G2) and its acceptance (G6), and a data steward who prepares the code maps, resolves the data-quality issues and fixes records at source. The table is the proposal from the BRD approvers (p.15-16); BDOI names the people (DMQ01).

Table 8: Business owner and data steward per object (proposal; DMQ01)

| Object | Business owner (signs G1, G2, G6) | Data steward |
| --- | --- | --- |
| R01 | Product Owner, Marketing Business System (MBS) | MBS data steward (to name) |
| R02 | Head, Comptrollership | Comptrollership data steward (to name) |
| R03 | Heads, Retail and Corporate Marketing | Marketing data steward (to name) |
| R04 | Head, Operations | Operations data steward (to name) |
| R05 | Product Owner, MBS | MBS data steward (to name) |
| R06 | Product Owner, MBS; TSU | MBS data steward (to name) |
| R07 | Head, Operations | Operations data steward (to name) |
| R08 | Head, Comptrollership; Product Owner FRBS and ACSL | Comptrollership data steward (to name) |
| R09 | Product Owner, Comptrollership - Disbursement | Disbursement data steward (to name) |
| R11 | Operations - Financial Transactions | Cashiering data steward (to name) |
| C01 | Product Owner, MBS; Heads, Retail and Corporate Marketing | Marketing data steward (to name) |
| C03 | Product Owner, Comptrollership - Disbursement | Disbursement data steward (to name) |
| C04 | Compliance | Compliance data steward (to name) |
| P01 | Head, Operations | Operations data steward (to name) |
| P02 | Head, Operations | Operations data steward (to name) |
| P03 | Heads, Retail and Corporate Marketing (Renewal) | Renewal data steward (to name); TSU for packages |
| P04 | CBG and Non-CBG Marketing (Submitted Policies) | Submitted Policies data steward (to name) |
| P05 | Head, Employee Benefits | EB data steward (to name) |
| F01 | Operations - Financial Transactions; Head, Comptrollership | Operations data steward (to name) |
| F02 | Operations - Financial Transactions | Cashiering data steward (to name) |
| F03 | Head, Operations (Collections) | Collections data steward (to name) |
| F04 | Operations - Remittance | Remittance data steward (to name) |
| F05 | Operations - Financial Transactions | Operations data steward (to name) |
| F06 | Operations - Cashiering | Cashiering data steward (to name) |
| F07 | Unit Head, Claims, RI and TU | Claims data steward (to name) |
| G01 | Head, Comptrollership | Comptrollership data steward (to name) |
| G02 | Head, Comptrollership | Comptrollership data steward (to name) |
| H01 | Audit / Compliance; legacy system owners | Compliance data steward (to name) |
| H02 | Audit / Compliance | Compliance data steward (to name) |

## 3.5 Client migration "2020 to present" and daily client batches

The umbrella BRD sizes a "one-time migration from Broker and source", "2020 to present", plus a daily "midday batch (new transactions)", an "EOD batch (new clients)" and a "client modification report" (R5 p.43; register DCR-173). The Data Migration BRD asks for a deduplicated client master (BRID 2.1). This document reconciles the two as follows, for BDOI to confirm:

•	One-time load. Clients created from 1-Jan-2020 to the freeze, plus older clients that have an in-force policy, an open item or activity since 2020 (DMQ05), are extracted in layouts C01 and C02, matched and deduplicated, and loaded two weeks before go-live.

•	Daily batches until the freeze. From the pre-load until the freeze, the legacy EOD produces a daily delta of new clients and of changed clients (the modification report) in the same layouts; BIBS loads it overnight (job MIG_CLIENT_DELTA). New transactions of the day ("midday batch") are not migrated as transactions: open items are loaded once, after the freeze.

•	No feed after go-live. After the freeze, legacy is read-only and BIBS is the system of record of the client master (BRD p.5), so the daily batches stop. If BDOI needs a client feed from another source after go-live (for example bank referrals), it is a separate interface and not part of this migration.

# 4 Source systems

## 4.1 Legacy systems in scope

The BRD names QPS and EBIX "e.g." (p.3). The other BRDs also name ISYS, the CMS and Excel masterlists. BDOI IT confirms the list and the system of record per object (DMQ03, DCR-195).

Table 9: Legacy systems and their role in the migration

| System | Holds (as known from the BRDs) | Role after the freeze |
| --- | --- | --- |
| EBIX | Booking, invoices, receipts (AR / OR), remittance, UPP, GL, payees, branches | Read-only for inquiry until the archive is loaded and the decommissioning checklist is signed |
| QPS | Quotations, clients (assured), covers and policies, packages, rates, sales organisation, renewals | Read-only; decommissioned after the last QPS-issued policy has renewed or lapsed |
| ISYS | Claims and ACSL reports, Marketing Diary, GL reports | Read-only; archived before decommissioning |
| CMS (Collection Management System) | Collection dispositions, promises, installment plans, assignments; client data from the bank | Read-only; archived before decommissioning |
| Excel masterlists and file shares | Submitted-policy masterlists, KYC documents, legacy documents | Migrated (P04) or archived with checksums, then removed per retention |

## 4.2 Source per object

Table 10: Source systems per data object (Y = holds the object; system of record per DMQ03)

| Object | Data object | EBIX | QPS | ISYS | CMS | Excel | File shares |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Lists of values and MIS values | Y | Y | - | - | - | - |
| R02 | Branches and invoicing branches | Y | - | - | - | - | - |
| R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Y | Y | - | - | - | - |
| R04 | Insurers and insurer branches | Y | Y | - | - | - | - |
| R05 | Product lines, cover types, products and risk codes | Y | Y | - | - | - | - |
| R06 | Packages (active package versions) | - | Y | - | - | - | - |
| R07 | Commission rates by insurer and product | Y | Y | - | - | - | - |
| R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Y | - | Y | - | - | - |
| R09 | Payees | Y | - | - | - | - | - |
| R10 | Users and roles | Y | Y | - | - | - | - |
| R11 | Receipt series in use (AR and OR, ATP and next number) | Y | - | - | - | - | - |
| C01 | Client master (individual and corporate) | Y | Y | - | Y | - | - |
| C03 | Client payout accounts (for refunds) | Y | - | - | - | - | - |
| C04 | KYC documents and IDs | - | Y | - | - | - | Y |
| C05 | Screening results and risk ratings | - | - | - | - | Y | - |
| P01 | In-force policy headers | Y | Y | - | - | - | - |
| P02 | Expired policies and policy history | Y | Y | - | - | - | - |
| P03 | RMEL cohorts January to May 2028 (renewals prepared in legacy, not booked at the freeze) | Y | Y | - | - | - | - |
| P04 | Submitted-policy masterlists | - | - | - | - | Y | - |
| P05 | Employee Benefits programmes | Y | - | - | - | - | - |
| F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Y | Y | - | - | - | - |
| F02 | Unapplied premium payments (UPP) with disposition in progress | Y | - | - | Y | - | - |
| F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | - | - | - | Y | - | - |
| F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Y | - | - | - | - | - |
| F05 | DP billing in process and DP commission receivable | Y | - | - | - | - | - |
| F06 | PDCs in the warehouse, check pick-ups and refunds in process | Y | - | - | - | - | - |
| F07 | Open claims | Y | - | Y | - | - | - |
| G01 | GL opening trial balance per account, branch and currency | Y | - | Y | - | - | - |
| G02 | GL history (journals and balances before cutover) | Y | - | Y | - | - | - |
| H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | Y | Y | Y | - | - | - |
| H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | Y | - | - | - | - | Y |

Where two systems hold the same object (clients in QPS, EBIX and the CMS; products in QPS and EBIX), each system sends its own extract. BIBS matches the records across systems and keeps one BIBS record with a cross-reference to every legacy key. The survivorship rule decides which value wins per field (section 6.8).

# 5 Target in BIBS

## 5.1 Target per object and load order

Every object lands in a BIBS module through that module's service. The load order follows the dependencies: reference data first, then clients, then policy headers, then open items, then the GL, so every record finds the records it refers to.

Table 11: Target in BIBS and load order

| Object | BIBS target (service or table) | BRD | Load order |
| --- | --- | --- | --- |
| R01 | lov_value through LovService; MIS field catalogue (Core Replacement CR-W1) | BRID 3.1 | 1 |
| R02 | org_branch (check only, code map BRANCH) | BRID 3.1 | 1 |
| R03 | cat_sales_unit, cat_sales_officer (catalog services) | BRID 3.1 | 2 |
| R04 | cat_insurer, cat_insurer_branch (InsurerService), party | BRID 3.1 | 2 |
| R05 | cat_product_line, cat_cover_type, cat_product (ProductCatalogService) | BRID 3.1 | 3 |
| R06 | cat_product_version, cat_package_insurer, cat_package_insurer_term | BRID 3.1 | 3 |
| R07 | cat_commission_rate | BRID 3.1 | 3 |
| R08 | Code map GL_ACCOUNT to coa_account (chart configured by Comptrollership) | BRID 5.1-8.1; AQ01 | 3 |
| R09 | party and payee through the DISB_PAYEE_MIGRATION service | AQ11 | 4 |
| R11 | csh_receipt_series | BRID 6.1 | 4 |
| C01 | crm_client through ClientOnboardingService.registerMigrated (new) | BRID 2.1 | 5 |
| C03 | crm_client_payout_account (ClientPayoutAccounts) | BRID 5.4 | 6 |
| C04 | BIBS archive (mig_archive_record, attachment LEGACY_DOCUMENT) | BRID 11.1 | 16 |
| P01 | acc_account through AccountService.importLegacy (new) | BRID 4.1 | 7 |
| P02 | BIBS archive record type POLICY | BRID 11.1 | 16 |
| P03 | mig_legacy_candidate served to Renewal (LegacyPolicySource) | BRID 12.1 | 13 |
| P04 | sbm_policy through SBM_MIGRATION | BRIDSP-33 | 14 |
| P05 | EB programme tables through EB_PROGRAMME_LOAD | BRD-8 | 14 |
| F01 | ops_invoice, ops_invoice_share, ops_invoice_component through LegacyInvoiceIntake (new); opening entry MIG_LEGACY_INVOICE_OPENING | BRID 5.2, 6.1-6.4, 7.1, 7.2, 8.1, 9.1-9.3, 10.1 | 8 |
| F02 | csh_unapplied through UnappliedService.createMigrated (new); opening entry MIG_UPP_OPENING | BRID 5.1-5.5, 6.3, 6.4 | 9 |
| F03 | Collections legacy state (CLX_LEGACY_ITEMS, LegacyItemStateService, new) | CQ07 | 10 |
| F04 | rem_hold_request, rem_special_request (remittance services) | BRID 8.1 | 11 |
| F05 | Part of F01; commission DP list service | BRID 7.1 | 8 |
| F06 | csh_pdc_item and the cashiering pick-up service | BRID 5.1 | 11 |
| F07 | bcl_claim through BCL_CLAIM_MIGRATION | CLQ14 | 14 |
| G01 | jnl_batch, jnl_line (SystemJournalService, journal type OPENING) | BRID 1.1b, 5.1-8.1 | 12 |
| G02 | BIBS archive record type GL_JOURNAL | BRID 11.1 | 16 |
| H01 | mig_archive_record (Legacy Inquiry) | BRID 11.1 | 16 |
| H02 | attachment (type LEGACY_DOCUMENT) linked to mig_archive_record | BRID 11.1 | 16 |

## 5.2 How migrated records are marked

•	Origin. Migrated clients, accounts and UPP carry origin MIGRATED; legacy invoices carry origin LEGACY and ledger context LEGACY. Screens show a LEGACY badge, the source system and the legacy number.

•	Key cross-reference. Every loaded record has a cross-reference from its legacy key (source system, object, legacy key) to the BIBS record. Users search clients and policies by their legacy numbers (FR-DM-033); reruns skip what is already loaded.

•	No side effects. Loads send no notification to clients or insurers, do not start onboarding workflows, and do not trigger sanction screening per client (one full screening run follows the client load, DMQ06, DCR-208).

•	Frozen original values. The values of each legacy invoice at load are frozen. The Prod Recon legacy change report compares every later change with them (BRID 10.1).

# 6 Migration approach

## 6.1 End-to-end process

Figure 1 shows the steps every object goes through, and who does each step.

Figure 1: Migration pipeline per data object: BDOI steps (left) and BIBS Migration Console steps (right)

Table 12: Steps, responsibilities and evidence

| # | Step | What happens | Who | Evidence |
| --- | --- | --- | --- | --- |
| 1 | Extract | BDOI IT extracts each object in the agreed layout with its control file | BDOI IT | Data file and control file |
| 2 | Secure transfer | Files are uploaded in the Migration Console or dropped on the agreed SFTP folder; never e-mailed | BDOI IT | Upload log with SHA-256 |
| 3 | Intake checks | BIBS checks checksum, header, row count, amount totals and hash total against the control file; a failing file is rejected as a whole | iorta Migration Operator | Extract status CHECKED or REJECTED |
| 4 | Staging and profiling | Rows are staged (masked outside production) and profiled; the profiling report goes to the data stewards | iorta Migration Lead | Profiling report per object |
| 5 | Cleansing | Issues at source are fixed in legacy by the stewards (5b); formats, defaults and mapped values are handled in staging (5a) | BDOI data stewards; iorta | Issue log (MIG-DQ-ISSUES) |
| 6 | Mapping | Legacy codes are mapped to BIBS codes in versioned code maps; the business owner approves each version (G2) | Data steward prepares; owner approves | MIG-MAP-VERSIONS, MIG-UNMAPPED-CODES |
| 7 | Validation and matching | Data-quality rules run on every row; clients are matched and deduplicated (G3) | BIBS; Data steward | MIG-DQ-ISSUES, MIG-CLIENT-MATCH |
| 8 | Load | Approved batches load through the BIBS services (G4) | Data Migration Lead approves; iorta runs | Batch log, MIG-REJECTS |
| 9 | Reconciliation | L1 counts, L2 amounts, L3 hash totals, L4 fields, L5 GL; breaks explained (G5) | Reconciliation approver | MIG-RECON-SUMMARY, MIG-GL-CLEARING |
| 10 | Acceptance | Business owner checks samples on the BIBS screens and accepts the object (G6) | Business owner; Data Migration Lead | Sign-off form |
| 11 | Purge | Staging payloads and files are deleted within 5 days of sign-off; counts, hashes and totals are kept | BIBS job | Purge log |

## 6.2 Extract templates

BDOI extracts each object in the layout of the Data Requirements Workbook. A layout gives, per field: name, description, type, length, mandatory flag, allowed values or code list, format, example, BIBS target field, validation rule and a source system hint. The CSV templates carry the same field names as their header row.

Table 13: Extract layouts (workbook sheets and CSV templates)

| Layout | Content | Object | Fields | Mandatory | Key | Amount totals |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | Lists of values and MIS values | R01 | 8 | 4 | list_type, code | - |
| R02 | Branches and invoicing branches | R02 | 5 | 4 | branch_code | - |
| R03 | Sales organisation (units and account officers) | R03 | 11 | 3 | record_type, unit_code, ao_user_id | - |
| R04 | Insurers | R04 | 10 | 3 | insurer_code | - |
| R04B | Insurer branches | R04 | 7 | 4 | insurer_code, branch_code | - |
| R05 | Product lines, cover types, products and risk codes | R05 | 9 | 4 | risk_code | - |
| R06 | Packages (active versions) | R06 | 10 | 6 | package_code, package_version, insurer_code | - |
| R07 | Commission rates by insurer and product | R07 | 5 | 4 | insurer_code, risk_code, effective_from | - |
| R08 | Chart of accounts mapping | R08 | 8 | 4 | legacy_account_code | - |
| R09 | Payees | R09 | 11 | 6 | payee_code | - |
| R11 | Receipt series in use | R11 | 8 | 7 | branch_code, kind, prefix | - |
| C01 | Client master | C01 | 36 | 6 | legacy_client_no | - |
| C02 | Client addresses and contacts | C01 | 13 | 4 | legacy_client_no, record_type, seq_no | - |
| C03 | Client payout accounts | C03 | 6 | 4 | legacy_client_no, account_no | - |
| P01 | In-force policy headers | P01 | 31 | 20 | legacy_policy_ref | sum_insured, gross_premium, net_premium |
| P01S | Policy insurer shares | P01 | 6 | 5 | legacy_policy_ref, share_seq | - |
| P03 | RMEL cohorts January to May 2028 (carried renewals) | P03 | 27 | 13 | legacy_policy_ref | expiring_premium, proposed_sum_insured, proposed_premium |
| F01 | Open legacy invoices - header | F01 | 38 | 24 | legacy_invoice_no | gross_premium, commission, vat_on_commission |
| F01S | Open legacy invoices - insurer shares | F01 | 5 | 5 | legacy_invoice_no, share_seq | - |
| F01C | Open legacy invoices - components and positions | F01 | 8 | 8 | legacy_invoice_no, component | booked, adjusted, paid, remitted, written_off, open_balance |
| F02 | Unapplied premium payments (UPP) | F02 | 21 | 11 | legacy_upp_ref | amount, balance |
| F03 | Open collection state | F03 | 12 | 3 | legacy_invoice_no, record_type, seq_no | promise_amount, installment_amount |
| F04 | Remittance in flight | F04 | 10 | 6 | legacy_batch_no, legacy_invoice_no | amount |
| F06 | PDCs, check pick-ups and refunds in process | F06 | 14 | 6 | record_type, reference | amount |
| G01 | GL opening trial balance | G01 | 10 | 8 | branch_code, currency, legacy_account_code, cost_center | debit_fc, credit_fc, debit_php, credit_php |
| H01 | Archive records (closed transactions and history) | H01 | 15 | 3 | record_type, legacy_key | amount |
| H02 | Archive documents index | H02 | 8 | 6 | record_type, legacy_key, file_name | - |

Rules for every file (workbook sheet "File Contract"):

•	File name <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv, one file per layout, source system and extract: the layout code, not the object code, starts the name. Three objects have sub-layouts sent as separate files with the same as-of date: R04 and R04B (insurers and their branches), P01 and P01S (policy headers and their insurer shares), F01, F01S and F01C (invoice headers, insurer shares and components).

•	CSV in UTF-8 without BOM, comma separator, RFC 4180 quoting, one header row; or XLSX with the header in row 1 of the first sheet.

•	Dates yyyy-MM-dd; amounts with a dot decimal, 2 decimals, no thousands separator; codes exactly as stored in legacy.

•	A control file <data file>.ctl.csv with the row count, the hash total of the key, the amount totals per column and currency, and the SHA-256 of the data file.

What BDOI provides per object:

Table 14: What BDOI provides per object

| Object | Data object | Templates | Source | Control totals | Due |
| --- | --- | --- | --- | --- | --- |
| R01 | Lists of values and MIS values | R01 | QPS, EBIX | Row count; count of distinct (list_type, code) | M3 (29 Jan 2027) |
| R02 | Branches and invoicing branches | R02 | EBIX | Row count | M3 (29 Jan 2027) |
| R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | R03 | QPS, EBIX | Row count per record type | M3 (29 Jan 2027) |
| R04 | Insurers and insurer branches | R04, R04B | QPS, EBIX | Row count per file | M3 (29 Jan 2027) |
| R05 | Product lines, cover types, products and risk codes | R05 | QPS, EBIX | Row count | M3 (29 Jan 2027) |
| R06 | Packages (active package versions) | R06 | QPS | Row count | M3 (29 Jan 2027) |
| R07 | Commission rates by insurer and product | R07 | QPS, EBIX | Row count | M3 (29 Jan 2027) |
| R08 | Chart of accounts mapping (legacy GL account to BIBS account) | R08 | EBIX, ISYS GL | Row count | M3 (29 Jan 2027) |
| R09 | Payees | R09 | EBIX, Disbursement files | Row count | M3 (29 Jan 2027) |
| R11 | Receipt series in use (AR and OR, ATP and next number) | R11 | EBIX | Row count | M3 (29 Jan 2027); final at T-3 |
| C01 | Client master (individual and corporate) | C01, C02 | QPS, EBIX, CMS | Row count; count of distinct legacy_client_no | M3 (29 Jan 2027); deltas daily from T-14 days |
| C03 | Client payout accounts (for refunds) | C03 | EBIX | Row count | M3 (29 Jan 2027) |
| C04 | KYC documents and IDs | H02 | QPS, file shares | Row count; SHA-256 per file | Before decommissioning |
| P01 | In-force policy headers | P01, P01S | QPS, EBIX | Row count; sum of sum_insured and gross_premium per currency; count of distinct legacy_policy_ref | M3 (29 Jan 2027); final at T-2 |
| P02 | Expired policies and policy history | H01 | QPS, EBIX | Row count and hash total per record type | Before decommissioning |
| P03 | RMEL cohorts January to May 2028 (renewals prepared in legacy, not booked at the freeze) | P03 | Legacy RMEL extract (EBIX, QPS); Marketing disposition files | Row count and count of distinct legacy_policy_ref per rmel_month; sums of expiring and proposed premium per currency | M3 (29 Jan 2027); final at T-2 |
| F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | F01, F01S, F01C | EBIX, QPS | Row count per file; sums per component, bucket and currency; count of distinct legacy_invoice_no | M3 (29 Jan 2027); final at T-2 |
| F02 | Unapplied premium payments (UPP) with disposition in progress | F02 | EBIX, CMS | Row count; sums of amount and balance per currency; count of distinct legacy_upp_ref | M3 (29 Jan 2027); final at T-2 |
| F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | F03 | CMS | Row count; sum of promise_amount per currency | M3 (29 Jan 2027); final at T-2 |
| F04 | Remittance in flight (batches not yet paid, holds, special remittances) | F04 | EBIX | Row count; sum of amount per currency | M3 (29 Jan 2027); final at T-2 |
| F06 | PDCs in the warehouse, check pick-ups and refunds in process | F06 | EBIX | Row count; sum of amount per currency and record type | M3 (29 Jan 2027); final at T-2 |
| G01 | GL opening trial balance per account, branch and currency | G01 | EBIX GL, ISYS GL | Row count; total debit and total credit per branch and currency (must be equal) | M3 (29 Jan 2027); final at T-2 |
| G02 | GL history (journals and balances before cutover) | H01 | EBIX GL, ISYS GL | Row count and debit / credit totals per period | Before decommissioning |
| H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | H01 | EBIX, QPS, ISYS | Row count, amount totals and hash total per record type | Before decommissioning |
| H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | H02 | File shares, EBIX | Row count; SHA-256 per file | Before decommissioning |

## 6.3 Secure transfer and staging

•	Files are received through the Migration Console upload, or through an SFTP drop that BDOI IT and iorta TechNXT set up (a seam of the intake; DMQ28). E-mail is never used.

•	Files land in an encrypted intake bucket in AWS ap-southeast-1 with a 5-day lifecycle.

•	The intake checks run before any row is staged. A file that fails is rejected with the reason and the difference, and BDOI IT re-sends it.

•	Staged rows keep the raw values as received and the mapped values. Outside production, names, addresses, TIN, ID, account and phone numbers, e-mail addresses and birth dates are masked at intake with a keyed, repeatable masking, so dedupe still works on masked data.

## 6.4 Profiling

After the first full extract (M3, 29 January 2027) and after each mock, iorta TechNXT profiles every staged object and sends the report to the data stewards. The report gives, per field: fill rate, distinct values, top values, values out of format, codes without a map entry, duplicates of the key, and, per object, the rows that fail each data-quality rule. For clients it gives the candidate duplicate pairs by score band; for open items it gives the totals by component, currency, branch and age band. The stewards use it to plan the cleansing and the code maps.

## 6.5 Cleansing: who fixes what

Cleansing is shared. BDOI owns the data and fixes it where it lives; iorta TechNXT fixes what is a matter of format or mapping.

Table 15: Cleansing responsibilities

| Issue | Example | Fixed by | Where |
| --- | --- | --- | --- |
| Wrong or missing business data | Client without birth date, invoice without insurer, TIN of another client | BDOI data steward | In legacy, before the next extract |
| Duplicate clients | Same person in QPS and EBIX with different numbers | BIBS matching; data steward decides doubtful pairs | Client Matching queue |
| Legacy codes without a BIBS value | Discontinued segment code, insurer branch not in BIBS | Data steward proposes; business owner approves | Code map version (MAP, DEFAULT, CREATE or REJECT) |
| Format differences | Date as dd/MM/yyyy, TIN with dashes, mobile without prefix | iorta TechNXT (extract layout or staging rule) | Extract job or staging |
| Records out of scope | Client not active since 2019, invoice fully settled | Business owner decides | Exclusion recorded in the batch |
| Open balances that do not add up | Components do not equal gross premium; open not equal to booked less paid | BDOI data steward with Comptrollership | In legacy (correction entry) before the freeze |
| Data that cannot be fixed before go-live | UPP without payor reference | Business owner waives with a reason and a plan | Waiver in the batch (G3) |

Thresholds for loading an object (configurable): master data may be loaded with at most 0.5 percent of rows rejected or waived; financial objects (open invoices, UPP, trial balance) load only with 0 errors, or with each excluded row approved by the business owner with a manual-entry plan (R3 section 8).

## 6.6 Mapping and code maps

Legacy codes are mapped to BIBS codes through code map sets, one per domain. Each set has versions: DRAFT, SUBMITTED, APPROVED, SUPERSEDED. The data steward prepares a version in the console or in the Excel template of the workbook and submits it; the business owner approves it (maker-checker). Each batch records the map versions it used, so every loaded value can be traced to the entry that produced it (BRID 3.1).

An entry maps a legacy code to a BIBS code (MAP), to the default of the set (DEFAULT), rejects the rows that carry it (REJECT), or creates a new BIBS value (CREATE). CREATE values are created through the owning master (for example the LOV master or the insurer master) and authorised there before any dependent object loads.

Table 16: Code map sets (BRID 3.1)

| Map set | What is mapped | BIBS master | Approves |
| --- | --- | --- | --- |
| LOV:<list> | One set per legacy list (market segment, ID type, nationality, source of funds, KYC risk rating, account type, ...) | lov_value | Product Owner, MBS |
| MIS:<field> | One set per MIS field (market segment, department, unit head, AO, region, area, branch, business origin, customer segment; umbrella p.40) | MIS field catalogue (CR-W1) | Product Owner, MBS |
| INSURER | Legacy insurer code to BIBS insurer | cat_insurer | Head, Operations |
| INSURER_BRANCH | Legacy insurer branch to BIBS insurer branch | cat_insurer_branch | Head, Operations |
| LINE | Legacy line of business to BIBS product line | cat_product_line | Product Owner, MBS |
| COVER_TYPE | Legacy cover type to BIBS cover type | cat_cover_type | Product Owner, MBS |
| PRODUCT | Legacy product / risk code to BIBS product code | cat_product | Product Owner, MBS |
| PACKAGE | Legacy package and version to the BIBS package version maintained by TSU; conditional entries (risk code, insurer, sum-insured band) where one legacy package splits (DMQ36) | cat_product_version | Product Owner, MBS (approves); MANCOM confirms the owner |
| BRANCH | Legacy branch to BIBS branch | org_branch | Head, Comptrollership |
| SALES_UNIT | Legacy region, department and team to BIBS sales unit | cat_sales_unit | Heads, Retail and Corporate Marketing |
| AO | Legacy AO code to BIBS account officer | cat_sales_officer | Heads, Retail and Corporate Marketing |
| USER | Legacy user ID to BIBS username (AO, handler, collector, requester) | BIBS users (User Access) | Unit Head, Analytics and Risk Management |
| COST_CENTER | Legacy cost centre to BIBS cost centre | Cost centre master | Head, Comptrollership |
| GL_ACCOUNT | Legacy GL account to BIBS account (legacy control accounts to Migration Clearing) | coa_account | Head, Comptrollership |
| BANK | Legacy bank code to BIBS bank list | Bank list (LOV) | Product Owner, Comptrollership - Disbursement |
| CURRENCY | Legacy currency code to ISO 4217 | Currency master | Head, Comptrollership |
| STATUS:<object> | Legacy statuses per object to BIBS statuses (CLIENT, KYC, INSURER, PRODUCT, POLICY, RENEWAL for the P03 dispositions, UPP, REMITTANCE, PDC) | Status of the target record | Owner of the object |
| DISPOSITION_TYPE | Legacy UPP disposition types to BIBS disposition types | csh_disposition_type_rule | Operations - Financial Transactions |
| DISPOSITION_CLX | Legacy collection dispositions to BIBS collection dispositions | Collections disposition list | Head, Operations (Collections) |
| DOCUMENT_TYPE | Legacy document types to archive document types | attachment document types | Compliance |

### 6.6.1 Package remapping

Legacy packages (QPS package code and version) must be mapped to the package names that TSU maintains in BIBS (BRD-3). The map is used for the package versions (R06), the package of each in-force policy header (P01) and the expiring and proposed package of the carried renewals (P03). The concept paper asked for a firm design choice, an owner and testing, and for a decision whether the mapping happens "during upload processing or during sanitation" (R10 p.2, Annex B, Annex C). That point stands with the single go-live (DMQ36, register DCR-241).

Table 17: Package remapping - options (DMQ36)

|  | At upload (migration intake) | During sanitation (Renewal checks) |
| --- | --- | --- |
| How | Code map set PACKAGE, versioned and approved by its owner (G2), applied in staging to R06, P01 and P03; conditional entries where one legacy package splits into several BIBS packages (by risk code, insurer or sum-insured band) | Candidates keep the legacy package; a Renewal sanitation check sends unmapped or ambiguous packages to the Exception bucket, and the processor picks the BIBS package per candidate |
| For | One approved map for headers and renewals; unmapped packages reported before load in every mock; reconciled field by field; tested before go-live | Handles cases that need judgement per account; never blocks a load |
| Against | The map must be complete at the map freeze; splits need qualifier rules | Choices per account are neither versioned nor approved; the same legacy package can be mapped two ways; headers still need a map at load; the work lands on renewal users in the first weeks after go-live; harder to audit |

Recommendation. Map at upload. A row whose package the map cannot resolve is not rejected: a carried renewal loads with package UNRESOLVED and goes to the Renewal Exception bucket, where TSU chooses the package; a header loads without a package. Each choice made in the Exception bucket is added to the next map version, so the exception route shrinks from mock to mock. Owner: TSU prepares the map as data steward, the Product Owner of Marketing Business System approves each version (G2), and MANCOM confirms the owner and the approach. Testing: the PACKAGE map is used in every mock; business verification samples cover every legacy package with more than one BIBS target.

## 6.7 Validation

Every staged row is checked against the data-quality rules of its layout before a batch can be approved for load. An ERROR stops the row; a WARNING loads it and reports it. The catalogue (workbook sheet "DQ Rules") has 51 rules:

Table 18: Data-quality rules by kind (full catalogue in the workbook, sheet DQ Rules)

| Kind | Rules | Rule IDs |
| --- | --- | --- |
| MANDATORY | 1 | DQ-001 |
| FORMAT | 6 | DQ-002, DQ-005, DQ-006, DQ-007, DQ-045, DQ-046 |
| LOOKUP | 4 | DQ-003, DQ-039, DQ-048, DQ-051 |
| UNIQUE | 4 | DQ-004, DQ-020, DQ-036, DQ-044 |
| PLAUSIBILITY | 5 | DQ-008, DQ-011, DQ-028, DQ-031, DQ-032 |
| CROSS_FIELD | 16 | DQ-009, DQ-013, DQ-014, DQ-015, DQ-017, DQ-019, DQ-021, DQ-024, DQ-025, DQ-029, DQ-038, DQ-041, DQ-042, DQ-043, DQ-049, DQ-050 |
| DUPLICATE_CLIENT | 1 | DQ-010 |
| REFERENTIAL | 6 | DQ-012, DQ-016, DQ-018, DQ-026, DQ-033, DQ-047 |
| BALANCE | 8 | DQ-022, DQ-023, DQ-027, DQ-030, DQ-034, DQ-035, DQ-037, DQ-040 |

## 6.8 Client matching and survivorship

Legacy clients of all source systems are matched with each other and with any client already in BIBS before any client is loaded (FR-DM-031). Keys and scores (proposal until DMQ04 is answered):

Table 19: Client matching keys

| Key | Rule | Score |
| --- | --- | --- |
| K1 | TIN, digits only | 100 |
| K2 | ID type and number | 100 |
| K3 | Last name, first name and birth date | 95 |
| K4 | Normalised corporate name with registration number (90 without) | 95 |
| K5 | Bank CIF, if BDOI confirms it as a key | 100 |
| K6 | E-mail; PH mobile | 40 each |
| K7 | Similar name (at least 0.85) with the same birth date or city | 70 |

Pairs scoring 90 or more merge automatically; 60 to 89 go to the data steward's review queue; below 60 are separate clients. The client batch cannot be approved while the queue has open pairs. Survivorship takes, per field, the first non-blank value by source priority (proposal: QPS for contact data, EBIX for billing data) or the most recently updated value. Every value that lost is kept for review (report MIG-CLIENT-MATCH).

## 6.9 Load through the BIBS services

An approved batch is loaded in chunks of 500 rows, four partitions in parallel, one transaction per chunk; a failing chunk is retried row by row so one bad row fails alone. Loading the same batch again creates no duplicate: rows already loaded and unchanged are skipped through the key cross-reference. The planning target is 50,000 rows an hour per partition, proven in the dress rehearsal.

Before sign-off a batch can be rerun (only the rejected rows, after a fix) or rolled back (when its loader can undo the records and nothing has changed them since the load). In the production cutover the rollback point is a database snapshot (section 11.5).

## 6.10 Reconciliation and sign-off

Every object is reconciled at up to five levels. The Reconciliation Approach and Sign-off document gives the measures per object, the sample plan for business verification and the sign-off forms.

Table 20: Reconciliation levels (BRID 1.1b)

| Level | Measure | Rule |
| --- | --- | --- |
| L1 | Record counts | Received = control count; loaded + skipped + rejected + excluded = staged |
| L2 | Amounts | Sum per amount column and currency: control total = staged = BIBS; difference 0.00 |
| L3 | Hash totals | Hash total of the key and SHA-256 per row equal between control, staging and BIBS keys |
| L4 | Fields | Every mapped field of every loaded row, read back from BIBS, equals the staged value |
| L5 | GL | Migration Clearing is 0.00 per branch and currency; legacy control accounts equal the legacy sub-ledgers |

Seven gates record the sign-offs of each object: G1 decision, G2 mapping, G3 validation, G4 load approval, G5 reconciliation, G6 object accepted, G7 go-live. A reconciliation with a break cannot be signed until the break is explained and the explanation approved. The operator who ran a batch cannot sign its reconciliation or acceptance.

# 7 Legacy invoices after go-live

This chapter is for the Cashiering, Remittance, Collections, Accounting and Operations users who will process legacy items in BIBS.

## 7.1 What a legacy invoice is

A legacy invoice is an invoice booked in EBIX or QPS before go-live that still has something open at the freeze: premium the client has not paid, premium paid but not yet remitted to the insurer, commission not yet collected from the insurer, or a PR2307 balance. It is not re-booked in BIBS. It is loaded into the BIBS Operations ledger with:

•	its legacy invoice number (kept as the BIBS invoice number unless it collides with a number of another source system, DMQ11), the source system and the legacy policy reference;

•	each component (basic premium, DST, premium tax or VAT, LGT, FST, other charges, DTIP, commission, VAT on commission, withholding tax, PR2307) with what was booked, paid, remitted, adjusted and written off in legacy, so its open balance equals the legacy open balance;

•	its insurer shares, client, AO, unit, branch and flags (direct payment, 2307);

•	an opening accounting entry that puts the open balances on the legacy sub-ledgers.

From then on BIBS processes it with the normal screens (Figure 2). The only difference from a BIBS invoice is where its postings go: to the legacy control accounts, so the legacy positions run off visibly and separately from the new business.

Figure 2: A legacy invoice and the processes that act on it after go-live (BRID 5.1-10.1)

## 7.2 Legacy sub-ledgers

The BRD asks for legacy Premium Receivable, Commission Receivable, DTIP and UPP sub-ledgers (BRID 5.2, 6.1, 6.3, 6.4, 7.1, 7.2, 8.1). Comptrollership assigns the account codes of the legacy control accounts and of the Migration Clearing account (DMQ18, DCR-197); this document names the accounts only.

Table 21: Legacy sub-ledgers (account codes assigned by Comptrollership, DMQ18)

| Legacy control account | Holds | Moved by |
| --- | --- | --- |
| Premium Receivable - Legacy (by component) | Open premium of legacy invoices | Payments, automatch, dispositions, DPPR reversals, write-offs, endorsements |
| PR 2307 - Legacy | Open PR2307 of legacy invoices | PR2307 reversals |
| Due to Insurers (DTIP) - Legacy | Premium payable to insurers on legacy invoices | Remittance, DPPR and PR2307 reversals, endorsements |
| Commission Receivable - Legacy | Commission and VAT on commission still due from insurers | Remittance, DP commission collection, endorsements |
| Unrealised Commission and Deferred Output VAT - Legacy | Commission not yet recognised as income | Realisation on collection |
| Unapplied Collections (UPP) - Legacy | Unapplied payments received in legacy | Automatch, dispositions, refunds, reclassification to income |
| Migration Clearing | Offsets of the opening entries and of the legacy control-account lines of the trial balance | Opening entries only; must be 0.00 |

## 7.3 Worked example: one legacy invoice from load to remittance

Legacy invoice I00123456 (EBIX), private car, PHP, lead insurer 100 percent. Booked in legacy before go-live: basic premium 20,000.00, DST 2,500.00, premium tax 400.00, LGT 150.00; gross premium 23,050.00; commission 4,000.00 (20 percent), VAT on commission 480.00, withholding tax on commission 400.00. Before the freeze the client paid 13,050.00, which covered DST, premium tax, LGT and 10,000.00 of the basic premium (the application order DST, premium tax / VAT, LGT, FST, other charges, basic). Nothing was remitted to the insurer. The figures are made up.

Table 22: Positions of I00123456 at the freeze (extract F01C)

| Component | Booked | Paid | Remitted | Open | Legacy sub-ledger |
| --- | --- | --- | --- | --- | --- |
| Basic premium | 20,000.00 | 10,000.00 | 0.00 | 10,000.00 | Premium Receivable - Legacy |
| DST | 2,500.00 | 2,500.00 | 0.00 | 0.00 | Premium Receivable - Legacy |
| Premium tax / VAT | 400.00 | 400.00 | 0.00 | 0.00 | Premium Receivable - Legacy |
| LGT | 150.00 | 150.00 | 0.00 | 0.00 | Premium Receivable - Legacy |
| DTIP | 23,050.00 | - | 0.00 | 23,050.00 | DTIP - Legacy |
| Commission | 4,000.00 | - | 0.00 | 4,000.00 | Commission Receivable - Legacy |
| VAT on commission | 480.00 | - | 0.00 | 480.00 | Commission Receivable - Legacy |
| Withholding tax | 400.00 | - | 0.00 | 400.00 | (settled at remittance) |

What happens after go-live:

Table 23: Life of I00123456 in BIBS

| When | Event in BIBS | Effect |
| --- | --- | --- |
| Load (T-2) | Invoice created in the Operations ledger with origin LEGACY; opening entry | Premium Receivable - Legacy 10,000.00 debit; DTIP - Legacy 23,050.00 credit; Commission Receivable - Legacy 4,480.00 debit; the unrealised part per DMQ13; the balance of the entry to Migration Clearing. Invoice 360 shows booked 23,050.00, applied 13,050.00, open 10,000.00 and the LEGACY badge |
| T+2 | The client pays 10,000.00 at the counter quoting I00123456 | BIBS finds the legacy invoice, issues a BIBS AR and applies the payment to basic. Entries: Dr Bank / Cr Unapplied Collections 10,000.00; Dr Unapplied Collections / Cr Premium Receivable - Legacy 10,000.00. The invoice is fully paid; the receipt is in the Cash Receipts Book |
| T+9 | Remittance extraction for the insurer | The invoice is extracted with paid AR 23,050.00 (13,050.00 paid in legacy and 10,000.00 in BIBS). Net due to the insurer 18,970.00 = 23,050.00 - 4,480.00 + 400.00. Entry: Dr DTIP - Legacy 23,050.00 and Dr CWT 400.00 / Cr Commission Receivable - Legacy 4,480.00 and Cr Due to Insurer for Disbursement 18,970.00. The schedule shows the legacy invoice number and source system; the commission OR is issued as for any batch |
| T+20 | Positive endorsement, additional basic premium 2,000.00 | The policy header is a migrated account (P01). BIBS books an endorsement invoice with a BI- number whose parent is I00123456 and ledger context LEGACY; its entries go to the legacy accounts; the service invoice is issued for the commission increase |
| Month end | Prod Recon legacy change report | Shows for I00123456 basic premium original 20,000.00, updated 22,000.00, delta 2,000.00, with the endorsement number, date and user (BRID 10.1) |

## 7.4 Unapplied premium payments (UPP)

Every legacy UPP item with a balance at the freeze is created in the BIBS Unapplied Payments workbench with origin MIGRATED, its legacy AR number and date, payor, client, sales unit, amount, balance, status and the references the payor gave (invoice, cover, PN, bank reference). An opening entry puts the balance on Unapplied Collections - Legacy. No new AR is issued for money already acknowledged in legacy (proposal, DMQ14, DCR-204).

Table 24: Processing legacy UPP in BIBS (BRID 5.1-5.5, 6.3, 6.4)

| Process | Example | Entries (by context) |
| --- | --- | --- |
| Automatch rerun (after every payment upload and hourly) | Legacy UPP of 5,000.00 quotes legacy invoice I00200001 (3,000.00 open) and new invoice BI-2028-000150 (2,000.00 open). The job applies both and closes the item | Dr Unapplied Collections - Legacy 3,000.00 / Cr Premium Receivable - Legacy 3,000.00; Dr Unapplied Collections - Legacy 2,000.00 / Cr Premium Receivable (new) 2,000.00 |
| Apply to another invoice (client instruction) | The client asks to apply a legacy UPP to another legacy invoice | Dr Unapplied Collections - Legacy / Cr Premium Receivable - Legacy |
| Refund | Approved refund of 1,500.00 | Dr Unapplied Collections - Legacy / Cr Refund Payable; payment request to Disbursement |
| Reclassification to other income | UPP of 1,500.00 unclaimed for more than 2 years; batch approved by the Cashiering TL and then top management (DMQ16) | Dr Unapplied Collections - Legacy / Cr Other Income (account per DMQ16); item closed |

## 7.5 Payments, reversals, remittance, endorsements and Prod Recon

Table 25: Other processes on legacy invoices

| Process (BRID) | What the user does | What BIBS does |
| --- | --- | --- |
| OTC payment (6.1) | Keys the legacy invoice number, ARN, policy or PN at the counter | Finds the legacy invoice, issues the AR, applies by component, posts to Premium Receivable - Legacy; Cash Receipts Book as usual |
| Autopay (6.2) | Uploads the bills payment, trade, CLPC or direct credit file as today | Matches rows that carry the legacy invoice number or the EBIX reference; applies and posts by the context of each invoice |
| DPPR batch reversal (7.1) | Uploads or selects the approved list of direct-payment legacy invoices; a checker approves | Reverses each open premium receivable against DTIP on the legacy sub-ledgers, one line at a time (Dr DTIP - Legacy / Cr Premium Receivable - Legacy); Commission Receivable effect per DMQ19 |
| PR2307 batch reversal (7.2) | Selects legacy invoices with PR2307 balances; approval | Offsets PR2307 - Legacy against DTIP - Legacy; commission effect per DMQ20 |
| Remittance (8.1) | Runs the extraction as today | Includes legacy invoices with paid premium not yet remitted; never remits again what was remitted in legacy; posts legacy lines to DTIP and Commission Receivable - Legacy |
| Endorsements (9.1-9.3) | Raises the endorsement request on the legacy invoice | Needs the migrated policy header; books the endorsement invoice in context LEGACY; non-financial changes update the account with no posting; renewal uses the updated values |
| Collections | Works the worklist as today | Legacy invoices above the threshold appear with the LEGACY badge; carried promises and assignments (F03) are shown |
| Prod Recon (10.1) | Runs the legacy change report | Lists original, updated and delta per change; legacy invoices are not part of the production register extract |

## 7.6 When the legacy context closes

The legacy sub-ledgers run off as legacy invoices are paid, remitted, reversed or written off and as legacy UPP is applied, refunded or reclassified. The report MIG-LEGACY-POSITIONS shows the open legacy positions by component, insurer, client and age each month. When no legacy invoice or UPP is open and the legacy control accounts and Migration Clearing are 0.00, Comptrollership decides whether to close the legacy accounts.

# 8 In-force policies and the renewal-driven transition

## 8.1 In-force policy headers

BRID 4.1 asks for a minimal header of in-force policies "when operationally required" (p.8); capability 4 is conditional (p.6). BIBS needs the header for three things: to locate active coverage for servicing, to endorse a legacy invoice (BRID 9 cannot be met without it), and to renew the policy in BIBS. The proposal is therefore to migrate the header of every policy in force at go-live (DMQ09, DCR-194), in layouts P01 (header) and P01S (insurer shares).

A header becomes a BIBS account with origin MIGRATED and status BOOKED: client, product and line, insurer and shares, policy number, inception and expiry, sum insured, premium, currency, payment arrangement, PN numbers, AO, unit and branch. It has no quotation, placement or BIBS invoice. Its legacy invoices link to it. It is found by ARN, policy number, legacy reference or client.

## 8.2 Renewal by RMEL cohort

The transition follows the renewal expiry month (RMEL, BRID 12.1). BIBS Renewal extracts policies 140 days before expiry, so at go-live the policies expiring in the next 140 days are already in their renewal cycle in legacy. For the proposed go-live of Monday 3 January 2028 these are the expiries of 3 January to 22 May 2028: the January-May 2028 cohorts that the superseded concept paper wanted to process in BIBS from August 2027 (DMQ26 partly answered; DMQ37, register DCR-199, DCR-240).

Figure 3: Transition by RMEL cohort (go-live proposed 3 January 2028)

Table 26: Treatment of each cohort (proposal, DMQ37)

| Cohort (expiry) | Treatment |
| --- | --- |
| Before go-live (up to 2 January 2028) | Renewed or lapsed in legacy; a renewal whose new term starts before go-live is placed and booked in legacy before the freeze and migrates as an in-force header with its open invoice |
| Go-live to go-live + 140 days (3 January to 22 May 2028) | Prepared in legacy from August 2027 as today (legacy RMEL extraction, dispositions, quotations, RAs). At the freeze every renewal not yet booked is carried (layout P03) with its disposition, handler, RA status and proposed terms; it continues in BIBS Renewal with source LEGACY and is placed and booked in BIBS from go-live |
| After go-live + 140 days (from 23 May 2028) | Extracted by BIBS Renewal from the migrated headers on the normal lead time, from the day after go-live |

The alternative is to do no renewal work in legacy for these expiries and let BIBS extract them all at go-live. It gives one process, but the January expiries would have days instead of 140 days for the insurer approval and the RA, and the workload would peak at go-live. The proposal keeps that catch-up extraction only as a safety net: at go-live BIBS extracts every migrated header expiring in the next 140 days that has no carried row, so no expiry is missed.

What BDOI provides for the carried cohorts (layout P03). One row per expiring policy term, keyed by its legacy policy reference: cohort month, expiring and proposed package, disposition and its date, handler, team leader review, RA sent with date and number, insurer approval status, proposed insurer, sum insured and premium, FFY and submitted-policy flags, placement status and remarks. The policy part comes from the legacy RMEL extract; the disposition part is today kept by the business units in spreadsheets and e-mail (RN BRD p.42), so BDOI consolidates it in one template per month (DMQ38, register DCR-243). In the mocks, P03 is sent per cohort month; in production once, after the freeze.

Validation and exception handling. A row is rejected when its expiring header is not in the P01 extract of the same load, when the expiry is outside go-live to go-live + 140 days, when the cover was already renewed in legacy, when a disposition, handler or insurer code is not mapped, when an RA date or a non-renewal reason is missing, or when the renewal is placed or bound but not booked (an in-flight item, DMQ33). An unmapped package is a warning (Package remapping, section 6.6.1). The rejected rows go to the Heads of Retail and Corporate Marketing after every mock and are fixed in the disposition files before the next one. A cohort completeness check proves that, per expiry month, the headers expiring in the window equal the carried rows plus the renewals already booked in legacy plus the rejected rows; the headers without a carried row are the catch-up candidates.

A legacy policy renews on the new-business path pre-filled from its header, because the header carries no BIBS rating data. The renewal account refers to the legacy reference, so the run-off tracker can link them. The tracker (report MIG-RUNOFF) shows, per expiry month, the legacy policies in force at go-live, renewed in BIBS, not renewed, lapsed and still open. Legacy systems are decommissioned when their last cohort has run off and the other checklist criteria are met (section 11.8).

# 9 History, archive and read-only access

History is not migrated into BIBS business tables. For each legacy system BDOI chooses how history stays available (DMQ24, DCR-209):

Table 27: Options for history

| Option | What it means | When |
| --- | --- | --- |
| Read-only legacy | The legacy application stays up in read-only mode, with its own access logging (BDOI IT). BIBS shows the legacy reference and a link | From the freeze until the system is decommissioned |
| BIBS archive | Closed transactions, expired policies, GL history and documents are loaded into the BIBS archive (layouts H01 and H02) and searched in Legacy Inquiry | Before a legacy system is decommissioned |

Legacy Inquiry searches the archive by client, policy or cover number, invoice, receipt, claim, date and record type, and shows each record read-only with its documents. Every search, view, download and export is logged (user, time, criteria, records, reason); the log cannot be changed; Compliance reviews it on screen and receives a monthly digest (FR-DM-110, FR-DM-111).

Retention. Archive records and access logs follow the retention rules: the umbrella BRD gives 5 years online and 15 years archive for historical data (R5 p.45). Reconciliation reports, sign-offs and run logs are kept as project records and are not purged with the staging data (proposed 10 years, DMQ29).

Archive reconciliation. Each archive load is reconciled against legacy by counts, amount totals and hash totals per record type, and Audit / Compliance checks samples in Legacy Inquiry before the system is decommissioned.

# 10 Migration cycles

## 10.1 Mocks, dress rehearsal and production

The migration is run five times before it counts, inside the SIT and UAT migration windows of the BDOI timeline and the full migration and cut-over window. Each run follows the same plan in the Migration Console, so timings and defects are measured and the production cutover repeats a rehearsed plan.

Mock-load order. In every run, reference data (R01-R07) and the client master (C01-C03) are loaded and accepted first, before any policy header, carried renewal or open item. This follows the load order, and it gives the SIT and UAT of the Drop 1 modules, Renewal first, migrated clients and reference data to test with from the first mock: the prerequisite the concept paper sets for renewal (R10 section VI).

Figure 4: Migration cycles on the BDOI timeline (go-live January 2028)

Table 28: Migration cycles with entry and exit criteria

| Cycle | When / where | Data and objects | Entry criteria | Exit criteria |
| --- | --- | --- | --- | --- |
| Mock 1 | 19-30 Apr 2027; SIT | Masked full extracts; reference data and clients first, then policy headers and carried renewals (P03) | Build waves DM0 and DM1-C deployed on SIT by 9 Apr 2027; layouts frozen (M2); draft code maps; extracts for Mock 1 received (M4) | Objects loaded; L1-L4 run; defects logged; timing per object recorded; profiling report and P03 rejects to the owners |
| Mock 2 | 5-16 Jul 2027; SIT | Masked full extracts; all objects | Mock 1 exit met; build waves DM1-A, DM1-B, DM2-A, DM2-B deployed by 18 Jun 2027; code maps approved (M5); legacy accounts and rules configured on SIT | All objects loaded; L1-L5 reconciled; Migration Clearing 0.00 per branch and currency; no open Critical migration defect |
| Mock 3 (UAT load) | 2-13 Aug 2027; UAT | Masked extracts refreshed; all objects | Mock 2 exit met; UAT readiness statement issued (R7, programme item 11) | Business owners verify samples on screen (G6 rehearsal); the Drop 1 end-to-end UAT (Aug-Dec 2027) runs on the migrated data; data-quality issues below the thresholds |
| Mock 4 (UAT refresh) | 4-15 Oct 2027; UAT | Fresh masked extracts; all objects, with the carried January-May 2028 cohorts | Mock 3 exit met; cut-over date, fallback and decommissioning criteria agreed (M6) | Run as a timed cut-over; cohort completeness proven; UAT continues on the refreshed data |
| Dress rehearsal | 15-26 Nov 2027 (reserve 6-10 Dec 2027); production-sized environment | Masked full-volume extracts taken after a legacy EOD | Mock 4 exit met; production-sized environment (performance test window); cutover plan frozen | Full cutover within the window with at least 20 percent margin; rollback (snapshot restore) rehearsed; go / no-go criteria measured |
| Production | 20 Dec 2027 (T-14) to 3 Jan 2028 (T) | Real data in production only | GNG-1 passed (Cutover Runbook) | GNG-3 GO; hypercare exit criteria (Cutover Runbook) |

Defects found in a cycle are fixed before the next one: in legacy (cleansing), in the code maps, in the layouts or in the loaders. The next cycle uses fresh extracts, so every fix is proven with new data.

## 10.2 Test data and masking

SIT and UAT receive masked extracts only. Masking is done at intake in BIBS with a keyed, repeatable method: the same person gets the same masked name and numbers in every file, so dedupe and matching behave as in production. Amounts, codes and transaction dates are not masked, so reconciliation and business verification work on real figures. Unmasked extracts never leave production (DMQ31, DCR-200).

# 11 Cutover strategy

## 11.1 Approach

•	Big bang for open items. All open items (invoices, UPP, collection state, remittance items, PDCs), the policy headers, the RMEL cohorts and the GL trial balance are loaded once, after the legacy freeze, over one weekend. They change every day, so a delta approach would add reconciliation risk for no benefit.

•	Pre-load and deltas for master data. Reference data and clients are loaded two weeks before go-live and kept current with daily client deltas until the freeze. This takes the largest objects out of the cutover window.

•	Year-end alignment. The BDOI timeline sets go-live in January 2028 (DMQ25). The proposal is Monday 3 January 2028, the first business day after the legacy year-end close, so the opening trial balance is a closed year-end balance and no P&L balance is carried. The last legacy business day is Wednesday 29 December 2027, because 30 and 31 December are holidays; the legacy EOD and year-end close run on 31 December (DMQ39, DCR-242). A later January date is possible but keeps legacy running into January and needs a January cut-off of the trial balance.

## 11.2 Freeze windows

Table 29: Freeze windows

| Freeze | From | Until | Scope | Exception route |
| --- | --- | --- | --- | --- |
| Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects |
| Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live |
| Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings in EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements, GL journals | None; an urgent item is recorded on paper and keyed in BIBS on T |
| BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board |
| BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical defect approved by the go / no-go board |

## 11.3 Parallel run

There is no parallel run of legacy and BIBS on the same items. A parallel run would need each receipt, application, remittance and endorsement keyed twice and reconciled daily, and it contradicts the principle that an open item is processed in one system only (BRD p.5). The controls that replace it are the four mocks and the dress rehearsal on full extracts, the go / no-go criteria measured on production data, the rollback point until the go / no-go, and the daily hypercare reconciliation after go-live.

## 11.4 Go / no-go

Three checkpoints decide the cutover. The criteria are measured by BIBS and recorded with their values (FR-DM-121). GNG-3 is the go-live decision on the Sunday before go-live at 18:00 (2 January 2028 for the proposed date):

Table 30: Go-live criteria (GNG-3)

| # | Criterion | Threshold |
| --- | --- | --- |
| 1 | Day-1 objects accepted (G6) | 100 percent |
| 2 | Count reconciliation per object | Received = control; loaded + skipped + rejected + excluded = staged |
| 3 | Financial rejects (open invoices, UPP, trial balance) | 0, or each excluded item approved with a manual-entry plan |
| 4 | Amount reconciliation of open items, UPP and trial balance | 0.00 per currency |
| 5 | Migration Clearing | 0.00 per branch and currency |
| 6 | Legacy control accounts vs legacy sub-ledgers | 0.00 |
| 7 | Client review queue; screening run | Empty; complete |
| 8 | Business smoke test on production | Passed |
| 9 | Rollback point (snapshot) | Taken and verified |
| 10 | Hypercare roster and support channels | In place |

GNG-1 (T-15, start the pre-load) and GNG-2 (T-5, enter the freeze) are in the Cutover Runbook.

## 11.5 Rollback

Until the go / no-go decision the rollback is a restore of the production database snapshot taken at the start of the production load, and legacy is reopened for business on Monday. After go-live, until the point of no return at 18:00 on the first business day, the same restore is possible with re-keying in legacy of the transactions keyed in BIBS that day. After the point of no return, issues are fixed forward in BIBS (DMQ32, DCR-200). The steps are in the Cutover Runbook.

## 11.6 Hypercare

Hypercare runs from go-live to the first month-end close. Every day: Migration Clearing 0.00, legacy control accounts against their sub-ledgers, automatch results, exception queues and failed jobs; defect triage twice a day. Exit requires no open Critical or High defect, 10 consecutive business days of clean daily checks, and the first month-end close with the ACSL GL-SL reconciliation (context LEGACY) without difference.

## 11.7 In-flight items at the freeze

Items in process in legacy at the freeze (pending endorsements, un-booked accounts, placements, PDCs, check pick-ups, refunds, remittance batches) are, in order of preference, completed in legacy before the freeze, carried forward in a layout (F04, F06), or re-keyed in BIBS after go-live from a list signed by the business owner (DMQ33, DMQ21). A renewal placed or bound in legacy but not booked is such an item; it is not carried in P03. The runbook schedules the completion drives from T-12.

## 11.8 Decommissioning

Each legacy system is decommissioned only against a signed checklist (FR-DM-123): final extracts reconciled, archive loaded and reconciled, Legacy Inquiry verified by Audit / Compliance, no open inquiry or claim that needs the system, the last legacy-booked policy expired plus the claims tail, access logs archived, retention covered, and sign-off by the system owner, Compliance and Comptrollership (DMQ27). The checklists per system are in the Cutover Runbook.

# 12 Data security

The migration follows the hosting appendix (R7) and the security controls of BIBS.

Table 31: Data protection controls

| Control | How it is applied |
| --- | --- |
| Hosting | All migration data (intake bucket, staging, archive) is in the BIBS environment in AWS ap-southeast-1 |
| Masked non-production data | Every non-production environment (SIT, UAT, dress rehearsal) receives data masked at intake; unmasked extracts never leave production |
| Staging purge within 5 days | Staging payloads and extract files are deleted within 5 days of the batch sign-off or rollback, or of an extract rejection (job MIG_STAGING_PURGE and a lifecycle rule on the intake bucket); an alert is raised when a signed-off batch still has payloads after the limit. Counts, hashes and totals are kept as evidence |
| Access restricted to the Philippines | The Migration Console, staging and the intake bucket are reachable only by migration roles and only from the Philippines (network allow-list and VPN at the infrastructure layer) |
| Encrypted transfer and storage | Files move through the console (TLS) or SFTP; at rest they are encrypted with KMS keys; never by e-mail or removable media |
| Access logging | Every console action (upload, validation, load, rerun, rollback, reconciliation, sign-off, decision) is audited; every access to archived history is written to the append-only legacy access log |
| Segregation of duties | The maker of a decision, map version, load or rollback never approves it; the operator of a batch cannot sign its reconciliation or acceptance |
| Least privilege | Migration roles are granted through User Access requests for the migration period and removed at hypercare exit |

# 13 Roles and responsibilities

## 13.1 Migration organisation

•	Go / no-go board: BDOI Program Manager (chair), Heads of Operations, Comptrollership, Marketing and Compliance, BDOI IT head, iorta TechNXT Project Manager. Decides at GNG-1, GNG-2, GNG-3 and the point of no return.

•	BDOI Data Migration Lead: runs the migration on the BDOI side: object register, decisions, load approvals (G4), acceptance with the owners (G6), cutover plan.

•	Data owners: department heads who own an object; approve its class, code maps, waivers and acceptance.

•	Data stewards: named staff per object; profile review, cleansing at source, code maps, client match review.

•	BDOI IT: extracts, control files, transfer, legacy freeze and read-only mode, archive extracts, decommissioning.

•	Comptrollership: legacy control accounts, Migration Clearing and accounting rules; reconciliation approver for financial objects (G5).

•	iorta TechNXT: Project Manager; Migration Lead (loaders, reconciliation, profiling, console); Migration Operator (intake, validation, loads); DevOps (environments, snapshots, access); QA (smoke tests, migration test plan).

## 13.2 RACI

R = responsible, A = accountable, C = consulted, I = informed.

Table 32: RACI. PM = BDOI Program Manager; DML = Data Migration Lead; OWN = data owners; STW = data stewards; BIT = BDOI IT; COMP = Comptrollership; CMP = Compliance; IPM = iorta Project Manager; IML = iorta Migration Lead; IOP = iorta Operator / DevOps; GNG = go / no-go board

| Activity | PM | DML | OWN | STW | BIT | COMP | CMP | IPM | IML | IOP | GNG |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Migration strategy and this document | A | R | C | I | C | C | C | R | R | I | I |
| Object register and decisions (G1) | I | R | A | C | C | C | C | I | C | I | I |
| Extract layouts and templates | I | A | C | C | R | C | I | I | R | I | - |
| Extracts and control files | I | A | I | C | R | I | I | I | C | I | - |
| Secure transfer and intake | I | A | - | - | R | - | C | I | C | R | - |
| Profiling report | I | I | I | C | I | I | - | I | R | C | - |
| Cleansing at source | I | A | C | R | R | C | - | I | C | - | - |
| Code maps (G2) | I | C | A | R | C | C | - | I | C | - | - |
| Client matching and survivorship | I | C | A | R | I | - | C | I | R | C | - |
| Validation and waivers (G3) | I | C | A | R | I | C | - | I | R | C | - |
| Load approval (G4) and loads | I | A | I | I | I | I | - | I | C | R | - |
| Reconciliation (G5) | I | C | C | C | I | A | - | I | R | C | - |
| Legacy accounts, clearing, rules | I | I | C | - | - | A | - | I | C | - | - |
| Business verification and acceptance (G6) | I | R | A | R | - | C | - | I | C | - | - |
| Mocks and dress rehearsal | A | R | C | C | R | C | I | R | R | R | I |
| Legacy freeze and read-only mode | C | A | I | - | R | I | I | I | I | - | I |
| Go / no-go (G7) | R | C | C | - | C | C | C | C | C | - | A |
| Rollback | C | C | - | - | R | I | - | R | R | R | A |
| Hypercare | A | R | C | C | C | C | I | R | R | R | I |
| Archive loads and Legacy Inquiry verification | I | R | C | C | R | C | A | I | R | C | - |
| Decommissioning | A | R | C | - | R | C | C | I | C | - | I |

# 14 Risks and mitigations

Table 33: Migration risks

| # | Risk | Impact | Mitigation |
| --- | --- | --- | --- |
| 1 | Legacy cannot give open balances per component or the paid / remitted split (DMQ12, DCR-207) | High | Profiling of the first full extracts (29 January 2027); "open-balance mode" (open balance loaded as booked, original values in the snapshot); split rules as configuration agreed with Comptrollership |
| 2 | Migration Clearing not 0.00 at cutover (detail and trial balance disagree) | High | Reconciliation in every mock from Mock 2; trial balance extracted after the same EOD as the detail; break explanations agreed with Comptrollership before GNG-3 |
| 3 | Duplicate clients merged wrongly, or not merged | High | Auto-merge only on hard keys; review queue for the rest; every lost value kept; client batches can be rolled back before sign-off |
| 4 | Answers to the build-shaping decisions arrive late (M1) | High | Decisions listed with dates (chapter 15); defaults in configuration where possible; build waves sequenced so late answers change configuration, not code |
| 5 | Load time exceeds the cutover window | Medium | Pre-load of reference data and clients; four partitions; dress rehearsal at full volume with 20 percent margin |
| 6 | Endorsements of legacy invoices without policy headers (BRID 9 depends on BRID 4.1) | High | Decide DMQ09 / DMQ22 by M1; proposal: headers of every in-force policy |
| 7 | Real personal data in a test environment | High | Masking at intake; unmasked files never leave production; 5-day purge; access only from the Philippines |
| 8 | Legacy postings after the freeze | High | Legacy set read-only at T-3 22:00 and tested; any late legacy transaction is a reconciliation break and is re-keyed in BIBS |
| 9 | In-flight items forgotten at the freeze | Medium | Completion drives from T-9; carry-forward layouts F04, F06; signed re-keying list |
| 10 | Code maps incomplete when transactions load | Medium | Unmapped-code report before load; gate G3 blocks the batch; map freeze at T-7 |
| 11 | BDOI steward capacity for cleansing and review | Medium | Named stewards per object by M2; profiling report per mock with the top issues; review queue sized from Mock 1 |
| 12 | Legacy system decommissioned before history is archived | Medium | Decommissioning only against the signed checklist; archive reconciled and verified by Audit / Compliance |
| 13 | Foreign-currency openings at the wrong rate (DMQ35) | Medium | Rate decision by M2; booking rate carried in the extract; reconciliation per currency |
| 14 | The draft BRD changes when it is signed (DCR-189) | Medium | This document and the FRS are re-issued; decisions are configuration where possible |
| 15 | Cut-over over the year-end holidays (24 December 2027 to 1 January 2028) | High | Date and last business day decided by M6 (DMQ39); tasks moved off holidays in the runbook; roster confirmed at T-29 |
| 16 | Carried renewals of January-May 2028 incomplete or late, because the dispositions are kept in spreadsheets (DMQ38) | High | Consolidated disposition template from Mock 1; P03 rejects to the owners after every mock; cohort completeness check; catch-up extraction at go-live |
| 17 | Package remapping errors (R10 Annex C) | Medium | Map at upload with an owner (DMQ36); unmapped packages reported in every mock; verification samples per legacy package; exception route in Renewal |

# 15 Dependencies and open decisions

## 15.1 Dependencies

Table 34: Dependencies

| # | Dependency | Owner | Needed by |
| --- | --- | --- | --- |
| D1 | Build waves DM0 and DM1-C of the migration module (reference data, clients, headers, carried renewals, PACKAGE map) deployed on SIT | iorta TechNXT | Mock 1 (deployed by 9 Apr 2027) |
| D2 | Build waves DM1-A, DM1-B, DM2-A, DM2-B (legacy invoices, UPP, reversals, remittance, endorsements, Prod Recon, cutover plan, run-off) deployed on SIT | iorta TechNXT | Mock 2 (deployed by 18 Jun 2027) |
| D3 | Build wave DM3 (end-to-end test, performance harness) | iorta TechNXT | Mock 2 (end-to-end test); dress rehearsal (performance harness) |
| D4 | Renewal module (BRD-6) in SIT for Mock 1 and live at go-live, with the legacy policy source, the carried candidates, the catch-up extraction and the package check | iorta TechNXT | Mock 1; go-live |
| D5 | Legacy control accounts, Migration Clearing and legacy rule lines set up by Comptrollership | BDOI Comptrollership | Mock 2 (SIT); T-25 (production) |
| D6 | Extracts in the templates with control files, and volumes per object | BDOI IT | M3 (29 Jan 2027), M4 (9 Apr 2027) and every mock |
| D7 | Named data owners and stewards | BDOI | M2 |
| D8 | Legacy systems can be set read-only with access logging; SFTP drop | BDOI IT | Dress rehearsal |
| D9 | Users of every persona created through User Access requests | BDOI and iorta TechNXT | T-24 |

## 15.2 Open decisions and the date each is needed by

Decisions marked M1 change what is built and are needed by 16 October 2026; M2 decisions are needed by 30 October 2026. Both dates are inside the requirements and mapping window of the BDOI timeline (September-October 2026), so the build can start in November 2026 on agreed layouts. The others are tied to the migration calendar. The register column refers to the BRD discrepancy and clarification register (R6); items DCR-240 to DCR-243 are raised with this version.

Table 35: Open decisions, register items (v1.1) and the date each is needed by

| ID | Register | Decision | Blocks | Needed by | BDOI owner |
| --- | --- | --- | --- | --- | --- |
| DCR-189 | DCR-189 | BRD sign-off | Baseline of this document set; FRS re-issue | M2 (30 Oct 2026) | Program Manager |
| DCR-173 | DCR-173 | Client migration period and daily client batches | C01 scope and delta design; build wave DM1-C | M1 (16 Oct 2026) | Product Owner, MBS |
| DMQ01 | DCR-195 | Data object inventory | All objects; gate G1 | M2 (30 Oct 2026) | Program Manager |
| DMQ02 | DCR-192 | Decision rule | Gate G1 | M2 (30 Oct 2026) | Program Manager |
| DMQ03 | DCR-195 | Source systems | All layouts | M1 (16 Oct 2026) | BDOI IT |
| DMQ04 | - | Client dedupe keys | C01 matching; DM1-C | M2 (30 Oct 2026) | Product Owner, MBS |
| DMQ05 | - | Client scope | C01 volumes; filter | M2 (30 Oct 2026) | Product Owner, MBS |
| DMQ06 | DCR-208 | Screening of migrated clients | C01 load; cutover task CT-050 | M2 (30 Oct 2026) | Compliance |
| DMQ07 | - | KYC documents | C04, H02 | M2 (30 Oct 2026) | Compliance |
| DMQ08 | - | Code map owners | Gate G2; all map sets | M2 (30 Oct 2026) | Product Owner, MBS |
| DMQ09 | DCR-194 | In-force header condition | P01, P01S; endorsements BRID 9; DM1-C | M1 (16 Oct 2026) | Head, Operations |
| DMQ10 | - | Legacy invoice scope | F01; DM1-A | M1 (16 Oct 2026) | Operations - Financial Transactions |
| DMQ11 | DCR-207 | Invoice numbers | F01 keys; payment matching | M1 (16 Oct 2026) | BDOI IT |
| DMQ12 | DCR-207 | Components and shares | F01C; DM1-A | M1 (16 Oct 2026) | BDOI IT; Comptrollership |
| DMQ13 | - | Commission state | F01 opening entry | M1 (16 Oct 2026) | Head, Comptrollership |
| DMQ14 | DCR-204 | UPP receipt and statuses | F02; DM1-B | M1 (16 Oct 2026) | Operations - Financial Transactions |
| DMQ15 | - | UPP matching references | F02 ref_ columns | M2 (30 Oct 2026) | Operations - Financial Transactions |
| DMQ16 | DCR-198, DCR-205 | Reclassification to income | FR-DM-055 configuration | M2 (30 Oct 2026) | Head, Comptrollership |
| DMQ17 | - | Legacy UPP refunds | FR-DM-054 configuration | M2 (30 Oct 2026) | Operations - Financial Transactions |
| DMQ18 | DCR-197 | Legacy sub-ledgers and GL | R08, G01; DM1-A; accounting rules | M1 (16 Oct 2026) | Head, Comptrollership |
| DMQ19 | DCR-198, DCR-206 | DPPR | FR-DM-070 rules | M2 (30 Oct 2026) | Head, Comptrollership |
| DMQ20 | - | PR2307 reversal | FR-DM-071 rules | M2 (30 Oct 2026) | Head, Comptrollership |
| DMQ21 | - | Remittance positions | F04 decision | M2 (30 Oct 2026) | Operations - Remittance |
| DMQ22 | DCR-194 | Endorsement coexistence | P01 condition; DM2-A | M1 (16 Oct 2026) | Head, Operations |
| DMQ23 | - | Legacy change report | FR-DM-100 report | M2 (30 Oct 2026) | Operations - Prod Recon |
| DMQ24 | DCR-209 | Read-only legacy or archive | H01, H02, C04; DM2-B | M2 (30 Oct 2026) | Audit / Compliance; BDOI IT |
| DMQ25 | DCR-200, DCR-242 | Cutover date and window | Whole calendar; runbook | M1 (16 Oct 2026) (month), M6 (1 Oct 2027) (date) | Program Manager |
| DMQ26 | DCR-199, DCR-240 | RMEL transition | P03; Renewal build | M1 (16 Oct 2026) | Heads, Retail and Corporate Marketing |
| DMQ27 | - | Decommissioning criteria | Decommissioning checklists | M6 (1 Oct 2027) | Program Manager; BDOI IT |
| DMQ28 | DCR-193 | Volumes and quality | Register volumes; performance test | M3 (29 Jan 2027) | BDOI IT |
| DMQ29 | DCR-193 | Consolidated NFR | NFR targets | M2 (30 Oct 2026) | Program Manager |
| DMQ30 | DCR-196 | Objects not in the BRD | R09, P04, P05, F06, F07 | M1 (16 Oct 2026) | Program Manager |
| DMQ31 | DCR-200 | Rehearsals and test data | Migration cycles | M2 (30 Oct 2026) | Program Manager; Compliance |
| DMQ32 | DCR-200 | Fallback | Runbook rollback | M6 (1 Oct 2027) | Program Manager |
| DMQ33 | DCR-200 | In-flight items at the freeze | F06; freeze plan | M2 (30 Oct 2026) | Head, Operations |
| DMQ34 | DCR-203 | Collection history | F03 | M2 (30 Oct 2026) | Head, Operations (Collections) |
| DCR-202 | DCR-202 | Write-back to legacy | C01 deltas; CSF ContactSyncGateway | M1 (16 Oct 2026) | Product Owner, MBS |
| DMQ35 | - | Foreign currency | F01, F02, G01 | M2 (30 Oct 2026) | Head, Comptrollership |
| DMQ36 | DCR-241 | Package remapping | R06, P01, P03; PACKAGE map; DM1-C | M1 (16 Oct 2026) | Product Owner, MBS; TSU |
| DMQ37 | DCR-199, DCR-240 | January-May 2028 renewals | P03; Renewal carried candidates and catch-up extraction | M1 (16 Oct 2026) | Heads, Retail and Corporate Marketing |
| DMQ38 | DCR-243 | RMEL and disposition sources | P03 layout; Mock 1 data | M2 (30 Oct 2026) | Heads, Retail and Corporate Marketing; BDOI IT |
| DMQ39 | DCR-242 | Year-end cut-over | Runbook calendar; G01 | M6 (1 Oct 2027) | Program Manager; Head of Comptrollership |

# 16 Timeline

## 16.1 Alignment with the BDOI timeline

The migration timeline follows the BDOI drop plan and timeline (R9): Drop 0 "Setup & Data Migration", go-live January 2028 (DMQ25), proposed Monday 3 January 2028 (DMQ39). It ties into the build of the migration module and into the UAT readiness programme (R7) as follows.

Table 36: Migration timeline on the BDOI calendar

| When (BDOI timeline stream) | Migration step | Link to build and UAT readiness |
| --- | --- | --- |
| 26 Sep 2026 (M0) | This document set issued (version 1.1 on the BDOI calendar) | FRS BRD-13 v1.1 under review |
| 16 Oct 2026 (M1) - requirements and mapping | Build-shaping decisions answered, including package remapping (DMQ36) and the January-May 2028 renewals (DMQ37) | Needed before the build waves start |
| 30 Oct 2026 (M2) - requirements and mapping | Owners, stewards, keys, remaining rules; object decisions signed (G1); layouts frozen, version 1 | Build starts in November 2026 on agreed layouts; migration test plan cases finalised |
| Nov 2026 to Mar 2027 - build | Build waves in mock order: DM0 and DM1-C first, then DM1-A, DM1-B, DM2-A, DM2-B; DM3 | DM0 and DM1-C on SIT by 9 Apr 2027; the rest by 18 Jun 2027 |
| 29 Jan 2027 (M3) | First full extracts with volumes; profiling | DM3 performance harness sized from the volumes |
| 9 Apr 2027 (M4) - SIT migration | Extracts for Mock 1 | - |
| 19-30 Apr 2027 - SIT migration | Mock 1 on SIT: reference data and clients first, then headers and carried renewals | Drop 1 SIT (Renewal first) tests on migrated clients and reference data |
| 18 Jun 2027 (M5) | Code maps approved for Mock 2, including PACKAGE | - |
| 5-16 Jul 2027 - SIT migration | Mock 2 on SIT, all objects, L1-L5 | Provides the "data migration dry run with reconciliation" of UAT readiness item 11 |
| 2-13 Aug 2027 - UAT migration | Mock 3 = UAT load | UAT readiness statement issued; the Drop 1 end-to-end UAT (Aug-Dec 2027) runs on migrated data |
| 1 Oct 2027 (M6) | Cut-over date and window, fallback and decommissioning criteria agreed | - |
| 4-15 Oct 2027 - UAT migration | Mock 4 = UAT refresh, timed as a cut-over, with the carried January-May 2028 cohorts | Business owners verify migrated data during UAT |
| 15-26 Nov 2027 - full migration and cut-over; performance test | Dress rehearsal on the production-sized environment (reserve 6-10 Dec 2027) | Performance and penetration test Nov-Dec 2027 |
| 4 Dec 2027 (T-30) to 3 Jan 2028 (T) - full migration and cut-over; ORR / PRR | Production cutover (Cutover Runbook): pre-load from 20 Dec, freeze 31 Dec 22:00, load 1 Jan, go / no-go 2 Jan 18:00 | ORR / PRR Dec 2027-Jan 2028; production release frozen from T-7 |
| 3 Jan 2028 (T) to the January month-end close | Hypercare; carried renewals placed and booked in BIBS | Production support runbook (deliverable 24) |
| Run-off (about 12-15 months) | Monthly run-off tracking; archive loads; decommissioning | - |

The plan has no slack between the build and Mock 1: if DM0 and DM1-C are not on SIT by 9 April 2027, Mock 1 moves within the SIT migration window (to May 2027) and Mock 2 stays in July; the reserve slot of the dress rehearsal (6-10 December 2027) is the last buffer before the cut-over.

# Glossary

| Term | Meaning |
| --- | --- |
| AR | Acknowledgment Receipt, issued for premium collected on behalf of an insurer |
| Archive | Read-only store of legacy history in BIBS, searched in Legacy Inquiry (BRID 11.1) |
| Carry forward | Treatment of an open operational or financial item that continues to be processed in BIBS |
| CMS | Collection Management System (legacy) |
| Code map | Versioned table that maps a legacy code of a source system to a BIBS code (BRID 3.1) |
| Cohort | The legacy policies expiring in one month (RMEL expiry month) |
| Control file | File sent with each extract with its row count, hash total, amount totals and SHA-256 |
| DPPR | Direct-payment premium receivable (reading to be confirmed, DMQ19) |
| DTIP | Due to Insurer - Premium |
| EBIX | Legacy booking, receivables and accounting system |
| Freeze | The time from which legacy data may no longer change (T-3 22:00; 31 December 2027 for the proposed date) |
| G1-G7 | Sign-off gates of a data object - decision, mapping, validation, load, reconciliation, acceptance, go-live |
| Go / no-go | The decision to go live, taken on measured criteria |
| ISYS | Legacy reporting system (claims and ACSL reports, Marketing Diary) |
| Layout | The field list of one extract file (a sheet of the workbook and a CSV template) |
| Legacy invoice | Invoice booked in EBIX or QPS before go-live and still open at the freeze, processed in BIBS |
| Legacy sub-ledger | Legacy control accounts and ledger items that hold the legacy positions apart from the new ones |
| Migration Clearing | GL account that takes the offset of every opening entry; must net to 0.00 |
| Mock | Rehearsal of the migration on a test environment with masked data |
| OTC | Over-the-counter payment |
| PR | Premium receivable |
| PR2307 | Premium receivable covered by the client's BIR Form 2307 |
| QPS | Legacy quotation, client and policy system |
| RMEL | Renewal Master Expiry List |
| Run-off | The period in which legacy policies expire and renew into BIBS |
| Staging | Temporary area in BIBS where extract rows are checked, mapped and validated before load |
| T | Go-live date - January 2028 (BDOI timeline), proposed Monday 3 January 2028 |
| UPP | Unapplied premium payment |
| Xref | Key cross-reference from a legacy key to the BIBS record created from it |

# Sign-off

By signing, BDOI approves the approach of this document and the proposed decisions per data object, subject to the open decisions of chapter 15, whose answers are applied through the object register, the code maps and the configuration.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services | BDO Unibank ESG |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Head, Operations | BDOI |  |  |
|  | Product Owner, Marketing Business System | BDOI |  |  |
|  | Head, Retail Marketing; Head, Corporate Marketing | BDOI |  |  |
|  | Compliance | BDOI |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |