## Cover
DOCUMENT REGISTER
Document Register
Current documents of BRD-11, BRD-03, BRD-06 and BRD-02 and the programme documents
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 16 Oct 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | One row per current document; standard documents not yet issued are listed as To be issued. Older versions are not kept. | 65
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Document Register, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | BRD
Register | Type
Register | Document
Register | File name
Register | Format
Register | Version
Register | Date
Register | Owner (BDOI)
Register | Prepared by
Register | Status |  | Issued for BDOI review, Signed off, To be issued, Superseded

## Register
Register
One row per current document; standard documents not yet issued are listed as To be issued. Older versions are not kept.
BRD | Type | Document | File name | Format | Version | Date | Owner (BDOI) | Prepared by | Status
BRD-11 | BPS | User Access Process and Storyboards | BIBS_BPS-BDOI_BRD-11_User_Access_Process_and_Storyboards_v1.6 | DOCX | 1.6 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | CR | Change Request Register | BIBS_CR_BRD-11_Change_Request_Register_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | CR | Effort Estimate | BIBS_CR_BRD-11_Effort_Estimate_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | DDI | User Access Data Dictionary | BIBS_DDI-BDOI_BRD-11_User_Access_Data_Dictionary_v1.0 | XLSX | 1.0 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | DSP | User Access Developer Specification | BIBS_DSP-BDOI_BRD-11_User_Access_Developer_Specification_v1.0 | DOCX | 1.0 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | FRS | User Access Maintenance | BIBS_FRS-BDOI_BRD-11_User_Access_Maintenance_v1.6 | DOCX | 1.6 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | FitGap | BRD vs OOTB vs Best Practice | BIBS_FitGap_BRD-11_BRD_vs_OOTB_vs_Best_Practice_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | ICD | Interface Test Pack | BIBS_ICD-BDOI_BRD-11_Interface_Test_Pack_v1.1 | XLSX | 1.1 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | ICD | SCIM OpenAPI | BIBS_ICD-BDOI_BRD-11_SCIM_OpenAPI_v1.1 | YAML | 1.1 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | ICD | User Access Interface Specification | BIBS_ICD-BDOI_BRD-11_User_Access_Interface_Specification_v1.1 | DOCX | 1.1 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | Inputs | Business Unit Requirements Collection | BIBS_Inputs_BRD-11_Business_Unit_Requirements_Collection_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | README | How to Read this Pack | BIBS_Inputs_BRD-11_How_to_Read_this_Pack_v1.0 | DOCX | 1.0 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | RNO | User Access Reports Notifications Outputs | BIBS_RNO-BDOI_BRD-11_User_Access_Reports_Notifications_Outputs_v1.6 | DOCX | 1.6 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | RTM | Test Cases and Traceability | BIBS_RTM_BRD-11_Test_Cases_and_Traceability_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | UAT | Business Unit Walkthrough Users | BIBS_UAT_BRD-11_Business_Unit_Walkthrough_Users_v1.3 | XLSX | 1.3 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | USR | User Access User Stories | BIBS_USR-BDOI_BRD-11_User_Access_User_Stories_v1.0 | XLSX | 1.0 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-11 | UXD | User Access UX Design | BIBS_UXD-BDOI_BRD-11_User_Access_UX_Design_v1.6 | DOCX | 1.6 | 16 Oct 2026 | BDOI Product Owner, User Access | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | CR | Change Request Register | BIBS_CR_BRD-03_Change_Request_Register_v1.0 | XLSX | 1.0 | 09 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | CR | Effort Estimate | BIBS_CR_BRD-03_Effort_Estimate_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | FRS | Product Maintenance | BIBS_FRS-BDOI_BRD-03_Product_Maintenance_v1.3 | DOCX | 1.3 | 11 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | FRS | Product Maintenance (changes highlighted) | BIBS_FRS-BDOI_BRD-03_Product_Maintenance_v1.3_Changes_Highlighted | DOCX | 1.3 | 11 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | FitGap | BRD vs OOTB vs Best Practice | BIBS_FitGap_BRD-03_BRD_vs_OOTB_vs_Best_Practice_v1.0 | XLSX | 1.0 | 09 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | Inputs | Business Unit Requirements Collection | BIBS_Inputs_BRD-03_Business_Unit_Requirements_Collection_v1.0 | XLSX | 1.0 | 09 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | RTM | Test Cases and Traceability | BIBS_RTM_BRD-03_Test_Cases_and_Traceability_v1.0 | XLSX | 1.0 | 09 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | UAT | Business Unit Walkthrough Users | BIBS_UAT_BRD-03_Business_Unit_Walkthrough_Users_v1.0 | XLSX | 1.0 | 09 Oct 2026 | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | Issued for BDOI review
BRD-03 | README | How to read this pack | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | BPS | Business Process and Storyboards | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | UXD | UX Design Specification | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | RNO | Reports, Notifications and Outputs | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | DSP | Developer Specification | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | DDI | Data Dictionary | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-03 | USR | User Stories | - | - | - | - | BDOI Product Owner, Product Maintenance | iorta TechNXT Project Team | To be issued
BRD-06 | CR | Change Request Register | BIBS_CR_BRD-06_Change_Request_Register_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | CR | Effort Estimate | BIBS_CR_BRD-06_Effort_Estimate_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | FRS | Renewal | BIBS_FRS-BDOI_BRD-06_Renewal_v1.2 | DOCX | 1.2 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | FRS | Renewal (changes highlighted) | BIBS_FRS-BDOI_BRD-06_Renewal_v1.2_Changes_Highlighted | DOCX | 1.2 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | FitGap | BRD vs OOTB vs Best Practice | BIBS_FitGap_BRD-06_BRD_vs_OOTB_vs_Best_Practice_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | Inputs | Business Unit Requirements Collection | BIBS_Inputs_BRD-06_Business_Unit_Requirements_Collection_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | RTM | Test Cases and Traceability | BIBS_RTM_BRD-06_Test_Cases_and_Traceability_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | UAT | Business Unit Walkthrough Users | BIBS_UAT_BRD-06_Business_Unit_Walkthrough_Users_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Renewal | iorta TechNXT Project Team | Issued for BDOI review
BRD-06 | README | How to read this pack | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | BPS | Business Process and Storyboards | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | UXD | UX Design Specification | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | RNO | Reports, Notifications and Outputs | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | DSP | Developer Specification | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | DDI | Data Dictionary | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-06 | USR | User Stories | - | - | - | - | BDOI Product Owner, Renewal | iorta TechNXT Project Team | To be issued
BRD-02 | CR | Change Request Register | BIBS_CR_BRD-02_Change_Request_Register_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | CR | Effort Estimate | BIBS_CR_BRD-02_Effort_Estimate_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | FRS | Operations Cashiering | BIBS_FRS-BDOI_BRD-02_Operations_Cashiering_v3.3 | DOCX | 3.3 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | FRS | Operations Cashiering (changes highlighted) | BIBS_FRS-BDOI_BRD-02_Operations_Cashiering_v3.3_Changes_Highlighted | DOCX | 3.3 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | FitGap | BRD vs OOTB vs Best Practice | BIBS_FitGap_BRD-02_BRD_vs_OOTB_vs_Best_Practice_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | Inputs | Business Unit Requirements Collection | BIBS_Inputs_BRD-02_Business_Unit_Requirements_Collection_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | RTM | Test Cases and Traceability | BIBS_RTM_BRD-02_Test_Cases_and_Traceability_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | UAT | Business Unit Walkthrough Users | BIBS_UAT_BRD-02_Business_Unit_Walkthrough_Users_v1.0 | XLSX | 1.0 | 11 Oct 2026 | BDOI Product Owner, Operations | iorta TechNXT Project Team | Issued for BDOI review
BRD-02 | README | How to read this pack | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | BPS | Business Process and Storyboards | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | UXD | UX Design Specification | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | RNO | Reports, Notifications and Outputs | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | DSP | Developer Specification | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | DDI | Data Dictionary | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
BRD-02 | USR | User Stories | - | - | - | - | BDOI Product Owner, Operations | iorta TechNXT Project Team | To be issued
Programme | NFR | Non Functional and Security Requirements | BIBS_NFR_BRD-00_Non_Functional_and_Security_Requirements_v2.0 | DOCX | 2.0 | 16 Oct 2026 | BIBS Product Owner | iorta TechNXT Project Team | Issued for BDOI review
Programme | Glossary | Programme Glossary | BIBS_Glossary_BRD-00_Programme_Glossary_v1.0 | XLSX | 1.0 | 16 Oct 2026 | BIBS Product Owner | iorta TechNXT Project Team | Issued for BDOI review
Programme | Log | Decision and Observation Log | BIBS_Log_BRD-00_Decision_and_Observation_Log_v1.0 | XLSX | 1.0 | 16 Oct 2026 | BIBS Product Owner | iorta TechNXT Project Team | Issued for BDOI review

## Lists
Status
Issued for BDOI review
Signed off
To be issued
Superseded