## Cover
CHANGE CONTROL
CR Effort Estimate
User Access Maintenance; goes with the FRS User Access Maintenance v1.6
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.3
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Effort | Man-days of 8 hours, plus or minus 20 percent, for the open change requests only. | 3
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
CR Effort Estimate, version 1.3. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Effort | CR
Effort | Title
Effort | Analysis and design
Effort | Backend
Effort | Frontend
Effort | Testing
Effort | Documentation and UAT
Effort | Total

## Effort
Effort
Man-days of 8 hours, plus or minus 20 percent, for the open change requests only.
CR | Title | Analysis and design | Backend | Frontend | Testing | Documentation and UAT | Total
CR-UA-007 | Data access by company and branch | 1.5 | 5 | 2 | 3 | 1 | 12.5
CR-UA-016 | Emergency direct edit of group profiles | 1 | 2.5 | 1 | 1.5 | 0.5 | 6.5
Total | Open change requests | 2.5 | 7.5 | 3 | 4.5 | 1.5 | 19