## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
BRD-06 Renewal - what the Business Unit provides for the FRS v1.2
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Start here | Start here – BRD-06 Renewal: what the Business Unit provides | 10
Documents and print formats | Documents and print formats – BRD-06 Renewal | 24
E-mail wordings | E-mail wordings – BRD-06 Renewal | 45
Schedules and timings | Schedules and timings – BRD-06 Renewal | 11
Parameters and thresholds | Parameters and thresholds – BRD-06 Renewal | 22
Lists of values | Lists of values – BRD-06 Renewal | 11
Master and reference data | Master and reference data – BRD-06 Renewal | 16
Approvers and users per role | Approvers and users per role – BRD-06 Renewal | 13
Integration inputs (BDOI IT) | Integration inputs (BDOI IT) – BRD-06 Renewal | 14
Open decisions | Open decisions – BRD-06 Renewal | 23
Questions and comments | Questions and comments | 0
Fill in the column BU response and set the Status of each row; questions go to the sheet Questions and comments. Items keep the IDs of the BDOI Requirements and Inputs by BRD v1.2 workbook where they exist.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Start here | No.
Start here | Sheet
Start here | Content
Start here | Owner
Start here | First due
Start here | Rows
Start here | Rows open
Start here | Status
Start here | Go to
Documents and print formats | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Documents and print formats | Item | What the item is about
Documents and print formats | BRD ID | BRD requirement the item serves
Documents and print formats | FRS reference | FR item or annex of the FRS v1.2
Documents and print formats | What is needed | What the Business Unit provides or decides
Documents and print formats | Format of the answer | How to answer
Documents and print formats | Example | An example of an answer
Documents and print formats | Provided by (role) | Role that answers
Documents and print formats | Needed by | Date of the drop plan
Documents and print formats | BU response | The answer of the Business Unit
Documents and print formats | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
E-mail wordings | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
E-mail wordings | Item | What the item is about
E-mail wordings | BRD ID | BRD requirement the item serves
E-mail wordings | FRS reference | FR item or annex of the FRS v1.2
E-mail wordings | What is needed | What the Business Unit provides or decides
E-mail wordings | Format of the answer | How to answer
E-mail wordings | Example | An example of an answer
E-mail wordings | Provided by (role) | Role that answers
E-mail wordings | Needed by | Date of the drop plan
E-mail wordings | BU response | The answer of the Business Unit
E-mail wordings | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Schedules and timings | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Schedules and timings | Item | What the item is about
Schedules and timings | BRD ID | BRD requirement the item serves
Schedules and timings | FRS reference | FR item or annex of the FRS v1.2
Schedules and timings | What is needed | What the Business Unit provides or decides
Schedules and timings | Format of the answer | How to answer
Schedules and timings | Example | An example of an answer
Schedules and timings | Provided by (role) | Role that answers
Schedules and timings | Needed by | Date of the drop plan
Schedules and timings | BU response | The answer of the Business Unit
Schedules and timings | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Parameters and thresholds | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Parameters and thresholds | Item | What the item is about
Parameters and thresholds | BRD ID | BRD requirement the item serves
Parameters and thresholds | FRS reference | FR item or annex of the FRS v1.2
Parameters and thresholds | What is needed | What the Business Unit provides or decides
Parameters and thresholds | Format of the answer | How to answer
Parameters and thresholds | Example | An example of an answer
Parameters and thresholds | Provided by (role) | Role that answers
Parameters and thresholds | Needed by | Date of the drop plan
Parameters and thresholds | BU response | The answer of the Business Unit
Parameters and thresholds | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Lists of values | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Lists of values | Item | What the item is about
Lists of values | BRD ID | BRD requirement the item serves
Lists of values | FRS reference | FR item or annex of the FRS v1.2
Lists of values | What is needed | What the Business Unit provides or decides
Lists of values | Format of the answer | How to answer
Lists of values | Example | An example of an answer
Lists of values | Provided by (role) | Role that answers
Lists of values | Needed by | Date of the drop plan
Lists of values | BU response | The answer of the Business Unit
Lists of values | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Master and reference data | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Master and reference data | Item | What the item is about
Master and reference data | BRD ID | BRD requirement the item serves
Master and reference data | FRS reference | FR item or annex of the FRS v1.2
Master and reference data | What is needed | What the Business Unit provides or decides
Master and reference data | Format of the answer | How to answer
Master and reference data | Example | An example of an answer
Master and reference data | Provided by (role) | Role that answers
Master and reference data | Needed by | Date of the drop plan
Master and reference data | BU response | The answer of the Business Unit
Master and reference data | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Approvers and users per role | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Approvers and users per role | Item | What the item is about
Approvers and users per role | BRD ID | BRD requirement the item serves
Approvers and users per role | FRS reference | FR item or annex of the FRS v1.2
Approvers and users per role | What is needed | What the Business Unit provides or decides
Approvers and users per role | Format of the answer | How to answer
Approvers and users per role | Example | An example of an answer
Approvers and users per role | Provided by (role) | Role that answers
Approvers and users per role | Needed by | Date of the drop plan
Approvers and users per role | BU response | The answer of the Business Unit
Approvers and users per role | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Integration inputs (BDOI IT) | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Integration inputs (BDOI IT) | Item | What the item is about
Integration inputs (BDOI IT) | BRD ID | BRD requirement the item serves
Integration inputs (BDOI IT) | FRS reference | FR item or annex of the FRS v1.2
Integration inputs (BDOI IT) | What is needed | What the Business Unit provides or decides
Integration inputs (BDOI IT) | Format of the answer | How to answer
Integration inputs (BDOI IT) | Example | An example of an answer
Integration inputs (BDOI IT) | Provided by (role) | Role that answers
Integration inputs (BDOI IT) | Needed by | Date of the drop plan
Integration inputs (BDOI IT) | BU response | The answer of the Business Unit
Integration inputs (BDOI IT) | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Open decisions | ID | Reference of the item (kept from the BDOI inputs workbook where it exists)
Open decisions | Item | What the item is about
Open decisions | BRD ID | BRD requirement the item serves
Open decisions | FRS reference | FR item or annex of the FRS v1.2
Open decisions | What is needed | What the Business Unit provides or decides
Open decisions | Format of the answer | How to answer
Open decisions | Example | An example of an answer
Open decisions | Provided by (role) | Role that answers
Open decisions | Needed by | Date of the drop plan
Open decisions | BU response | The answer of the Business Unit
Open decisions | Status | Open until answered; Received; Confirmed by the project | Open, Received, Confirmed
Questions and comments | No. | Running number
Questions and comments | Item or section | ID of the item, or FRS section / annex
Questions and comments | Question or comment | The question or comment
Questions and comments | Raised by | Name and role
Questions and comments | Date | Date raised
Questions and comments | Answer of the project | Filled in by iorta TechNXT
Questions and comments | Status | Open, Received, Confirmed | Open, Received, Confirmed

## Start here
Start here – BRD-06 Renewal: what the Business Unit provides
Fill in the sheets in this order (decisions and lists first, then data). Each sheet is self-contained: title block, column guide above the header, an example row to overwrite. Rows open: the formula counts the rows still Open.
No. | Sheet | Content | Owner | First due | Rows | Rows open | Status | Go to
1 | Documents and print formats | 24 items | Product Owner, Renewal | 30-Nov-2026 | 24 |  | Not started | Open →
2 | E-mail wordings | 45 items | Product Owner, Renewal; Compliance | 30-Nov-2026 | 45 |  | Not started | Open →
3 | Schedules and timings | 11 items | Product Owner, Renewal; BDOI IT | 16-Jul-2027 | 11 |  | Not started | Open →
4 | Parameters and thresholds | 22 items | Product Owner, Renewal | 30-Nov-2026 | 22 |  | Not started | Open →
5 | Lists of values | 11 items | Business Administrator | 31-Jan-2027 | 11 |  | Not started | Open →
6 | Master and reference data | 16 items | Product Owner, Renewal; Business Administrator | 31-Jan-2027 | 16 |  | Not started | Open →
7 | Approvers and users per role | 13 items | Product Owner, Renewal; PMO | 30-Nov-2026 | 13 |  | Not started | Open →
8 | Integration inputs (BDOI IT) | 14 items | BDOI IT | 31-Jan-2027 | 14 |  | Not started | Open →
9 | Open decisions | 23 items | Product Owner, Renewal | 30-Nov-2026 | 23 |  | Not started | Open →
10 | Questions and comments | Questions of the Business Unit on any item | Any reviewer |  | 0 |  | Not started | Open →

## Documents and print formats
Documents and print formats – BRD-06 Renewal
Purpose | Items of the kind 'Documents and print formats' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-DOC-01 | Renewal Advice (first and second notice) | BRRN.010 | Annex AF (DO-01) | Confirm the layout of the Renewal Advice (first and second notice) shown in Annex AF, or give the layout. BDOI reference: Annex L: approved templates BDOI-005 to BDOI-008, one per line (Motor, PAR CLG, PAR Non-CLG, Other Lines) - they prevail. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 | Confirmed as in Annex AF | Received
RC-DOC-01 | Renewal Advice (first and second notice) | BRRN.010 | Annex AF (DO-01) | Confirm the layout of the Renewal Advice (first and second notice) shown in Annex AF, or give the layout. BDOI reference: Annex L: approved templates BDOI-005 to BDOI-008, one per line (Motor, PAR CLG, PAR Non-CLG, Other Lines) - they prevail. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-02 | Not for Renewal Letter and No Advice Letter | BRD 1.003 / 3.009 | Annex AF (DO-02) | Confirm the layout of the Not for Renewal Letter and No Advice Letter shown in Annex AF, or give the layout. BDOI reference: Annexes O and P: heading only - layout to be provided. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-03 | Insurer extract | BRD 1.003 / 3.009 | Annex AF (DO-03) | Confirm the layout of the Insurer extract shown in Annex AF, or give the layout. BDOI reference: FRRN.021 lets the user choose the fields; Annex H gives the CBG return layout. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-04 | Expiry list download | BRD 1.003 / 3.009 | Annex AF (DO-04) | Confirm the layout of the Expiry list download shown in Annex AF, or give the layout. BDOI reference: FRRN.004.06: file name RMEL_<MMM>_<YYYY>_<MMDDYYYY>.xlsx. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-05 | Renewal account details | BRD 1.003 / 3.009 | Annex AF (DO-05) | Confirm the layout of the Renewal account details shown in Annex AF, or give the layout. BDOI reference: FRRN.014.06: Renewal Account Details.xlsx. | Confirm, or a sample (Excel or PDF) with the fields in order | Confirmed as in Annex AF | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-06 | Quick Proposal and Full Proposal | BRRN.010 | Annex AF (DO-06) | Give the layout and wording of: Proposal of a For Proposal renewal (FRRN.017.01). BDOI reference: Annexes I and J: heading only. | Template (Word or PDF) with the fields in order | Template attached | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-07 | TSU quotation request | BRRN.010 | Annex AF (DO-07) | Confirm BDOI's template of this FRS for: Request of a For Quotation renewal to TSU (FRRN.018.01). BDOI reference: Annex K: given (14 lines). | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-08 | NRNS reminder, SFU and FFY reminder letters | BRRN.010 | Annex AF (DO-08) | Give the layout and wording of: Reminders before expiry (FRRN.023.03, FRRN.048.01). BDOI reference: Annexes N, Q and R: heading only. | Template (Word or PDF) with the fields in order | Template attached | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-09 | Non-acceptance letter | BRRN.010 | Annex AF (DO-09) | Give the layout and wording of: Tell the client that the policy expired without renewal (FRRN.023.03). BDOI reference: Not in BDOI's FRS (row added to Annex M). | Template (Word or PDF) with the fields in order | Template attached | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-10 | CLPC billing file and e-mail | BRRN.010 | Annex AF (DO-10) | Confirm BDOI's template of this FRS for: Billing of CBG Home and FFY Motor renewals (FRRN.027). BDOI reference: Annex S: given (form BFP-001-2026-0). | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-11 | Placement slip and placement file | BRRN.040 | Annex AF (DO-11) | Confirm BDOI's template of this FRS for: Placement with the insurer (FRRN.029.02). BDOI reference: Annex T: heading only (slip); Annex U: given (file). | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-12 | Insurance Advice | BRRN.010 | Annex AF (DO-12) | Confirm BDOI's template of this FRS for: Advice to the mortgagee bank (FRRN.032). BDOI reference: Annex W: given. | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-13 | E-policy e-mail | BRRN.010 | Annex AF (DO-13) | Confirm BDOI's template of this FRS for: Sending of the e-policy to the client (FRRN.033.04). BDOI reference: Annex X: given. | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-14 | Service invoice | BRRN.010 | Annex AF (DO-14) | Confirm BDOI's template of this FRS for: Invoice of the brokerage service on booking (FRRN.035). BDOI reference: Annex Y: given (image). | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-15 | Hold cover request | BRRN.010 | Annex AF (DO-15) | Give the layout and wording of: Request of a hold cover or extension (FRRN.036). BDOI reference: Annex Z: heading only. | Template (Word or PDF) with the fields in order | Template attached | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DOC-16 | Upload results and exports of lists | BRRN.010 | Annex AF (DO-16) | Confirm BDOI's template of this FRS for: Processing results of the LAMD, BDOFC/SOLD, insurer disposition, renewal update, hold cover and e-policy uploads; audit log export. BDOI reference: File names given (FRRN.012.03, 012.08, 043.01). | Confirm | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-RPT-01 | CLPC Billing Reports (Non-Built-In FIP; Built-In HLS Amortized and Non-Built-In; HLS Amortized Loan Release) | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report CLPC Billing Reports (Non-Built-In FIP; Built-In HLS Amortized and Non-Built-In; HLS Amortized Loan Release). | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
RC-RPT-02 | Successful and Fall-Out Accounts per Stage | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report Successful and Fall-Out Accounts per Stage. | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
RC-RPT-03 | Successfully and Unsuccessfully Sent ePolicy | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report Successfully and Unsuccessfully Sent ePolicy. | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
RC-RPT-04 | Accounts without Policy Number | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report Accounts without Policy Number. | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
RC-RPT-05 | Unapplied Payment Report with Disposition | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report Unapplied Payment Report with Disposition. | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
RC-RPT-06 | LAMD reconciliation reports (Tagged as RMU; RMU without booking; not RMU with booking; tagged as submitted; not RMU and no submitted record) | BRRN.019 | FRRN.044.01; Annex AG | Give the columns, filters, sort and output of the report LAMD reconciliation reports (Tagged as RMU; RMU without booking; not RMU with booking; tagged as submitted; not RMU and no submitted record). | Columns in order; filters; Excel or PDF | Account, status, premium; by month | Marketing and Processing Heads | 30-Nov-2026 |  | Open
DOC-08 | Documents of Renewal | BRRN.010 | Annex AF | Documents of Renewal: give the BDOI layout, logo placement and wording of the 10 documents the system generates (Renewal account details - [renewal ref]; Renewals for your decision - batch [batch no]; Notice on your policy [policy no]; Your policy [policy no] will not be renewed; Your policy [policy no] has expired; Reminder: renewal of your policy [policy no]; Renewal Advice (first year free) - [assured name] - policy [policy no]; Renewal Advice - [assured name] - policy [policy no]; Second notice: Renewal Advice - [assured name] - policy [policy no]; Follow-up on the renewal of your mortgaged property - policy [policy no]), as a filled-in sample of each. | Templates | - | Product Owner, Renewal | 16-Jul-2027 |  | Open
CLR-RN-25 | Insurer extract (28 columns) | BRD 3.009 | FRRN.025; Annex AF | Insurer extract: Confirm the 28 columns, or name the columns to keep on screen. | Confirm, or the columns to keep on screen | Confirmed | Product Owner, Renewal | 30-Nov-2026 |  | Open

## E-mail wordings
E-mail wordings – BRD-06 Renewal
Purpose | Items of the kind 'E-mail wordings' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal; Compliance
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: AE.01 | Account assigned to the Account Officer | BRD 1.005.1.2; 1.005.2 | Annex AE; FRRN.010.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> assigned to you. Text: Give the disposition of the renewal of <client>, expiring <expiry date> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 | Approved | Received
AE.01 | Account assigned to the Account Officer | BRD 1.005.1.2; 1.005.2 | Annex AE; FRRN.010.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> assigned to you. Text: Give the disposition of the renewal of <client>, expiring <expiry date> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.02 | Account assigned for processing | BRD 3.005.1 | Annex AE; FRRN.010.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> assigned to you for processing. Text: <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.03 | Account classified Exception | BRRN.023 | Annex AE; FRRN.008.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: Exception. Text: A check failed on the renewal of <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.04 | LAMD line applied to an account | BRRN.029, 039 | Annex AE; FRRN.012.02 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: LAMD loan fully paid, or <renewal reference>: LAMD loan under RMU. Text: Moved from <status> to <status>, or Checks run again; stage <status> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.05 | Transfer to another unit requested | BRD 1.006.5; 1.007.1 | Annex AE; FRRN.011.05, FRRN.011.06 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> transferred to your unit. Text: Accept or decline the renewal of <client>: <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.06 | Transfer accepted or declined | BRD 1.007.4, 1.007.5 | Annex AE; FRRN.011.05 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: transfer accepted, or <renewal reference>: transfer declined. Text: The transfer to <unit> was accepted, or The transfer to <unit> was declined: <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.07 | Account returned to the Account Officer | BRD 1.008.2; 2.007.1 | Annex AE; FRRN.020.02, FRRN.002.08 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> returned to you. Text: <return reason>: <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.08 | Account returned by Processing | BRD 3.008.2; 4.006.2 | Annex AE; FRRN.031.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> returned by Processing. Text: <return reason>: <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.09 | Account re-opened | BRD 2.004.10; 3.004.5 | Annex AE; FRRN.014.07 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> re-opened. Text: To the Account Officer - Give a new disposition: <reason>; to the Team Leads - <reason> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.10 | Account posted for processing | BRD 1.008.3 | Annex AE; FRRN.020.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> posted for processing. Text: <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.11 | Insurer disposition recorded | BRD 3.009.6; BRRN.035 | Annex AE; FRRN.013.02, FRRN.013.05 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: insurer response <disposition>. Text: Applied to the renewal, or Not applied: check the Insurer tab | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.12 | Client accepted the renewal | BRRN.040 | Annex AE; FRRN.025.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> accepted by the client. Text: <client> accepted the renewal by <method> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.13 | Renewal account ready for placement | BRRN.040 | Annex AE; FRRN.028.02, FRRN.029.02 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: ready for placement. Text: <n> placement slip(s) of <ARN> generated; send them from Placement | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.14 | Renewal booked | BRRN.040 | Annex AE; FRRN.035.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> renewed. Text: Booked with invoice <invoice no.> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.15 | Renewal closed, expired without renewal | BRRN.025, 037 | Annex AE; FRRN.023.03 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> closed: expired without renewal. Text: The policy of <client> expired on <date>; Operations sends the No Advice Letter, or The policy of <client> expired on <date>; the Account Officer sends the Non-Renewal Letter | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.16 | Go-live take-over completed | BRRN.005 | Annex AE; FRRN.045.01 | Approve the wording, the trigger and the recipients. Subject: Go-live renewals taken over (<n>). Text: <n> renewals, <n> urgent; by expiry month <month>: <count>, ... | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.17 | Package choice approved or rejected | BRRN.020 | Annex AE; FRRN.046.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: package choice approved, or <renewal reference>: package choice rejected. Text: <package version> applies to the renewal, or <package version> was rejected: <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.18 | Alert - extraction run failed | BRRN.030 | Annex AE; FRRN.004.04 | Approve the wording, the trigger and the recipients. Subject: Renewal extraction failed. Text: The renewal extraction of <date> failed: <reason> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.19 | Alert - insurer answer overdue | BRD 3.009.6 | Annex AE; FRRN.021 | Approve the wording, the trigger and the recipients. Subject: Insurer renewal batch overdue. Text: Insurer <insurer> has not answered batch <batch no.> due <date> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.20 | Alert - letter not delivered | BRRN.010 | Annex AE; FRRN.022.02, FRRN.023.02 | Approve the wording, the trigger and the recipients. Subject: Renewal letter not delivered. Text: Letter <letter no.> was not delivered: <error> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.21 | Alert - exception ageing | BRRN.029 (R29-05) | Annex AE; FRRN.008.01 | Approve the wording, the trigger and the recipients. Subject: Renewal exception ageing. Text: Renewal <renewal reference> is an Exception since <date> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.22 | Renewal Advice e-mail (first notice) | BRRN.010; BRD 1.010.7 | Annex AE; FRRN.022.01, FRRN.022.02 | Approve the wording, the trigger and the recipients. Subject: Renewal Advice - <assured name> - policy <policy no.>. Text: Dear <client name>, Your policy <policy no.> with <insurer name> expires on <expiry date>. We are pleased to offer its renewal for the period <renewal from> to <renewal to> on the following terms: Product: <product name> Sum insured: <currency> <sum insured> Renewal premium: <currency> <gross premium> To renew, please reply to this e-mail, sign and return this Renewal Advice, or pay the renewal premium on or before <expiry date>. Renewal reference: <renewal reference> Account officer: <account officer name> Thank you for your continued trust, BDO Insurance and Reinsurance Brokers, Inc. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.23 | Renewal Advice e-mail (second / last notice) | BRRN.010 | Annex AE; FRRN.022.01 | Approve the wording, the trigger and the recipients. Subject: Second notice: Renewal Advice - <assured name> - policy <policy no.>. Text: Dear <client name>, This is our second notice on the renewal of your policy <policy no.> with <insurer name>, which expires on <expiry date>. The renewal terms remain: Sum insured: <currency> <sum insured> Renewal premium: <currency> <gross premium> Please reply to this e-mail, sign and return this Renewal Advice, or pay the renewal premium on or before <expiry date> to keep your cover. Renewal reference: <renewal reference> Account officer: <account officer name> BDO Insurance and Reinsurance Brokers, Inc. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.24 | Password e-mail | BRRN.010; BRD 1.010.7.1 | Annex AE; FRRN.024.01, FRRN.022.02 | Approve the wording, the trigger and the recipients. Subject: Password for: <subject of the protected e-mail>. Text: The documents sent to you in the e-mail "<subject>" are password protected. Password: <password> This e-mail was sent separately for your security. Please do not forward it. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.25 | No Advice Letter e-mail | BRRN.001 | Annex AE; FRRN.023.01, FRRN.023.02 | Approve the wording, the trigger and the recipients. Subject: Notice on your policy <policy no.>. Text: Dear <client name>, This is to inform you that your policy <policy no.> with <insurer name>, expiring on <expiry date>, will not be renewed through BDO Insurance and Reinsurance Brokers, Inc. No further action is needed from you. Reference: <renewal reference> Account officer: <account officer name> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.26 | Non-Renewal Letter e-mail | BRRN.009, 037 | Annex AE; FRRN.023.02, FRRN.038.03 | Approve the wording, the trigger and the recipients. Subject: Your policy <policy no.> will not be renewed. Text: Dear <client name>, We regret to inform you that your policy <policy no.> with <insurer name>, expiring on <expiry date>, is not for renewal: <reason>. For questions, please contact your account officer <account officer name>. Reference: <renewal reference> BDO Insurance and Reinsurance Brokers, Inc. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.27 | NRNS reminder letter e-mail | BRRN.025 | Annex AE; FRRN.023.03 | Approve the wording, the trigger and the recipients. Subject: Reminder: renewal of your policy <policy no.>. Text: Dear <client name>, Your policy <policy no.> with <insurer name> expires on <expiry date> and its renewal has not been confirmed yet. Please contact your account officer <account officer name> to renew your cover. Reference: <renewal reference> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.28 | Non-acceptance letter e-mail | BRRN.025, 037 | Annex AE; FRRN.023.03 | Approve the wording, the trigger and the recipients. Subject: Your policy <policy no.> has expired. Text: Dear <client name>, Your policy <policy no.> with <insurer name> expired on <expiry date> without renewal, as we did not receive your acceptance of the Renewal Advice. Your property or risk is no longer covered by this policy. Please contact your account officer <account officer name> if you wish to be covered again. Reference: <renewal reference> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.29 | Renewal Advice of a free-first-year account (FFY) | BRRN.010 (submitted policies) | Annex AE; FRRN.048.01 | Approve the wording, the trigger and the recipients. Subject: Renewal Advice (first year free) - <assured name> - policy <policy no.>. Text: Dear <client name>, The first year of your policy <policy no.> with <insurer name> was free of charge and ends on <expiry date>. To keep your cover, we offer its renewal for the period <renewal from> to <renewal to>: Sum insured: <currency> <sum insured> Renewal premium: <currency> <gross premium> To renew, please sign and return this Renewal Advice, or pay the renewal premium on or before <expiry date>. Renewal reference: <renewal reference> Account officer: <account officer name> Thank you for your trust, BDO Insurance and Reinsurance Brokers, Inc. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.30 | SFU letter (mortgaged accounts) | BRRN.010 (submitted policies) | Annex AE; FRRN.048.01 | Approve the wording, the trigger and the recipients. Subject: Follow-up on the renewal of your mortgaged property - policy <policy no.>. Text: Dear <client name>, Your property is mortgaged to the bank and must stay insured. Your policy <policy no.> expires on <expiry date> and we have not received your answer to our Renewal Advice. Please sign and return the Renewal Advice, or pay the renewal premium, on or before <expiry date>. Renewal reference: <renewal reference> Account officer: <account officer name> Thank you, BDO Insurance and Reinsurance Brokers, Inc. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.31 | Request for renewal disposition to the insurer | BRD 3.009.5; 4.007.5 | Annex AE; FRRN.021 | Approve the wording, the trigger and the recipients. Subject: Renewals for your decision - batch <batch no.>. Text: Dear <insurer name>, Please find attached the policies expiring from <expiry from> to <expiry to> that we propose for renewal (<count> accounts). Please return the file with your decision on each account (Renew As Is, Revise or Reject) by <reply date>. BDO Insurance and Reinsurance Brokers, Inc. - Processing | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.32 | Hold cover request e-mail | BRRN.042 | Annex AE; FRRN.036.02, FRRN.036.06 | Approve the wording, the trigger and the recipients. Subject: Hold cover request - <ARN> - <client name>. Text: Please hold cover the risk below for thirty (30) days from <start date> under reference <reference> while the placement is being completed. Kindly confirm the hold cover and your reference number. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.33 | Step of the progression not completed | BRRN.040 | Annex AE; FRRN.028.02 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>. Text: <what could not be completed, as recorded in the remarks of the account> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.34 | Hold cover rejected by the insurer | BRRN.042 | Annex AE; FRRN.037.02 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: hold cover rejected by <insurer>. Text: <insurer's remarks>, or Rejected by the insurer | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.35 | Hold cover and placement files to the insurer | BRRN.042; BRRN.040 | Annex AE; FRRN.036.06; FRRN.29.04 | Approve the wording, the trigger and the recipients. Subject: <document type> - <file name>. Text: Please find attached <file name>. | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.36 | Placement not sent | BRRN.040 | Annex AE; FRRN.29.04 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> placement not sent. Text: Check the Channel Monitor | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.37 | Placement response received | BRRN.040 | Annex AE; FRRN.030.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> placement approved, or placement rejected. Text: <reason of the rejection> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.38 | Account submitted for posting | BRD 1.008.3 | Annex AE; FRRN.016.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> submitted for posting. Text: Approve the posting of the renewal of <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.39 | Transfer request received | BRD 1.006.5; 1.007.1 | Annex AE; FRRN.011.01; FRRN.011.05 | Approve the wording, the trigger and the recipients. Subject: <transfer request number>: transfer request for a New Business opportunity. Text: Review the transfer request of <client> from <unit>: <justification> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.40 | Transfer request decided | BRD 1.007.4, 1.007.5 | Annex AE; FRRN.011.05 | Approve the wording, the trigger and the recipients. Subject: <transfer request number>: <Accepted, Rejected or Returned for Clarification>. Text: Transfer request of <renewal reference> to <unit>: <outcome> - <remarks> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.41 | Direct-to-Insurer Payment to approve | BRRN.040 | Annex AE; FRRN.014.05 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: Direct-to-Insurer Payment to approve. Text: <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.42 | Direct-to-Insurer Payment decided | BRRN.040 | Annex AE; FRRN.014.05 | Approve the wording, the trigger and the recipients. Subject: <renewal reference>: Direct-to-Insurer Payment approved, or rejected. Text: <rejection reason> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.43 | Account returned for correction | BRRN.038 | Annex AE; FRRN.26.01 | Approve the wording, the trigger and the recipients. Subject: <renewal reference> returned for correction. Text: <reason of the return> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
AE.44 | TSU request to approve, assigned and updated | BRRN.033 | Annex AE; FRRN.018.01 | Approve the wording, the trigger and the recipients. Subject: <request number> pending your approval; <request number> assigned to you; <request number>: <Approved, Rejected or Returned>, For TSU Processing, comparative table updated, proposal completed by TSU. Text: <client> | Approve, or the new wording | Approved | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-EML-01 | Sender and footer of the e-mails | BRRN.010 | Annex AE | The sender address of each environment and the standard footer or disclaimer of BDOI e-mails. | Address per environment; footer text | renewals@ (domain of BDOI) | BDOI IT | 16-Jul-2027 |  | Open

## Schedules and timings
Schedules and timings – BRD-06 Renewal
Purpose | Items of the kind 'Schedules and timings' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal; BDOI IT
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-SCH-01 | Daily extraction | BRRN.030 | Annex AG; FRRN.004.04 | Confirm when it runs (Every day 01:00) and who is told: Alert to the administrators if it fails. | Time and recipients, or Confirm | Every day 01:00 | Product Owner, Renewal | 16-Jul-2027 | Every day 01:00 | Received
RC-SCH-01 | Daily extraction | BRRN.030 | Annex AG; FRRN.004.04 | Confirm when it runs (Every day 01:00) and who is told: Alert to the administrators if it fails. | Time and recipients, or Confirm | Every day 01:00 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-02 | Re-evaluation | BRRN.020 | Annex AG; FRRN.007.01 | Confirm when it runs (Every day 01:30) and who is told: Notice when an account turns Exception. | Time and recipients, or Confirm | Every day 01:30 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-03 | Letter run | BRRN.025, 037 | Annex AG; FRRN.023.03 | Confirm when it runs (Every day 06:00) and who is told: -. | Time and recipients, or Confirm | Every day 06:00 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-04 | Expiry sweep | BRRN.025 | Annex AG; FRRN.023.03 | Confirm when it runs (Every day 00:15) and who is told: Notice to the officers of the account. | Time and recipients, or Confirm | Every day 00:15 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-05 | Renewal alerts | BRRN.029 | Annex AG; FRRN.008.01, 021 | Confirm when it runs (Every day) and who is told: Administrators and Team Leads (alerts). | Time and recipients, or Confirm | Every day | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-06 | Attention flags | BRRN.036 | Annex AG; FRRN.044.03 | Confirm when it runs (Every day) and who is told: No message (BRRN.036). | Time and recipients, or Confirm | Every day | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-07 | CBG Home billing | FRRN.27.01 | Annex AG; FRRN.27.01 | Confirm when it runs (Every day) and who is told: -. | Time and recipients, or Confirm | Every day | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-08 | FFY Motor billing | FRRN.27.01 | Annex AG; FRRN.27.01 | Confirm when it runs (10th and 25th of the month) and who is told: -. | Time and recipients, or Confirm | 10th and 25th of the month | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-09 | CBG hold cover requests | FRRN.036.04 | Annex AG; FRRN.036.04 | Confirm when it runs (Every day (75 days before expiry)) and who is told: -. | Time and recipients, or Confirm | Every day (75 days before expiry) | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-10 | CBG Home hold cover extension | FRRN.036.05 | Annex AG; FRRN.036.05 | Confirm when it runs (15th of the month) and who is told: -. | Time and recipients, or Confirm | 15th of the month | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-SCH-11 | Go-live extraction | BRRN.005 | Annex AG; FRRN.045.01 | Confirm when it runs (Once, after the sign-off of the migration load) and who is told: Notice with the counts. | Time and recipients, or Confirm | Once, after the sign-off of the migration load | Product Owner, Renewal | 16-Jul-2027 |  | Open

## Parameters and thresholds
Parameters and thresholds – BRD-06 Renewal
Purpose | Items of the kind 'Parameters and thresholds' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-PAR-01 | Lead days of the daily extraction | BRRN.030 | Annex AC.7 | Confirm the value of lead days of the daily extraction. By default: 140 days; per market segment if given. | Value | 140 days; per market segment if given | Product Owner, Renewal | 16-Jul-2027 | 140 days; per market segment if given | Received
RC-PAR-01 | Lead days of the daily extraction | BRRN.030 | Annex AC.7 | Confirm the value of lead days of the daily extraction. By default: 140 days; per market segment if given. | Value | 140 days; per market segment if given | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-02 | Go-live take-over window | BRRN.005 | Annex AC.7 | Confirm the value of go-live take-over window. By default: From go-live to 31-May-2028; urgent up to 31-Jan-2028. | Value | From go-live to 31-May-2028; urgent up to 31-Jan-2028 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-03 | Segments initiated in bulk | BRRN.021 | Annex AC.7 | Confirm the value of segments initiated in bulk. By default: CLG. | Value | CLG | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-04 | TSI threshold | BRRN.020; SC-12 | Annex AC.7 | Confirm the value of tsi threshold. By default: PHP 250,000,000.00. | Value | PHP 250,000,000.00 | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-05 | Outstanding premium threshold | BRD 1.011 | Annex AC.7 | Confirm the value of outstanding premium threshold. By default: PHP 0.00 (any balance). | Value | PHP 0.00 (any balance) | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-06 | Financial-impact tolerance | BRRN.038 | Annex AC.7 | Confirm the value of financial-impact tolerance. By default: PHP 0.00 (any change). | Value | PHP 0.00 (any change) | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-07 | Renewal Advice first and last notice | BRRN.010 | Annex AC.7 | Confirm the value of renewal advice first and last notice. By default: 75 and 45 days before expiry (Annex M). | Value | 75 and 45 days before expiry (Annex M) | BDOI (given) | 16-Jul-2027 |  | Open
RC-PAR-08 | Late Renewal Advice warning | BRRN.010 | Annex AC.7 | Confirm the value of late renewal advice warning. By default: Less than 30 days before expiry. | Value | Less than 30 days before expiry | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-09 | NRNS reminder checkpoint | BRRN.025 | Annex AC.7 | Confirm the value of nrns reminder checkpoint. By default: 75 days before expiry (Annex M). | Value | 75 days before expiry (Annex M) | BDOI (given) | 16-Jul-2027 |  | Open
RC-PAR-10 | NRNS waiting days after the effective expiry date | BRRN.037 | Annex AC.7 | Confirm the value of nrns waiting days after the effective expiry date. By default: 0 days, per segment. | Value | 0 days, per segment | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-11 | Non-acceptance letter | BRRN.025 | Annex AC.7 | Confirm the value of non-acceptance letter. By default: On the effective expiry date (0 days). | Value | On the effective expiry date (0 days) | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-12 | No Advice Letter / Non-Renewal Letter | BRRN.001, 037 | Annex AC.7 | Confirm the value of no advice letter / non-renewal letter. By default: 1 day after expiry; Non-CBG Non-Renewal Letter 3 days (Annex M). | Value | 1 day after expiry; Non-CBG Non-Renewal Letter 3 days (Annex M) | BDOI (given) | 16-Jul-2027 |  | Open
RC-PAR-13 | Re-open of Not for Renewal | BRD 2.004.10 | Annex AC.7 | Confirm the value of re-open of not for renewal. By default: Until the expiry date plus 30 days. | Value | Until the expiry date plus 30 days | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-14 | Exception ageing alert | BRRN.029 (R29-05) | Annex AC.7 | Confirm the value of exception ageing alert. By default: 5 working days. | Value | 5 working days | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-15 | Attention flag (ageing) of the listing | BRRN.036 | Annex AC.7 | Confirm the value of attention flag (ageing) of the listing. By default: IBG 60, Leasing 60, others 30 days before expiry. | Value | IBG 60, Leasing 60, others 30 days before expiry | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-16 | Insurer reply days | BRD 3.009 | Annex AC.7 | Confirm the value of insurer reply days. By default: 10 days after sending. | Value | 10 days after sending | Product Owner, Renewal | 16-Jul-2027 |  | Open
RC-PAR-17 | Hold cover durations | BRRN.042 | Annex AC.7 | Confirm the value of hold cover durations. By default: Non-CBG 30, CBG 90; transferred CBG Home 30, CBG Motor 60 days (FRRN.036.01). | Value | Non-CBG 30, CBG 90; transferred CBG Home 30, CBG Motor 60 days (FRRN.036.01) | BDOI (given) | 16-Jul-2027 |  | Open
RC-PAR-18 | Placement turnaround time | BRRN.040 | Annex AC.7 | Confirm the value of placement turnaround time. By default: 3 business days packaged, 10 non-package; cut-off 3 PM (FRRN.29.05). | Value | 3 business days packaged, 10 non-package; cut-off 3 PM (FRRN.29.05) | BDOI (given) | 16-Jul-2027 |  | Open
RC-PAR-19 | Inactivity warning and session end | BRD x.001 | Annex AC.7 | Confirm the value of inactivity warning and session end. By default: 15 and 30 minutes. | Value | 15 and 30 minutes | System Administrator | 16-Jul-2027 |  | Open
RC-PAR-20 | Lines excluded from Renewal | Decision D3 | Annex AC.7 | Confirm the value of lines excluded from renewal. By default: HMO, group life, group personal accident (Employee Benefits). | Value | HMO, group life, group personal accident (Employee Benefits) | Product Owner, Renewal | 16-Jul-2027 |  | Open
CLR-RN-27 | Exception ageing days and recipients | BRRN.029 / 037 | Annex AC.7 | Exception ageing: Give the ageing days and the recipients. | Days; roles | 5 working days | Product Owner, Renewal | 30-Nov-2026 |  | Open
CLR-RN-33 | NRNS waiting days per segment | BRRN.029 / 037 | Annex AC.7 | NRNS waiting period: Give the waiting days per segment (RQ18). | Days; roles | 5 working days | Product Owner, Renewal | 30-Nov-2026 |  | Open

## Lists of values
Lists of values – BRD-06 Renewal
Purpose | Items of the kind 'Lists of values' the FRS v1.2 needs from the Business Unit.
Who fills it in | Business Administrator
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-LOV-01 | Renewal dispositions | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Renewal dispositions (default: For Renewal; Not for Renewal; For Quotation; For Proposal; Lost Business (labels maintained; the values drive the workflow)). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 | Unit Sold | Received
RC-LOV-01 | Renewal dispositions | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Renewal dispositions (default: For Renewal; Not for Renewal; For Quotation; For Proposal; Lost Business (labels maintained; the values drive the workflow)). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-02 | Non-renewal reasons | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Non-renewal reasons (default: The ten reasons of the BRD and the eleven of FRRN.014.02). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-03 | Return reasons | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Return reasons (default: The 39 reasons of Annex V and Disapproved). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-04 | Transfer reasons | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Transfer reasons (default: To be given by BDOI (requirements collection workbook)). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-05 | Follow-up channels and outcomes | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Follow-up channels and outcomes (default: Call, E-mail, SMS; outcomes to be given by BDOI). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-06 | Override reasons | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Override reasons (default: To be given by BDOI). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-07 | Insurer dispositions | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Insurer dispositions (default: The nine values of FRRN.013.02, each counted as Approve, Revise or Reject). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-08 | Client acceptance statuses | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Client acceptance statuses (default: Pending Client Response; Accepted; Rejected; Request for Revision; Not Applicable (FRRN.025.01)). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-09 | Placement rejection reasons | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Placement rejection reasons (default: The reasons of FRRN.030.01.02). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-10 | KYC statuses | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list KYC statuses (default: Due; Upcoming; Not Required; Pending Follow-Up; Completed (FRRN.039.02)). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open
RC-LOV-11 | Document types of Renewal | BRD 5.003 | Annex AC.8; template R01 | Give or confirm the values of the list Document types of Renewal (default: RA acceptance; signed Renewal Advice; LAMD report; insurer disposition file; renewal letter; Renewal Advice). Template: tab R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2. | Values in template R01 | Unit Sold | Business Administrator | 31-Jan-2027 |  | Open

## Master and reference data
Master and reference data – BRD-06 Renewal
Purpose | Items of the kind 'Master and reference data' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal; Business Administrator
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-DAT-01 | Renewal parameters (lead days, thresholds, notice and waiting days, durations) | BRD 5.003 | Annex AK; FRRN.040.03 | Provide renewal parameters (lead days, thresholds, notice and waiting days, durations) from Annex AC; BDOI's values of this FRS; status: Defaults given; values to confirm. | Template System parameters; SLA and turnaround of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab System parameters | Product Owner, Renewal | 31-Jan-2027 | Filled tab System parameters | Received
RC-DAT-01 | Renewal parameters (lead days, thresholds, notice and waiting days, durations) | BRD 5.003 | Annex AK; FRRN.040.03 | Provide renewal parameters (lead days, thresholds, notice and waiting days, durations) from Annex AC; BDOI's values of this FRS; status: Defaults given; values to confirm. | Template System parameters; SLA and turnaround of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab System parameters | Product Owner, Renewal | 31-Jan-2027 |  | Open
RC-DAT-02 | Lists of values of Renewal (reasons, outcomes, insurer dispositions) | BRD 5.003 | Annex AK; FRRN.049.01 | Provide lists of values of renewal (reasons, outcomes, insurer dispositions) from Annex AC; Annex V; status: Partly given. | Template R01 Lists of values and MIS values of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab R01 Lists of values and MIS values | Business Administrator | 31-Jan-2027 |  | Open
RC-DAT-03 | Risk codes with the Renewable indicator | BRD 5.003 | Annex AK; FRRN.038 | Provide risk codes with the renewable indicator from Product catalogue; BDOI risk code list; status: To be provided. | Template R05 Product lines, cover types (risk codes) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab R05 Product lines, cover types (risk codes) | MBS | 31-Jan-2027 |  | Open
RC-DAT-04 | Sanitation rules and decision matrix | BRD 5.003 | Annex AK; FRRN.040 | Provide sanitation rules and decision matrix from Annex C; FRRN.008; status: Given in part (CBG Home empty). | Template Configured on screens (Renewal Setup) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab Configured on screens (Renewal Setup) | Product Owner, Renewal | 31-Jan-2027 |  | Open
RC-DAT-05 | Duplicate criteria per line | BRD 5.003 | Annex AK; FRRN.006.01 | Provide duplicate criteria per line from Annex B; status: Given. | Template Configured on screens of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab Configured on screens | Business Administrator | 31-Jan-2027 |  | Open
RC-DAT-06 | Sales organisation and assignment hierarchy | BRD 5.003 | Annex AK; FRRN.010 | Provide sales organisation and assignment hierarchy from Annex F; status: Given (Annex F); Corporate as embedded document. | Template R03 Sales organisation (units and officers) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab R03 Sales organisation (units and officers) | Marketing Heads | 31-Jan-2027 |  | Open
RC-DAT-07 | RMU Account Officer codes | BRD 5.003 | Annex AK; FRRN.041.01 | Provide rmu account officer codes from LAMD; status: To be provided. | Template Configured on screens (RMU Account Maintenance) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab Configured on screens (RMU Account Maintenance) | LAMD | 31-Jan-2027 |  | Open
RC-DAT-08 | Annual renewal budgets | BRD 5.003 | Annex AK; FRRN.042 | Provide annual renewal budgets from Marketing; status: To be provided. | Template Budget upload template (FRRN.042.03) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab Budget upload template (FRRN.042.03) | Marketing Heads | 31-Jan-2027 |  | Open
RC-DAT-09 | Insurers: renewal and placement e-mail addresses, MFT enrolment, renewable lists | BRD 5.003 | Annex AK; FRRN.021, 029.04, 036.06 | Provide insurers: renewal and placement e-mail addresses, mft enrolment, renewable lists from Insurers; status: To be provided. | Template R04 Insurers; R04B Insurer branches of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab R04 Insurers | Processing Head | 31-Jan-2027 |  | Open
RC-DAT-10 | Letter and document templates | BRD 5.003 | Annex AK; FRRN.049.02 | Provide letter and document templates from Annexes L, W, X; templates still to come (N to R, T, Z); status: Partly given. | Template PM-08 Document templates; Document templates of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab PM-08 Document templates | Product Owner, Renewal | 31-Jan-2027 |  | Open
RC-DAT-11 | Holiday calendar (business days of TAT and ageing) | BRD 5.003 | Annex AK; FRRN.003.02.01, 29.05 | Provide holiday calendar (business days of tat and ageing) from BDOI; status: To be provided. | Template D0-03 Holiday calendar of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab D0-03 Holiday calendar | Administration | 31-Jan-2027 |  | Open
RC-DAT-12 | Incentive criteria | BRD 5.003 | Annex AK; FRRN.034.01 | Provide incentive criteria from Product Maintenance; status: To be provided. | Template PM-10 Incentive criteria of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab PM-10 Incentive criteria | MBS | 31-Jan-2027 |  | Open
RC-DAT-13 | Package code map of legacy packages | BRD 5.003 | Annex AK; FRRN.046.01 | Provide package code map of legacy packages from Data migration; status: To be provided. | Template R06 Package code map (legacy packages) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab R06 Package code map (legacy packages) | MBS | 31-Jan-2027 |  | Open
RC-DAT-14 | Migrated policies in force and Renewal Advices already sent | BRD 5.003 | Annex AK; FRRN.045 | Provide migrated policies in force and renewal advices already sent from Legacy systems; unit trackers; status: Decided 26-Sep-2026. | Template Data migration templates (Data Migration FRS) of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab Data migration templates (Data Migration FRS) | Data owners; Renewal processing team | 31-Jan-2027 |  | Open
RC-DAT-15 | Users and profiles of Renewal | BRD 5.003 | Annex AK; FRRN.001.05 | Provide users and profiles of renewal from BDOI; status: To be provided. | Template UA-01 Users and roles; UA-02 Role matrix of the Master Data and Configuration Upload Templates v1.2 (not copied here) | Filled tab UA-01 Users and roles | User Access Administrator | 31-Jan-2027 |  | Open
CFG-124 | Renewal buckets and decision matrix | BRRN.031, 034 | FRRN.040; Annex AC | Renewal buckets and decision matrix: The renewal bucket rules, the decision matrix and the non-renewable risk codes | Rules as Annex C | - | Product Owner, Renewal | 16-Jul-2027 |  | Open

## Approvers and users per role
Approvers and users per role – BRD-06 Renewal
Purpose | Items of the kind 'Approvers and users per role' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal; PMO
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-APR-01 | Users of the role Marketing Team Lead | BRD 1.001-1.011 | Annex AC.1; Annex AD | Name the users of the role Marketing Team Lead with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 | a013000101, Juan dela Cruz, Retail Marketing 1 | Received
RC-APR-01 | Users of the role Marketing Team Lead | BRD 1.001-1.011 | Annex AC.1; Annex AD | Name the users of the role Marketing Team Lead with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-02 | Users of the role Marketing Account Officer / Admin (Account Broker) | BRD 2.001-2.009 | Annex AC.1; Annex AD | Name the users of the role Marketing Account Officer / Admin (Account Broker) with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-03 | Users of the role Processing Team Lead | BRD 3.001-3.011 | Annex AC.1; Annex AD | Name the users of the role Processing Team Lead with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-04 | Users of the role Processing Officer / Broker | BRD 4.001-4.09 | Annex AC.1; Annex AD | Name the users of the role Processing Officer / Broker with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-05 | Users of the role Business Administrator | BRD 5.001-5.005 | Annex AC.1; Annex AD | Name the users of the role Business Administrator with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-06 | Users of the role System Administrator | BRD 6.001-6.002 | Annex AC.1; Annex AD | Name the users of the role System Administrator with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-07 | Users of the role LAMD user | BRRN.024, 029 | Annex AC.1; Annex AD | Name the users of the role LAMD user with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
RC-APR-08 | Users of the role Contact Center user | BRRN.026 | Annex AC.1; Annex AD | Name the users of the role Contact Center user with their unit, and the approvers of each stage of Annex AD where the role approves. | User ID, name, unit | a013000101, Juan dela Cruz, Retail Marketing 1 | User Access Administrator | 31-Jan-2027 |  | Open
TD-06 | UAT testers | - | Signoff Sheet; Annex AO.4 | Name the UAT testers of BRD-06 Renewal (at least two per business unit, with their user IDs and group profiles) and provide the business data of the UAT scenarios: the clients, policies, insurers and amounts each scenario of the test plan uses, from the migrated data of Trial migration 3 or as additional cases. | Names, or signature | - | Product Owner, Renewal | 16-Jul-2027 |  | Open
SO-06-1 | Signature of the FRS | - | Signoff Sheet; Annex AO.4 | Sign the FRS and sign-off set of BRD-06 Renewal. | Names, or signature | - | Product Owner, Renewal | 30-Nov-2026 |  | Open
SO-06-2 | Approval of the test plan | - | Signoff Sheet; Annex AO.4 | Approve the test plan of BRD-06 Renewal. | Names, or signature | - | Product Owner, Renewal | 18-Dec-2026 |  | Open
SO-06-3 | UAT sign-off certificate | - | Signoff Sheet; Annex AO.4 | Sign the UAT sign-off certificate of BRD-06 Renewal. | Names, or signature | - | Product Owner, Renewal | 17-Dec-2027 |  | Open
CLR-RN-40 | Signatories | - | Signoff Sheet; Annex AO.4 | Signatories: Confirm the signatories. | Names, or signature | - | Product Owner, Renewal | 30-Nov-2026 |  | Open

## Integration inputs (BDOI IT)
Integration inputs (BDOI IT) – BRD-06 Renewal
Purpose | Items of the kind 'Integration inputs (BDOI IT)' the FRS v1.2 needs from the Business Unit.
Who fills it in | BDOI IT
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RC-INT-04 | Claims | BRRN.010 / 029 / 035 / 040 | Annex AH | To be provided: total-loss indicator (Annex AN) | Decision, date and contact | - | BDOI IT | 31-Jan-2027 | - | Received
RC-INT-04 | Claims | BRRN.010 / 029 / 035 / 040 | Annex AH | To be provided: total-loss indicator (Annex AN) | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RC-INT-06 | BDOFC and BDOSOLD reports | BRRN.010 / 029 / 035 / 040 | Annex AH | To be provided: effect of a match (Annex AN) | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RC-INT-07 | Insurers | BRRN.010 / 029 / 035 / 040 | Annex AH | MFT set-up and directories per insurer (if in scope): To be provided: MFT scope (Annex AO C17) | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RC-INT-08 | CCM (client communications) | BRRN.010 / 029 / 035 / 040 | Annex AH | CCM interface and delivery statuses (if in scope): To be provided: CCM scope for go-live | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RC-INT-09 | E-mail of the system | BRRN.010 / 029 / 035 / 040 | Annex AH | Sender address and relay per environment: To be provided | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RC-INT-10 | CLPC / LMS | BRRN.010 / 029 / 035 / 040 | Annex AH | LMS shared directory (if available): To be provided | Decision, date and contact | - | BDOI IT | 31-Jan-2027 |  | Open
RQ16 | Approved recipient domains for the Renewal Advice e-mails, if any. | - | Annex AN.3.5 (RQ16; CLR-RN-12) | Approved recipient domains for the Renewal Advice e-mails, if any. | List of domains, or None |  | BDOI IT | 31-Jan-2027 |  | Open
RQ28 | Availability, maintenance window, recovery and retention values (the B | - | Annex AN.3.9 (RQ28) | Availability, maintenance window, recovery and retention values (the BRD says "follow existing QPS set up"). | Values per item of Annex AJ |  | BDOI IT | 31-Jan-2027 |  | Open
CLR-RN-38 | How the insurers give their renewable lists and who maintains them. | - | Annex AN.3.14 (CLR-RN-38) | How the insurers give their renewable lists and who maintains them. | Channel; owner |  | BDOI IT; Processing Head | 31-Jan-2027 |  | Open
D-RN-01 | Dependency | - | Annex AN.2; FRRN.005.01, 018.02, 035.01 | The business type Renewal of the account is shared with the New Business booking. | Date when it is in place | 31-Jan-2027 | BDOI IT | 31-Jan-2027 |  | Open
D-RN-02 | Dependency | - | Annex AN.2; FRRN.007.02, 014.01 | The Claims module gives the claims of the expiring term and the total-loss settlement tag. | Date when it is in place | 31-Jan-2027 | BDOI IT | 31-Jan-2027 |  | Open
D-RN-03 | Dependency | - | Annex AN.2; FRRN.048 | Submitted Policies hands its expiring records over to Renewal. | Date when it is in place | 31-Jan-2027 | BDOI IT | 31-Jan-2027 |  | Open
D-RN-06 | Dependency | - | Annex AN.2; FRRN.021, 022.02 | The e-mail relay (or CCM) of the BDOI environment is available for client and insurer e-mails. | Date when it is in place | 31-Jan-2027 | BDOI IT | 31-Jan-2027 |  | Open
D-RN-08 | Dependency | - | Annex AN.2; FRRN.034.01 | The incentive criteria of Product Maintenance are given. | Date when it is in place | 31-Jan-2027 | BDOI IT | 31-Jan-2027 |  | Open

## Open decisions
Open decisions – BRD-06 Renewal
Purpose | Items of the kind 'Open decisions' the FRS v1.2 needs from the Business Unit.
Who fills it in | Product Owner, Renewal
How it is used | The project applies each confirmed answer to the FRS, the configuration or the templates; data go through the upload templates v1.2.
Due | The date in the column Needed by (drop plan).
Depends on | The decisions of the sheet Open decisions where an item names one.
Mandatory: Mandatory * | Mandatory * | Optional | Optional | Mandatory * | Mandatory * | Optional | Mandatory * | Mandatory * | Optional | Mandatory *
Format: Text | Text | Text | Text | Text | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Reference of the item (kept from the BDOI inputs workbook where it exists) | What the item is about | BRD requirement the item serves | FR item or annex of the FRS v1.2 | What the Business Unit provides or decides | How to answer | An example of an answer | Role that answers | Date of the drop plan | The answer of the Business Unit | Open until answered; Received; Confirmed by the project
ID * | Item * | BRD ID | FRS reference | What is needed * | Format of the answer * | Example | Provided by (role) * | Needed by * | BU response | Status *
Example – overwrite or delete: RQ04 | Lead days of the daily extraction per segment or line (140 proposed), | - | Annex AN.3.1 (RQ04) | Lead days of the daily extraction per segment or line (140 proposed), in addition to the generation by date range of FRRN.004. | Days per market segment (Non-CBG, CBG Motor, CBG Home) |  | Product Owner, Renewal | 30-Nov-2026 | Confirmed | Received
RQ04 | Lead days of the daily extraction per segment or line (140 proposed), | - | Annex AN.3.1 (RQ04) | Lead days of the daily extraction per segment or line (140 proposed), in addition to the generation by date range of FRRN.004. | Days per market segment (Non-CBG, CBG Motor, CBG Home) |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ09 | Outstanding balance | - | Annex AN.3.2 (RQ09) | Outstanding balance: which balances count (the expiring invoice only, the client, all years), the threshold, and who may override. | Scope; amount; role |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ10 | Definition of the 34 summary counters of the Renewal Status Report, in | - | Annex AN.3.3 (RQ10) | Definition of the 34 summary counters of the Renewal Status Report, including For ARF, Renew to TSU, Disapproved and to Other Bank. | Rule per counter (status, disposition, reason) |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ11 | Ageing, overdue and high-risk criteria of the renewal listing, and whe | - | Annex AN.3.4 (RQ11; CLR-RN-35) | Ageing, overdue and high-risk criteria of the renewal listing, and whether the Account Officer may be notified. | Days per segment; criteria; Yes / No |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ21 | Contact Center follow-up outcomes and the lists the Contact Center see | - | Annex AN.3.6 (RQ21) | Contact Center follow-up outcomes and the lists the Contact Center sees. | List of outcomes; lists |  | Contact Center Head | 30-Nov-2026 |  | Open
RQ22 | Source of the KYC data of bank clients and the KYC review dates. | - | Annex AN.3.7 (RQ22) | Source of the KYC data of bank clients and the KYC review dates. | Source system; field |  | Compliance | 31-Jan-2027 |  | Open
RQ25 | Financial-impact tolerance (any change, or an amount or %) for the rou | - | Annex AN.3.8 (RQ25) | Financial-impact tolerance (any change, or an amount or %) for the routing to the New Business path. | Amount or % |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ29 | Late Renewal Requests Report | - | Annex AN.3.10 (RQ29) | Late Renewal Requests Report: needed as a variant of the renewal listing? | Yes / No; columns |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RQ30 | Renewal of an account whose package version has expired with no curren | - | Annex AN.3.11 (RQ30) | Renewal of an account whose package version has expired with no current version. | Rule |  | MBS | 30-Nov-2026 |  | Open
RQ33 | The incentive criteria and whether the evaluation is shared with New B | - | Annex AN.3.12 (RQ33; CLR-RN-37) | The incentive criteria and whether the evaluation is shared with New Business. | Criteria (line, product, segment, conditions) |  | Product Owner, Renewal; MBS | 30-Nov-2026 |  | Open
CLR-RN-31 | What is a structural change that routes a renewal to the New Business | - | Annex AN.3.13 (CLR-RN-31) | What is a structural change that routes a renewal to the New Business path, and is the routing automatic? | Definition; Automatic / Manual |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
CLR-RN-28 | How the claims of migrated policies are found at sanitation (migrated | - | Annex AN.3.15 (CLR-RN-28; RQ13) | How the claims of migrated policies are found at sanitation (migrated claims or a manual flag). | Choice |  | Product Owner, Renewal; Claims | 30-Nov-2026 |  | Open
CLR-RN-17 | Place of the upload of dispositioned files (Processing Worklist propos | - | Annex AN.3.16 (CLR-RN-17) | Place of the upload of dispositioned files (Processing Worklist proposed). | Confirm / other place |  | Processing Head | 30-Nov-2026 |  | Open
CLR-RN-19 | What the Contact Center and LAMD users see on the renewal account. | - | Annex AN.3.17 (CLR-RN-19) | What the Contact Center and LAMD users see on the renewal account. | Confirm the proposal of FRRN.001.02 |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
CLR-RN-21 | Codes typed in Renewal Setup, or drop-downs by name. | - | Annex AN.3.18 (CLR-RN-21) | Codes typed in Renewal Setup, or drop-downs by name. | Confirm / drop-downs |  | Business Administrator | 30-Nov-2026 |  | Open
CLR-RN-22 | Side stages on the step bar and the short status labels in the lists. | - | Annex AN.3.19 (CLR-RN-22; CLR-RN-24) | Side stages on the step bar and the short status labels in the lists. | Confirm |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
CLR-RN-23 | Processing completes the missing mandatory fields of a migrated policy | - | Annex AN.3.20 (CLR-RN-23) | Processing completes the missing mandatory fields of a migrated policy before the Renewal Advice. | Confirm |  | Processing Head | 30-Nov-2026 |  | Open
CLR-RN-26 | Landing page of the Renewal users after sign-in (Renewal Home or the c | - | Annex AN.3.21 (CLR-RN-26) | Landing page of the Renewal users after sign-in (Renewal Home or the common dashboard). | Choice |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
CLR-RN-39 | The classification filter and the export by classification stay on the | - | Annex AN.3.22 (CLR-RN-39) | The classification filter and the export by classification stay on the RMEL. | Confirm |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DEC-23 | What a BDOFC or SOLD match changes on the renewal account (FRRN.012.07 | - | Annex AN.3.23 (BDOFC) | What a BDOFC or SOLD match changes on the renewal account (FRRN.012.07). | Rule per report type |  | Product Owner, Renewal | 30-Nov-2026 |  | Open
RC-DEC-24 | The sanitation rules of CBG Home (Annex C) and the fields updated auto | - | Annex AN.3.24 (CBG-HOME) | The sanitation rules of CBG Home (Annex C) and the fields updated automatically for CBG Home and Non-CBG (FRRN.009.01). | Rules as Annex C; field list |  | Product Owner, Renewal; CBG | 30-Nov-2026 |  | Open
DCR-065 | Slips of the BRD text | - | Annex AN.3.25 (DCR-065; DCR-076; DCR-077) | Slips of the BRD text: labels of 1.003.4.1.1.21-24 all read 1.21; RA IDs 4.09.x; the workshop table titled for New Business; the source IDs of BRRN.020-040. | Corrected BRD pages or confirmation |  | BRD owner (ESG - Business Project Services) | 30-Nov-2026 |  | Open
DCR-061 | Confirm the signed BRD text is final; the Processing Officer profile ( | - | Annex AN.3.26 (DCR-061; DCR-066; DCR-068; DCR-069) | Confirm the signed BRD text is final; the Processing Officer profile (BRD 4.001.1.1 reads Operations Team Leader); the recipient of an account returned by Processing (3.008.2.5); the approval e-mail of the addenda. | Confirmation |  | Product Owner, Renewal | 30-Nov-2026 |  | Open

## Questions and comments
Questions and comments
Purpose | Any question or comment of the Business Unit on the items or on the FRS v1.2.
Who fills it in | Any reviewer; the project answers.
How it is used | Answered within 3 working days.
Due | Before the sign-off of the FRS.
Depends on | -
Mandatory: Mandatory * | Mandatory * | Mandatory * | Mandatory * | Optional | Optional | Optional
Format: Number | Text | Text | Text | Date dd-Mmm-yyyy | Text | Text
Allowed values: Free text | Free text | Free text | Free text | Free text | Free text | Open, Received, Confirmed
What to enter: Running number | ID of the item, or FRS section / annex | The question or comment | Name and role | Date raised | Filled in by iorta TechNXT | Open, Received, Confirmed
No. * | Item or section * | Question or comment * | Raised by * | Date | Answer of the project | Status
Example – overwrite or delete: 1 | AE.22 | Can the Renewal Advice e-mail also go to the Account Officer? | Product Owner |  |  | Open

## Lists
Status | Status
Not started | Open
In progress | Received
Completed | Confirmed