PROJECT PLAN

Project Plan - Summary

Phases and drops to the go-live of January 2028, milestones, sign-offs, test windows, trial migrations, cut-over, hypercare and the dependencies on BDOI

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-PLAN-BRD-00-S |
| Version | 1.0 |
| Date | 08 October 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 08 Oct 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | Program Manager, Business Project Services (pending) | First issue; plan as of 08-Oct-2026, after the BRD versions and the component baseline decisions of that day |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Steering committee | Approver | BDOI | Approval of the plan and its milestones |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Plan, drops and dependencies |
| BIBS Product Owner | Reviewer | BDOI | Scope and sign-off dates |
| Business owners of BRD-01 to BRD-13 | Reviewers | BDOI | Sign-off, UAT and training dates of their units |
| Head, BDOI IT; Head, BDOI Information Security | Reviewers | BDOI | Environments, integrations and security tests |
| Project team | Delivery | iorta TechNXT | Execution and weekly status |

Contents

1 Purpose, audience and scope	4

1.1 Purpose	4

1.2 Audience	4

1.3 Scope	4

2 Planning basis	4

3 Timeline	5

3.1 Phases	7

4 Milestones	7

5 Sign-offs	9

6 SIT and UAT windows, trial migrations and performance test	10

7 Cut-over, go-live and hypercare	10

8 Dependencies on BDOI	11

9 Critical path	13

10 Governance of the plan	13

11 Top risks to the plan	13

12 References	14

13 Decisions and open points for BDOI	14

# 1 Purpose, audience and scope

## 1.1 Purpose

This summary presents the plan that takes BIBS (BDOI Broker System on iNXT BrokerVerse) from the requirements of 2026 to the go-live of all modules together in January 2028 and the close of the hypercare and the true-ups. It is the reading guide to the Project Plan workbook BIBS_Delivery_BRD-00_Project_Plan_v1.0.xlsx, which holds the timeline by month, the milestones, the sign-offs, the test windows, the cut-over and hypercare phases and the dependencies on BDOI.

## 1.2 Audience

The steering committee and the Program Manager of Business Project Services (approval), the BIBS Product Owner and the business owners of each BRD (sign-off, UAT and training dates of their units), BDOI IT and Information Security (environments, integrations, security tests) and the iorta TechNXT project team (execution).

## 1.3 Scope

The plan covers the three BDOI drops and the programme-level activities:

•	Drop 0 - Setup and Data Migration: BRD-03 Product Maintenance, BRD-11 User Access Maintenance and BRD-13 Data Migration, with the GL accounts and reference tables of BRD-05;

•	Drop 1 - Transactional: BRD-01 New Business, BRD-02 Operations, BRD-04 Collections, BRD-05 Accounting, Disbursement and ACSL, BRD-06 Renewal, BRD-09 Customer Servicing Facility, BRD-10 Sanction Screening and BRD-12 Submitted Policies;

•	Drop 2 - Independent: BRD-07 Claims and BRD-08 Employee Benefits, with Production Reconciliation and the Marketing Collection extraction;

•	Programme: environments, integrations with BDO systems, performance and penetration tests, organisational change management, training, knowledge transfer, operational readiness, cut-over, hypercare and the true-ups after go-live.

Reinsurance is phase 2 and outside this plan; Remittance handles the reinsurance transactions in Drop 1. BIBS is a broker system: the insurer-company functions of the platform (insurer underwriting, insurer claims, treaty and cession accounting, actuarial reserves, group consolidation, insurer taxes) are not part of the BIBS release.

# 2 Planning basis

Table 1: What the plan rests on

| Basis | Content |
| --- | --- |
| BDOI drop plan and programme timeline (26-Sep-2026) | Requirements Drop 1 and migration Sep - Nov 2026, Drop 2 Dec 2026 - Feb 2027; development Drop 1 Nov 2026 - Feb 2027, migration Nov 2026 - Mar 2027, Drop 2 Mar - Apr 2027; SIT Drop 1 Jan - Jul 2027, migration Apr - Jul 2027, Drop 2 Jul - Sep 2027; UAT Drop 1 Aug - Dec 2027, migration Aug - Oct 2027, Drop 2 Oct - Nov 2027; performance and penetration test Nov - Dec 2027; ORR / PRR Dec 2027 - Jan 2028; full migration and cut-over Nov 2027 - Jan 2028; go-live January 2028 |
| BDOI answers of 26-Sep-2026 | All modules go live together; no early go-live; drops split the workload, the platform goes to UAT complete; documents in S3 only; reinsurance phase 2 |
| Drop 0 closure summary v2.0 (5-Oct-2026) | Sign-off dates of the Drop 0 sets; configuration due milestones D1 to D7; decisions DEC-01 to DEC-15; risks RSK-01 to RSK-07; dependencies DEP-01 to DEP-07 |
| Data Migration Handbook (BRD-13) | Milestones M0 to M6; four trial migrations and a dress rehearsal; cut-over phases A to H for T = Monday 3-Jan-2028; hypercare to T+30 and true-ups to T+120 |
| Programme alignment pack | Deliverable dates per stream, integration inventory, IER review, open questions IQ01 to IQ35 |
| Versions of 8-Oct-2026 | New versions of ten BDOI source documents; component baseline: PostgreSQL 16, Valkey 8, Apache Kafka 3.9, OpenJDK 21 LTS, Spring Boot 3.5, React, Node 22 LTS (packaging only), nginx, managed Kubernetes, Kubernetes Gateway API |

# 3 Timeline

The figure shows the activities of the plan by month; the workbook sheet Timeline has the same rows with their owners and outputs. Today (8-Oct-2026) the programme is in the requirements phase of Drop 0 and Drop 1 and absorbs the BRD versions received the same day.

Figure 1: BIBS programme timeline, September 2026 to May 2028

Table 2: Activities of the timeline

| ID | Stream | Activity | Start | End | Owner |
| --- | --- | --- | --- | --- | --- |
| P-01 | Requirements | Drop 0 and Drop 1 requirements and FRS (setup, upstream, downstream) | 01-Sep-2026 | 30-Nov-2026 | Business owners; iorta Business Analyst lead |
| P-02 | Requirements | Absorb the BRD versions of 8-Oct-2026 (FRS re-base, traceability, test cases, sign-off sets v2.1) | 08-Oct-2026 | 13-Nov-2026 | iorta Business Analyst lead |
| P-03 | Requirements | Data migration requirements, object decisions and mapping | 01-Sep-2026 | 30-Nov-2026 | Data Migration Lead |
| P-04 | Requirements | Drop 2 requirements and FRS (Claims, Employee Benefits, Production Reconciliation, Marketing Collection extraction) | 01-Dec-2026 | 26-Feb-2027 | Business owners; iorta Business Analyst lead |
| P-05 | Requirements | Customer Servicing Case Management (CSF addendum) through change control | 12-Oct-2026 | 26-Feb-2027 | Product Owner, CSF; Change Control Board |
| P-06 | Development | Component baseline of 8-Oct-2026: Valkey 8 and the Kubernetes Gateway API | 08-Oct-2026 | 30-Nov-2026 | iorta Solution Architect; BDOI IT |
| P-07 | Development | Drop 1 development, first wave (setup and upstream: Submitted Policies, Renewal foundation, EIAM sign-in, document store) | 02-Nov-2026 | 23-Dec-2026 | iorta development team |
| P-08 | Development | Drop 1 development, second wave (downstream: Renewal completion, bank channels, changes from the signed FRS) | 04-Jan-2027 | 26-Feb-2027 | iorta development team |
| P-09 | Development | Migration Console and loaders | 02-Nov-2026 | 31-Mar-2027 | iorta Migration Lead |
| P-10 | Development | Drop 2 development, third wave (Claims, Employee Benefits without portal, CSF, EGL, EDP and insurer exchanges, other reports) | 01-Mar-2027 | 30-Apr-2027 | iorta development team |
| P-11 | Development | Integrations with BDO systems through Apigee X (EIAM, UIDM-ISC, CCM, LMS, HL-LOAS, PMS, CMS / New BOB, OBPCS, Old BOB, AFTS) | 04-Jan-2027 | 30-Jun-2027 | BDOI IT; BDO IT EIAM, IGA and API teams; iorta Solution Architect |
| P-12 | Development | Spring Boot 4 assessment (proposed) and upgrade window if BDOI approves | 11-Jan-2027 | 25-Jun-2027 | iorta Solution Architect; BDOI IT; Change Control Board |
| P-13 | Testing | Drop 1 system integration test (SIT) | 04-Jan-2027 | 30-Jul-2027 | iorta QA lead |
| P-14 | Testing | Drop 2 system integration test (SIT) | 01-Jul-2027 | 30-Sep-2027 | iorta QA lead |
| P-15 | Testing | Drop 1 user acceptance test (UAT), end to end on migrated data | 02-Aug-2027 | 17-Dec-2027 | BIBS Product Owner; business owners |
| P-16 | Testing | Drop 2 user acceptance test (UAT) | 01-Oct-2027 | 30-Nov-2027 | Business owners of BRD-07 and BRD-08 |
| P-17 | Testing | Early security scan in SIT (proposed) | 01-Jun-2027 | 30-Jun-2027 | BDOI Information Security |
| P-18 | Testing | Performance and penetration test | 01-Nov-2027 | 15-Dec-2027 | BDOI IT; BDOI Information Security |
| P-19 | Data migration | SIT migration: Trial migrations 1 (19-30 Apr) and 2 (5-16 Jul) | 19-Apr-2027 | 16-Jul-2027 | Data Migration Lead; iorta Migration Lead |
| P-20 | Data migration | UAT migration: Trial migrations 3 (2-13 Aug) and 4 (4-15 Oct) | 02-Aug-2027 | 15-Oct-2027 | Data Migration Lead; iorta Migration Lead |
| P-21 | Data migration | Dress rehearsal on production-sized data (reserve slot 6-10 Dec 2027) | 15-Nov-2027 | 26-Nov-2027 | Data Migration Lead; iorta Migration Lead |
| P-22 | Readiness | Environments: SIT, UAT, Pre-Prod, production and DR on managed Kubernetes | 02-Nov-2026 | 01-Nov-2027 | BDOI IT; iorta infrastructure team |
| P-23 | Readiness | Organisational change management and communications | 12-Oct-2026 | 02-Feb-2028 | BIBS Product Owner; iorta change and training lead |
| P-24 | Readiness | Key user training (UAT testers) and train-the-trainer | 19-Jul-2027 | 17-Sep-2027 | iorta change and training lead |
| P-25 | Readiness | End-user training by persona | 18-Oct-2027 | 10-Dec-2027 | BDOI trainers; iorta change and training lead |
| P-26 | Readiness | Knowledge transfer to BDOI application support and BDO IT operations | 07-Jun-2027 | 02-Feb-2028 | iorta Project Manager; BDOI IT |
| P-27 | Readiness | Operational and production readiness review (ORR / PRR) | 01-Dec-2027 | 31-Dec-2027 | BDOI IT; iorta Project Manager |
| P-28 | Cut-over | Cut-over phases A-E: readiness, pre-load and deltas, legacy freeze, production load, reconciliation and go / no-go | 04-Dec-2027 | 02-Jan-2028 | Go / no-go board; Data Migration Lead |
| P-29 | Cut-over | Go-live of all modules together (T = Monday 3-Jan-2028) | 03-Jan-2028 | 03-Jan-2028 | Steering committee |
| P-30 | Cut-over | Hypercare and true-up 1 (T+1 to T+30) | 04-Jan-2028 | 02-Feb-2028 | iorta Project Manager; BDOI application support |
| P-31 | Cut-over | Final true-up and legacy GL close (T+31 to T+120) | 03-Feb-2028 | 02-May-2028 | Head, Comptrollership |

## 3.1 Phases

Table 3: Phases of the programme

| Phase | Window | What is done and what closes it |
| --- | --- | --- |
| Requirements and sign-off | Sep 2026 - Feb 2027 | FRS, test plans and sign-off sets per BRD; clarifications decided; Drop 0 closed by the steering committee (proposed 9-Dec-2026); Drop 1 FRS signed by 30-Nov-2026, Drop 2 by 26-Feb-2027 |
| Development and configuration | Nov 2026 - Jun 2027 | Three development waves (setup and upstream; downstream; independent modules), each about two months; Migration Console; integrations through Apigee X; configuration inputs D1 to D5 |
| System integration test | Jan - Sep 2027 | Drop 1 SIT Jan - Jul 2027 on the SIT environment from 4-Jan-2027; Drop 2 SIT Jul - Sep 2027; Trial migrations 1 and 2 |
| User acceptance test | Aug - Dec 2027 | Drop 1 end to end on migrated data (Trial migration 3); Drop 2 Oct - Nov 2027; Trial migration 4 |
| Readiness | Jun 2027 - Jan 2028 | Knowledge transfer from 7-Jun-2027; key user training Jul 2027; train-the-trainer Sep 2027; end-user training 18-Oct to 10-Dec-2027; performance and penetration test; dress rehearsal 15-26 Nov 2027; ORR / PRR |
| Cut-over and go-live | 4-Dec-2027 - 3-Jan-2028 | Phases A to F; go / no-go on Sunday 2-Jan-2028; go-live Monday 3-Jan-2028 |
| Hypercare and true-ups | 4-Jan - 2-May-2028 | Hypercare to 2-Feb-2028 with the first month-end close; hand-over to production support; true-ups closed 2-May-2028 |

# 4 Milestones

Table 4: Programme milestones

| ID | Date | Milestone | Drop | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| MS-01 | 05-Oct-2026 | Drop 0 sign-off sets v2.0 issued (BRD-03, BRD-11, BRD-13) with the BDOI answers to DMQ36-DMQ39 (M0) | Drop 0 | iorta Project Manager | Done |
| MS-02 | 08-Oct-2026 | New versions of ten BDOI documents received; component baseline decided (PostgreSQL 16, Valkey 8, Kafka 3.9, OpenJDK 21, Spring Boot 3.5, Node 22 LTS, nginx, managed Kubernetes, Gateway API) | All | BIBS Product Owner; BDOI IT | Done |
| MS-03 | 16-Oct-2026 | Scope-shaping migration decisions (M1): DEC-02, DEC-03 (part), DEC-11, DEC-12 | Drop 0 | Business owners; Head, Comptrollership | Open |
| MS-04 | 23-Oct-2026 | FRS re-based on the BRD versions of 8-Oct-2026 issued for review (proposed) | All | iorta Business Analyst lead | Open |
| MS-05 | 30-Oct-2026 | BRD-13 Data Migration set signed; object decisions (gate G1); layouts frozen v1 (M2); decision on the Data Migration V0.03 conflicts and on Customer Servicing Case Management (proposed) | Drop 0 | Data Migration Lead; Program Manager | Open |
| MS-06 | 13-Nov-2026 | Drop 1 FRS issued with the BDOI comments resolved | Drop 1 | iorta Business Analyst lead | Open |
| MS-07 | 30-Nov-2026 | BRD-03 Product Maintenance set signed; Drop 1 FRS signed (BRD-01, 02, 04, 05, 06, 09, 10, 12) | Drop 0, Drop 1 | Product owners of each BRD | Open |
| MS-08 | 01-Dec-2026 | BRD-11 User Access Maintenance set signed; configuration drafts due (D1) | Drop 0 | Product Owner, Marketing Business System; BDOI Information Security; BDOI IT | Open |
| MS-09 | 09-Dec-2026 | Drop 0 closed by the steering committee; Drop 1 opened (proposed date) | Drop 0 | Program Manager, Business Project Services | Open |
| MS-10 | 18-Dec-2026 | Drop 1 test plans approved | Drop 1 | Business owners; iorta QA lead | Open |
| MS-11 | 04-Jan-2027 | SIT environment ready; platform set-up for Drop 1 SIT (D2); Drop 1 SIT starts | Drop 1 | BDOI IT; Head, Comptrollership | Open |
| MS-12 | 29-Jan-2027 | First full extracts with control files and volumes (M3) | Drop 0 | BDOI IT | Open |
| MS-13 | 31-Jan-2027 | Drop 2 integration specifications (EGL, EDP, CARMS, insurer exchanges); EIAM and UIDM-ISC specifications (proposed date within Q1 2027) | Drop 1, Drop 2 | BDOI IT; BDO IT EIAM and IGA teams | Open |
| MS-14 | 26-Feb-2027 | Drop 2 FRS signed (BRD-07, BRD-08); Drop 1 development complete | Drop 1, Drop 2 | Product Owners, Claims and Employee Benefits | Open |
| MS-15 | 31-Mar-2027 | Migration Console and loaders ready; Spring Boot 4 decision (proposed) | Drop 0 | iorta Migration Lead; BDOI IT | Open |
| MS-16 | 09-Apr-2027 | Extracts for Trial migration 1 (M4); reference data for SIT (D3); role-to-permission matrix and SIT / UAT users | Drop 0 | BDOI IT; Business Administration; BDOI Information Security | Open |
| MS-17 | 30-Apr-2027 | Drop 2 development complete | Drop 2 | iorta Project Manager | Open |
| MS-18 | 18-Jun-2027 | Code maps approved, including the package code map (M5, D4) | Drop 0 | Data owners; TSU | Open |
| MS-19 | 30-Jun-2027 | Drop 2 test plans approved; early security scan in SIT completed (proposed) | Drop 2 | Business owners; BDOI Information Security | Open |
| MS-20 | 16-Jul-2027 | UAT plans and sign-off forms issued; values for UAT (D5); UAT testers named | Drop 1 | BIBS Product Owner; business owners | Open |
| MS-21 | 30-Jul-2027 | Drop 1 SIT exit; UAT readiness statement; key users trained | Drop 1 | iorta QA lead; BIBS Product Owner | Open |
| MS-22 | 02-Aug-2027 | Drop 1 UAT starts on migrated data (Trial migration 3) | Drop 1 | BIBS Product Owner | Open |
| MS-23 | 30-Sep-2027 | Drop 2 SIT exit and UAT readiness statement | Drop 2 | iorta QA lead | Open |
| MS-24 | 01-Oct-2027 | Pre-Prod ready; cut-over date, window, fallback and decommissioning criteria agreed; year-end option A confirmed (M6) | Programme | Program Manager; Head, Comptrollership; BDOI IT | Open |
| MS-25 | 01-Nov-2027 | Production values of every configuration item (D6); production and DR environments ready (proposed) | Programme | Configuration owners; BDOI IT | Open |
| MS-26 | 26-Nov-2027 | Dress rehearsal completed and its report signed | Drop 0 | Data Migration Lead; iorta Migration Lead | Open |
| MS-27 | 30-Nov-2027 | Drop 2 UAT signed | Drop 2 | Product Owners, Claims and Employee Benefits | Open |
| MS-28 | 14-Dec-2027 | Renewal processing team ready for the January expiries (T-20) | Drop 1 | Head of the Renewal processing team | Open |
| MS-29 | 15-Dec-2027 | ORR / PRR evidence pack; performance and penetration test closed | Programme | BDOI IT; BDOI Information Security | Open |
| MS-30 | 17-Dec-2027 | Drop 1 UAT signed; end-user training complete; go-live readiness review (proposed) | Drop 1 | Steering committee | Open |
| MS-31 | 27-Dec-2027 | Code map and reference value freeze (D7, T-7) | Drop 0 | Data Migration Lead | Open |
| MS-32 | 31-Dec-2027 | Last legacy end of day and final extracts (T-3) | Programme | BDOI IT | Open |
| MS-33 | 02-Jan-2028 | Reconciliation, verification and go / no-go (T-1) | Programme | Go / no-go board | Open |
| MS-34 | 03-Jan-2028 | Go-live of BIBS, all modules together (T) | Programme | Steering committee | Open |
| MS-35 | 21-Jan-2028 | True-up 1 posted, reconciled and signed (T+18) | Programme | Head, Comptrollership | Open |
| MS-36 | 02-Feb-2028 | First month-end close completed; hypercare exit; hand-over to production support (T+30) | Programme | Go / no-go board | Open |
| MS-37 | 02-May-2028 | True-ups closed (T+120); legacy GL locked on 18-Apr-2028 | Programme | Head, Comptrollership | Open |

# 5 Sign-offs

Each document set is signed as one unit by the roles of its BRD approval sheet ("Who signs what" in the 00 Start Here of the set). After signature, nothing changes without a change request (see the Delivery Methodology). The BRD versions of 8-Oct-2026 are absorbed in version 2.1 of the issued sets (or the next minor version of an FRS issued alone) before signature, so that each set is signed once against the current BRD.

Table 5: Sign-offs

| Document set or decision | BRDs | Version | Due | Signatories |
| --- | --- | --- | --- | --- |
| Data Migration sign-off set | BRD-13 | v2.0 (re-base on BRD V0.03 in v2.1) | 30-Oct-2026 | Program Manager, Business Project Services; Data Migration Lead; Head, Comptrollership; Head, Operations; BDOI IT |
| Product Maintenance sign-off set | BRD-03 | v2.0 | 30-Nov-2026 | Product Owner, Marketing Business System; MBS; TSU; Business Project Services |
| User Access Maintenance sign-off set | BRD-11 | v2.0 | 01-Dec-2026 | Product Owner, Marketing Business System; BDOI Information Security; BDOI IT; Business Administrators |
| Drop 0 closure summary and configuration inputs | BRD-03, 11, 13 | v2.0 | 09-Dec-2026 | Steering committee (chair: Program Manager, Business Project Services) |
| Drop 1 FRS and sign-off sets | BRD-01, 02, 04, 05, 06, 09, 10, 12 | v2.1 / next minor (re-base on 8-Oct-2026) | 30-Nov-2026 | Product owner of each BRD; Business Project Services (traceability); BDOI IT (Technical Specification) |
| Drop 1 test plans | Drop 1 BRDs | v1.x | 18-Dec-2026 | Business owners; iorta QA lead |
| Drop 2 FRS | BRD-07, BRD-08 (and CSF Case Management if approved) | v1.x | 26-Feb-2027 | Product Owners, Claims and Employee Benefits; Business Project Services |
| Drop 2 test plans | BRD-07, BRD-08 | v1.x | 30-Jun-2027 | Business owners; iorta QA lead |
| Drop 1 UAT sign-off certificates | Drop 0 and Drop 1 BRDs | - | 17-Dec-2027 | Product owner of each BRD; BIBS Product Owner |
| Drop 2 UAT sign-off certificates | BRD-07, BRD-08 | - | 30-Nov-2027 | Product owners of BRD-07 and BRD-08 |
| Dress rehearsal report | BRD-13 | - | 26-Nov-2027 | Data Migration Lead; iorta Migration Lead |
| ORR / PRR approval | Programme | - | 31-Dec-2027 | Head, BDOI IT; Head, BDOI Information Security; iorta Project Manager |
| Go / no-go decision | Programme | - | 02-Jan-2028 | Go / no-go board |
| Hypercare exit and hand-over | Programme | - | 02-Feb-2028 | Go / no-go board; BDOI application support; BDO IT operations |

# 6 SIT and UAT windows, trial migrations and performance test

Table 6: SIT, UAT, trial migrations and the performance test

| Window | Start | End | Env. | Entry criteria | Exit criteria |
| --- | --- | --- | --- | --- | --- |
| Drop 1 SIT | 04-Jan-2027 | 30-Jul-2027 | SIT | Test plans approved (18-Dec-2026); SIT environment and D2 set-up ready (4-Jan-2027); release notes delivered | All Must-have cases passed; no open Severity 1 or 2 incident; Severity 3 with a workaround agreed; regression passed on the last release |
| Drop 2 SIT | 01-Jul-2027 | 30-Sep-2027 | SIT | Drop 2 test plans approved (30-Jun-2027); integration specifications agreed | As Drop 1 SIT; integration test with EGL, EDP and insurer exchanges passed |
| Trial migration 1 | 19-Apr-2027 | 30-Apr-2027 | SIT | Extracts M4 received (9-Apr-2027); Migration Console ready | Profiling report to the owners; timings recorded |
| Trial migration 2 | 05-Jul-2027 | 16-Jul-2027 | SIT | Code maps approved (M5, 18-Jun-2027) | All objects end to end; L1-L5 reconciled; Migration Clearing 0.00 |
| Drop 1 UAT (end to end) | 02-Aug-2027 | 17-Dec-2027 | UAT | SIT exit; UAT readiness statement (30-Jul-2027); UAT plans and sign-off forms (16-Jul-2027); key users trained; Trial migration 3 loaded | Every UAT scenario passed or accepted with a workaround; sign-off certificate per BRD |
| Trial migration 3 | 02-Aug-2027 | 13-Aug-2027 | UAT | Trial migration 2 exit | Business verification on screen; UAT runs on migrated data |
| Drop 2 UAT | 01-Oct-2027 | 30-Nov-2027 | UAT | Drop 2 readiness statement (30-Sep-2027) | Sign-off certificates of BRD-07 and BRD-08 |
| Trial migration 4 | 04-Oct-2027 | 15-Oct-2027 | UAT | Fixes from Trial migration 3 released | Timed as a cut-over; go-live renewal extraction; a test opening-balance adjustment |
| Performance and penetration test | 01-Nov-2027 | 15-Dec-2027 | Pre-Prod | Pre-Prod ready (1-Oct-2027) at production size | Peak of 429 concurrent users within the response-time targets; no open critical or high finding |
| Dress rehearsal | 15-Nov-2027 | 26-Nov-2027 | Pre-Prod | Production values D6 loaded (1-Nov-2027) | Full volume within the window with 20 percent margin; rollback rehearsed |

The UAT of Drop 1 runs end to end on migrated data: Trial migration 3 loads the UAT environment in August 2027, and Trial migration 4 in October 2027 is timed as a cut-over. Business users therefore test their processes on their own clients, policies and open items.

# 7 Cut-over, go-live and hypercare

Go-live T is proposed for Monday 3-Jan-2028, at the year-end boundary (year-end option A, awaiting the confirmation of Comptrollership, DEC-01). Days are calendar days; tasks that would fall on the year-end holidays are placed on the nearest working day. The detailed cut-over runbook (tasks CT-001 onwards) is in the Data Migration Handbook.

Table 7: Cut-over and hypercare phases

| Phase | Name | Days | Dates | Main activities | Owner |
| --- | --- | --- | --- | --- | --- |
| A | Readiness | T-30 to T-15 | 4 to 19 Dec 2027 | Dress rehearsal confirmed; cut-over team, command centre and hypercare roster named; communications to branches, insurers and bank channels; Renewal team readiness (14-Dec-2027) | Program Manager; Data Migration Lead |
| B | Pre-load and daily deltas | T-14 to T-4 | 20 to 30 Dec 2027 | Reference data and clients pre-loaded; daily deltas; map freeze on 27-Dec-2027 (T-7) | Data Migration Lead; BDOI IT |
| C | Legacy freeze and final extracts | T-3 | Fri 31 Dec 2027 | Last legacy end of day; preliminary December trial balance signed as the provisional opening | BDOI IT; Head, Comptrollership |
| D | Production load | T-2 | Sat 1 Jan 2028 | Final extracts validated and loaded in load order | iorta Migration Lead |
| E | Reconciliation, verification and go / no-go | T-1 | Sun 2 Jan 2028 | L1-L5 reconciliation; business verification; go / no-go decision | Go / no-go board |
| F | Go-live | T | Mon 3 Jan 2028 | Command centre opens 07:00; go-live renewal extraction; users start | iorta Project Manager |
| G | Hypercare and true-up 1 | T+1 to T+30 | 4 Jan to 2 Feb 2028 | Daily hypercare check; issue triage at 10:00 and 16:00; week-1 review; true-up 1 (21-Jan-2028); first month-end close; hypercare exit (2-Feb-2028) | iorta Project Manager; BDOI application support |
| H | Final true-up and legacy GL close | T+31 to T+120 | Feb to 2 May 2028 | Interim true-up 2 if needed; audited FY2027 statements; final true-up; legacy GL locked (18-Apr-2028); true-ups closed | Head, Comptrollership |

Hypercare exit on 2-Feb-2028 requires: the first month-end close completed with the ACSL reconciliation without difference, true-up 1 signed, no open Severity 1 incident and no Severity 2 older than five working days, the adoption KPIs of the first month met (see the Change Management and Training Framework) and the knowledge transfer readiness assessment passed.

# 8 Dependencies on BDOI

The plan depends on decisions, data, environments, integrations and people that BDOI provides. Each dependency has an owner and a date; a late dependency is raised in the weekly programme meeting and, when it moves a milestone, at the steering committee.

Table 8: Dependencies on BDOI

| ID | Type | Dependency | Provided by | Needed by | Effect if late |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | Decision | Answers to the M1 and M2 decisions of the Data Migration set (DEC-02, DEC-03, DEC-11, DEC-12) | BDOI business owners | 16-Oct-2026 | Layouts frozen late; Trial migration 1 scope reduced |
| DEP-02 | Decision | Position on the Data Migration BRD V0.03 conflicts: renewals in progress (BRID_MIG 12.1 against DMQ37), claims, submitted policies, payees and e-policy linking in scope | Program Manager; Head of the Renewal processing team; Head, Comptrollership | 30-Oct-2026 | New layouts after M2; migration effort and trial scope change |
| DEP-03 | Decision | Scope and drop of Customer Servicing Case Management (CSF addendum, BRCSFCM.001-.012) | Product Owner, CSF; Change Control Board | 30-Oct-2026 | Case Management cannot be delivered for go-live |
| DEP-04 | Decision | Sign-off of the Drop 0 sets (BRD-13, BRD-03, BRD-11) and of the Drop 1 FRS | Product owners | 30-Nov-2026 | Development starts on unsigned scope; rework |
| DEP-05 | Data | Organisation, chart of accounts, accounting rules and bank accounts for Drop 1 SIT (D2) | Head, Comptrollership | 04-Jan-2027 | SIT runs on seed values; postings retested |
| DEP-06 | Environment | SIT environment on managed Kubernetes with PostgreSQL 16, Valkey 8, Kafka 3.9, document store and Gateway API | BDOI IT | 04-Jan-2027 | SIT start slips day for day |
| DEP-07 | Integration | EIAM sign-in specification (tenant, claims, session life, OIDC or SAML 2.0) and application registration | BDO IT EIAM team | 31-Jan-2027 | Sign-in stays local in SIT; directory sign-in tested late |
| DEP-08 | Integration | UIDM-ISC option (accounts only, accounts and roles, or aggregation only) and SCIM provisioning connector | BDO IT IGA team | 31-Jan-2027 | User provisioning tested late; manual user loading at go-live |
| DEP-09 | Data | First full extracts with control files and volumes (M3) | BDOI IT | 29-Jan-2027 | Trial migration 1 on partial data |
| DEP-10 | Integration | Drop 2 integration specifications: EGL, EDP (SD 11), CARMS, insurer exchanges | BDOI IT | 31-Jan-2027 | Drop 2 interfaces descoped or delivered after go-live |
| DEP-11 | Integration | Bank channel layouts and transport: CMS / New BOB, OBPCS, Old BOB, AFTS, PMS | BDOI IT | 26-Feb-2027 | Manual uploads at go-live |
| DEP-12 | Integration | CCM sending mode, sender addresses and attachment limits | BDOI IT | 26-Feb-2027 | E-mail tested late |
| DEP-13 | Integration | Apigee X proxies, products and credentials for the BIBS integrations in SIT, UAT and production | BDO IT API team | 31-Mar-2027 | Integration test slips into UAT |
| DEP-14 | Decision | Spring Boot 4 upgrade before go-live or after hypercare | BDOI IT; Change Control Board | 31-Mar-2027 | Upgrade forced late or carried into production support |
| DEP-15 | Decision | DR region and data residency (IQ26) | BDOI IT; BDOI Information Security | 31-Mar-2027 | DR not ready at go-live |
| DEP-16 | Data | Role-to-permission matrix and the users of the SIT and UAT testers (D3) | Business Administration; BDOI Information Security | 09-Apr-2027 | Testers without access; UAT starts late |
| DEP-17 | Data | Code maps approved, including the package code map (M5) | Data owners; TSU | 18-Jun-2027 | Trial migration 2 incomplete |
| DEP-18 | Resource | Named application support team (L1 and L2) and BDO IT operations staff for knowledge transfer | BDOI IT; BDO IT operations | 31-May-2027 | Hand-over at hypercare exit at risk |
| DEP-19 | Resource | Penetration test provider named; early SIT scan approved (IQ35) | BDOI Information Security | 31-May-2027 | Findings arrive in December 2027 |
| DEP-20 | Resource | UAT testers named per BRD (at least two per business unit) and released for the UAT windows | Business owners | 16-Jul-2027 | UAT coverage reduced |
| DEP-21 | Environment | UAT environment and training environment with training users | BDOI IT | 19-Jul-2027 | Training and UAT start late |
| DEP-22 | Resource | BDOI trainers named for train-the-trainer (one per business unit and persona group) | Business owners | 30-Jul-2027 | End-user training delivered by iorta only; capacity limit |
| DEP-23 | Environment | Pre-Prod at production size | BDOI IT | 01-Oct-2027 | Dress rehearsal not production-sized |
| DEP-24 | Decision | Year-end option A confirmed; point of no return confirmed (DEC-01, DEC-13) | Head, Comptrollership; Program Manager | 01-Oct-2027 | Cut-over calendar changes |
| DEP-25 | Environment | Production and DR environments | BDOI IT | 01-Nov-2027 | Go-live date at risk |
| DEP-26 | Data | Production values of every configuration item (D6) | Configuration owners | 01-Nov-2027 | Dress rehearsal on non-production values |

# 9 Critical path

The critical path to the go-live runs through: the sign-off of the Drop 0 and Drop 1 sets (30-Nov-2026 and 1-Dec-2026) - the SIT environment and the D2 set-up (4-Jan-2027) - the first full extracts (29-Jan-2027) - Trial migration 1 (19-Apr-2027) - code maps approved (18-Jun-2027) - Trial migration 2 and the Drop 1 SIT exit (30-Jul-2027) - Drop 1 UAT on Trial migration 3 (2-Aug-2027) - Pre-Prod (1-Oct-2027) - production values D6 and production environments (1-Nov-2027) - dress rehearsal (26-Nov-2027) - UAT sign-off (17-Dec-2027) - map freeze (27-Dec-2027) - go / no-go (2-Jan-2028). Each step has between zero and two weeks of float; a slip of a dependency on this path moves the go-live unless the next step is compressed.

Figure 2: Critical path to the go-live

# 10 Governance of the plan

•	The iorta TechNXT Project Manager keeps the plan and the RAID log and reports weekly to the programme meeting (progress against milestones, dependencies due in the next four weeks, High risks and issues).

•	The steering committee meets monthly and at each drop closure, approves milestone changes and decides escalations.

•	A change to a milestone date in the workbook is made only after the steering committee decision; the version of the workbook increases and the change is recorded on its cover.

# 11 Top risks to the plan

Table 9: High risks

| ID | Risk | P x I | Rating | Owner | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R-02 | Customer Servicing Case Management enters scope | 5 x 4 = 20 | High | Product Owner, CSF; Program Manager | Change request to the CCB by 30-Oct-2026 with the impact analysis; proposed delivery with Drop 2 (requirements to 26-Feb-2027, development Mar-Apr 2027, SIT Jul-Sep 2027) |
| R-03 | Data Migration BRD V0.03 conflicts with earlier BDOI answers | 4 x 4 = 16 | High | Data Migration Lead; Program Manager | Position paper per conflict with our proposal; decision at M2 (30-Oct-2026); Handbook and test plan re-based on V0.03 |
| R-16 | Short lead time of the January 2028 renewals | 4 x 4 = 16 | High | Head of the Renewal processing team | Day-1 priority queue (go-live extraction at 04:00, January expiries flagged urgent); January staffing plan signed; Renewal team trained and practised on Trial migration 4 and dress-rehearsal data by 14-Dec-2027 |
| R-17 | Business user capacity in Q4 2027 | 4 x 4 = 16 | High | BIBS Product Owner; business owners | Named UAT testers per BRD by 16-Jul-2027; UAT calendar per unit; key users trained in July so they test and coach; end-user training in short persona sessions of 3 to 4 hours |
| R-01 | New BRD versions of 8-Oct-2026 to absorb | 5 x 3 = 15 | High | iorta Business Analyst lead | Comparison of every old and new version done; FRS re-based to v2.1 or the next minor version with a user-story view and storyboard index; restated requirements raised as clarifications; re-issue by 23-Oct-2026 (proposed) |
| R-08 | Environment provisioning late | 3 x 5 = 15 | High | BDOI IT | Environment checklist per environment agreed by 30-Nov-2026; restated IER sizing; monthly environment review at the steering committee; acceptance test of each environment one week before its date |

The full risk register is the workbook BIBS_Delivery_BRD-00_Risk_Register_RAID_Log_v1.0.xlsx.

# 12 References

•	BDOI drop plan and programme timeline (received 26-Sep-2026) and the BDOI answers of 26-Sep-2026.

•	Drop 0 closure summary and configuration inputs workbook, version 2.0 (5-Oct-2026).

•	BRD-13 Data Migration Handbook, sign-off set v2.0, and the Data Migration BRD V0.03.

•	BIBS programme alignment pack: drops, integrations and infrastructure, version 1.0.

•	Change Management Register and summary, version 1.0.

•	BDOI source documents received on 8-Oct-2026 and the client decisions on the component baseline of the same day.

•	IER Workbook v20 (infrastructure estimate).

# 13 Decisions and open points for BDOI

Table 10: Decisions and open points

| No. | Decision or open point (our proposal) | Owner | Needed by | Ref. |
| --- | --- | --- | --- | --- |
| PP-01 | Confirm go-live T = Monday 3-Jan-2028 with the year-end option A | Steering committee; Head, Comptrollership | 1-Oct-2027 (we ask with the Drop 0 closure) | IQ01, DEC-01 |
| PP-02 | Confirm the Drop 0 closure on 9-Dec-2026 at the steering committee | Program Manager | 30-Nov-2026 | Drop 0 closure |
| PP-03 | Decide the scope and drop of Customer Servicing Case Management; we propose Drop 2 (development Mar - Apr 2027) through a change request | Product Owner, CSF; CCB | 30-Oct-2026 | R-02 |
| PP-04 | Decide the Data Migration V0.03 conflicts (renewals in progress, claims, submitted policies, payees, e-policy linking) | Program Manager; Head of the Renewal processing team | 30-Oct-2026 (M2) | R-03 |
| PP-05 | Confirm the environment dates: SIT 4-Jan-2027, UAT and training 19-Jul-2027, Pre-Prod 1-Oct-2027, production and DR 1-Nov-2027 | BDOI IT | 30-Nov-2026 | R-08 |
| PP-06 | Approve the early security scan in SIT in June 2027 and name the penetration test provider | BDOI Information Security | 31-May-2027 | IQ35 |
| PP-07 | Decide the Spring Boot 4 upgrade window: May - Jun 2027 (our proposal) or after hypercare | BDOI IT; CCB | 31-Mar-2027 | R-06 |
| PP-08 | Confirm the UAT sign-off date of Drop 1 (17-Dec-2027) and the hypercare exit criteria | BIBS Product Owner | 16-Jul-2027 | - |
| PP-09 | Name the UAT testers, trainers and the application support team on the dates of the dependencies DEP-18, DEP-20 and DEP-22 | Business owners; BDOI IT | As listed | - |