## Cover
PROJECT PLAN
BIBS Project Plan
Drops, milestones, sign-offs, test windows, trial migrations, cut-over and hypercare to the go-live of January 2028
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 08 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Timeline | Gantt view by month from September 2026 to May 2028; bars coloured by kind of work (legend below the chart); go-live month outlined in red | 31
Milestones | Milestones of the programme in date order, from the Drop 0 sets to the close of the true-ups | 37
Sign-offs | Sign-offs of the document sets, test results and go-live decisions | 14
Test windows | SIT and UAT windows per drop, trial migrations, dress rehearsal and the performance test | 10
Cut-over and hypercare | Cut-over phases A-H from readiness to the final true-up | 8
BDOI dependencies | Decisions, data, environments, integrations and people the plan needs from BDOI | 26
Legend
DONE | Milestone reached
OPEN | Milestone ahead
Dates are those of the BDOI drop plan and programme timeline (26-Sep-2026), the Drop 0 closure summary v2.0 and the Data Migration Handbook; dates marked proposed are iorta TechNXT proposals listed as open points for BDOI. Status as of 08-Oct-2026.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
BIBS Project Plan, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Milestones | ID | Milestone identifier
Milestones | Date | Date of the milestone
Milestones | Milestone | What is reached on the date
Milestones | Drop | BDOI drop
Milestones | Gate / sign-off | Kind of milestone
Milestones | Owner | Who reaches or signs the milestone
Milestones | Status | Done or Open | Done, Open
Milestones | Source | Document that gives the date
Sign-offs | Document set | Set or decision that is signed
Sign-offs | BRDs | BRDs covered
Sign-offs | Drop | BDOI drop
Sign-offs | Version | Version signed
Sign-offs | Due | Sign-off due date
Sign-offs | Signatories | Who signs (BRD approval sheets and closure summary)
Sign-offs | Status | Open or Done | Open, Done
Test windows | Window | Test or migration window
Test windows | Drop | BDOI drop
Test windows | Start | First day
Test windows | End | Last day
Test windows | Environment | Environment used
Test windows | Entry criteria | What must be true to start
Test windows | Exit criteria | What must be true to finish
Cut-over and hypercare | Phase | Phase of the cut-over plan of the Data Migration Handbook
Cut-over and hypercare | Name | Phase name
Cut-over and hypercare | Days | Days relative to go-live T
Cut-over and hypercare | Dates | Calendar dates for T = Monday 3-Jan-2028
Cut-over and hypercare | Main activities | What happens in the phase
Cut-over and hypercare | Owner | Who leads the phase
BDOI dependencies | ID | Dependency identifier
BDOI dependencies | Type | Decision, data, environment, integration or resource | Decision, Data, Environment, Integration, Resource
BDOI dependencies | Dependency | What BDOI provides or decides
BDOI dependencies | Provided by | BDOI or BDO owner
BDOI dependencies | Needed by | Date needed
BDOI dependencies | Needed for | Activity that waits for it
BDOI dependencies | Effect if late | What happens when it is late

## Timeline
Timeline
Gantt view by month from September 2026 to May 2028; bars coloured by kind of work (legend below the chart); go-live month outlined in red
ID | Stream | Activity | Drop | Start | End | Owner | Gate or output | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27 | Nov 27 | Dec 27 | Jan 28 | Feb 28 | Mar 28 | Apr 28 | May 28
P-01 | Requirements | Drop 0 and Drop 1 requirements and FRS (setup, upstream, downstream) | Drop 0, Drop 1 | 2026-09-01 | 2026-11-30 | Business owners; iorta Business Analyst lead | FRS signed (BRD-03, 11 and the Drop 1 BRDs)
P-02 | Requirements | Absorb the BRD versions of 8-Oct-2026 (FRS re-base, traceability, test cases, sign-off sets v2.1) | All | 2026-10-08 | 2026-11-13 | iorta Business Analyst lead | FRS and sets re-issued; clarifications raised
P-03 | Requirements | Data migration requirements, object decisions and mapping | Drop 0 | 2026-09-01 | 2026-11-30 | Data Migration Lead | Gate G1; layouts frozen v1 (M2)
P-04 | Requirements | Drop 2 requirements and FRS (Claims, Employee Benefits, Production Reconciliation, Marketing Collection extraction) | Drop 2 | 2026-12-01 | 2027-02-26 | Business owners; iorta Business Analyst lead | Drop 2 FRS signed
P-05 | Requirements | Customer Servicing Case Management (CSF addendum) through change control | Drop 2 (proposed) | 2026-10-12 | 2027-02-26 | Product Owner, CSF; Change Control Board | CR decided; FRS BRD-09 extended
P-06 | Development | Component baseline of 8-Oct-2026: Valkey 8 and the Kubernetes Gateway API | Programme | 2026-10-08 | 2026-11-30 | iorta Solution Architect; BDOI IT | Platform release on the agreed baseline
P-07 | Development | Drop 1 development, first wave (setup and upstream: Submitted Policies, Renewal foundation, EIAM sign-in, document store) | Drop 0, Drop 1 | 2026-11-02 | 2026-12-23 | iorta development team | Release into SIT
P-08 | Development | Drop 1 development, second wave (downstream: Renewal completion, bank channels, changes from the signed FRS) | Drop 1 | 2027-01-04 | 2027-02-26 | iorta development team | Release into SIT
P-09 | Development | Migration Console and loaders | Drop 0 | 2026-11-02 | 2027-03-31 | iorta Migration Lead | Ready for Trial migration 1
P-10 | Development | Drop 2 development, third wave (Claims, Employee Benefits without portal, CSF, EGL, EDP and insurer exchanges, other reports) | Drop 2 | 2027-03-01 | 2027-04-30 | iorta development team | Release into SIT
P-11 | Development | Integrations with BDO systems through Apigee X (EIAM, UIDM-ISC, CCM, LMS, HL-LOAS, PMS, CMS / New BOB, OBPCS, Old BOB, AFTS) | Drop 0, Drop 1 | 2027-01-04 | 2027-06-30 | BDOI IT; BDO IT EIAM, IGA and API teams; iorta Solution Architect | Integration test passed in SIT
P-12 | Development | Spring Boot 4 assessment (proposed) and upgrade window if BDOI approves | Programme | 2027-01-11 | 2027-06-25 | iorta Solution Architect; BDOI IT; Change Control Board | Decision by 31-Mar-2027; upgraded release before Trial migration 2
P-13 | Testing | Drop 1 system integration test (SIT) | Drop 0, Drop 1 | 2027-01-04 | 2027-07-30 | iorta QA lead | SIT exit report; UAT readiness statement
P-14 | Testing | Drop 2 system integration test (SIT) | Drop 2 | 2027-07-01 | 2027-09-30 | iorta QA lead | SIT exit report; UAT readiness statement
P-15 | Testing | Drop 1 user acceptance test (UAT), end to end on migrated data | Drop 0, Drop 1 | 2027-08-02 | 2027-12-17 | BIBS Product Owner; business owners | UAT sign-off certificates
P-16 | Testing | Drop 2 user acceptance test (UAT) | Drop 2 | 2027-10-01 | 2027-11-30 | Business owners of BRD-07 and BRD-08 | UAT sign-off certificates
P-17 | Testing | Early security scan in SIT (proposed) | Programme | 2027-06-01 | 2027-06-30 | BDOI Information Security | Findings triaged before UAT
P-18 | Testing | Performance and penetration test | Programme | 2027-11-01 | 2027-12-15 | BDOI IT; BDOI Information Security | Test reports; no open critical or high finding
P-19 | Data migration | SIT migration: Trial migrations 1 (19-30 Apr) and 2 (5-16 Jul) | Drop 0 | 2027-04-19 | 2027-07-16 | Data Migration Lead; iorta Migration Lead | L1-L5 reconciled; Migration Clearing 0.00
P-20 | Data migration | UAT migration: Trial migrations 3 (2-13 Aug) and 4 (4-15 Oct) | Drop 0 | 2027-08-02 | 2027-10-15 | Data Migration Lead; iorta Migration Lead | Business verification on screen; timed as a cut-over
P-21 | Data migration | Dress rehearsal on production-sized data (reserve slot 6-10 Dec 2027) | Drop 0 | 2027-11-15 | 2027-11-26 | Data Migration Lead; iorta Migration Lead | Dress rehearsal report signed
P-22 | Readiness | Environments: SIT, UAT, Pre-Prod, production and DR on managed Kubernetes | Programme | 2026-11-02 | 2027-11-01 | BDOI IT; iorta infrastructure team | Each environment accepted on its date
P-23 | Readiness | Organisational change management and communications | Programme | 2026-10-12 | 2028-02-02 | BIBS Product Owner; iorta change and training lead | Readiness surveys; go-live communications
P-24 | Readiness | Key user training (UAT testers) and train-the-trainer | Programme | 2027-07-19 | 2027-09-17 | iorta change and training lead | Key users certified; BDOI trainers certified
P-25 | Readiness | End-user training by persona | Programme | 2027-10-18 | 2027-12-10 | BDOI trainers; iorta change and training lead | 95 percent of named users trained and assessed
P-26 | Readiness | Knowledge transfer to BDOI application support and BDO IT operations | Programme | 2027-06-07 | 2028-02-02 | iorta Project Manager; BDOI IT | Readiness assessment passed; hand-over at hypercare exit
P-27 | Readiness | Operational and production readiness review (ORR / PRR) | Programme | 2027-12-01 | 2027-12-31 | BDOI IT; iorta Project Manager | Evidence pack by 15-Dec-2027; ORR / PRR approved
P-28 | Cut-over | Cut-over phases A-E: readiness, pre-load and deltas, legacy freeze, production load, reconciliation and go / no-go | Programme | 2027-12-04 | 2028-01-02 | Go / no-go board; Data Migration Lead | Go decision on T-1 (2-Jan-2028)
P-29 | Cut-over | Go-live of all modules together (T = Monday 3-Jan-2028) | Programme | 2028-01-03 | 2028-01-03 | Steering committee | BIBS in production
P-30 | Cut-over | Hypercare and true-up 1 (T+1 to T+30) | Programme | 2028-01-04 | 2028-02-02 | iorta Project Manager; BDOI application support | Hypercare exit; hand-over to production support
P-31 | Cut-over | Final true-up and legacy GL close (T+31 to T+120) | Programme | 2028-02-03 | 2028-05-02 | Head, Comptrollership | True-ups closed; legacy GL locked 18-Apr-2028
Legend
Requirements and sign-off
Development and configuration
Testing
Data migration
Readiness, training and support
Cut-over, go-live and hypercare

## Milestones
Milestones
Milestones of the programme in date order, from the Drop 0 sets to the close of the true-ups
ID | Date | Milestone | Drop | Gate / sign-off | Owner | Status | Source
MS-01 | 2026-10-05 | Drop 0 sign-off sets v2.0 issued (BRD-03, BRD-11, BRD-13) with the BDOI answers to DMQ36-DMQ39 (M0) | Drop 0 | Issue | iorta Project Manager | Done | Drop 0 closure summary; Handbook M0
MS-02 | 2026-10-08 | New versions of ten BDOI documents received; component baseline decided (PostgreSQL 16, Valkey 8, Kafka 3.9, OpenJDK 21, Spring Boot 3.5, Node 22 LTS, nginx, managed Kubernetes, Gateway API) | All | Baseline | BIBS Product Owner; BDOI IT | Done | Source documents of 8-Oct-2026; client decisions of 8-Oct-2026
MS-03 | 2026-10-16 | Scope-shaping migration decisions (M1): DEC-02, DEC-03 (part), DEC-11, DEC-12 | Drop 0 | Decision | Business owners; Head, Comptrollership | Open | Handbook M1; Drop 0 closure DEP-01
MS-04 | 2026-10-23 | FRS re-based on the BRD versions of 8-Oct-2026 issued for review (proposed) | All | Issue | iorta Business Analyst lead | Open | Proposed
MS-05 | 2026-10-30 | BRD-13 Data Migration set signed; object decisions (gate G1); layouts frozen v1 (M2); decision on the Data Migration V0.03 conflicts and on Customer Servicing Case Management (proposed) | Drop 0 | Sign-off | Data Migration Lead; Program Manager | Open | Drop 0 closure exit criteria; Handbook M2
MS-06 | 2026-11-13 | Drop 1 FRS issued with the BDOI comments resolved | Drop 1 | Issue | iorta Business Analyst lead | Open | Programme alignment pack, section 4.1
MS-07 | 2026-11-30 | BRD-03 Product Maintenance set signed; Drop 1 FRS signed (BRD-01, 02, 04, 05, 06, 09, 10, 12) | Drop 0, Drop 1 | Sign-off | Product owners of each BRD | Open | Drop 0 closure; alignment pack
MS-08 | 2026-12-01 | BRD-11 User Access Maintenance set signed; configuration drafts due (D1) | Drop 0 | Sign-off | Product Owner, Marketing Business System; BDOI Information Security; BDOI IT | Open | Drop 0 closure D1
MS-09 | 2026-12-09 | Drop 0 closed by the steering committee; Drop 1 opened (proposed date) | Drop 0 | Steering committee | Program Manager, Business Project Services | Open | Drop 0 closure summary, chapter 9
MS-10 | 2026-12-18 | Drop 1 test plans approved | Drop 1 | Approval | Business owners; iorta QA lead | Open | Alignment pack
MS-11 | 2027-01-04 | SIT environment ready; platform set-up for Drop 1 SIT (D2); Drop 1 SIT starts | Drop 1 | Entry | BDOI IT; Head, Comptrollership | Open | Drop 0 closure D2, DEP-02
MS-12 | 2027-01-29 | First full extracts with control files and volumes (M3) | Drop 0 | Data | BDOI IT | Open | Handbook M3; DEP-03
MS-13 | 2027-01-31 | Drop 2 integration specifications (EGL, EDP, CARMS, insurer exchanges); EIAM and UIDM-ISC specifications (proposed date within Q1 2027) | Drop 1, Drop 2 | Data | BDOI IT; BDO IT EIAM and IGA teams | Open | Alignment pack; DEC-05
MS-14 | 2027-02-26 | Drop 2 FRS signed (BRD-07, BRD-08); Drop 1 development complete | Drop 1, Drop 2 | Sign-off | Product Owners, Claims and Employee Benefits | Open | Alignment pack
MS-15 | 2027-03-31 | Migration Console and loaders ready; Spring Boot 4 decision (proposed) | Drop 0 | Readiness | iorta Migration Lead; BDOI IT | Open | Alignment pack; proposed
MS-16 | 2027-04-09 | Extracts for Trial migration 1 (M4); reference data for SIT (D3); role-to-permission matrix and SIT / UAT users | Drop 0 | Data | BDOI IT; Business Administration; BDOI Information Security | Open | Handbook M4; D3; DEP-05
MS-17 | 2027-04-30 | Drop 2 development complete | Drop 2 | Release | iorta Project Manager | Open | Alignment pack
MS-18 | 2027-06-18 | Code maps approved, including the package code map (M5, D4) | Drop 0 | Approval | Data owners; TSU | Open | Handbook M5; DEP-06
MS-19 | 2027-06-30 | Drop 2 test plans approved; early security scan in SIT completed (proposed) | Drop 2 | Approval | Business owners; BDOI Information Security | Open | Alignment pack
MS-20 | 2027-07-16 | UAT plans and sign-off forms issued; values for UAT (D5); UAT testers named | Drop 1 | Readiness | BIBS Product Owner; business owners | Open | Drop 0 closure D5
MS-21 | 2027-07-30 | Drop 1 SIT exit; UAT readiness statement; key users trained | Drop 1 | Exit | iorta QA lead; BIBS Product Owner | Open | Alignment pack
MS-22 | 2027-08-02 | Drop 1 UAT starts on migrated data (Trial migration 3) | Drop 1 | Entry | BIBS Product Owner | Open | BDOI timeline
MS-23 | 2027-09-30 | Drop 2 SIT exit and UAT readiness statement | Drop 2 | Exit | iorta QA lead | Open | Alignment pack
MS-24 | 2027-10-01 | Pre-Prod ready; cut-over date, window, fallback and decommissioning criteria agreed; year-end option A confirmed (M6) | Programme | Decision | Program Manager; Head, Comptrollership; BDOI IT | Open | Handbook M6; DEC-01; DEC-13
MS-25 | 2027-11-01 | Production values of every configuration item (D6); production and DR environments ready (proposed) | Programme | Readiness | Configuration owners; BDOI IT | Open | Drop 0 closure D6
MS-26 | 2027-11-26 | Dress rehearsal completed and its report signed | Drop 0 | Exit | Data Migration Lead; iorta Migration Lead | Open | Handbook
MS-27 | 2027-11-30 | Drop 2 UAT signed | Drop 2 | Sign-off | Product Owners, Claims and Employee Benefits | Open | BDOI timeline
MS-28 | 2027-12-14 | Renewal processing team ready for the January expiries (T-20) | Drop 1 | Readiness | Head of the Renewal processing team | Open | Cut-over task CT-013
MS-29 | 2027-12-15 | ORR / PRR evidence pack; performance and penetration test closed | Programme | Readiness | BDOI IT; BDOI Information Security | Open | Alignment pack
MS-30 | 2027-12-17 | Drop 1 UAT signed; end-user training complete; go-live readiness review (proposed) | Drop 1 | Sign-off | Steering committee | Open | Proposed
MS-31 | 2027-12-27 | Code map and reference value freeze (D7, T-7) | Drop 0 | Freeze | Data Migration Lead | Open | Drop 0 closure D7
MS-32 | 2027-12-31 | Last legacy end of day and final extracts (T-3) | Programme | Cut-over | BDOI IT | Open | Cut-over phase C
MS-33 | 2028-01-02 | Reconciliation, verification and go / no-go (T-1) | Programme | Go / no-go | Go / no-go board | Open | Cut-over phase E
MS-34 | 2028-01-03 | Go-live of BIBS, all modules together (T) | Programme | Go-live | Steering committee | Open | BDOI answer A1
MS-35 | 2028-01-21 | True-up 1 posted, reconciled and signed (T+18) | Programme | Sign-off | Head, Comptrollership | Open | Cut-over CT-084
MS-36 | 2028-02-02 | First month-end close completed; hypercare exit; hand-over to production support (T+30) | Programme | Exit | Go / no-go board | Open | Cut-over CT-085, CT-086
MS-37 | 2028-05-02 | True-ups closed (T+120); legacy GL locked on 18-Apr-2028 | Programme | Closure | Head, Comptrollership | Open | Cut-over phase H

## Sign-offs
Sign-offs
Sign-offs of the document sets, test results and go-live decisions
Document set | BRDs | Drop | Version | Due | Signatories | Status
Data Migration sign-off set | BRD-13 | Drop 0 | v2.0 (re-base on BRD V0.03 in v2.1) | 2026-10-30 | Program Manager, Business Project Services; Data Migration Lead; Head, Comptrollership; Head, Operations; BDOI IT | Open
Product Maintenance sign-off set | BRD-03 | Drop 0 | v2.0 | 2026-11-30 | Product Owner, Marketing Business System; MBS; TSU; Business Project Services | Open
User Access Maintenance sign-off set | BRD-11 | Drop 0 | v2.0 | 2026-12-01 | Product Owner, Marketing Business System; BDOI Information Security; BDOI IT; Business Administrators | Open
Drop 0 closure summary and configuration inputs | BRD-03, 11, 13 | Drop 0 | v2.0 | 2026-12-09 | Steering committee (chair: Program Manager, Business Project Services) | Open
Drop 1 FRS and sign-off sets | BRD-01, 02, 04, 05, 06, 09, 10, 12 | Drop 1 | v2.1 / next minor (re-base on 8-Oct-2026) | 2026-11-30 | Product owner of each BRD; Business Project Services (traceability); BDOI IT (Technical Specification) | Open
Drop 1 test plans | Drop 1 BRDs | Drop 1 | v1.x | 2026-12-18 | Business owners; iorta QA lead | Open
Drop 2 FRS | BRD-07, BRD-08 (and CSF Case Management if approved) | Drop 2 | v1.x | 2027-02-26 | Product Owners, Claims and Employee Benefits; Business Project Services | Open
Drop 2 test plans | BRD-07, BRD-08 | Drop 2 | v1.x | 2027-06-30 | Business owners; iorta QA lead | Open
Drop 1 UAT sign-off certificates | Drop 0 and Drop 1 BRDs | Drop 1 | - | 2027-12-17 | Product owner of each BRD; BIBS Product Owner | Open
Drop 2 UAT sign-off certificates | BRD-07, BRD-08 | Drop 2 | - | 2027-11-30 | Product owners of BRD-07 and BRD-08 | Open
Dress rehearsal report | BRD-13 | Drop 0 | - | 2027-11-26 | Data Migration Lead; iorta Migration Lead | Open
ORR / PRR approval | Programme | Programme | - | 2027-12-31 | Head, BDOI IT; Head, BDOI Information Security; iorta Project Manager | Open
Go / no-go decision | Programme | Programme | - | 2028-01-02 | Go / no-go board | Open
Hypercare exit and hand-over | Programme | Programme | - | 2028-02-02 | Go / no-go board; BDOI application support; BDO IT operations | Open

## Test windows
Test windows
SIT and UAT windows per drop, trial migrations, dress rehearsal and the performance test
Window | Drop | Start | End | Environment | Entry criteria | Exit criteria
Drop 1 SIT | Drop 0, Drop 1 | 2027-01-04 | 2027-07-30 | SIT | Test plans approved (18-Dec-2026); SIT environment and D2 set-up ready (4-Jan-2027); release notes delivered | All Must-have cases passed; no open Severity 1 or 2 incident; Severity 3 with a workaround agreed; regression passed on the last release
Drop 2 SIT | Drop 2 | 2027-07-01 | 2027-09-30 | SIT | Drop 2 test plans approved (30-Jun-2027); integration specifications agreed | As Drop 1 SIT; integration test with EGL, EDP and insurer exchanges passed
Trial migration 1 | Drop 0 | 2027-04-19 | 2027-04-30 | SIT | Extracts M4 received (9-Apr-2027); Migration Console ready | Profiling report to the owners; timings recorded
Trial migration 2 | Drop 0 | 2027-07-05 | 2027-07-16 | SIT | Code maps approved (M5, 18-Jun-2027) | All objects end to end; L1-L5 reconciled; Migration Clearing 0.00
Drop 1 UAT (end to end) | Drop 0, Drop 1 | 2027-08-02 | 2027-12-17 | UAT | SIT exit; UAT readiness statement (30-Jul-2027); UAT plans and sign-off forms (16-Jul-2027); key users trained; Trial migration 3 loaded | Every UAT scenario passed or accepted with a workaround; sign-off certificate per BRD
Trial migration 3 | Drop 0 | 2027-08-02 | 2027-08-13 | UAT | Trial migration 2 exit | Business verification on screen; UAT runs on migrated data
Drop 2 UAT | Drop 2 | 2027-10-01 | 2027-11-30 | UAT | Drop 2 readiness statement (30-Sep-2027) | Sign-off certificates of BRD-07 and BRD-08
Trial migration 4 | Drop 0 | 2027-10-04 | 2027-10-15 | UAT | Fixes from Trial migration 3 released | Timed as a cut-over; go-live renewal extraction; a test opening-balance adjustment
Performance and penetration test | Programme | 2027-11-01 | 2027-12-15 | Pre-Prod | Pre-Prod ready (1-Oct-2027) at production size | Peak of 429 concurrent users within the response-time targets; no open critical or high finding
Dress rehearsal | Drop 0 | 2027-11-15 | 2027-11-26 | Pre-Prod | Production values D6 loaded (1-Nov-2027) | Full volume within the window with 20 percent margin; rollback rehearsed

## Cut-over and hypercare
Cut-over and hypercare
Cut-over phases A-H from readiness to the final true-up
Phase | Name | Days | Dates | Main activities | Owner
A | Readiness | T-30 to T-15 | 4 to 19 Dec 2027 | Dress rehearsal confirmed; cut-over team, command centre and hypercare roster named; communications to branches, insurers and bank channels; Renewal team readiness (14-Dec-2027) | Program Manager; Data Migration Lead
B | Pre-load and daily deltas | T-14 to T-4 | 20 to 30 Dec 2027 | Reference data and clients pre-loaded; daily deltas; map freeze on 27-Dec-2027 (T-7) | Data Migration Lead; BDOI IT
C | Legacy freeze and final extracts | T-3 | Fri 31 Dec 2027 | Last legacy end of day; preliminary December trial balance signed as the provisional opening | BDOI IT; Head, Comptrollership
D | Production load | T-2 | Sat 1 Jan 2028 | Final extracts validated and loaded in load order | iorta Migration Lead
E | Reconciliation, verification and go / no-go | T-1 | Sun 2 Jan 2028 | L1-L5 reconciliation; business verification; go / no-go decision | Go / no-go board
F | Go-live | T | Mon 3 Jan 2028 | Command centre opens 07:00; go-live renewal extraction; users start | iorta Project Manager
G | Hypercare and true-up 1 | T+1 to T+30 | 4 Jan to 2 Feb 2028 | Daily hypercare check; issue triage at 10:00 and 16:00; week-1 review; true-up 1 (21-Jan-2028); first month-end close; hypercare exit (2-Feb-2028) | iorta Project Manager; BDOI application support
H | Final true-up and legacy GL close | T+31 to T+120 | Feb to 2 May 2028 | Interim true-up 2 if needed; audited FY2027 statements; final true-up; legacy GL locked (18-Apr-2028); true-ups closed | Head, Comptrollership

## BDOI dependencies
BDOI dependencies
Decisions, data, environments, integrations and people the plan needs from BDOI
ID | Type | Dependency | Provided by | Needed by | Needed for | Effect if late
DEP-01 | Decision | Answers to the M1 and M2 decisions of the Data Migration set (DEC-02, DEC-03, DEC-11, DEC-12) | BDOI business owners | 2026-10-16 | Migration layouts and object scope | Layouts frozen late; Trial migration 1 scope reduced
DEP-02 | Decision | Position on the Data Migration BRD V0.03 conflicts: renewals in progress (BRID_MIG 12.1 against DMQ37), claims, submitted policies, payees and e-policy linking in scope | Program Manager; Head of the Renewal processing team; Head, Comptrollership | 2026-10-30 | Data object register and Handbook v2.1 | New layouts after M2; migration effort and trial scope change
DEP-03 | Decision | Scope and drop of Customer Servicing Case Management (CSF addendum, BRCSFCM.001-.012) | Product Owner, CSF; Change Control Board | 2026-10-30 | FRS BRD-09 extension and the Drop 2 plan | Case Management cannot be delivered for go-live
DEP-04 | Decision | Sign-off of the Drop 0 sets (BRD-13, BRD-03, BRD-11) and of the Drop 1 FRS | Product owners | 2026-11-30 | Freeze of the Drop 1 development scope | Development starts on unsigned scope; rework
DEP-05 | Data | Organisation, chart of accounts, accounting rules and bank accounts for Drop 1 SIT (D2) | Head, Comptrollership | 2027-01-04 | Drop 1 SIT postings | SIT runs on seed values; postings retested
DEP-06 | Environment | SIT environment on managed Kubernetes with PostgreSQL 16, Valkey 8, Kafka 3.9, document store and Gateway API | BDOI IT | 2027-01-04 | Drop 1 SIT | SIT start slips day for day
DEP-07 | Integration | EIAM sign-in specification (tenant, claims, session life, OIDC or SAML 2.0) and application registration | BDO IT EIAM team | 2027-01-31 | Directory sign-in in SIT | Sign-in stays local in SIT; directory sign-in tested late
DEP-08 | Integration | UIDM-ISC option (accounts only, accounts and roles, or aggregation only) and SCIM provisioning connector | BDO IT IGA team | 2027-01-31 | Provisioning in SIT | User provisioning tested late; manual user loading at go-live
DEP-09 | Data | First full extracts with control files and volumes (M3) | BDOI IT | 2027-01-29 | Profiling and load sizing | Trial migration 1 on partial data
DEP-10 | Integration | Drop 2 integration specifications: EGL, EDP (SD 11), CARMS, insurer exchanges | BDOI IT | 2027-01-31 | Drop 2 development (Mar-Apr 2027) | Drop 2 interfaces descoped or delivered after go-live
DEP-11 | Integration | Bank channel layouts and transport: CMS / New BOB, OBPCS, Old BOB, AFTS, PMS | BDOI IT | 2027-02-26 | Cashiering and Disbursement channels in SIT | Manual uploads at go-live
DEP-12 | Integration | CCM sending mode, sender addresses and attachment limits | BDOI IT | 2027-02-26 | Renewal Advices, e-policies and notifications | E-mail tested late
DEP-13 | Integration | Apigee X proxies, products and credentials for the BIBS integrations in SIT, UAT and production | BDO IT API team | 2027-03-31 | Integration test | Integration test slips into UAT
DEP-14 | Decision | Spring Boot 4 upgrade before go-live or after hypercare | BDOI IT; Change Control Board | 2027-03-31 | Upgrade window May-Jun 2027 | Upgrade forced late or carried into production support
DEP-15 | Decision | DR region and data residency (IQ26) | BDOI IT; BDOI Information Security | 2027-03-31 | Production and DR set-up | DR not ready at go-live
DEP-16 | Data | Role-to-permission matrix and the users of the SIT and UAT testers (D3) | Business Administration; BDOI Information Security | 2027-04-09 | Access in SIT and UAT | Testers without access; UAT starts late
DEP-17 | Data | Code maps approved, including the package code map (M5) | Data owners; TSU | 2027-06-18 | Trial migration 2 | Trial migration 2 incomplete
DEP-18 | Resource | Named application support team (L1 and L2) and BDO IT operations staff for knowledge transfer | BDOI IT; BDO IT operations | 2027-05-31 | Knowledge transfer from 7-Jun-2027 | Hand-over at hypercare exit at risk
DEP-19 | Resource | Penetration test provider named; early SIT scan approved (IQ35) | BDOI Information Security | 2027-05-31 | Security tests | Findings arrive in December 2027
DEP-20 | Resource | UAT testers named per BRD (at least two per business unit) and released for the UAT windows | Business owners | 2027-07-16 | UAT | UAT coverage reduced
DEP-21 | Environment | UAT environment and training environment with training users | BDOI IT | 2027-07-19 | Key user training and UAT | Training and UAT start late
DEP-22 | Resource | BDOI trainers named for train-the-trainer (one per business unit and persona group) | Business owners | 2027-07-30 | Train-the-trainer from 6-Sep-2027 | End-user training delivered by iorta only; capacity limit
DEP-23 | Environment | Pre-Prod at production size | BDOI IT | 2027-10-01 | Performance test and dress rehearsal | Dress rehearsal not production-sized
DEP-24 | Decision | Year-end option A confirmed; point of no return confirmed (DEC-01, DEC-13) | Head, Comptrollership; Program Manager | 2027-10-01 | Cut-over calendar and GL opening | Cut-over calendar changes
DEP-25 | Environment | Production and DR environments | BDOI IT | 2027-11-01 | Production values, ORR and cut-over | Go-live date at risk
DEP-26 | Data | Production values of every configuration item (D6) | Configuration owners | 2027-11-01 | Dress rehearsal | Dress rehearsal on non-production values

## _lists (hidden)
Done | Open | Decision
Open | Done | Data
Environment
Integration
Resource