## Cover
RACI MATRIX
BIBS RACI Matrix
Who is responsible, accountable, consulted and informed for each activity of the programme
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 08 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
RACI | One row per activity; role codes are explained on the sheet Roles | 59
Roles | The roles of the matrix with their organisation | 24
R = responsible (does the work); A = accountable (approves; exactly one per activity); C = consulted before; I = informed after. BDOI roles first, then iorta TechNXT roles.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
BIBS RACI Matrix, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
RACI | Area | Phase or area of the programme
RACI | Activity | Activity
RACI | Deliverable or evidence | What shows the activity is done
RACI | SC | Steering committee (BDOI) | R, A, C, I, A/R
RACI | PGM | Program Manager, Business Project Services (BDO Unibank ESG) | R, A, C, I, A/R
RACI | BPO | BIBS Product Owner (BDOI) | R, A, C, I, A/R
RACI | BO | Business owner of the BRD (BDOI) | R, A, C, I, A/R
RACI | BPS | Business Project Services analysts (BDO Unibank ESG) | R, A, C, I, A/R
RACI | KU | Key users and UAT testers (BDOI) | R, A, C, I, A/R
RACI | DML | Data Migration Lead and data owners (BDOI) | R, A, C, I, A/R
RACI | COMP | Head, Comptrollership (BDOI) | R, A, C, I, A/R
RACI | CMP | Compliance (BDOI) | R, A, C, I, A/R
RACI | BIT | BDOI IT (BDOI) | R, A, C, I, A/R
RACI | ISEC | BDOI Information Security (BDOI) | R, A, C, I, A/R
RACI | EIAM | BDO IT EIAM team (BDO Unibank) | R, A, C, I, A/R
RACI | IGA | BDO IT IGA team (BDO Unibank) | R, A, C, I, A/R
RACI | API | BDO IT API team (BDO Unibank) | R, A, C, I, A/R
RACI | OPS | BDO IT operations (BDO Unibank) | R, A, C, I, A/R
RACI | APS | BDOI application support (BDOI) | R, A, C, I, A/R
RACI | IPM | iorta Project Manager (iorta TechNXT) | R, A, C, I, A/R
RACI | ISA | iorta Solution Architect (iorta TechNXT) | R, A, C, I, A/R
RACI | IBA | iorta Business Analyst lead (iorta TechNXT) | R, A, C, I, A/R
RACI | IDEV | iorta development team (iorta TechNXT) | R, A, C, I, A/R
RACI | IQA | iorta QA lead and testers (iorta TechNXT) | R, A, C, I, A/R
RACI | IDO | iorta infrastructure team (iorta TechNXT) | R, A, C, I, A/R
RACI | IML | iorta Migration Lead (iorta TechNXT) | R, A, C, I, A/R
RACI | ICT | iorta change and training lead (iorta TechNXT) | R, A, C, I, A/R
Roles | Code | Column code on the sheet RACI
Roles | Role | Role
Roles | Organisation | BDOI, BDO Unibank or iorta TechNXT
Roles | What the role does in the programme | Scope of the role
Roles | Accountable for | Number of activities where the role is accountable
Roles | Responsible for | Number of activities where the role is responsible

## RACI
RACI
One row per activity; role codes are explained on the sheet Roles
Area | Activity | Deliverable or evidence | SC | PGM | BPO | BO | BPS | KU | DML | COMP | CMP | BIT | ISEC | EIAM | IGA | API | OPS | APS | IPM | ISA | IBA | IDEV | IQA | IDO | IML | ICT
Governance | Steering committee: direction, drop closure, go-live decision | Minutes; decisions | SC: A; PGM: R; BPO: C; BO: C; BIT: I; ISEC: I; IPM: R
Governance | Programme plan and weekly programme meeting | Project Plan; weekly status report | SC: I; PGM: A; BPO: C; BO: C; BIT: C; IPM: R
Governance | RAID log upkeep and escalation of High items | RAID log | SC: I; PGM: A; BPO: C; BO: C; BIT: C; ISEC: C; IPM: R
Governance | Change Control Board: CR approval, rejection, deferral | Signed CR form; change register | SC: I; PGM: C; BPO: A; BO: C; CMP: C; BIT: C; IPM: R; ISA: C; IBA: C
Requirements | Issue BRDs and new BRD versions | BRD with approval sheet | BO: A; BPS: R; KU: C; IPM: I; IBA: I
Requirements | Write and re-base the FRS, test plans and sign-off sets | FRS; sign-off set | BPO: I; BO: C; BPS: I; KU: C; IPM: A; ISA: C; IBA: R; IQA: C
Requirements | Review the FRS and record comments | Comments log of the sign-off workbook | BO: A; BPS: R; KU: R; CMP: C; BIT: C; ISEC: C; IPM: I
Requirements | Decide the proposed business rules and clarifications | Decided CLR rows; decision log | BPO: I; BO: A; BPS: C; KU: R; CMP: C; IPM: I; IBA: C
Requirements | Sign the FRS and sign-off set of a BRD | Sign-off certificate | SC: I; BO: A/R; BPS: C; BIT: C; ISEC: C; IPM: I
Requirements | Traceability check against the BRD | Traceability chapter checked | PGM: A; BO: I; BPS: R; IBA: C
Design | Solution architecture and component baseline | Architecture documents; baseline decisions | BPO: I; BIT: A; ISEC: C; API: C; OPS: C; IPM: I; ISA: R
Design | Technical Specification per sign-off set | Technical Specification | BIT: A; ISEC: C; IPM: I; ISA: R; IDEV: C
Design | Interface contracts with BDO systems | Interface contract per system | BO: C; BIT: A; API: C; IPM: I; ISA: R; IDEV: C
Design | Identity and access design: EIAM sign-in, UIDM-ISC provisioning, MFA, break-glass | Identity design; role matrix | BPO: I; BIT: C; ISEC: A; EIAM: C; IGA: C; ISA: R
Design | UX screen design and screen register | UX screen deck; screen register | BPO: A; BO: C; KU: C; IBA: R; ICT: I
Design | Data migration design: objects, layouts, code maps, reconciliation | Handbook; Migration Workbook | PGM: I; BO: C; DML: A; CMP: C; BIT: C; IML: R
Design | Infrastructure sizing and IER restatement | Restated IER | PGM: I; BIT: A; OPS: C; ISA: R; IDO: C
Development | Application development and configuration | Release with release notes | BPO: I; IPM: A; ISA: C; IBA: C; IDEV: R
Development | Code review and quality gates on every change | Gate results per change | IPM: I; ISA: A; IDEV: R; IQA: C
Development | Security scans and remediation of findings | Scan reports; SBOM | BIT: I; ISEC: C; ISA: A; IDEV: R; IDO: R
Development | EIAM application registration and conditional access | Registered application; claims | BIT: I; ISEC: C; EIAM: A/R; ISA: C
Development | UIDM-ISC connector and provisioning set-up | Connector configured | BIT: I; ISEC: C; IGA: A/R; ISA: C
Development | Apigee X proxies, products and credentials | Proxies per environment | BIT: C; API: A/R; IPM: I; ISA: C
Development | Integration development on the BIBS side | Interfaces in the release | BIT: C; API: C; IPM: I; ISA: A; IDEV: R
Development | Configuration inputs (lists, parameters, products, chart of accounts) | Configuration workbook rows | BO: A; KU: R; DML: C; IPM: I; IBA: R
Test | Test plans and test cases per BRD | Approved test plan | BO: A; KU: C; IPM: I; IBA: C; IQA: R
Test | System integration test (SIT) and regression | SIT exit report | BPO: I; BO: I; IPM: A; IBA: C; IDEV: C; IQA: R
Test | Integration test with BDO systems | Integration test report | BIT: A/R; EIAM: C; IGA: C; API: C; IPM: I; ISA: C; IQA: R
Test | UAT preparation: scenarios, testers, data, sign-off forms | UAT plan | BPO: A; BO: C; KU: R; IPM: I; IBA: C; IQA: R
Test | UAT execution | UAT results | BPO: I; BO: A; KU: R; IPM: I; IBA: C; IQA: C
Test | Performance test | Performance test report | SC: I; BIT: A; OPS: C; ISA: C; IQA: R; IDO: R
Test | Penetration test and security sign-off | Penetration test report; acceptance | SC: I; BIT: C; ISEC: A/R; ISA: C; IDO: C
Test | Usability tests with users | Usability findings and fixes | BPO: A; BO: I; KU: C; IBA: C; ICT: R
Migration | Extracts from the legacy systems with control files | Extract files | PGM: I; DML: C; BIT: A/R; IML: C
Migration | Data cleansing and code maps | Approved code maps | BO: I; KU: R; DML: A/R; IML: C
Migration | Trial migrations and the dress rehearsal | Trial reports; dress rehearsal report | PGM: I; DML: A; BIT: C; IQA: C; IML: R
Migration | Reconciliation sign-off of the financial objects | Signed reconciliation | PGM: I; DML: R; COMP: A; IML: C
Migration | Cut-over execution and go / no-go | Cut-over log; go decision | SC: A; BO: C; KU: I; DML: R; BIT: R; IPM: C; IML: R
Deployment | Environment provisioning (SIT, UAT, Pre-Prod, production, DR) | Accepted environment | BIT: A/R; OPS: R; IPM: I; ISA: C; IDO: C
Deployment | Release deployment to SIT and UAT | Deployment record | BIT: C; IPM: A; IQA: I; IDO: R
Deployment | Release deployment to Pre-Prod and production | Change record; deployment record | BPO: I; BIT: A; ISEC: C; OPS: R; IDO: R
Deployment | DR set-up and DR drill | DR drill report | SC: I; BIT: A; OPS: R; ISA: C; IDO: C
Deployment | Operational and production readiness review (ORR / PRR) | ORR / PRR evidence pack | SC: I; BIT: A; ISEC: C; OPS: C; APS: C; IPM: R; IDO: R
Training | Training needs and impact analysis | Training needs per persona | BPO: A; BO: C; KU: C; IPM: I; ICT: R
Training | Training material, user guides and quick-reference guides | Material per persona | BPO: A; BO: I; KU: C; IBA: C; ICT: R
Training | Training environment and training users | Training environment ready | BPO: I; BIT: A/R; IDO: R; ICT: C
Training | Train-the-trainer | Certified BDOI trainers | BPO: A; BO: I; KU: C; ICT: R
Training | End-user training delivery and assessment | Attendance and assessment records | SC: I; BPO: C; BO: A; KU: R; ICT: R
Training | Communications to users, branches, insurers and bank channels | Communication log | SC: I; BPO: A; BO: R; CMP: C; ICT: R
Support | Knowledge transfer to application support and BDO IT operations | KT sessions; readiness assessment | SC: I; BIT: A; OPS: C; APS: C; IPM: R; ISA: R; IDO: R
Support | Hypercare (T+1 to T+30) | Daily hypercare report; issue log | SC: I; BO: C; BIT: C; APS: R; IPM: A; IDEV: R; IQA: R; IML: R
Support | L1 service desk after go-live | Tickets logged and routed | BO: I; BIT: A; OPS: C; APS: R
Support | L2 application support (configuration, data, user access) | Resolved tickets | BO: I; KU: C; BIT: A; APS: R; IPM: C
Support | L3 product support (fixes and patches) | Patch releases | BIT: I; APS: C; IPM: A; ISA: C; IDEV: R
Support | Vulnerability patching after go-live | Patch releases within the agreed times | SC: I; BIT: C; ISEC: A; OPS: R; ISA: C; IDEV: R
Sign-off | Drop closure | Drop closure summary signed | SC: A; PGM: R; BO: C; BIT: C; ISEC: C; IPM: I
Sign-off | UAT sign-off per BRD | UAT sign-off certificate | SC: I; BPO: I; BO: A; KU: R; IQA: C
Sign-off | Go-live approval | Go-live decision | SC: A; PGM: R; BO: C; KU: I; BIT: C; ISEC: C; APS: I; IPM: C
Sign-off | Hypercare exit and hand-over to production support | Hand-over record | SC: A; BO: I; BIT: C; OPS: C; APS: C; IPM: R

## Roles
Roles
The roles of the matrix with their organisation
Code | Role | Organisation | What the role does in the programme | Accountable for | Responsible for
SC | Steering committee | BDOI | Chaired by the Program Manager, Business Project Services; BIBS Product Owner, heads of Operations, Comptrollership, Marketing, Compliance, BDOI IT and Information Security; iorta TechNXT engagement lead | 5 | 0
PGM | Program Manager, Business Project Services | BDO Unibank ESG | Plan, drops, budget and traceability check against the BRDs | 3 | 3
BPO | BIBS Product Owner | BDOI | Owner of the BIBS scope and backlog of change requests; chairs the Change Control Board | 8 | 0
BO | Business owner of the BRD | BDOI | Product owner or department head named on the BRD approval sheet (for example Head, Comptrollership for BRD-05; Product Owner, Renewal for BRD-06) | 9 | 2
BPS | Business Project Services analysts | BDO Unibank ESG | BRD owners; traceability review of the FRS | 0 | 3
KU | Key users and UAT testers | BDOI | Named business users per unit and persona; test, coach and feed back | 0 | 8
DML | Data Migration Lead and data owners | BDOI | Owner of the migration objects, extracts, code maps and reconciliation | 3 | 3
COMP | Head, Comptrollership | BDOI | Owner of the finance set-up, the GL opening and the reconciliation of the financial objects | 1 | 0
CMP | Compliance | BDOI | Chief Compliance Officer and unit: screening, KYC, retention, audit | 0 | 0
BIT | BDOI IT | BDOI | Owner of the environments, extracts, interfaces and the Technical Specification review | 15 | 5
ISEC | BDOI Information Security | BDOI | Owner of the security settings, role matrix, separation of duties and security tests | 3 | 1
EIAM | BDO IT EIAM team | BDO Unibank | Microsoft Entra ID: application registration, single sign-on, conditional access | 1 | 1
IGA | BDO IT IGA team | BDO Unibank | UIDM-ISC: joiner, mover and leaver provisioning, aggregation and certification | 1 | 1
API | BDO IT API team | BDO Unibank | Apigee X gateway: proxies, products, credentials, policies | 1 | 1
OPS | BDO IT operations | BDO Unibank | ITIO-SRE and ITSD-AMS: monitoring, backups, DR, service desk tooling | 0 | 4
APS | BDOI application support | BDOI | L1 and L2 support of BIBS after hypercare | 0 | 3
IPM | iorta Project Manager | iorta TechNXT | Plan, RAID log, status, change requests, releases | 6 | 7
ISA | iorta Solution Architect | iorta TechNXT | Architecture, integrations, security design, technical specification | 3 | 6
IBA | iorta Business Analyst lead | iorta TechNXT | FRS, clarifications, traceability, functional configuration | 0 | 3
IDEV | iorta development team | iorta TechNXT | Application development, configuration and code review | 0 | 7
IQA | iorta QA lead and testers | iorta TechNXT | Test plans, SIT, regression, UAT support | 0 | 6
IDO | iorta infrastructure team | iorta TechNXT | Deployment pipeline, environments set-up support, monitoring, releases | 0 | 7
IML | iorta Migration Lead | iorta TechNXT | Migration Console, loads, reconciliation reports, cut-over runbook | 0 | 4
ICT | iorta change and training lead | iorta TechNXT | Change management, training, user guides, knowledge base | 0 | 6

## _lists (hidden)
R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R | R
A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R | A/R