## Cover
NFR REGISTER
Non-Functional Requirements Register
Measurable NFRs of BIBS with verification and owners
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-00
Version | 1.0
Date | 8 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
NFR register | One row per NFR; filter by category, status or test type | 99
Reconciliation | The catalogue against the FRS non-functional chapters, the register and the IER | 15
Summary | NFRs per category and status | 18
Legend
ALIGNED | The sources agree, or BDOI has answered; the target stands unless BDOI changes it
DECISION | The BRDs give conflicting values; BDOI decides (register item named in Source); our proposal applies until then
PROPOSED | No BDOI value exists; iorta TechNXT proposes the target for BDOI to confirm
Companion of the Word document 'Non-Functional Requirements' of the same version. The targets here are the ones quoted in the System Requirements Specification and the Test Strategy.
Precedence of sources: BDOI decision, IER workbook v20, BIBS-wide value of the discrepancy register v1.2, BRD values, iorta TechNXT proposal.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Non-Functional Requirements Register, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
NFR register | NFR ID | NFR-<category>-<nn>
NFR register | Category | Category of the NFR
NFR register | Title | Short name
NFR register | Requirement | What BIBS must do
NFR register | Measurable target | The value accepted as met
NFR register | How it is measured | Metric, conditions and evidence
NFR register | Verification method | Test, Analysis, Inspection or Walk-through | Test, Analysis, Inspection, Walk-through
NFR register | Test type | Test type of the Test Strategy
NFR register | Verified in | Test stage and dates
NFR register | Owner (iorta TechNXT) | Role accountable for meeting the target
NFR register | Accepted by (BDOI) | Role that accepts the evidence
NFR register | Source | BRD pages, IER, register items and design documents
NFR register | FRS reconciliation | How the FRS non-functional chapters relate to the target
NFR register | Status | ALIGNED, DECISION or PROPOSED | ALIGNED, DECISION, PROPOSED
NFR register | Priority | Must or Should | Must, Should
Reconciliation | Theme | NFR theme
Reconciliation | BRD values | Values of the BRDs with pages (register v1.2, NFR comparison sheet)
Reconciliation | FRS statements | What the non-functional chapters of the FRS state
Reconciliation | IER workbook v20 | What the infrastructure estimate states
Reconciliation | Catalogue target | NFR of this register
Reconciliation | Difference and action | What changes where
Reconciliation | Register / questions | Register items and open questions
Summary | Category | Category code and name
Summary | NFRs | Number of NFRs
Summary | Must | Must-have NFRs
Summary | Aligned | Status ALIGNED
Summary | BDOI decision | Status DECISION
Summary | Proposed | Status PROPOSED

## NFR register
NFR register
One row per NFR; filter by category, status or test type
NFR ID | Category | Title | Requirement | Measurable target | How it is measured | Verification method | Test type | Verified in | Owner (iorta TechNXT) | Accepted by (BDOI) | Source | FRS reconciliation | Status | Priority
NFR-PRF-01 | Performance | Screen response time | Every screen opens, and every single-record action (save, submit, approve) completes, within the target at the design load. | p95 at most 2.0 seconds and p99 at most 4.0 seconds | Click to usable screen, measured by the load tool over a 60-minute run at the design load of NFR-CAP-01 with the transaction mix of NFR-CAP-02, from the BDO network to the production-sized Pre-Prod | Test | Performance (load) | Baseline in SIT (Jun 2027); NFT on Pre-Prod (1 Nov to 15 Dec 2027) | iorta Performance Test Lead | BIBS Product Owner | BRD-00 p.42 (under 5 s for every role); BRD-12 p.13 (2 s); BRD-9 p.13 (3 s); BRD-1 p.210 and BRD-6 p.186 (10 s); register DCR-137, DCR-165; CRQ21 | FRS BRD-00 and BRD-12 state 2 s; FRS BRD-01 to BRD-10 state online p95 under 3 s. The catalogue sets 2 s; the FRS chapters take this value at their next issue once BDOI confirms (XQ08). | DECISION | Must
NFR-PRF-02 | Performance | Search and work-list response time | The first page of any search result or work list is shown within the target; lists are paged on the server. | First page (up to 50 rows) p95 at most 3.0 seconds; each further page p95 at most 2.0 seconds | Load-tool timing of the searches of each persona (client, account, invoice, receipt, claim, case) at the design load | Test | Performance (load) | NFT on Pre-Prod | iorta Performance Test Lead | BIBS Product Owner | BRD-9 p.13 (retrieval and search under 3 s); BRD-4 NFR 15 (5 s); BRD-10 p.22-24 (3 to 5 s) | FRS BRD-04 and BRD-09 (server-side paging, indexed search keys) meet this target; no FRS states a slower value. | PROPOSED | Must
NFR-PRF-03 | Performance | Interactive reports | An on-screen report or its export is produced within the target; larger reports run as background jobs (NFR-PRF-04). | At most 20 seconds (p95) for a report of up to 30,000 rows | Report run time from request to the first page shown or the file offered, at year-5 data volume | Test | Performance (volume) | NFT on Pre-Prod | iorta Performance Test Lead | BIBS Product Owner | BRD-6 p.186 and BRD-11 p.11 (20 s); BRD-5 p.133-137 (10 to 20 s first load); register DCR-137 | FRS BRD-06 states 20 s at 30,000 rows; FRS BRD-05 and BRD-11 run heavy reports in batches. Aligned. | DECISION | Must
NFR-PRF-04 | Performance | Long-running reports, extracts and scheduled files | Reports and files that exceed NFR-PRF-03 run as background jobs with progress shown; the user keeps working meanwhile. | Daily file at most 3 minutes, weekly at most 10 minutes, monthly at most 15 minutes, at year-5 volumes | Job run history (start, end, rows) of the scheduled report jobs during the volume test | Test | Performance (volume) | NFT on Pre-Prod; dress rehearsal (15 to 26 Nov 2027) | iorta Performance Test Lead | Head, Operations | BRD-4 NFR 15 (daily 3 min, weekly 10 min, monthly 15 min); BRD-7 p.39-40 (reports 5 min) | FRS BRD-04 generates the files off-peak in the background; FRS BRD-07 runs reports under 5 minutes. Aligned. | ALIGNED | Must
NFR-PRF-05 | Performance | Bulk uploads | An upload file is acknowledged at once and processed in the background with a result per row. | Acknowledgement within 3 seconds; a 5,000-row file validated and committed within 10 minutes | Upload of a 5,000-row file of each bulk template during the volume test | Test | Performance (volume) | NFT on Pre-Prod | iorta Performance Test Lead | BIBS Product Owner | BRD-5 p.133-137 (upload or download 3 s per file); FRS BRD-01 (bulk uploads up to 5,000 rows per file) | FRS BRD-01 commits row by row; the 10-minute ceiling is new and is added at the next issue. | PROPOSED | Should
NFR-PRF-06 | Performance | Document generation and batch printing | Business documents (slips, advices, receipts, SOA, vouchers) are generated within the target. | One document p95 at most 5 seconds; a batch of 50 documents at most 10 seconds | Time from request to the PDF offered, at the design load | Test | Performance (load) | NFT on Pre-Prod | iorta Performance Test Lead | Head, Operations | BRD-2 p.115 (batch print of 50 documents under 10 s) | FRS BRD-02 runs batch print as a background job with progress. Aligned. | ALIGNED | Must
NFR-PRF-07 | Performance | Night batch window | The scheduled jobs of the night (booking batch, remittance extraction, GL-SL reconciliation, Collections files, renewal extraction, screening, application file) finish before the service window opens. | The chain from 20:00 to 05:30 PHT completes before 06:00 PHT at year-5 volumes; a failed job can be re-run within the window | Run history of every scheduled job in the volume test and the dress rehearsal | Test | Performance (volume) | NFT on Pre-Prod; dress rehearsal | iorta Solution Architect | Head, BDOI IT | Register DCR-133 (service window from 06:00); programme alignment pack, section 6.5 (job times) | Each FRS names the times of its jobs (for example FRS BRD-02 remittance extraction 20:00 PHT, FRS BRD-12 processing 21:30 PHT). Aligned. | PROPOSED | Must
NFR-PRF-08 | Performance | Notifications and e-mail | Users are told of status changes, approvals and pending work without delay. | In-app notification within 1 minute of the event; e-mail handed to CCM within 5 minutes | Time stamps of the event, the notification and the hand-over to CCM in SIT and NFT | Test | System integration | SIT; NFT on Pre-Prod | iorta QA lead | BIBS Product Owner | FRS BRD-00 FR-CR-020; integration INT-13 (CCM) | No FRS gives a time; new value. | PROPOSED | Should
NFR-PRF-09 | Performance | Sign-in time | Single sign-on through EIAM completes quickly once the identity provider answers. | p95 at most 3 seconds from the identity provider's answer to the role home page, excluding the user's own MFA entry | Load-tool timing of the sign-in journey at the morning peak (08:00 to 10:00) | Test | Performance (load) | NFT on Pre-Prod | iorta Performance Test Lead | Head, BDOI IT | Integration INT-01 (EIAM); BRD-1 p.210 peak hours 08:00-10:00 | No FRS gives a time; new value. | PROPOSED | Should
NFR-CAP-01 | Capacity and volume | Users | BIBS serves every named user of BDOI and the concurrent sessions of the peak. | 1,344 named users; design load 150 concurrent users in year 1, growing 20% a year (311 in year 5); peak test at 429 concurrent sessions | Concurrent sessions in the load and peak tests; named users from the user register at go-live | Test | Performance (peak) | NFT on Pre-Prod | iorta Performance Test Lead | BIBS Product Owner | BRD-00 p.42 (1,344 named, 429 concurrent); BRD-1 p.210 (485 / 145, growth 20%); IER architecture sheet (about 1,200 internal users); register DCR-166, DCR-232; CRQ21, CRQ24 | FRS BRD-01 sizes for 150 concurrent plus 20% a year; the other FRS fall within that sizing. Aligned; the peak case follows the umbrella BRD. | DECISION | Must
NFR-CAP-02 | Capacity and volume | Transaction volumes | BIBS carries the business volumes of the BRDs for five years. | Year 1: New Business 21,200 transactions and 1,300 endorsements a month; Renewal 25,800 a month; Collections 1,200 updates a day; Claims 55 bookings and 1,096 updates a day; CSF 144,400 a year; Submitted Policies 63,000 sanitations a year. Growth 20% a year (Submitted Policies 25%) | Volume test at year-5 volumes (year 1 x 2.07; Submitted Policies x 2.44); job and screen timings within NFR-PRF targets | Test | Performance (volume) | NFT on Pre-Prod | iorta Performance Test Lead | BIBS Product Owner | BRD-1 p.210; BRD-6 p.186; BRD-4 NFR 15.01-15.05; BRD-7 p.39; BRD-9 p.13; BRD-12 p.13; BRD-00 p.42-45 | Same values in the FRS of BRD-01, 04, 06, 07, 09 and 12; FRS BRD-02 assumes its volumes within the BRD-1 sizing (OQ44). | ALIGNED | Must
NFR-CAP-03 | Capacity and volume | Data and document volume | Storage is sized for five years of data and documents with headroom. | Five years (60 months) at 20% growth a year with at least 30% free capacity at the end of year 5; migrated base up to 1,000,000 client rows and 500,000 open items | Capacity plan from the profiling extracts (M3) and the trial migrations, reviewed each quarter | Analysis | Capacity analysis | After Trial migration 2 (Jul 2027); before go-live | iorta Solution Architect | Cloud and Digital Operations Engineering (IER owner) | IER HW & SW Requirements (60 months; 15% growth a year); Data Migration Handbook (1,000,000 clients, 500,000 open items); programme alignment pack 6.3 (database re-sized without documents) | The Handbook states the migration sizing. The IER uses 15% growth; the catalogue uses the 20% of the BRDs, so the IER sizing is updated (open point). | PROPOSED | Must
NFR-CAP-04 | Capacity and volume | File sizes | Users attach and upload files up to the limits; larger bulk files go straight to the document store. | Attachments up to 10 MB a file; uploads through the screens up to 25 MB; bulk files up to 5 GB by direct transfer; limits are parameters | Upload at and one step above each limit in SIT | Test | System (boundary) | SIT | iorta QA lead | Head, BDOI IT | Platform configuration (attachment and upload limits); BDO UX guidelines (format hint on upload fields) | The upload screens of each FRS show the limit. Aligned. | PROPOSED | Should
NFR-CAP-05 | Capacity and volume | Peak periods | The month-end, mid-month and year-end peaks are carried without missing the response targets. | 1.5 times the average daily volume on the 15th, the 30th, month-end and year-end, within NFR-PRF-01 and NFR-PRF-02 | Peak scenario of the load test (one hour at 1.5 times the design hourly rate) | Test | Performance (peak) | NFT on Pre-Prod | iorta Performance Test Lead | Head, Comptrollership | BRD-2 (15th and 30th); BRD-5 (month-end and year-end); BRD-9 (first quarter); BRD-1 and BRD-6 (08:00-10:00 and 15:00-17:00) | The FRS list the peaks and keep batch jobs outside them. Aligned. | PROPOSED | Must
NFR-AVL-01 | Availability | Availability in the service window | BIBS is available to users throughout the service window. | 99.9% of the service window each month (about 25 minutes of unplanned unavailability in a month of 26 service days) | Synthetic sign-in and screen check every minute from the BDO network; monthly service report | Analysis | Operational acceptance | Pre-Prod soak (Nov 2027); measured monthly from go-live | iorta Solution Architect | Head, BDOI IT | Register DCR-134 (99.9% in service hours); BRD-2, 3, 9, 10, 12 (99.9%); BRD-8 (99.99%); BRD-5 Add.1 (100%) | FRS BRD-05 notes that 100% is not measurable; FRS BRD-08 notes 99.99% applied to the dropped portal. The catalogue sets 99.9% for all modules. | DECISION | Must
NFR-AVL-02 | Availability | Service window | One service window serves every module; production runs 24 x 7 so jobs and interfaces run outside it. | 06:00 to 22:00 PHT Monday to Saturday, plus month-end weekends; production infrastructure 24 x 7 | Configuration of the monitoring calendar and the job schedule | Inspection | Operational acceptance | ORR / PRR (Dec 2027) | iorta Solution Architect | BIBS Product Owner | Register DCR-133; IER Assumptions 3 and 4 (non-production 12 x 5, production 24 x 7); BRD service hours from 06:00 (BRD-4, 7, 9) to 22:00 (BRD-1, 4, 6, 9) | FRS BRD-02, 03, 05 and 07 refer to the BRD-1 window 07:00-22:00; the catalogue opens at 06:00 for Collections, Claims and CSF. | DECISION | Must
NFR-AVL-03 | Availability | Planned maintenance | Planned work happens in one window outside every module's service hours. | 00:00 to 04:00 PHT; at most 45 minutes of planned downtime a month; announced 5 business days ahead; releases without downtime where the change allows | Change calendar and monthly service report | Inspection | Operational acceptance | ORR / PRR; monthly from go-live | iorta Solution Architect | Head, BDOI IT | Register DCR-138 and DCR-134; BRD-10 p.25 and BRD-12 p.14 (00:00-04:00, 45 minutes a month) | FRS BRD-09 notes the BRD window 21:00-05:00 overlaps use (CSQ12); FRS BRD-05 notes 19:00-07:00. The catalogue takes 00:00-04:00. | DECISION | Must
NFR-AVL-04 | Availability | No single point of failure | Production keeps running when one pod, node or availability zone fails. | Backend at least 3 pods over 3 availability zones (at least 2 available during changes); web tier at least 2 pods; PostgreSQL 16 Multi-AZ; Kafka 3 brokers; Valkey primary and replica in two zones | Resilience test - stop a pod, drain a node, fail over the database and one zone - with users signed in; no lost transaction | Test | Resilience | NFT on Pre-Prod | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | IER HW & SW Requirements (Multi-AZ PROD, MSK 3 brokers); programme alignment pack 6.4 (Kubernetes sizing); component baseline of 8-Oct-2026 | The FRS refer to the platform deployment. Aligned. | ALIGNED | Must
NFR-AVL-05 | Availability | Graceful degradation | A failed cache or event-streaming service does not stop screen work. | Valkey outage - sign-in checks fall back to PostgreSQL; Kafka outage - events wait in the outbox and are delivered on recovery with none lost or delivered twice to the consumer | Resilience test with Valkey and Kafka stopped for 15 minutes under load | Test | Resilience | NFT on Pre-Prod | iorta Solution Architect | Head, BDOI IT | Security controls (fail-closed fallback of the token checks); platform cache and events design (transactional outbox, dead letters) | Not in the FRS (platform behaviour). | ALIGNED | Must
NFR-REC-01 | Recovery (RTO, RPO, backup and DR) | Recovery point objective (RPO) | At most the target of committed work is lost in a disaster. | RPO at most 15 minutes for data and documents | DR drill - time of the last transaction recovered against the time of the declared failure | Test | Disaster recovery | DR drill on the DR environment (Dec 2027), then twice a year | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | IER Architecture Diagram and HW & SW Requirements (RPO 15 minutes, DR replica RPO at most 15 min); register DCR-135, DCR-225; BRD-9 BRCSF-011.001 (backup every 15 minutes) | FRS BRD-02, 03 and 08 quote the BRD value of 24 hours and FRS BRD-04, 07 and 09 4 hours; the IER value of 15 minutes is stricter and governs. | ALIGNED | Must
NFR-REC-02 | Recovery (RTO, RPO, backup and DR) | Recovery time objective (RTO) | Service is restored within the target after a declared disaster; critical services first. | RTO at most 4 hours; sign-in, Cashiering, Remittance, booking and the GL first | DR drill - time from the DR decision to the service open in the DR region with business verification passed | Test | Disaster recovery | DR drill (Dec 2027), then twice a year | iorta DevOps and Platform Lead | Head, BDOI IT | IER (RTO 4 hours); BRD-2, 3, 4, 7, 8, 9 (4 hours); BRD-12 p.14 (critical services 4 hours, full recovery 24 hours); register DCR-135 | Every FRS that states an RTO states 4 hours. Aligned. | ALIGNED | Must
NFR-REC-03 | Recovery (RTO, RPO, backup and DR) | Backup | Data and documents are backed up continuously and kept for the retention period. | Continuous transaction-log archiving plus a base backup every 4 hours; backups encrypted and kept 7 years; document store versioned with cross-region replication | Backup reports and the restore test of NFR-REC-04 | Inspection | Operational acceptance | ORR / PRR | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | Register DCR-102, DCR-135, DCR-136; BRD-00 p.45 (every 4 hours, kept 5 years); BRD-2 and BRD-8 (kept 7 years) | FRS BRD-02 and BRD-08 keep backups 7 years; FRS BRD-01, 04, 05, 10, 12 quote 5 years. The catalogue takes 7 years (the longest). | DECISION | Must
NFR-REC-04 | Recovery (RTO, RPO, backup and DR) | Restore and DR drills | Recovery is proven before go-live and kept proven afterwards. | Point-in-time restore tested every quarter; DR failover drill before go-live (Dec 2027) and twice a year after; each with a written result | Drill reports with RPO and RTO achieved | Test | Disaster recovery | Pre-Prod and DR (Dec 2027); quarterly and half-yearly after go-live | iorta DevOps and Platform Lead | Head, BDOI IT | Operations runbook (quarterly restore test); IER DR environment | Not in the FRS. | PROPOSED | Must
NFR-REC-05 | Recovery (RTO, RPO, backup and DR) | DR region | A second AWS region hosts the DR copy of BIBS once BDOI confirms data residency. | Database cross-region replica, document store cross-region replication, standby Kubernetes cluster scaled from 0 to 6 backend pods at failover | DR environment acceptance and the DR drill | Test | Disaster recovery | DR environment ready by 1 Nov 2027 (DEP-25) | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | IER PROD DR (cross-region read replica) and diagram (warm standby); register DCR-225; programme alignment pack 6.4; IQ26 | Not in the FRS. | DECISION | Must
NFR-SCL-01 | Scalability | Horizontal scaling without downtime | The web, jobs and integration workloads scale out and in without interrupting users. | Production backend 3 to 6 pods in year 1 and 4 to 8 in year 5 by CPU-based autoscaling; a scale-out completes within 5 minutes | Step-load test from the design load to the peak; pod count and response times recorded | Test | Performance (stress) | NFT on Pre-Prod | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | Programme alignment pack 6.4; BRD-7 p.37 (no downtime when scaling the application); IER Kubernetes guideline 9 (autoscaling) | FRS BRD-07 refers to the Technical Specification. Aligned. | ALIGNED | Must
NFR-SCL-02 | Scalability | Data-tier scaling | Database storage grows online; a compute change of the managed database fits the maintenance window. | Storage grows without downtime; a compute class change at most 120 minutes of downtime, inside the maintenance window | Change rehearsal on Pre-Prod | Test | Operational acceptance | Pre-Prod (Nov 2027) | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | BRD-4 p.54-55 and BRD-7 p.37 (up to 120 minutes for data storage scaling) | FRS BRD-04 and BRD-07 quote the BRD. Aligned. | ALIGNED | Should
NFR-SCL-03 | Scalability | Stateless application tier | Any pod serves any request; a scheduled job runs once across pods. | No user session state in the pods; each job run holds a cluster-wide lock; 0 duplicate job runs in the volume test | Inspection of the deployment; job run history with several pods in SIT and NFT | Inspection | System integration | SIT (two pods from Jan 2027); NFT | iorta Solution Architect | Head, BDOI IT | Operations runbook (stateless application, job lock); programme alignment pack 6.4 (SIT runs two pods to test the job lock) | Not in the FRS. | ALIGNED | Must
NFR-SCL-04 | Scalability | Growth headroom | The production cluster carries the year-5 load with headroom. | At the year-5 peak, CPU and memory use of the cluster below 70% | Resource metrics during the year-5 volume and peak tests | Test | Performance (stress) | NFT on Pre-Prod | iorta Performance Test Lead | Cloud and Digital Operations Engineering (IER owner) | IER K8S sheets (threshold 0.79 on worker nodes); programme alignment pack 6.4 | Not in the FRS. | PROPOSED | Should
NFR-SEC-01 | Security | Single sign-on with EIAM | BDO users sign in once with their enterprise identity; BIBS keeps the roles. | Every BDO user signs in through EIAM (Microsoft Entra ID) by OpenID Connect or SAML 2.0; local passwords only for the named break-glass administrators | SIT sign-in cases for both protocols; list of local accounts at go-live | Test | System integration; security | SIT (after the EIAM specification, DEP-07) | iorta Security Lead | BDOI Information Security | Drop plan integration EIAM (INT-01); security controls (single sign-on, break-glass); BRD-11 UAM-NFR-11, 17, 33 | FRS BRD-11 FR-UA-003 describes directory sign-in through EUA; the EIAM single sign-on replaces it at the next issue (IQ04). | ALIGNED | Must
NFR-SEC-02 | Security | Second factor | Privileged users prove a second factor. | TOTP second factor for every privileged role and every break-glass administrator; EIAM conditional access for single sign-on users | Security-access cases of the BRD-11 test plan; configuration review of the MFA policy | Test | Security | SIT | iorta Security Lead | BDOI Information Security | Security controls (TOTP, policy PRIVILEGED as delivered); drop plan EIAM | FRS BRD-11 covers the sign-in; the MFA policy is a security parameter changed under a second approval. | PROPOSED | Must
NFR-SEC-03 | Security | User provisioning and leavers | Joiners, movers and leavers reach BIBS from UIDM-ISC; dormant accounts are disabled. | SCIM 2.0 provisioning from UIDM-ISC (planned); a leaver disabled in BIBS within 1 hour of the UIDM-ISC change; accounts dormant for 90 days disabled by the daily job | SIT provisioning cases; access review report after the first month of production | Test | System integration; security | SIT (after DEP-08) | iorta Security Lead | BDOI Information Security | Drop plan integration UIDM-ISC (INT-02); BRD-11 UAM-NFR-09 (dormant users disabled); IQ05, DCR-229 | FRS BRD-11 keeps access requests in BIBS; the share between UIDM-ISC and BIBS requests is open (IQ05). | DECISION | Must
NFR-SEC-04 | Security | Role and data-scope access control | Every function is checked against the user's permissions and every record against the user's companies and branches; makers never approve their own work. | 0 successful unauthorised accesses in the security-access cases of every test plan and in the penetration test; every refusal logged | Security-access test cases (one per protected action) and the penetration test | Test | Security | SIT; UAT; penetration test | iorta QA lead | BDOI Information Security | Security controls (permissions, company and branch scope, segregation of duties); BRD-4 NFR 3 and BRD-7 NFR (protection against direct object reference) | Each FRS has a role-access FR (for example FR-PM-002, FR-OP-002, FR-CL-001, FR-CM-002, FR-SS-001). | ALIGNED | Must
NFR-SEC-05 | Security | Session and lock-out | Idle sessions end and repeated failures lock the account. | Inactivity warning at 15 minutes and sign-out at 30 minutes; absolute session end 8 hours; lock-out after 3 consecutive failed attempts | Security-access cases of the BRD-11 test plan | Test | Security | SIT | iorta Security Lead | BDOI Information Security | BRD-11 UAM-NFR-19, 34; BRD-1 p.93 and BRD-6 p.44 (warning 15, log-out 30); BRD-4 p.53 and BRD-7 p.35 (15 minutes); register DCR-140, DCR-142 | FRS BRD-11 FR-UA-001 and 002 apply 15 / 30 minutes and 3 attempts; FRS BRD-07 aligns its 15 minutes under CLQ24. | DECISION | Must
NFR-SEC-06 | Security | Encryption in transit and at rest | Data is encrypted on every connection and in every store. | TLS 1.2 or higher on every connection (browser, Gateway API, between workloads, to the managed services); database, document store and backups encrypted with customer-managed keys per environment | Configuration review and TLS scan of every listener | Inspection | Security | Pre-Prod; ORR / PRR | iorta Security Lead | BDOI Information Security | Security controls (TLS at the edge and to the pods); programme alignment pack 6.3 (KMS keys per environment); BRD-8 derived privacy requirement (encryption in transit and at rest) | FRS BRD-08 states encryption of sensitive personal information. Aligned. | PROPOSED | Must
NFR-SEC-07 | Security | Secure development gates | Every change passes the security gates of the CI pipeline before it can be released. | SAST (CodeQL and SonarQube security rules) with no new high finding; Java dependencies fail at CVSS 7.0 or higher; web packages fail on high or critical advisories; container images fail on high or critical findings with a fix; secret detection over the full history; a software bill of materials kept with every release | CI pipeline reports attached to each release note | Inspection | Security (SAST and dependency scanning) | Every change, from development to production | iorta Security Lead | BDOI Information Security | Quality gates (dependency and supply-chain checks, SAST, SBOM) | Not in the FRS. | ALIGNED | Must
NFR-SEC-08 | Security | DAST and penetration test | The running application is tested from outside before go-live. | DAST scan of each release candidate in SIT and Pre-Prod with no open high or critical finding; early scan in SIT in June 2027; independent penetration test 1 Nov to 15 Dec 2027; critical and high findings closed before go-live | Scan and penetration test reports with the re-test of each finding | Test | Security (DAST, penetration test) | SIT (Jun 2027); Pre-Prod (Nov to Dec 2027) | iorta Security Lead | BDOI Information Security | BDOI programme timeline (performance and penetration test Nov to Dec 2027); programme alignment pack (early security scan, IQ35); project plan DEP-19 | Not in the FRS. | PROPOSED | Must
NFR-SEC-09 | Security | Integration security | System-to-system traffic is authenticated separately from users. | Every inbound interface passes the Apigee X gateway with its own client credentials; user tokens are refused on the integration paths; each partner system has its own credentials | Security cases of the interface tests in SIT | Test | Security; system integration | SIT (after DEP-13) | iorta Security Lead | Head, BDOI IT | Security controls (separate security chain of the integration services); drop plan integrations; brief of 8-Oct-2026 (Apigee X gateway) | Not in the FRS. | ALIGNED | Must
NFR-SEC-10 | Security | Protection of documents that leave BDOI | Documents sent outside BDOI are protected. | Every outbound document (slips, advices, SOA, schedules, reports) is a password-protected PDF or Excel file with the password sent separately; e-mail only to approved domains | Document-output cases of the test plans; review of the recipient policy | Test | System | SIT; UAT | iorta QA lead | BDOI Information Security | FRS BRD-00 FR-CR-071; BRD-1 security (outbound documents encrypted or password protected); BRD-6 (encrypted, password-protected RA and insurer files) | FRS BRD-01, 02, 03, 06 and 08 apply it. Aligned. | ALIGNED | Must
NFR-SEC-11 | Security | Uploaded files | Uploaded files cannot carry malware into BIBS. | Every uploaded file scanned for malware and held in quarantine until clean; Office files refused above 1,000 parts or 100 times expansion | Upload cases with a test malware signature and an oversized archive in SIT | Test | Security | SIT | iorta Security Lead | BDOI Information Security | Programme alignment pack 6.3 (quarantine prefix, malware scan); platform configuration (Office file limits) | Not in the FRS. | ALIGNED | Must
NFR-SEC-12 | Security | Vulnerability remediation | Security findings in production are fixed within set times. | Critical within 7 days, high within 30 days, medium within 90 days; an accepted finding expires after at most 6 months | Monthly vulnerability report | Inspection | Operational acceptance | From go-live, monthly | iorta Security Lead | BDOI Information Security | Quality gates (accepted findings expire after at most six months) | Not in the FRS. | PROPOSED | Must
NFR-PRV-01 | Privacy | Masked data outside production | Personal data never reaches a non-production environment unmasked. | Names, TIN, addresses, contact details and bank account numbers masked in DEV, SIT, training and UAT; 0 unmasked records found in the masking verification of each migration load | Masking verification report of each trial migration and of each copy to UAT | Test | Data migration; security | Trial migrations 1 to 4 (Apr to Oct 2027) | iorta Migration Lead | Data Protection Officer, BDOI | FRS BRD-00 NFR table (non-production data masked, hosting appendix); Data Migration Handbook (staging security) | FRS BRD-00 and the Handbook state it. Aligned. | ALIGNED | Must
NFR-PRV-02 | Privacy | Data residency and support access | Production data stays in the agreed region and is reached only by authorised personnel in the Philippines. | Production in AWS ap-southeast-1; DR region confirmed by BDOI after the data-residency check; production access only by named personnel in the Philippines, each session logged | Access review of the AWS accounts and the bastion log before go-live and every quarter | Inspection | Security | ORR / PRR; quarterly | iorta DevOps and Platform Lead | Data Protection Officer, BDOI | FRS BRD-00 NFR table (hosting appendix: AWS ap-southeast-1, access from the Philippines); register DCR-225; IQ26 | FRS BRD-00 states it. Aligned. | DECISION | Must
NFR-PRV-03 | Privacy | Sensitive personal information | Health-related and member data of Employee Benefits is handled as sensitive personal information. | Access by department access class; every download logged; no health data in the member roster | Security-access and document cases of the BRD-08 test plan | Test | Security | SIT and UAT of Drop 2 | iorta QA lead | Data Protection Officer, BDOI | FRS BRD-08 NFR table (data privacy, derived; EBQ15) | FRS BRD-08 states it. Aligned. | ALIGNED | Must
NFR-PRV-04 | Privacy | Data-subject requests | BDOI can answer a client's request to access or correct personal data. | The personal data held on one client found and exported within 1 business day; corrections recorded with the audit trail | UAT scenario run by the DPO's delegate | Test | User acceptance | UAT (Drop 1) | iorta Business Analyst lead | Data Protection Officer, BDOI | Data Privacy Act 2012 (rights of the data subject); FRS BRD-09 (contact update with audit trail) | FRS BRD-09 FR-CSF-040 records contact changes; the export for a data-subject request is new. | PROPOSED | Should
NFR-PRV-05 | Privacy | Migration staging purge | Migration staging data does not outlive its purpose. | Staged data and files purged within 5 days of the batch sign-off; access only for the migration roles | Purge job history and access log after each trial migration | Inspection | Data migration | Trial migrations; cut-over | iorta Migration Lead | Data Protection Officer, BDOI | Data Migration Handbook (staging security); platform configuration (staging retention 5 days) | The Handbook states it. Aligned. | ALIGNED | Must
NFR-PRV-06 | Privacy | Security event alerts | Events that may indicate a personal-data breach reach BDO Information Security quickly. | Alerts within 15 minutes for repeated failed sign-ins, privilege changes, refused data-scope access and exports above 10,000 rows | Alert test in Pre-Prod with the SIEM of BDO | Test | Security | Pre-Prod (Nov 2027) | iorta Security Lead | BDOI Information Security | Data Privacy Act 2012 (security incident management by the personal information controller); BRD-4 NFR 4 (audit exportable); BRD-11 UAM-NFR-40 (escalation of privilege changes) | FRS BRD-11 raises an alert for privilege increases (UQ07); the other alerts are new. | PROPOSED | Should
NFR-ACC-01 | Accessibility | WCAG 2.2 level AA | Every screen meets the success criteria of WCAG 2.2 at levels A and AA. | 0 open level A or AA failures on the screens of each sign-off set; 0 serious or critical issues in the scan of every screen | Scan of every screen with an accessibility checker plus a manual check of keyboard use, focus order and screen-reader labels on the main journey of each persona | Test | Accessibility | SIT of each drop; re-check in UAT | iorta UX Lead | BIBS Product Owner | BRD-11 UAM-NFR-05 (options for impaired vision or colour blindness); BDO UX guidelines (AA contrast, keyboard use) | FRS BRD-11 applies the BDO UX contrast rules; the WCAG 2.2 AA level is new and is added to the screen standards appendix at the next issue. | PROPOSED | Must
NFR-ACC-02 | Accessibility | Keyboard use | Every function works with the keyboard alone. | Every action reachable by keyboard with a visible focus ring; rows open with Enter; tabs move with the arrow keys | Manual keyboard pass on each screen family | Test | Accessibility | SIT | iorta UX Lead | BIBS Product Owner | BDO UX guidelines (keyboard use of tabs and tables, visible focus rings) | Screen standards appendix of the FRS. Aligned. | ALIGNED | Must
NFR-ACC-03 | Accessibility | Contrast and colour | Text and status are readable for users with low vision or colour blindness. | Text contrast at least 4.5:1 (3:1 for large text and controls); a status is never shown by colour alone | Contrast check of every colour token and pill tone; screen review | Inspection | Accessibility | SIT | iorta UX Lead | BIBS Product Owner | BDO UX guidelines (contrast, AA contrast of every pill and tag tone, overdue shown with icon and text) | Screen standards appendix of the FRS. Aligned. | ALIGNED | Must
NFR-ACC-04 | Accessibility | Zoom and reflow | Screens stay usable when users enlarge the text. | Usable at 200% browser zoom and at a 320-pixel reflow width without loss of content or function | Manual check of each screen family at 200% zoom | Test | Accessibility | SIT | iorta UX Lead | BIBS Product Owner | WCAG 2.2 success criteria 1.4.4 and 1.4.10 | New; added to the screen standards appendix at the next issue. | PROPOSED | Should
NFR-USE-01 | Usability and low-click workflows | Low-click navigation | Daily work starts from the role home page with few clicks. | Any daily task reached in at most 2 clicks from the role home page or the menu; a record opened from a search result in 1 click; the main action of a record (submit, approve) at most 1 click away | Click count of the top 5 tasks of each persona in the end-to-end walkthroughs of the FRS | Walk-through | Usability | SIT (screen review); UAT | iorta UX Lead | BIBS Product Owner | BRD-00 p.5 (role-based self-service, centralised dashboards); FRS BRD-00 FR-CR-001 and FR-CR-010 (persona menus, role home) | The FRS walkthroughs and storyboard indexes give the click paths; the counts are new targets. | PROPOSED | Must
NFR-USE-02 | Usability and low-click workflows | Work lists and bulk actions | Queues let users act on many items at once where the FRS allows bulk processing. | Every queue offers filters, saved views and an action on selected rows; 50 items dispositioned without opening each record | Walk-through of each queue of the FRS with 50 seed items | Walk-through | Usability | SIT; UAT | iorta UX Lead | BIBS Product Owner | FRS BRD-00 FR-CR-083 (bulk and individual processing); BRD-1 p.142-144 (bulk processing across segments) | FRS BRD-01, 04, 06 and 10 specify bulk actions. Aligned. | ALIGNED | Must
NFR-USE-03 | Usability and low-click workflows | Data entry | Users key each value once, with defaults and look-ups. | A value is never asked twice in one journey; known values defaulted; dates dd-MMM-yyyy; amounts with thousands separators and two decimals; field errors shown inline with what to do | Screen review against the screen standards appendix of each FRS | Inspection | Usability | SIT | iorta UX Lead | BIBS Product Owner | BDO UX guidelines (input fields, error text); client screen rules (dd-MMM-yyyy dates, formatted amounts) | Screen standards appendix of the FRS. Aligned. | ALIGNED | Must
NFR-USE-04 | Usability and low-click workflows | Consistent screens | Every screen follows the BDO UX guidelines and the BDOI UX design. | Records shown in tables or tree tables with row action menus, never as free text; labels not codes; user names not log-ins; 0 deviations open at the end of SIT | Screen-by-screen review of the UX screen register of each sign-off set | Inspection | Usability | SIT | iorta UX Lead | BIBS Product Owner | FRS BRD-00 FR-CR-092 (BDO brand, design system and user journeys); BDO UX guidelines; BDOI UX design | Every FRS has the screen standards appendix. Aligned. | ALIGNED | Must
NFR-USE-05 | Usability and low-click workflows | Learnability | Trained users complete their main tasks without help. | 90% of first attempts at the top task of each persona completed without help in UAT; System Usability Scale score of at least 75 in the UAT survey | UAT observation sheet and SUS survey of the UAT testers | Test | Usability | UAT | iorta UX Lead | BIBS Product Owner | BRD-9 p.13 (user-friendly, intuitive); BRD-00 BR-178 to BR-181 (design system and user journeys) | New target. | PROPOSED | Should
NFR-USE-06 | Usability and low-click workflows | Help and messages | Users find help in the application and messages say what to do next. | Help page for every screen family; every message of the messages catalogue states the next action | Review of the messages catalogue of each FRS and of the Help Center pages | Inspection | Usability | SIT | iorta Business Analyst lead | BIBS Product Owner | FRS BRD-11 (in-app Help Center, UQ18); messages catalogue chapter of each FRS | Messages catalogue of each FRS. Aligned. | ALIGNED | Should
NFR-RSP-01 | Responsive and mobile-first | Responsive layout | Screens work on phone, tablet and desktop widths. | Every screen usable from 360 to 1920 pixels wide with no horizontal page scroll; wide tables scroll inside their frame or collapse to cards on phones | Check of each screen family at 360, 768, 1280 and 1920 pixels | Test | Responsive (cross-device) | SIT | iorta UX Lead | BIBS Product Owner | BRD-2, 3, 5, 6, 8, 9, 10 (same performance on mobile and desktop); BRD-1 p.210 (any BDO-issued device) | The FRS state responsive screens. Aligned. | ALIGNED | Must
NFR-RSP-02 | Responsive and mobile-first | Mobile parity | The same functions and response times apply on BDO-issued mobile devices. | Same functions and NFR-PRF targets on a BDO-issued phone or tablet on the BDO network; touch targets at least 44 pixels | Main journey of each persona run on a BDO-issued phone and tablet | Test | Responsive (cross-device) | SIT; UAT | iorta UX Lead | BIBS Product Owner | BRD rows 'same performance on mobile and desktop'; BDO UX guidelines (buttons 44 to 48 pixels) | The FRS state no device restriction. Aligned. | ALIGNED | Must
NFR-RSP-03 | Responsive and mobile-first | Supported browsers | Users need only a browser. | Current and previous major versions of Microsoft Edge and Google Chrome on Windows, Safari on iOS and Chrome on Android; no plug-in or local install | Main journeys run on each browser | Test | Responsive (cross-device) | SIT | iorta QA lead | Head, BDOI IT | BRD-11 UAM-NFR-28 (browser only on workstations) | FRS BRD-11 states it. Aligned. | PROPOSED | Must
NFR-LOC-01 | Localisation | Language and business terms | The screens use English and BDOI's own business terms. | English user interface; BDOI terms (ARN, PRF, TSU, DP, RA, CLPC, FFY) exactly as in the BRDs; every acronym in the glossary | Review of the labels in the UX screen register of each sign-off set | Inspection | Usability | SIT | iorta Business Analyst lead | BIBS Product Owner | Writing standard of the client documents; BRD glossaries | Glossary of each FRS. Aligned. | ALIGNED | Must
NFR-LOC-02 | Localisation | Dates and time zone | Business dates follow Philippine time. | Business date in Asia/Manila (PHT); dates shown dd-MMM-yyyy and times in PHT; time stamps stored in UTC | Cut-off and date cases around midnight PHT in SIT | Test | System (boundary) | SIT | iorta QA lead | Head, Comptrollership | Platform configuration (business zone Asia/Manila); screen rules (dd-MMM-yyyy) | The FRS quote job times in PHT. Aligned. | ALIGNED | Must
NFR-LOC-03 | Localisation | Currency and amounts | Amounts follow the company's base currency and BDOI's foreign-currency rules. | Base currency PHP from the company record; USD and other currencies with daily and month-end revaluation rates; amounts with two decimals and thousands separators; reports in several currencies | Currency cases of the BRD-01 and BRD-05 test plans | Test | System | SIT | iorta QA lead | Head, Comptrollership | FRS BRD-00 FR-CR-091; FRS BRD-05 (monthly revaluation rate, USD revaluation) | FRS BRD-00 and BRD-05 state it. Aligned. | ALIGNED | Must
NFR-LOC-04 | Localisation | Philippine formats and calendar | Philippine identifiers, addresses and working days are handled correctly. | TIN, mobile numbers and addresses (region, province, city or municipality, barangay) validated to Philippine formats; business-day rules follow the holiday calendar kept by the Business Administrator | Validation cases of client onboarding and date rules in SIT | Test | System | SIT | iorta QA lead | BIBS Product Owner | FRS BRD-01 (client record, EOPT details: TIN and registered address); programme alignment pack 4.2 (non-working days of the go-live calendar) | FRS BRD-01 validates the client record; the holiday calendar is a list maintained on screen. | PROPOSED | Should
NFR-MNT-01 | Maintainability | Code quality gates | Every change passes the static quality gates before it is merged. | Formatting, compiler warnings as errors, Checkstyle, PMD with duplication at 120 tokens, SpotBugs, ArchUnit architecture rules, TypeScript strict and SonarJS rules; cognitive complexity at most 15 per function in the web client | CI pipeline report of every change | Inspection | Static analysis | Every change | iorta Development Lead | Head, BDOI IT | Quality gates (backend and frontend gates) | Not in the FRS. | ALIGNED | Must
NFR-MNT-02 | Maintainability | Code coverage | New and changed code is covered by unit testing. | Line coverage above 90% on new and changed code (new-code gate of SonarQube); overall line coverage at least 80% and branch coverage at least 65% | Coverage reports of the CI pipeline and the SonarQube quality gate of each change | Inspection | Unit testing | Every change | iorta Development Lead | Head, BDOI IT | Quality gates (overall gate 80% lines, 65% branches); programme target for new code | Not in the FRS. | PROPOSED | Must
NFR-MNT-03 | Maintainability | Modular structure | Each business area is a separate module of one application, with checked boundaries. | One package per bounded context; 0 cycles between modules; boundary rules checked on every change | Architecture rules in the CI pipeline | Inspection | Static analysis | Every change | iorta Solution Architect | Head, BDOI IT | Architecture option decision (modular monolith); quality gates (ArchUnit) | Not in the FRS. | ALIGNED | Must
NFR-MNT-04 | Maintainability | Technology baseline and support horizon | Every component runs on a version under upstream support. | PostgreSQL 16, Valkey 8, Apache Kafka 3.9, OpenJDK 21 LTS, Spring Boot 3.5, React (compiled with Node 22 LTS, not used in production), nginx, managed Kubernetes with the Gateway API; baseline reviewed every year and before go-live | Technology review record; software bill of materials of each release | Inspection | Operational acceptance | Before go-live; yearly | iorta Solution Architect | Head, BDOI IT | Client decisions of 8-Oct-2026 (component baseline; Valkey replaces Redis; Gateway API replaces ingress-nginx) | Not in the FRS. The IER rows for Redis 7, Kafka 3.6 and ingress-nginx are updated (open point). | ALIGNED | Must
NFR-MNT-05 | Maintainability | Releases and rollback | Releases do not stop users and can be rolled back. | Rolling deployment with no pod unavailable; data changes compatible with the previous release; rollback by redeploying the previous release within 30 minutes | Release and rollback rehearsal on Pre-Prod | Test | Operational acceptance | Pre-Prod (Nov 2027) | iorta DevOps and Platform Lead | Head, BDOI IT | Operations runbook (rolling update, expand-migrate-contract, rollback by previous image) | Not in the FRS. | PROPOSED | Must
NFR-MNT-06 | Maintainability | Documentation kept current | The technical and support documents match each release. | Technical specification, configuration guide, runbook and data dictionary updated with each release; release notes list every changed function | Release checklist | Inspection | Operational acceptance | Each release; ORR / PRR | iorta Project Manager | Head, BDOI IT | BRD-11 UAM-NFR-29 (system documentation); deliverables plan items 23 to 25 | FRS BRD-11 points to the administration guide. Aligned. | PROPOSED | Should
NFR-CFG-01 | Configurability | No hard-coded business rules | Business rule values are data maintained on screen, not program code. | Every rate, limit, number of days, threshold, numbering prefix, approver and message text is a parameter, list of values, rule table or template; 0 client names, codes or currency literals in the application code, checked on every change | Rule column of every FR (Configurable or Fixed) and the code check of the CI pipeline | Inspection | Static analysis; configuration review | Every change; SIT | iorta Solution Architect | BIBS Product Owner | Deliverables plan item 16 (configuration over code); client review of hard-coded rules; FRS rule tables | Every FRS rule states Configurable or Fixed and where it is maintained. | ALIGNED | Must
NFR-CFG-02 | Configurability | Effective dates and approval of configuration | Configuration changes are dated, kept in history and approved by a second user. | Every change of a list, parameter or rule has an effective date and a second-user approval; security parameters need a second approval by a security administrator | Configuration cases of the BRD-00 and BRD-11 test plans | Test | System | SIT | iorta QA lead | BIBS Product Owner | FRS BRD-00 FR-CR-060; security controls (security parameters under a second approval) | FRS BRD-00 and BRD-11 state it. Aligned. | ALIGNED | Must
NFR-CFG-03 | Configurability | Configurable workflows | Approval stages, approver matrices, SLA timers and escalations change without a release. | Each workflow of the FRS configurable on screen: stages, approver matrix, SLA hours, escalation rules | Workflow configuration cases in SIT | Test | System | SIT | iorta QA lead | BIBS Product Owner | FRS BRD-00 FR-CR-080; FRS BRD-10 FR-SS-013 to 015; FRS BRD-11 (approver rules are parameters) | Workflow chapters of each FRS. Aligned. | ALIGNED | Must
NFR-CFG-04 | Configurability | Document and e-mail templates | Business users maintain the templates of documents and e-mails. | Every document and e-mail template edited by the Business Administrator, downloaded and uploaded as Word, under maker-checker | Template cases in SIT | Test | System | SIT | iorta QA lead | BIBS Product Owner | FRS BRD-00 FR-CR-050; deliverables plan item 17 (templates to and from Word) | Document outputs chapter of each FRS. Aligned. | ALIGNED | Should
NFR-CFG-05 | Configurability | Branding by theme pack | Brand, logo and colours come from configuration. | BDO Insure brand applied from the theme pack of the deployment; no brand element fixed in the screens | Inspection of the theme pack and the screens | Inspection | Configuration review | SIT | iorta UX Lead | BIBS Product Owner | Client review of hard-coded rules (theme pack); FRS BRD-00 FR-CR-092 | FRS BRD-00 states the brand. Aligned. | ALIGNED | Should
NFR-OBS-01 | Observability | Metrics and dashboards | Operations sees the health and load of every workload. | Application, JVM, request, connection-pool and business metrics sent to the BDO monitoring platform; dashboards per workload (web, jobs, integration, web tier) and for the managed services | Dashboard review in Pre-Prod during the NFT | Inspection | Operational acceptance | Pre-Prod; ORR / PRR | iorta DevOps and Platform Lead | Head, BDOI IT | Operations runbook (metrics on the management port); IER VDI and K8S sheets (Dynatrace); IQ30 | Not in the FRS. | DECISION | Must
NFR-OBS-02 | Observability | Logs | Logs let support trace every event without exposing personal data. | One line per event with time stamp, correlation ID, user and module; shipped to the BDO log platform within 1 minute; no passwords or full personal identifiers in logs | Log review in Pre-Prod; search of a correlation ID from a user error | Inspection | Operational acceptance | Pre-Prod; ORR / PRR | iorta DevOps and Platform Lead | BDOI Information Security | Operations runbook (logs, correlation ID); security controls (no passwords in logs); BRD-11 UAM-NFR-21 (error log sent to a remote log server) | FRS BRD-11 refers to the Technical Specification. Aligned. | PROPOSED | Must
NFR-OBS-03 | Observability | Alerts | Faults raise alerts before users report them. | Alerts for an error rate above 1% over 5 minutes, p95 above its NFR-PRF target for 10 minutes, a failed job, a new dead letter, a security-store failure and a certificate expiring within 30 days; the on-call person notified within 5 minutes | Alert test in Pre-Prod (each condition provoked once) | Test | Operational acceptance | Pre-Prod (Nov 2027) | iorta DevOps and Platform Lead | Head, BDOI IT | Operations runbook (security-store alert, dead letters); BRD-11 UAM-NFR-25 (failed batch e-mail) | FRS BRD-11 FR-UA-071 e-mails failed runs. Aligned. | PROPOSED | Must
NFR-OBS-04 | Observability | Correlation of requests and events | One reference follows a request from the screen to the logs and the integration events. | Every request carries a correlation ID; an unexpected error shows the user a reference found in the logs; integration events carry the same ID | SIT case - provoke an error and find its reference in the logs | Test | System integration | SIT | iorta QA lead | Head, BDOI IT | Operations runbook (correlation ID, error reference) | Not in the FRS. | ALIGNED | Must
NFR-OBS-05 | Observability | Job monitoring | Every scheduled job is visible on screen with its history. | Run history (start, end, records, result, trigger, user) for every job; failures e-mailed to the job's recipients; manual runs restricted to authorised roles | Job cases of the BRD-04 and BRD-11 test plans | Test | System | SIT | iorta QA lead | Head, Operations | BRD-11 UAM-NFR-24, 25; BRD-4 NFR 12 (batch security) | FRS BRD-04 and BRD-11 state it. Aligned. | ALIGNED | Must
NFR-SUP-01 | Supportability | Support levels | Each support level has a defined role from go-live. | L1 BDOI service desk, L2 BDOI application support, L3 iorta TechNXT; each level named and trained before the hypercare exit (2 Feb 2028) | Knowledge-transfer sign-off and support roster | Inspection | Operational acceptance | ORR / PRR; hypercare exit | iorta Project Manager | Head, BDOI IT | Production support approach (support levels); project plan DEP-18 (named L1 and L2 team) | Not in the FRS. | ALIGNED | Must
NFR-SUP-02 | Supportability | Incident handling within the agreed service levels | Production incidents are answered and resolved within the response and resolution times of their priority (P1 to P4) in the support service levels. | At least 95% of incidents each month within the response and resolution times of their priority | Monthly service report | Analysis | Operational acceptance | From go-live, monthly | iorta Project Manager | Head, BDOI IT | Production support approach and service levels (priorities P1 to P4) | Not in the FRS. | PROPOSED | Must
NFR-SUP-03 | Supportability | Error references and coded messages | Support finds the cause of a reported error quickly. | Every unexpected error shows a reference found in the logs; every business error shows a message of the messages catalogue with its code | Message cases of each test plan | Test | System | SIT | iorta QA lead | Head, BDOI IT | Operations runbook (error reference); messages catalogue of each FRS | Messages catalogue of each FRS. Aligned. | ALIGNED | Must
NFR-SUP-04 | Supportability | Hypercare | The project team supports the first month of production. | Hypercare from T+1 to T+30 (4 Jan to 2 Feb 2028) with issue triage at 10:00 and 16:00 each business day | Hypercare log and exit report | Inspection | Operational acceptance | Hypercare | iorta Project Manager | BIBS Product Owner | Cut-over plan of the Data Migration Handbook (T-30 to T+30); project plan phase G | The Handbook states it. Aligned. | ALIGNED | Must
NFR-SUP-05 | Supportability | Administration without a command line | Support runs routine tasks from screens. | Jobs started, stopped and re-run, caches cleared and integration events re-sent from administration screens; 0 routine tasks that need a command line | Walk-through of the runbook's routine tasks with L2 support | Walk-through | Operational acceptance | Knowledge transfer (from Jun 2027); ORR / PRR | iorta DevOps and Platform Lead | Head, BDOI IT | BRD-11 UAM-NFR-24, 26 (no command line); operations runbook (routine support tasks) | FRS BRD-11 refers to the platform tools. Aligned. | ALIGNED | Should
NFR-AUD-01 | Auditability | Complete audit trail | Every action is recorded with who, what, when and from where. | Every create, update, approve, post, reverse, sign-in, sign-out, report run and export recorded with the user, time, source IP, module, record, old and new values and a success or failure indicator, in the same transaction as the change | Audit cases of each test plan | Test | System | SIT | iorta QA lead | Internal Audit, BDOI | Security controls (audit); BRD-2 p.67, p.186 (IT audit trail standard, seven items); BRD-4 NFR 4; register DCR-145 | Each FRS has an audit FR (for example FR-CR-030, FR-NB-016, FR-PM-005, FR-CM-003, FR-SS-091). Aligned. | ALIGNED | Must
NFR-AUD-02 | Auditability | Audit records cannot be changed | No one changes or deletes an audit record. | 0 successful changes or deletions of audit records by any user, administrator or the application | Security case - attempt to change an audit record through the screens and the data store | Test | Security | SIT; penetration test | iorta Security Lead | Internal Audit, BDOI | Security controls (insert-only audit trail, refused in the data store) | FRS BRD-10 FR-SS-091 (immutable audit log). Aligned. | ALIGNED | Must
NFR-AUD-03 | Auditability | Audit enquiry and export | Auditors find and export audit records themselves. | Audit trail filtered by user, period, module and record on screen; one month for one user exported within 2 minutes | Audit report case at year-1 data volume | Test | Performance (volume) | NFT on Pre-Prod | iorta QA lead | Internal Audit, BDOI | BRD-4 NFR 4 (exportable audit log); BRD-11 UAM-NFR-41 (User Access Audit Log report) | FRS BRD-04 and BRD-11 state the reports. Aligned. | PROPOSED | Should
NFR-AUD-04 | Auditability | Master-data change log | Changes to master data keep old and new values field by field. | Users and roles, products and versions, insurers and branches, commission rates, lists of values, chart of accounts, payees and parameters logged field by field with old and new values | Change-log cases of the BRD-00 and BRD-05 test plans | Test | System | SIT | iorta QA lead | Internal Audit, BDOI | FRS BRD-00 FR-CR-031 (CRQ07) | FRS BRD-00 states it. Aligned. | ALIGNED | Must
NFR-RET-01 | Data retention | Retention per record type | Each record type has its retention rule. | Default 5 years online and 15 years archive; Claims 10 years online and 15 archive; Accounting vouchers and reports, Sanction Screening and Submitted Policies 5 years online and 5 archive | Retention rule list reviewed by the record owners; monthly retention review report | Inspection | Configuration review | UAT (Drop 1); before go-live | iorta Business Analyst lead | BIBS Product Owner | BRD-00 p.45 (5 / 15 years); BRD-7 p.41 (10 / 15); BRD-5 Add.1, BRD-10 p.25, BRD-12 p.14 (5 / 5); register DCR-136; CRQ22 | Each FRS names the retention rule of its records (for example renewal candidates, broker claims, submitted policies); the values wait for CRQ22 and Q39. | DECISION | Must
NFR-RET-02 | Data retention | Archive, purge and legal hold | Records leave the online store only under approved rules. | Monthly review lists eligible records; archive and purge run only after BDOI approves the retention decision (Q39); records and files under legal hold never purged | Retention review report; legal-hold case in SIT | Test | System | SIT | iorta Solution Architect | Head, Comptrollership | FRS BRD-01 FR-NB-137; programme alignment pack 6.3 (Object Lock, legal hold) | FRS BRD-01 states it. Aligned. | ALIGNED | Must
NFR-RET-03 | Data retention | Audit log retention | Audit records outlive the records they describe. | Audit records 5 years online and archived to 16 years | Retention rule of the audit records | Inspection | Configuration review | Before go-live | iorta Solution Architect | Internal Audit, BDOI | BRD-7 p.41 (audit logs archive 16 years); BRD-00 p.45 (5 / 15 years) | FRS BRD-07 aligns the 16-year audit archive under CLQ24. | DECISION | Must
NFR-RET-04 | Data retention | Document storage tiers | Older documents move to cheaper storage and stay retrievable. | Documents to infrequent-access storage after 90 days and to archive storage after 1 year; any document retrieved within 1 minute | Lifecycle configuration review; retrieval case of an archived document | Test | System | Pre-Prod | iorta DevOps and Platform Lead | Cloud and Digital Operations Engineering (IER owner) | Programme alignment pack 6.3 (lifecycle to Standard-IA and Glacier Instant Retrieval); IER (S3 lifecycle) | Not in the FRS. | ALIGNED | Should
NFR-RET-05 | Data retention | AML records | KYC and screening records are kept as AMLA requires. | KYC documents and screening cases kept at least 5 years after the end of the client relationship | Retention rules of screening cases and list entries reviewed by Compliance | Inspection | Configuration review | UAT (Drop 1) | iorta Business Analyst lead | Compliance Officer, BDOI | BRD-10 p.25 (5 years online, 5 archive); RA 9160 (AMLA), as amended | FRS BRD-10 states the rules of screening cases and list entries (5 / 5). Aligned. | ALIGNED | Must
NFR-INT-01 | Interoperability | Integration gateway and contracts | Every system-to-system interface is published through the BDO gateway with a written contract. | Every service interface through Apigee X, described in OpenAPI 3 with versioned contracts; every file interface with an agreed layout and control totals | Interface catalogue review; contract tests in SIT | Inspection | Service interface (API) | SIT | iorta Solution Architect | Head, BDOI IT | Drop plan integrations (all external touch-points owned by BDOI IT); brief of 8-Oct-2026 (Apigee X) | Interfaces and integration chapter of each FRS. Aligned. | ALIGNED | Must
NFR-INT-02 | Interoperability | Business events | Business events reach their consumers exactly once from the consumer's view. | Events published through a transactional outbox; 0 events lost in the resilience test; failed events kept as dead letters and re-sent from the administration screen | Resilience test with the event stream stopped (NFR-AVL-05); dead-letter case in SIT | Test | Resilience | SIT; NFT | iorta Solution Architect | Head, BDOI IT | Platform cache and events design (outbox, dead letters); operations runbook | Not in the FRS. | ALIGNED | Must
NFR-INT-03 | Interoperability | Identity standards | Identity interfaces use open standards. | OpenID Connect and SAML 2.0 with EIAM; SCIM 2.0 provisioning from UIDM-ISC | Interface tests in SIT | Test | System integration | SIT | iorta Security Lead | Head, BDOI IT | Drop plan integrations EIAM and UIDM-ISC; security controls | FRS BRD-11 (directory sign-in, IQ04, IQ05). | ALIGNED | Must
NFR-INT-04 | Interoperability | File interfaces | Inbound files are validated, reconciled and reported. | Every inbound file (PDC list, bills payment, bank and insurer files) validated against its layout; each run reconciled to its control totals; errors reported per row; a failed transfer retried up to 3 times | File cases of the BRD-02 and BRD-05 test plans | Test | System integration | SIT | iorta QA lead | Head, Operations | Programme alignment pack 5 (PMS, OBPCS, Old BOB, CMS / New BOB, insurer systems); FRS BRD-02 (payment files) | FRS BRD-02 and BRD-05 specify the layouts. Aligned. | PROPOSED | Must
NFR-INT-05 | Interoperability | E-mail through CCM | All outbound e-mail goes through the BDO communications service. | 100% of outbound e-mail sent through CCM with its delivery status recorded | E-mail cases in SIT | Test | System integration | SIT (after DEP-12) | iorta Solution Architect | Head, BDOI IT | Drop plan integration CCM (INT-13); IQ11 | Notifications chapters of the FRS. The sending mode (SMTP or service call) is open (IQ11). | DECISION | Must
NFR-INT-06 | Interoperability | Unavailable partner systems | An unavailable external system does not block users. | Outbound messages queued and retried for 24 hours; an alert after 3 failed attempts; users keep working | Resilience case with a partner simulator switched off in SIT | Test | Resilience | SIT; NFT | iorta Solution Architect | Head, BDOI IT | Programme alignment pack 5 (integration inventory) | Not in the FRS. | PROPOSED | Should

## Reconciliation
Reconciliation
The catalogue against the FRS non-functional chapters, the register and the IER
Theme | BRD values | FRS statements | IER workbook v20 | Catalogue target | Difference and action | Register / questions
Screen response | Under 5 s (BRD-00); 2 s (BRD-12); 3 s (BRD-9); 3 to 5 s (BRD-10); 5 s (BRD-2, 3, 4, 7); 5 to 10 s (BRD-5); 10 s (BRD-1, 6, 11) | Online p95 under 3 s (FRS BRD-01 to BRD-10); 2 s (FRS BRD-00, BRD-12) | Not stated | NFR-PRF-01: p95 2.0 s, p99 4.0 s | Stricter than nine FRS; the FRS take the value at their next issue after BDOI confirms | DCR-137, DCR-165, XQ08
Reports | 20 s (BRD-6, 11); 10 to 20 s (BRD-5); 5 min (BRD-7); daily 3 / weekly 10 / monthly 15 min (BRD-4) | Same values; heavy reports as jobs | Not stated | NFR-PRF-03 and NFR-PRF-04 | None | DCR-137
Users | 1,344 named / 429 concurrent (BRD-00); 485 / 145 (BRD-1); module counts in each BRD | 150 concurrent plus 20% a year (FRS BRD-01); others within that sizing | About 1,200 internal users (architecture sheet); growth 15% a year | NFR-CAP-01: design 150 + 20% a year; peak test 429 | IER growth 15% against 20% in the BRDs; IER re-sized with 20% | DCR-166, DCR-232, CRQ21, CRQ24
Availability | 99.9% (BRD-2, 3, 9, 10, 12); 99.99% (BRD-8); 100% (BRD-5 Add.1); 'follow QPS' (BRD-1, 6, 11) | Same deployment as BRD-1; one BIBS-wide set being agreed | Production 24 x 7 | NFR-AVL-01: 99.9% of the service window | BRD-5 and BRD-8 values withdrawn when BDOI confirms | DCR-134, DCR-057
Service window | From 06:00-22:00 Mon-Fri plus month-end weekends (BRD-4) to 08:00-18:00 Mon-Fri (BRD-10) | BRD-1 window 07:00-22:00 governs (OQ44) | Non-production 12 x 5 | NFR-AVL-02: 06:00-22:00 Mon-Sat plus month-end weekends | Earlier opening (06:00) than the FRS state; FRS aligned at next issue | DCR-133
Maintenance window | 00:00-04:00 (BRD-10, 12); 19:00-07:00 (BRD-5); 21:00-05:00 (BRD-9); bank standard (others) | CSQ12 overlap noted (FRS BRD-09) | Not stated | NFR-AVL-03: 00:00-04:00, 45 minutes a month | BRD-5 and BRD-9 windows withdrawn | DCR-138, CSQ12
RPO | 24 h (BRD-2, 3, 8); 4 h (BRD-4, 7, 9); backup every 15 min (BRD-9) | Quoted from the BRDs | 15 minutes | NFR-REC-01: 15 minutes | IER value governs; stricter than every BRD | DCR-135, DCR-225
RTO | 4 h (BRD-2, 3, 4, 7, 8, 9); critical 4 h, full 24 h (BRD-12) | 4 h | 4 hours | NFR-REC-02: 4 hours | None | DCR-135
Backup | Every 4 h, kept 5 years (BRD-00, 1, 4, 7); kept 7 years (BRD-2, 8); daily (BRD-5, 10, 12) | Platform backup; 7 years (FRS BRD-02, 08) | Automated backups; DR replica | NFR-REC-03: continuous log archiving, base every 4 h, kept 7 years | Longest retention taken | DCR-102, DCR-136
Retention | 5 / 15 years (BRD-00, 1, 2, 4, 8, 9); 10 / 15, audit 16 (BRD-7); 5 / 5 (BRD-5, 10, 12) | Rules per record type; values wait for CRQ22 and Q39 | S3 lifecycle to IA and Glacier | NFR-RET-01, NFR-RET-03 | Per record type; BDOI confirms values | DCR-136, CRQ22, Q39
Session and lock-out | Warning 15, log-out 30 min (BRD-1, 6, 11); 15 min (BRD-4, 7); lock-out 3 attempts (BRD-4, 7, 11) | FRS BRD-11: 15 / 30 minutes, 3 attempts | Not stated | NFR-SEC-05 | BRD-4 and BRD-7 15-minute log-out replaced by 30 minutes | DCR-140, DCR-142
Sign-in | Windows credentials, EUA, SSO or LDAP (BRD-4, 7, 11) | Directory sign-in through EUA (FRS BRD-11, Q42) | Not stated | NFR-SEC-01: EIAM single sign-on, OIDC or SAML 2.0 | EIAM replaces EUA; FRS BRD-11 updated at next issue | DCR-143, IQ04
Platform components | Not stated | Not stated | Redis 7, Kafka 3.6, ingress-nginx, JDK 17 and Node 20 on the VDI list | NFR-MNT-04: Valkey 8, Kafka 3.9, OpenJDK 21, Node 22, Gateway API | IER rows updated to the baseline of 8-Oct-2026 | DCR-224, DCR-228
DR region | DR server (BRD-4, 7) | Platform HA and DR | Cross-region read replica; diagram shows ap-southeast-1 warm standby | NFR-REC-05 | BDOI IT names the region after the data-residency check | DCR-225, IQ26
Accessibility | Options for impaired vision or colour blindness (BRD-11) | BDO UX contrast rules (FRS BRD-11) | Not stated | NFR-ACC-01 to 04: WCAG 2.2 AA | New level; screen standards appendix updated | -

## Summary
Summary
NFRs per category and status
Category | NFRs | Must | Aligned | BDOI decision | Proposed
PRF Performance | 9 | 6 | 2 | 2 | 5
CAP Capacity and volume | 5 | 4 | 1 | 1 | 3
AVL Availability | 5 | 5 | 2 | 3 | 0
REC Recovery (RTO, RPO, backup and DR) | 5 | 5 | 2 | 2 | 1
SCL Scalability | 4 | 2 | 3 | 0 | 1
SEC Security | 12 | 12 | 6 | 2 | 4
PRV Privacy | 6 | 4 | 3 | 1 | 2
ACC Accessibility | 4 | 3 | 2 | 0 | 2
USE Usability and low-click workflows | 6 | 4 | 4 | 0 | 2
RSP Responsive and mobile-first | 3 | 3 | 2 | 0 | 1
LOC Localisation | 4 | 3 | 3 | 0 | 1
MNT Maintainability | 6 | 5 | 3 | 0 | 3
CFG Configurability | 5 | 3 | 5 | 0 | 0
OBS Observability | 5 | 5 | 2 | 1 | 2
SUP Supportability | 5 | 4 | 4 | 0 | 1
AUD Auditability | 4 | 3 | 3 | 0 | 1
RET Data retention | 5 | 4 | 3 | 2 | 0
INT Interoperability | 6 | 5 | 3 | 1 | 2

## _lists (hidden)
Test | ALIGNED | Must
Analysis | DECISION | Should
Inspection | PROPOSED
Walk-through