## Cover
CHANGE CONTROL
CR Effort Estimate
Operations Remittance; goes with the FRS Operations Remittance v1.0
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.0
Date | 17 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Effort | Man-days of 8 hours, plus or minus 20 percent, for the open change requests only. | 1
Delivery Work | Partial and gap requirements of the BRD scope: delivery work of the programme, not change requests; indicative man-days for planning. | 6
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
CR Effort Estimate, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Effort | CR
Effort | Title
Effort | Analysis and design
Effort | Backend
Effort | Frontend
Effort | Testing
Effort | Documentation and UAT
Effort | Total
Delivery Work | No.
Delivery Work | Delivery work in the BRD scope
Delivery Work | Requirements
Delivery Work | Man-days

## Effort
Effort
Man-days of 8 hours, plus or minus 20 percent, for the open change requests only.
CR | Title | Analysis and design | Backend | Frontend | Testing | Documentation and UAT | Total
Total | No open change request | 0 | 0 | 0 | 0 | 0 | 0

## Delivery Work
Delivery Work
Partial and gap requirements of the BRD scope: delivery work of the programme, not change requests; indicative man-days for planning.
No. | Delivery work in the BRD scope | Requirements | Man-days
DW-RMT-01 | Excel extract in the layout of the current report: heading, 35 columns with the Mall Assurance columns, totals and closing lines (IF-RMT-01) | FRID.RMT.001.03, 001.08, 002.02, 007.01 | 6
DW-RMT-02 | Pipe-delimited text extract with header control totals and detail records (IF-RMT-02) | FRID.RMT.001.03, 001.09 | 5
DW-RMT-03 | Settlement number per insurer (insurer code + 8 digits) and the YYYYMMDD file and report naming | FRID.RMT.001.04, 006.02, 014.02 | 3
DW-RMT-04 | Remittance Settings screen: extraction schedule, output folders, file pattern | FRID.RMT.003.01 | 4
DW-RMT-05 | Insurer OR return read from the returned extract layout (Excel and text) with the header totals check | FRID.RMT.008.01 | 5
DW-RMT-06 | Annex III layouts: Mall Assurance columns of the Normal schedule, List of Remitted Accounts | FRID.RMT.014.01 | 4