## Cover
USER ACCEPTANCE
Business Unit Walkthrough Users
Operations Remittance; goes with the FRS Operations Remittance v1.0
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.0
Date | 17 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | One walkthrough account per persona of the FRS Operations Remittance; the people are fictitious. | 8
Script | The storyboards of the Process and Storyboards v1.0, step by step. | 13
Legend
Pass
Fail
Blocked
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona
Users | Walkthrough account
Users | Does
Users | Screens
Users | Sign-in
Script | Storyboard
Script | Step
Script | Who
Script | Screen
Script | Does
Script | Sees
Script | Result |  | Not run, Pass, Fail, Blocked

## Users
Users
One walkthrough account per persona of the FRS Operations Remittance; the people are fictitious.
Persona | Walkthrough account | Does | Screens | Sign-in
Remittance Processor | Rosa Remittance Processor | Runs manual extractions, reviews the batches assigned to him, excludes and restores accounts, submits, holds or returns batches, sends the schedule to the insurer and uploads the insurer ORs. | Remittance Workbench, Extraction, Remittance Batches, Insurer OR Upload, DTIP Status | Issued separately by the iorta TechNXT Project Team
Remittance Team Leader | Ramon Remittance Lead | Approves or returns submitted batches, reassigns batches, approves special remittance requests, keeps the early remittance incentive rules and follows the extraction runs. | Remittance Batches, Special Remittance, Incentive Rules, Report Centre | Issued separately by the iorta TechNXT Project Team
Marketing Collection | Miguel Marketing Collection | Requests holds and special remittances for the accounts of the marketing unit and asks for a remittance schedule to be sent to the insurer. | Remittance Holds, Special Remittance | Issued separately by the iorta TechNXT Project Team
Marketing Team Leader | Marta Marketing Lead | Approves hold requests, extensions and cancellations. | Remittance Holds | Issued separately by the iorta TechNXT Project Team
Disbursement | Dante Disbursement | Receives the payment request of each approved batch and pays the insurer; the payment status comes back to Remittance. | Disbursement Queue (BRD-05) | Issued separately by the iorta TechNXT Project Team
Comptrollership | Consuelo Comptroller | Reads the remittance reports and the DTIP status. | Report Centre, DTIP Status | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | Reads batches, holds, special remittances, their history and the reports. Changes nothing. | Remittance Batches, Report Centre | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | Keeps the group profiles, the lists of values and the extraction schedule. | User Access screens (BRD-11), Job Monitor | Issued separately by the iorta TechNXT Project Team

## Script
Script
The storyboards of the Process and Storyboards v1.0, step by step.
Storyboard | Step | Who | Screen | Does | Sees | Result
SB-RMT-01 Evening extraction to approved batch | 1 | System | Extraction | The evening run checks the four invoices | Three extracted; the check payment Unextracted - due: check within the holding period | Not run
SB-RMT-01 Evening extraction to approved batch | 2 | Remittance Processor | Remittance Workbench | Opens the notice of the run | Batch ALPHA00000001 Normal - Peso with 3 accounts | Not run
SB-RMT-01 Evening extraction to approved batch | 3 | Remittance Processor | Remittance Batch | Excludes one account with a reason, previews | 2 accounts and their totals; the exclusion in the history | Not run
SB-RMT-01 Evening extraction to approved batch | 4 | Remittance Processor | Remittance Batch | Submits the batch | For Approval; the Team Leader is told | Not run
SB-RMT-01 Evening extraction to approved batch | 5 | Remittance Team Leader | Remittance Batch | Approves | Approved; payment request in the Disbursement queue | Not run
SB-RMT-02 Schedule to the insurer and OR upload | 1 | Marketing Collection | Remittance Batch | Asks to send the schedule | Request recorded | Not run
SB-RMT-02 Schedule to the insurer and OR upload | 2 | Remittance Processor | Remittance Batch | Sends the schedule | Schedule sent with date and recipient | Not run
SB-RMT-02 Schedule to the insurer and OR upload | 3 | Remittance Processor | Insurer OR Upload | Uploads the returned file | 2 lines read; 1 updated; 1 Amount mismatch | Not run
SB-RMT-02 Schedule to the insurer and OR upload | 4 | Remittance Processor | Insurer OR Upload | Opens the exception report | The mismatch with OR amount and paid PR | Not run
SB-RMT-03 Hold requested and released | 1 | Marketing Collection | Remittance Holds | Requests a hold until 30-Nov with a reason | For Approval | Not run
SB-RMT-03 Hold requested and released | 2 | Marketing Team Leader | Remittance Holds | Approves | Active; assigned to a processor | Not run
SB-RMT-03 Hold requested and released | 3 | System | Extraction | The evening run | Invoice Unextracted - due: account on hold | Not run
SB-RMT-03 Hold requested and released | 4 | Marketing Collection | Remittance Holds | Releases the hold | Released; extracted by the next run | Not run

## Lists
Result
Not run
Pass
Fail
Blocked