## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
Claims; goes with the FRS Claims v1.0
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-07
Version | 1.0
Date | 17 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Inputs | Open questions, dependencies and settings of the FRS Claims v1.0. | 31
Legend
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Inputs | No.
Inputs | What BDOI provides or decides
Inputs | Owner
Inputs | Needed by
Inputs | Status |  | Open, Received, Confirmed
Inputs | Answer

## Inputs
Inputs
Open questions, dependencies and settings of the FRS Claims v1.0.
No. | What BDOI provides or decides | Owner | Needed by | Status | Answer
Q-CL-01 | BDOI's mapping calls the Claims Authorization Code an EBIX function, out of scope, while BRCLM.001 asks to disable it for unpaid covers. Keep the code in BIBS (as stated in FRCLM.021.02) or remove it? | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-02 | Unpaid or partly paid policy: return the form to the Account Officer (BDOI's FRS) or record the claim flagged unpaid with the code disabled (BRD)? Both are proposed: record, flag and return to the AO. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-03 | Claims Reporting Form: which fields are mandatory for Marketing, and may a handler create a claim without a form? | Claims Unit Head; Marketing | 15 Dec 2026 | Open
Q-CL-04 | Annex F lists 29 values mixing statuses (Follow Up, New PLA) and settlement outcomes, plus Open and Closed; the BRD has 18 statuses and 10 settlement types. Confirm the lists and which values need Team Leader or Team Head approval. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-05 | Annexes R, S and T are empty: settlement fields, settlement check registry, certificate of no claim. Does BDOI receive settlement checks for safekeeping (the dashboard lists 'Settlement Check for Safekeeping')? This changes CLQ10 (no claim money through BDOI). | Claims Unit Head; Comptrollership | 15 Dec 2026 | Open
Q-CL-06 | Approval workflow: which actions need approval (follow-up, record corrections, temporary closure, reopen, settlement, denial), with which levels, and the time limit before escalation. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-07 | Visibility: handler sees only his claims (BDOI's FRS) while BRCLM.003 gives view access to all covers. Confirm for claims, covers and reports, including branch users. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-08 | Lead measures LM1, LM2, LM3 and the claims grouping 'Motor vs Non-Motor': definitions. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-09 | TAT: working days on which calendar; start events (adjuster's report submitted, documents complete); TAT per insurer from the SLA or one table (Annex AB). | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-10 | Annex Q: default of the next follow-up date ('Today's Date + ???') per status. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-11 | Annex P: 'Name' field (difference with the claimant); Completed date versus Date of Settlement; Claim CorpDept, Claim Origin values. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-12 | Sustainability report: purpose, columns and recipients (title only in FRCLM.018). | Risk; Sustainability Office | 15 Dec 2026 | Open
Q-CL-13 | Claims KRA: send Annex AC (Claims KRA workbook) with the criteria and weights. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-14 | Claim types: Annex M mixes the 8 codes of the core system with 98 types of claim of the category list, with duplicates (Fire / Fire/Lightning, Theft / Robbery). Confirm the two lists and Annex L (empty). | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-15 | Report annexes U to Z have headings only: send the column lists of each layout. | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-16 | Total Loss: 75% of the loss for Motor, the whole sum insured for Non-Motor; set by the handler or computed? Used by Renewal (CLQ28). | Claims Unit Head | 15 Dec 2026 | Open
Q-CL-17 | Legacy claims: years and statuses to migrate (Annex C reference not received). | Claims Unit Head; Data Migration | 15 Dec 2026 | Open
Q-CL-18 | Annex B copies the definitions of the Collections FRS (CMS, DP, PTP, SOA); send the claims terms. | BDOI System Analyst | 15 Dec 2026 | Open
D-CLM-01 | BDOI gives the annexes referred to and not received: Claims Core FRS Data Mapping, Data Migration data mapping, Motor and Non-Motor process flows, Insurers Directory, Claims KRA. | BDOI | Before SIT | Open
D-CLM-02 | BDOI completes Annexes L, R, S and T and the columns of the report annexes U to Z. | BDOI | Before SIT | Open
D-CLM-03 | BDO IT confirms the e-mail service (CCM) and the insurers' claims mailboxes (IS-CLM-01). | BDOI IT | Before SIT | Open
D-CLM-04 | Data Migration loads the open and historical claims and the masters (DM-CLM-01, DM-CLM-02). | BDOI | Before SIT | Open
D-CLM-05 | UIDM-ISC carries the claims group profiles and the reporting lines of the handler groups. | BDOI | Before SIT | Open
P-01 | Confirm the value of: BCL_DEFAULT_CURRENCY: claim currency when the cover has none (default PHP) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-02 | Confirm the value of: BCL_FOLLOW_UP_DAYS: days to the next follow-up (default 7) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-03 | Confirm the value of: BCL_AGEING_BUCKETS: ageing brackets (default 30, 60, 90, 180) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-04 | Confirm the value of: BCL_PAST_DUE_DAYS: past due threshold (default 90) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-05 | Confirm the value of: BCL_PRONE_MIN_CLAIMS / BCL_PRONE_YEARS: claims-prone location (default 3 / 3) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-06 | Confirm the value of: BCL_AUTH_DP_POLICY: authorization on a direct-payment cover (default CONFIRM) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-07 | Confirm the value of: Scorecard rating bands (default A 95, B 90, C 85, D 80, F below 80) | BDOI Product Owner, Claims | 15 Dec 2026 | Open
P-08 | Confirm the value of: TAT targets per insurer (Annex AB) (default Motor 2, 3 or 7 working days; Non-Motor 10 or 15; check 10) | BDOI Product Owner, Claims | 15 Dec 2026 | Open

## Lists
Status
Open
Received
Confirmed