## Start here
UX screen register BRD-2 Operations
The screen images of the set for the BDOI UX Design team
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-2 Operations (Drop 1)
Version and date |  | Version 2.1, 08 October 2026
For |  | BDOI UX Design team (UXD)
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | Open the sheet UX screen register: one row per screen image of the 07 deck and the 09 image package, with the screen, the personas, the flow and step, the state and the FRS section.
2 | Filter Changed in this issue = Y to see the images that are new or changed in this issue; the change reference names the comment or change request behind the change.
3 | Set the UXD status of each row (Not started, In design, Ready for review, Approved) and write the UXD comments; leave the other columns as issued.
4 | Import the CSV of the image package into the design tool to link each design to its screen image.
5 | Raise questions on the sheet Questions and comments; the project team answers there. At the next issue the UXD status and comments of the unchanged rows are carried over.
The register
Step | ID | Template | What it holds | Kept by | Rows entered | Mandatory cells missing | Status | Open
1 | UXR | UX screen register | 189 screen images of 89 screens; 51 changed in this issue | BDOI UX Design team |  |  | Not started | Open →
Changes in this issue
Change reference |  | What changed |  |  |  |  | Screens
v2.1-01 |  | Check pick-up removed from scope (CSHID.009): the Check Pick-up screen is withdrawn and the Check Pick-ups Due tile of the Cashiering Workbench goes with it (FR-OP-017, CLR-OP-38) |  |  |  |  | SCR-OP-07
v2.1-02 |  | PR 2307 reversal owned by Marketing Collection: Receive, Validate and Post Report and Route to Disbursement move from the Cashier to Marketing Collection, Settle in Cash is withdrawn and Release to Insurer posts nothing (FR-OP-113, 121; CLR-OP-40, 41) |  |  |  |  | SCR-OP-19, SCR-OP-36
v2.1-03 |  | Minimal balances cleared when the payment is processed; the sweep becomes a safety net and minimal excess never reaches Unapplied Payments (FR-OP-023, CLR-OP-39) |  |  |  |  | SCR-OP-11, SCR-OP-22
v2.1-04 |  | Remittance: pending financial endorsements block the extraction, extraction source kept, draft schedule before submission (FR-OP-030 to 034, CLR-OP-44 to 46) |  |  |  |  | SCR-OP-24, SCR-OP-26
v2.1-05 |  | Early remittance incentive moved to Remittance (RMTID.041) and the peso-equivalent tolerance of the reconciliation (FR-OP-038, 075, 078; CLR-OP-47, 49) |  |  |  |  | SCR-OP-35, SCR-OP-45
v2.1-06 |  | Returned endorsement requests go to the Marketing owner of the account, with the return and resubmission history (FR-OP-053, CLR-OP-52) |  |  |  |  | SCR-OP-39
v2.1-07 |  | Commission Receivables: DP entries from the tagging, read-only review, rule-based exclusion, eligibility from the fully paid status, statuses Valid, Invalid and Returned, Statement of Account, SLA incentives and invoice-level ageing (FR-OP-090 to 099, CLR-OP-54 to 62) |  |  |  |  | SCR-OP-51, SCR-OP-52, SCR-OP-53, SCR-OP-54, SCR-OP-56, SCR-OP-57, SCR-OP-60
Other sheets
Sheet |  |  | What it holds
Reference lists |  |  | The lists of the drop-downs: states and UXD statuses
Questions and comments |  |  | Questions and comments of the UX Design team, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## UX screen register
UXR UX screen register | [13 empty] | Step 1 of 1
← Back to Start here | Step 1 of 1. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per screen image of BRD-2 Operations (the 07 deck and the 09 image package): the screen, personas, flow and step, state, FRS section and requirements, the image file, and the UXD status and comments of the UX Design team. Changed in this issue marks the images that are new or changed in this issue, with the change reference.
Provided by | BDOI UX Design team (UXD status and comments); iorta TechNXT project team (the other columns)
Due | With each design review; the rows are re-issued with each version of the set
How it is loaded | Kept by the UX Design team; at a new issue the UXD status and comments of the unchanged rows are carried over and the changed rows are flagged
Source | FRS v2.1 and the screens of the SIT environment (seed data)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (UX Design team lead) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | No | Yes | No | Yes | Conditional: when Changed in this issue is Y
Format | SCR-, NAV- or DO- and a number | Text | Text | Flow ID and title | Whole number | From the list | Section number | FR-... separated by commas | <Screen ID>_<state>.png | Text | From the list | Text | Y or N | Reference
Allowed values | Free entry | Free entry | Free entry | Free entry | A whole number from 1 to 99 | List State of a screen image: 12 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Not started, In design, Ready for review, Approved (list UXD status) | Free entry | Y or N | Free entry
What to enter | The screen of the image, as in the FRS and the deck | The title of the screen | The personas who see the screen in this state | The end-to-end flow that shows the image, if any | The step of the flow | The state of the screen on the image | The section of the FRS (or handbook) that specifies the screen | The functional requirements of the screen | The file of the image package (09) | The caption of the image | The status of the design of this screen state, kept by the UX Design team | Comments of the UX Design team on the screen state | Y when the image is new or changed in this issue of the set | The change reference (comment, change request or issue change) that changed the image
Row | Screen ID * | Screen name * | Persona(s) * | Flow | Step | State * | FRS section * | Requirement IDs | Image file * | What the image shows | UXD status * | UXD comments | Changed in this issue * | Change reference
Example – overwrite or delete | SCR-OP-01 | Operations Home | Cashier |  |  | Default | 13.1.1 | FR-OP-002, FR-OP-003 | SCR-OP-01_home.png | Operations Home of a Cashier: the invoice finder and the Cashiering work tiles | Not started |  | N
| SCR-OP-01 | Operations Home | Cashier | - |  | Default | 13.1.1 | FR-OP-002, FR-OP-003 | SCR-OP-01_home.png | Operations Home of a Cashier: the invoice finder and the Cashiering work tiles | Not started |  | N
| SCR-OP-01 | Operations Home | Remittance Team Leader / Head | - |  | Default | 13.1.1 | FR-OP-002, FR-OP-003 | SCR-OP-01_home-tl.png | Operations Home of the Remittance Team Leader: the Remittance work tiles | Not started |  | N
| SCR-OP-02 | Invoice Search | Cashier | - |  | Default | 13.1.2 | FR-OP-004, FR-OP-005 | SCR-OP-02_list.png | Invoice Search, All Invoices tab | Not started |  | N
| SCR-OP-02 | Invoice Search | Cashier | - |  | Default | 13.1.2 | FR-OP-004, FR-OP-005 | SCR-OP-02_filters.png | Invoice Search with the filter panel open | Not started |  | N
| SCR-OP-03 | Invoice 360 | Remittance Team Leader / Head | - |  | Default | 13.1.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_record.png | Invoice 360 of a paid and fully remitted invoice, Components & Balances tab | Not started |  | N
| SCR-OP-03 | Invoice 360 | Remittance Team Leader / Head | - |  | Default | 13.1.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_transactions.png | Policy Transactions tab: the original booking and the endorsement, with the journal of the booking expanded | Not started |  | N
| SCR-OP-03 | Invoice 360 | Remittance Team Leader / Head | - |  | Default | 13.1.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_remittances.png | Remittances tab: the remittance batches of the invoice | Not started |  | N
| SCR-OP-03 | Invoice 360 | Remittance Team Leader / Head | - |  | Default | 13.1.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_movements.png | Movements tab: booking, application and remittance movements | Not started |  | N
| SCR-OP-04 | Hand-offs and Extracts | Cashier | - |  | Default | 13.1.4 | FR-OP-130 | SCR-OP-04_extracts.png | Extract Repository tab with the files produced by Remittance and Production Reconciliation | Not started |  | N
| SCR-OP-05 | Report Archive | Cashier | - |  | Default | 13.1.5 | FR-OP-009 | SCR-OP-05_list.png | Report Archive with the runs and their parameters | Not started |  | N
| SCR-OP-06 | Notification Settings | Cashier | - |  | Default | 13.1.6 | FR-OP-036 | SCR-OP-06_list.png | Notification Settings of the Operations events | Not started |  | N
| SCR-OP-07 | Cashiering Workbench | Cashier | - |  | Default | 13.2.1 | FR-OP-003 | SCR-OP-07_home.png | Cashiering Workbench with the work queues of the section | Not started |  | Y | v2.1-01
| SCR-OP-08 | Receive Payment | Cashier | - |  | Default | 13.2.2 | FR-OP-011, FR-OP-018, FR-OP-019, FR-OP-020 | SCR-OP-08_preview.png | Receive Payment with the application preview of an unpaid invoice | Not started |  | N
| SCR-OP-08 | Receive Payment | Cashier | - |  | Validation error | 13.2.2 | FR-OP-011, FR-OP-018, FR-OP-019, FR-OP-020 | SCR-OP-08_error.png | Receive Payment with the field messages of an empty form | Not started |  | N
| SCR-OP-09 | Receipts | Cashier | - |  | Default | 13.2.3 | FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024 | SCR-OP-09_list.png | Receipts: acknowledgement and official receipts | Not started |  | N
| SCR-OP-09 | Receipts | Cashiering Team Leader / Head | - |  | Default | 13.2.3 | FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024 | SCR-OP-09_actions.png | Cancellations and Reinstatements tab of the Cashiering Team Leader | Not started |  | N
| SCR-OP-09 | Receipts | Cashier | - |  | Filled | 13.2.3 | FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024 | SCR-OP-09_issue-or.png | Issue Official Receipt dialog for a service fee | Not started |  | N
| SCR-OP-10 | Receipt | Cashier | - |  | Default | 13.2.4 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_record.png | Receipt with its applications by component | Not started |  | N
| SCR-OP-10 | Receipt | Cashier | - |  | Confirmation with reason | 13.2.4 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_cancel.png | Cancel Receipt dialog with the reason | Not started |  | N
| SCR-OP-10 | Receipt | Cashiering Team Leader / Head | - |  | Pending approval | 13.2.4 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_approval.png | Receipt with a cancellation request for approval: workflow header and Approve and Post | Not started |  | N
| SCR-OP-11 | Unapplied Payments | Cashier | - |  | Default | 13.2.5 | FR-OP-022 | SCR-OP-11_list.png | Unapplied Payments, Unapplied tab | Not started |  | Y | v2.1-03
| SCR-OP-11 | Unapplied Payments | Cashiering Team Leader / Head | - |  | Pending approval | 13.2.5 | FR-OP-022 | SCR-OP-11_approval.png | For Approval tab of the Cashiering Team Leader with Approve Selected | Not started |  | Y | v2.1-03
| SCR-OP-12 | Unapplied Payment | Cashier | - |  | Filled | 13.2.6 | FR-OP-022, FR-OP-023, FR-OP-120 | SCR-OP-12_record.png | Unapplied payment with the disposition form filled for a refund | Not started |  | N
| SCR-OP-12 | Unapplied Payment | Cashiering Team Leader / Head | - |  | Pending approval | 13.2.6 | FR-OP-022, FR-OP-023, FR-OP-120 | SCR-OP-12_approval.png | Unapplied payment with a refund for approval: workflow header, Approve and the disposition history | Not started |  | N
| SCR-OP-13 | Incoming Requests | Cashier | - |  | Default | 13.2.7 | FR-OP-022, FR-OP-130 | SCR-OP-13_list.png | Incoming Requests: Collector Requests, To Do | Not started |  | N
| SCR-OP-13 | Incoming Requests | Cashier | - |  | Confirmation with reason | 13.2.7 | FR-OP-022, FR-OP-130 | SCR-OP-13_accept.png | Accept Request dialog of a collector request | Not started |  | N
| SCR-OP-14 | Pre-booked Payments | Cashier | - |  | Pending approval | 13.2.8 | FR-OP-018, FR-OP-132 | SCR-OP-14_list.png | Pre-booked Payments waiting for booking | Not started |  | N
| SCR-OP-15 | Payment Uploads | Cashier | - |  | Default | 13.2.9 | FR-OP-008, FR-OP-015, FR-OP-016 | SCR-OP-15_wizard.png | Payment Uploads, Bills Payment: template and upload steps | Not started |  | N
| SCR-OP-16 | PDC Warehouse | Cashier | - |  | Default | 13.2.10 | FR-OP-016 | SCR-OP-16_list.png | PDC Warehouse by maturity month | Not started |  | N
| SCR-OP-16 | PDC Warehouse | Cashier | - |  | Filled | 13.2.10 | FR-OP-016 | SCR-OP-16_add.png | Warehouse Post-dated Check dialog | Not started |  | N
| SCR-OP-18 | Batch Print | Cashier | - |  | Default | 13.2.11 | FR-OP-025 | SCR-OP-18_list.png | Batch Print: receipts to print and the print batches | Not started |  | N
| SCR-OP-19 | BIR 2307 | Cashier | - |  | Default | 13.2.12 | FR-OP-113, FR-OP-121 | SCR-OP-19_list.png | BIR 2307, Tagged by Marketing tab | Not started |  | Y | v2.1-02
| SCR-OP-19 | BIR 2307 | Marketing Collection | - |  | Filled | 13.2.12 | FR-OP-113, FR-OP-121 | SCR-OP-19_tag.png | Tag BIR 2307 dialog of Marketing Collection | Not started |  | Y | v2.1-02
| SCR-OP-20 | Commission ORs | Cashier | - |  | Default | 13.2.13 | FR-OP-021 | SCR-OP-20_page.png | Commission ORs: upload steps and the staged commission payments | Not started |  | N
| SCR-OP-21 | Receipt Series | Cashiering Team Leader / Head | - |  | Default | 13.2.14 | FR-OP-010 | SCR-OP-21_list.png | Receipt Series with the numbers left | Not started |  | N
| SCR-OP-21 | Receipt Series | Cashiering Team Leader / Head | - |  | Filled | 13.2.14 | FR-OP-010 | SCR-OP-21_new.png | New Receipt Series dialog | Not started |  | N
| SCR-OP-22 | Cashiering Setup | Cashiering Team Leader / Head | - |  | Default | 13.2.15 | FR-OP-015, FR-OP-023 | SCR-OP-22_layouts.png | Cashiering Setup, Payment File Layouts tab | Not started |  | Y | v2.1-03
| SCR-OP-22 | Cashiering Setup | Cashiering Team Leader / Head | - |  | Default | 13.2.15 | FR-OP-015, FR-OP-023 | SCR-OP-22_minimal.png | Cashiering Setup, Minimal Balance tab with the rules | Not started |  | Y | v2.1-03
| SCR-OP-23 | Remittance Workbench | Remittance Team Leader / Head | - |  | Default | 13.3.1 | FR-OP-003 | SCR-OP-23_home.png | Remittance Workbench with the work queues | Not started |  | N
| SCR-OP-24 | Extraction | Remittance Processor | - |  | Default | 13.3.2 | FR-OP-030, FR-OP-031, FR-OP-038 | SCR-OP-24_list.png | Extraction with the Run Extraction card and the extraction runs | Not started |  | Y | v2.1-04
| SCR-OP-24 | Extraction | Remittance Processor | - |  | Read-only or locked | 13.3.2 | FR-OP-030, FR-OP-031, FR-OP-038 | SCR-OP-24_tags.png | Extraction run with the tag and reasons of each invoice examined | Not started |  | Y | v2.1-04
| SCR-OP-25 | Remittance Batches | Remittance Processor | - |  | Default | 13.3.3 | FR-OP-032, FR-OP-033, FR-OP-035, FR-OP-036 | SCR-OP-25_list.png | Remittance Batches, Review in Process tab | Not started |  | N
| SCR-OP-25 | Remittance Batches | Remittance Team Leader / Head | - |  | Pending approval | 13.3.3 | FR-OP-032, FR-OP-033, FR-OP-035, FR-OP-036 | SCR-OP-25_approval.png | Remittance Batches, For Approval tab of the Remittance Team Leader | Not started |  | N
| SCR-OP-26 | Remittance Batch | Remittance Processor | - |  | Default | 13.3.4 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_review.png | Remittance batch in review: workflow header, totals strip and the accounts | Not started |  | Y | v2.1-04
| SCR-OP-26 | Remittance Batch | Remittance Processor | - |  | Confirmation with reason | 13.3.4 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_preview.png | Preview Submission dialog with the totals | Not started |  | Y | v2.1-04
| SCR-OP-26 | Remittance Batch | Remittance Team Leader / Head | - |  | Read-only or locked | 13.3.4 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_closed.png | Remittance batch with the insurer's OR received: the completed workflow | Not started |  | Y | v2.1-04
| SCR-OP-26 | Remittance Batch | Remittance Team Leader / Head | - |  | Read-only or locked | 13.3.4 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_documents.png | Documents and Receipts tab: schedule, payment request and the ORs | Not started |  | Y | v2.1-04
| SCR-OP-27 | Insurer OR Upload | Remittance Processor | - |  | Default | 13.3.5 | FR-OP-037 | SCR-OP-27_page.png | Insurer OR Upload with the upload history | Not started |  | N
| SCR-OP-27 | Insurer OR Upload | Remittance Processor | - |  | Default | 13.3.5 | FR-OP-037 | SCR-OP-27_run.png | Upload run with the accounts updated and the result of each record | Not started |  | N
| SCR-OP-28 | Remittance Holds | Marketing Team Leader / Unit Head (hold approver) | - |  | Pending approval | 13.3.6 | FR-OP-111 | SCR-OP-28_list.png | Remittance Holds, For Approval tab | Not started |  | N
| SCR-OP-28 | Remittance Holds | Marketing Collection | - |  | Filled | 13.3.6 | FR-OP-111 | SCR-OP-28_new.png | New Hold Request dialog | Not started |  | N
| SCR-OP-29 | Remittance Hold | Marketing Team Leader / Unit Head (hold approver) | - |  | Pending approval | 13.3.7 | FR-OP-111 | SCR-OP-29_approval.png | Hold request for approval with the workflow header | Not started |  | N
| SCR-OP-30 | Special Remittance | Remittance Team Leader / Head | - |  | Pending approval | 13.3.8 | FR-OP-040, FR-OP-112 | SCR-OP-30_list.png | Special Remittance, For Approval tab | Not started |  | N
| SCR-OP-30 | Special Remittance | Marketing Collection | - |  | Filled | 13.3.8 | FR-OP-040, FR-OP-112 | SCR-OP-30_new.png | New Special Remittance dialog | Not started |  | N
| SCR-OP-31 | Special Remittance Request | Remittance Team Leader / Head | - |  | Default | 13.3.9 | FR-OP-040, FR-OP-112 | SCR-OP-31_record.png | Special remittance request with its workflow | Not started |  | N
| SCR-OP-32 | DTIP Status | Remittance Processor | - |  | Default | 13.3.10 | FR-OP-030, FR-OP-039 | SCR-OP-32_list.png | DTIP Status per invoice | Not started |  | N
| SCR-OP-32 | DTIP Status | Remittance Processor | - |  | Default | 13.3.10 | FR-OP-030, FR-OP-039 | SCR-OP-32_batches.png | Accounts in Batches tab | Not started |  | N
| SCR-OP-33 | Remittance Deductions | ACSL Team Leader (confirms deductions) | - |  | Default | 13.3.11 | FR-OP-035 | SCR-OP-33_list.png | Remittance Deductions, For Confirmation tab | Not started |  | N
| SCR-OP-33 | Remittance Deductions | ACSL Processor (remittance deductions) | - |  | Filled | 13.3.11 | FR-OP-035 | SCR-OP-33_new.png | New Remittance Deduction dialog | Not started |  | N
| SCR-OP-34 | Remittance Deduction | ACSL Team Leader (confirms deductions) | - |  | Default | 13.3.12 | FR-OP-035 | SCR-OP-34_record.png | Remittance deduction for confirmation | Not started |  | N
| SCR-OP-35 | Incentive Rules | Remittance Team Leader / Head | - |  | Default | 13.3.13 | FR-OP-038, FR-OP-078 | SCR-OP-35_list.png | Incentive Rules | Not started |  | Y | v2.1-05
| SCR-OP-35 | Incentive Rules | Remittance Team Leader / Head | - |  | Filled | 13.3.13 | FR-OP-038, FR-OP-078 | SCR-OP-35_new.png | New incentive rule | Not started |  | Y | v2.1-05
| SCR-OP-36 | Disbursement Queue | Disbursement | - |  | Default | 13.3.14 | FR-OP-036, FR-OP-120, FR-OP-121 | SCR-OP-36_list.png | Disbursement Queue, To Acknowledge tab | Not started |  | Y | v2.1-02
| SCR-OP-36 | Disbursement Queue | Disbursement | - |  | Filled | 13.3.14 | FR-OP-036, FR-OP-120, FR-OP-121 | SCR-OP-36_dv.png | Assign DV Number dialog | Not started |  | Y | v2.1-02
| SCR-OP-37 | Adjustment Workbench | Adjustment Processor | - |  | Default | 13.4.1 | FR-OP-050, FR-OP-061 | SCR-OP-37_list.png | Adjustment Workbench with the policy of every request | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | - |  | Default | 13.4.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_policy.png | Step 1, Policy: the booked invoice chosen and its policy details | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | - |  | Filled | 13.4.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_request.png | Step 2, Request: a flat cancellation with its reason and effective date | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | - |  | Filled | 13.4.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_recompute.png | Step 3, Recompute & Submit: before and after and per insurer | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | - |  | Validation error | 13.4.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_error.png | Step 2 with the field messages of an incomplete request | Not started |  | N
| SCR-OP-39 | Endorsement Request | Adjustment Team Leader | - |  | Pending approval | 13.4.3 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_approval.png | Endorsement request for approval: policy chips, facts and the workflow header | Not started |  | Y | v2.1-06
| SCR-OP-39 | Endorsement Request | Adjustment Team Leader | - |  | Default | 13.4.3 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_policy.png | Policy tab: the policy and placement with the links to the account and the invoice | Not started |  | Y | v2.1-06
| SCR-OP-39 | Endorsement Request | Adjustment Team Leader | - |  | Read-only or locked | 13.4.3 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_accounting.png | Accounting tab of a posted cancellation: the GL entries | Not started |  | Y | v2.1-06
| SCR-OP-39 | Endorsement Request | Adjustment Team Leader | - |  | Read-only or locked | 13.4.3 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_transactions.png | Policy Transactions tab: the booking and the cancellation with their journals | Not started |  | Y | v2.1-06
| SCR-OP-40 | Posting Batches | Adjustment Processor | - |  | Default | 13.4.4 | FR-OP-056 | SCR-OP-40_ready.png | Posting Batches, Ready for Posting | Not started |  | N
| SCR-OP-40 | Posting Batches | Adjustment Processor | - |  | Read-only or locked | 13.4.4 | FR-OP-056 | SCR-OP-40_posted.png | Posting Batches, Posted Batches with their outcome | Not started |  | N
| SCR-OP-41 | Batch Request Upload | Adjustment Processor | - |  | Default | 13.4.5 | FR-OP-050, FR-OP-056 | SCR-OP-41_wizard.png | Batch Request Upload: template and upload steps | Not started |  | N
| SCR-OP-42 | Minimal Balance File | Adjustment Processor | - |  | Default | 13.4.6 | FR-OP-059 | SCR-OP-42_page.png | Minimal Balance File with the balances written off or credited | Not started |  | N
| SCR-OP-43 | Reconciliation Workbench | Production Reconciliation Handler | - |  | Default | 13.5.1 | FR-OP-003 | SCR-OP-43_home.png | Reconciliation Workbench with the work queues | Not started |  | N
| SCR-OP-44 | Reconciliation Cycles | Production Reconciliation Handler | - |  | Default | 13.5.2 | FR-OP-075, FR-OP-079 | SCR-OP-44_list.png | Reconciliation Cycles | Not started |  | N
| SCR-OP-45 | Reconciliation Cycle | Production Reconciliation Handler | - |  | Default | 13.5.3 | FR-OP-075, FR-OP-077, FR-OP-078, FR-OP-079 | SCR-OP-45_items.png | Reconciliation cycle: workflow header and the items by bucket | Not started |  | Y | v2.1-05
| SCR-OP-45 | Reconciliation Cycle | Production Reconciliation Handler | - |  | Filled | 13.5.3 | FR-OP-075, FR-OP-077, FR-OP-078, FR-OP-079 | SCR-OP-45_review.png | Item review dialog: BDOI and insurer values side by side with the feedback | Not started |  | Y | v2.1-05
| SCR-OP-45 | Reconciliation Cycle | Production Reconciliation Handler | - |  | Default | 13.5.3 | FR-OP-075, FR-OP-077, FR-OP-078, FR-OP-079 | SCR-OP-45_incentive.png | Early Incentive tab: the incentive expected per invoice | Not started |  | Y | v2.1-05
| SCR-OP-46 | Production Extracts | Production Reconciliation Handler | - |  | Default | 13.5.4 | FR-OP-071, FR-OP-072, FR-OP-073 | SCR-OP-46_list.png | Production Extracts | Not started |  | N
| SCR-OP-46 | Production Extracts | Production Reconciliation Handler | - |  | Filled | 13.5.4 | FR-OP-071, FR-OP-072, FR-OP-073 | SCR-OP-46_new.png | New Production Extract dialog | Not started |  | N
| SCR-OP-47 | Insurer Feedback | Production Reconciliation Handler | - |  | Default | 13.5.5 | FR-OP-074, FR-OP-075 | SCR-OP-47_list.png | Insurer Feedback uploads | Not started |  | N
| SCR-OP-47 | Insurer Feedback | Production Reconciliation Handler | - |  | Default | 13.5.5 | FR-OP-074, FR-OP-075 | SCR-OP-47_upload.png | Upload Insurer Feedback dialog | Not started |  | N
| SCR-OP-48 | Unbooked Accounts | Production Reconciliation Handler | - |  | Default | 13.5.6 | FR-OP-076 | SCR-OP-48_list.png | Unbooked Accounts, Not Booked tab | Not started |  | N
| SCR-OP-49 | Extract Schedules | Production Reconciliation Handler | - |  | Default | 13.5.7 | FR-OP-070 | SCR-OP-49_list.png | Extract Schedules | Not started |  | N
| SCR-OP-49 | Extract Schedules | Production Reconciliation Handler | - |  | Filled | 13.5.7 | FR-OP-070 | SCR-OP-49_new.png | New Extract Schedule dialog | Not started |  | N
| SCR-OP-50 | Commission Workbench | Commission Receivables Handler | - |  | Default | 13.6.1 | FR-OP-003 | SCR-OP-50_home.png | Commission Workbench with the work queues | Not started |  | N
| SCR-OP-51 | DP Lists | Commission Receivables Handler | - |  | Default | 13.6.2 | FR-OP-090, FR-OP-091 | SCR-OP-51_list.png | DP Lists, Lists Received | Not started |  | Y | v2.1-07
| SCR-OP-51 | DP Lists | Commission Receivables Handler | - |  | Default | 13.6.2 | FR-OP-090, FR-OP-091 | SCR-OP-51_upload.png | Upload DP List dialog | Not started |  | Y | v2.1-07
| SCR-OP-52 | DP Accounts | Commission Receivables Handler | - |  | Default | 13.6.3 | FR-OP-091, FR-OP-092, FR-OP-094 | SCR-OP-52_list.png | DP Accounts, Billed tab | Not started |  | Y | v2.1-07
| SCR-OP-52 | DP Accounts | Commission Receivables Handler | - |  | Default | 13.6.3 | FR-OP-091, FR-OP-092, FR-OP-094 | SCR-OP-52_account.png | Account dialog of a direct payment account with its validation rules | Not started |  | Y | v2.1-07
| SCR-OP-53 | DP Billings | Commission Receivables Handler | - |  | Pending approval | 13.6.4 | FR-OP-092, FR-OP-093, FR-OP-099 | SCR-OP-53_list.png | DP Billings, Awaiting Insurer tab | Not started |  | Y | v2.1-07
| SCR-OP-54 | DP Billing | Commission Receivables Handler | - |  | Pending approval | 13.6.5 | FR-OP-092, FR-OP-093, FR-OP-094 | SCR-OP-54_awaiting.png | DP billing awaiting the insurer's answer | Not started |  | Y | v2.1-07
| SCR-OP-54 | DP Billing | Commission Receivables Handler | - |  | Filled | 13.6.5 | FR-OP-092, FR-OP-093, FR-OP-094 | SCR-OP-54_answers.png | Record Insurer Answers dialog | Not started |  | Y | v2.1-07
| SCR-OP-55 | Insurer Responses | Commission Receivables Handler | - |  | Pending approval | 13.6.6 | FR-OP-093 | SCR-OP-55_list.png | Insurer Responses: billings waiting for the insurer | Not started |  | N
| SCR-OP-56 | Incentive Schemes | Commission Receivables Team Leader / Head | - |  | Default | 13.6.7 | FR-OP-095 | SCR-OP-56_list.png | Incentive Schemes | Not started |  | Y | v2.1-07
| SCR-OP-56 | Incentive Schemes | Commission Receivables Team Leader / Head | - |  | Filled | 13.6.7 | FR-OP-095 | SCR-OP-56_new.png | New Incentive Scheme dialog | Not started |  | Y | v2.1-07
| SCR-OP-57 | Incentive Runs | Commission Receivables Team Leader / Head | - |  | Default | 13.6.8 | FR-OP-095 | SCR-OP-57_list.png | Incentive Runs | Not started |  | Y | v2.1-07
| SCR-OP-57 | Incentive Runs | Commission Receivables Team Leader / Head | - |  | Filled | 13.6.8 | FR-OP-095 | SCR-OP-57_compute.png | Compute Incentive dialog | Not started |  | Y | v2.1-07
| SCR-OP-58 | BIR Certificates | Comptrollership | - |  | Default | 13.6.9 | FR-OP-096 | SCR-OP-58_list.png | BIR Certificates of Comptrollership | Not started |  | N
| SCR-OP-58 | BIR Certificates | Commission Receivables Handler | - |  | Filled | 13.6.9 | FR-OP-096 | SCR-OP-58_new.png | Submit BIR Certificate dialog | Not started |  | N
| SCR-OP-59 | BIR Certificate | Comptrollership | - |  | Default | 13.6.10 | FR-OP-096 | SCR-OP-59_record.png | BIR certificate submission for Comptrollership | Not started |  | N
| SCR-OP-60 | Estimated Items | Commission Receivables Handler | - |  | Filled | 13.6.11 | FR-OP-097 | SCR-OP-60_flag.png | Flag Invoice as Estimated dialog | Not started |  | Y | v2.1-07
| SCR-OP-61 | Interfaces | System Administrator | - |  | Default | 13.7.1 | FR-OP-004, FR-OP-008, FR-OP-130, FR-OP-131 | SCR-OP-61_feeds.png | Interfaces, Feeds tab | Not started |  | N
| SCR-OP-61 | Interfaces | System Administrator | - |  | Default | 13.7.1 | FR-OP-004, FR-OP-008, FR-OP-130, FR-OP-131 | SCR-OP-61_runs.png | Interfaces, Run Log tab | Not started |  | N
| SCR-OP-61 | Interfaces | System Administrator | - |  | Filled | 13.7.1 | FR-OP-004, FR-OP-008, FR-OP-130, FR-OP-131 | SCR-OP-61_replay.png | Replay Booked Invoices dialog | Not started |  | N
| SCR-OP-62 | FFY Register | Cashier | - |  | Default | 13.7.2 | FR-OP-004 | SCR-OP-62_list.png | FFY Register as the Operations users see it | Not started |  | N
| SCR-OP-63 | Report Centre (Operations reports) | Remittance Team Leader / Head | - |  | Default | 13.7.3 | FR-OP-009, FR-OP-028, FR-OP-041, FR-OP-062, FR-OP-080, FR-OP-098, FR-OP-099 | SCR-OP-63_list.png | Report Centre, the Operations reports | Not started |  | N
| SCR-OP-64 | Report | Remittance Team Leader / Head | - |  | Default | 13.7.4 | FR-OP-009 | SCR-OP-64_record.png | Remittance Tracker run on screen | Not started |  | N
| SCR-NB-29 | Pre-booking Confirmation | Processing (books the accounts) | WT-A A booked invoice from the client's payment to the insurer's official receipt | 1 | Success message | 14.1 | FR-NB-110, FR-NB-113, FR-NB-114, FR-NB-117, FR-NB-118, FR-NB-119 | SCR-NB-29_wt-a-step-01.png | WT-A step 1: Opens the account from Ready to Book, checks the invoice and the journal preview and clicks Book Account | Not started |  | N
| SCR-OP-02 | Invoice Search | Cashier | WT-A A booked invoice from the client's payment to the insurer's official receipt | 2 | Default | 14.1 | FR-OP-004, FR-OP-005 | SCR-OP-02_wt-a-step-02.png | WT-A step 2: Searches the ARN on Invoice Search | Not started |  | N
| SCR-OP-08 | Receive Payment | Cashier | WT-A A booked invoice from the client's payment to the insurer's official receipt | 3 | Filled | 14.1 | FR-OP-011, FR-OP-018, FR-OP-019, FR-OP-020 | SCR-OP-08_wt-a-step-03.png | WT-A step 3: Opens Receive Payment, enters the ARN, the payor, the amount paid and the payment date, and checks the preview | Not started |  | N
| SCR-OP-10 | Receipt | Cashier | WT-A A booked invoice from the client's payment to the insurer's official receipt | 4 | Success message | 14.1 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_wt-a-step-04.png | WT-A step 4: Clicks Issue AR and Apply | Not started |  | N
| SCR-OP-24 | Extraction | Remittance Processor | WT-A A booked invoice from the client's payment to the insurer's official receipt | 5 | Success message | 14.1 | FR-OP-030, FR-OP-031, FR-OP-038 | SCR-OP-24_wt-a-step-05.png | WT-A step 5: Enters the invoice number on Extraction and clicks Run Extraction, then opens the run | Not started |  | Y | v2.1-04
| SCR-OP-26 | Remittance Batch | Remittance Processor | WT-A A booked invoice from the client's payment to the insurer's official receipt | 6 | Pending approval | 14.1 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_wt-a-step-06.png | WT-A step 6: Opens the batch, checks the totals strip and the account, clicks Preview and Submit and submits the batch | Not started |  | Y | v2.1-04
| SCR-OP-26 | Remittance Batch | Remittance Team Leader / Head | WT-A A booked invoice from the client's payment to the insurer's official receipt | 7 | Success message | 14.1 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_wt-a-step-07.png | WT-A step 7: Opens the batch from For Approval and clicks Approve and Push | Not started |  | Y | v2.1-04
| SCR-OP-36 | Disbursement Queue | Disbursement | WT-A A booked invoice from the client's payment to the insurer's official receipt | 8 | Success message | 14.1 | FR-OP-036, FR-OP-120, FR-OP-121 | SCR-OP-36_wt-a-step-08.png | WT-A step 8: Acknowledges the payment request and assigns the DV number | Not started |  | Y | v2.1-02
| SCR-OP-27 | Insurer OR Upload | Remittance Processor | WT-A A booked invoice from the client's payment to the insurer's official receipt | 9 | Success message | 14.1 | FR-OP-037 | SCR-OP-27_wt-a-step-09.png | WT-A step 9: Uploads the insurer's schedule with its OR number and opens the upload run | Not started |  | N
| SCR-OP-03 | Invoice 360 | Remittance Processor | WT-A A booked invoice from the client's payment to the insurer's official receipt | 10 | Read-only or locked | 14.1 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_wt-a-step-10.png | WT-A step 10: Opens Invoice 360 of the invoice, Remittances tab | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 1 | Filled | 14.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_wt-b-step-01.png | WT-B step 1: Opens New Request, searches the policy number and ticks the invoice | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 2 | Filled | 14.2 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_wt-b-step-02.png | WT-B step 2: Chooses Financial – Change of Cover, Flat Cancellation, the reason, the effective date and the description, and clicks Recompute | Not started |  | N
| SCR-OP-39 | Endorsement Request | Marketing Collection | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 3 | Pending approval | 14.2 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_wt-b-step-03.png | WT-B step 3: Clicks Submit for Validation | Not started |  | Y | v2.1-06
| SCR-OP-39 | Endorsement Request | Adjustment Processor | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 4 | Pending approval | 14.2 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_wt-b-step-04.png | WT-B step 4: Opens the request from the workbench and clicks Validate | Not started |  | Y | v2.1-06
| SCR-OP-39 | Endorsement Request | Adjustment Team Leader | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 5 | Success message | 14.2 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_wt-b-step-05.png | WT-B step 5: Opens the request and clicks Approve | Not started |  | Y | v2.1-06
| SCR-OP-40 | Posting Batches | Adjustment Processor | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 6 | Success message | 14.2 | FR-OP-056 | SCR-OP-40_wt-b-step-06.png | WT-B step 6: Ticks the request on Posting Batches and clicks Post Selected | Not started |  | N
| SCR-OP-39 | Endorsement Request | Adjustment Processor | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 7 | Read-only or locked | 14.2 | FR-OP-006, FR-OP-052, FR-OP-053, FR-OP-055, FR-OP-056, FR-OP-057, FR-OP-060, FR-OP-061, FR-OP-114 | SCR-OP-39_wt-b-step-07.png | WT-B step 7: Opens the Policy Transactions tab of the request and the journal of the last transaction | Not started |  | Y | v2.1-06
| SCR-OP-12 | Unapplied Payment | Cashier | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 8 | Pending approval | 14.2 | FR-OP-022, FR-OP-023, FR-OP-120 | SCR-OP-12_wt-b-step-08.png | WT-B step 8: Opens the unapplied payment left by the re-application, assigns a refund to the client and submits it | Not started |  | N
| SCR-OP-12 | Unapplied Payment | Cashiering Team Leader / Head | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 9 | Success message | 14.2 | FR-OP-022, FR-OP-023, FR-OP-120 | SCR-OP-12_wt-b-step-09.png | WT-B step 9: Opens the unapplied payment and clicks Approve | Not started |  | N
| SCR-OP-36 | Disbursement Queue | Disbursement | WT-B Cancellation of a paid and remitted policy, from the request to the refund | 10 | Default | 14.2 | FR-OP-036, FR-OP-120, FR-OP-121 | SCR-OP-36_wt-b-step-10.png | WT-B step 10: Opens the Disbursement Queue | Not started |  | Y | v2.1-02
| SCR-OP-54 | DP Billing | Commission Receivables Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 1 | Success message | 14.3 | FR-OP-092, FR-OP-093, FR-OP-094 | SCR-OP-54_wt-c-step-01.png | WT-C step 1: Opens the billing, clicks Record Answers, marks the account Approved and saves | Not started |  | Y | v2.1-07
| SCR-OP-54 | DP Billing | Commission Receivables Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 2 | Success message | 14.3 | FR-OP-092, FR-OP-093, FR-OP-094 | SCR-OP-54_wt-c-step-02.png | WT-C step 2: Clicks Record Collection with the collection date and the bank account | Not started |  | Y | v2.1-07
| SCR-OP-03 | Invoice 360 | Commission Receivables Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 3 | Read-only or locked | 14.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_wt-c-step-03.png | WT-C step 3: Opens Invoice 360 of the direct payment invoice, Movements tab | Not started |  | N
| SCR-OP-45 | Reconciliation Cycle | Production Reconciliation Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 4 | Filled | 14.3 | FR-OP-075, FR-OP-077, FR-OP-078, FR-OP-079 | SCR-OP-45_wt-c-step-04.png | WT-C step 4: Opens the cycle, the With Discrepancy item, and records the company concerned, the disposition and the feedback | Not started |  | Y | v2.1-05
| SCR-OP-45 | Reconciliation Cycle | Production Reconciliation Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 5 | Success message | 14.3 | FR-OP-075, FR-OP-077, FR-OP-078, FR-OP-079 | SCR-OP-45_wt-c-step-05.png | WT-C step 5: Selects the insurer-only item and sets its disposition | Not started |  | Y | v2.1-05
| SCR-OP-48 | Unbooked Accounts | Production Reconciliation Handler | WT-C Direct payment commission and the reconciliation of the insurer's production | 6 | Default | 14.3 | FR-OP-076 | SCR-OP-48_wt-c-step-06.png | WT-C step 6: Opens Unbooked Accounts | Not started |  | N
| SCR-OP-29 | Remittance Hold | Marketing Team Leader / Unit Head (hold approver) | WT-D Controls and the messages the user sees | 1 | Success message | 14.4 | FR-OP-111 | SCR-OP-29_wt-d-step-01.png | WT-D step 1: Marketing Collection raises a hold on the invoice with its reason and hold-until date; the Marketing Team Leader opens it and clicks Approve hold | Not started |  | N
| SCR-OP-38 | New Endorsement Request | Marketing Collection | WT-D Controls and the messages the user sees | 2 | Validation error | 14.4 | FR-OP-050, FR-OP-051, FR-OP-054, FR-OP-055, FR-OP-058 | SCR-OP-38_wt-d-step-02.png | WT-D step 2: Searches on New Request the invoice that is in the remittance batch for approval | Not started |  | N
| SCR-OP-10 | Receipt | Cashier | WT-D Controls and the messages the user sees | 3 | Pending approval | 14.4 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_wt-d-step-03.png | WT-D step 3: Opens a receipt, clicks Cancel Receipt, chooses the reason and submits the cancellation | Not started |  | N
| SCR-OP-10 | Receipt | Cashiering Team Leader / Head | WT-D Controls and the messages the user sees | 4 | Success message | 14.4 | FR-OP-011, FR-OP-012, FR-OP-013, FR-OP-014, FR-OP-024, FR-OP-025, FR-OP-027 | SCR-OP-10_wt-d-step-04.png | WT-D step 4: Opens the receipt and clicks Approve and Post | Not started |  | N
| SCR-OP-26 | Remittance Batch | Remittance Team Leader / Head | WT-D Controls and the messages the user sees | 5 | Validation error | 14.4 | FR-OP-032, FR-OP-033, FR-OP-034, FR-OP-035, FR-OP-036, FR-OP-038, FR-OP-110 | SCR-OP-26_wt-d-step-05.png | WT-D step 5: Submits the batch in review for approval, then tries to approve it | Not started |  | Y | v2.1-04
| DO-01 | Acknowledgement receipt (AR) | - | - |  | Document as received | 17.1 | FR-OP-011, FR-OP-025 | DO-01_document.png | Acknowledgement receipt (AR): first page as generated | Not started |  | N
| DO-02 | Official receipt (OR) for service fees and commission | - | - |  | Document as received | 17.2 | FR-OP-012, FR-OP-021 | DO-02_document.png | Official receipt (OR) for service fees and commission: first page as generated | Not started |  | N
| DO-03 | Remittance schedule | - | - |  | Document as received | 17.3 | FR-OP-034, FR-OP-110 | DO-03_document.png | Remittance schedule: first page as generated | Not started |  | N
| DO-04 | Payment request of a remittance batch | - | - |  | Document as received | 17.4 | FR-OP-034, FR-OP-035 | DO-04_document.png | Payment request of a remittance batch: first page as generated | Not started |  | N
| DO-05 | Endorsement slip | - | - |  | Document as received | 17.5 | FR-OP-060, FR-OP-114 | DO-05_document.png | Endorsement slip: first page as generated | Not started |  | N
| DO-06 | Validation slip | - | - |  | Document as received | 17.6 | FR-OP-060 | DO-06_document.png | Validation slip: first page as generated | Not started |  | N
| DO-07 | Production register | - | - |  | Document as received | 17.7 | FR-OP-072, FR-OP-073 | DO-07_document.png | Production register: first page as generated, with a selection of the columns | Not started |  | N
| DO-08 | Direct payment commission billing | - | - |  | Document as received | 17.8 | FR-OP-092 | DO-08_document.png | Direct payment commission billing: first page as generated, with a selection of the columns | Not started |  | N
| NAV-OP-01 | Cashier: landing page | Cashier | - |  | Landing page | 12.3 | - | NAV-OP-01_landing.png | Cashier: landing page after sign-in | Not started |  | N
| NAV-OP-01 | Cashier: menu | Cashier | - |  | Menu | 12.3 | - | NAV-OP-01_menu.png | Cashier: menu, every group open | Not started |  | N
| NAV-OP-02 | Cashiering Team Leader / Head: landing page | Cashiering Team Leader / Head | - |  | Landing page | 12.3 | - | NAV-OP-02_landing.png | Cashiering Team Leader / Head: landing page after sign-in | Not started |  | N
| NAV-OP-02 | Cashiering Team Leader / Head: menu | Cashiering Team Leader / Head | - |  | Menu | 12.3 | - | NAV-OP-02_menu.png | Cashiering Team Leader / Head: menu, every group open | Not started |  | N
| NAV-OP-03 | Remittance Processor: landing page | Remittance Processor | - |  | Landing page | 12.3 | - | NAV-OP-03_landing.png | Remittance Processor: landing page after sign-in | Not started |  | N
| NAV-OP-03 | Remittance Processor: menu | Remittance Processor | - |  | Menu | 12.3 | - | NAV-OP-03_menu.png | Remittance Processor: menu, every group open | Not started |  | N
| NAV-OP-04 | Remittance Team Leader / Head: landing page | Remittance Team Leader / Head | - |  | Landing page | 12.3 | - | NAV-OP-04_landing.png | Remittance Team Leader / Head: landing page after sign-in | Not started |  | N
| NAV-OP-04 | Remittance Team Leader / Head: menu | Remittance Team Leader / Head | - |  | Menu | 12.3 | - | NAV-OP-04_menu.png | Remittance Team Leader / Head: menu, every group open | Not started |  | N
| NAV-OP-05 | Production Reconciliation Handler: landing page | Production Reconciliation Handler | - |  | Landing page | 12.3 | - | NAV-OP-05_landing.png | Production Reconciliation Handler: landing page after sign-in | Not started |  | N
| NAV-OP-05 | Production Reconciliation Handler: menu | Production Reconciliation Handler | - |  | Menu | 12.3 | - | NAV-OP-05_menu.png | Production Reconciliation Handler: menu, every group open | Not started |  | N
| NAV-OP-06 | Adjustment Processor: landing page | Adjustment Processor | - |  | Landing page | 12.3 | - | NAV-OP-06_landing.png | Adjustment Processor: landing page after sign-in | Not started |  | N
| NAV-OP-06 | Adjustment Processor: menu | Adjustment Processor | - |  | Menu | 12.3 | - | NAV-OP-06_menu.png | Adjustment Processor: menu, every group open | Not started |  | N
| NAV-OP-07 | Adjustment Team Leader: landing page | Adjustment Team Leader | - |  | Landing page | 12.3 | - | NAV-OP-07_landing.png | Adjustment Team Leader: landing page after sign-in | Not started |  | N
| NAV-OP-07 | Adjustment Team Leader: menu | Adjustment Team Leader | - |  | Menu | 12.3 | - | NAV-OP-07_menu.png | Adjustment Team Leader: menu, every group open | Not started |  | N
| NAV-OP-08 | Commission Receivables Handler: landing page | Commission Receivables Handler | - |  | Landing page | 12.3 | - | NAV-OP-08_landing.png | Commission Receivables Handler: landing page after sign-in | Not started |  | N
| NAV-OP-08 | Commission Receivables Handler: menu | Commission Receivables Handler | - |  | Menu | 12.3 | - | NAV-OP-08_menu.png | Commission Receivables Handler: menu, every group open | Not started |  | N
| NAV-OP-09 | Commission Receivables Team Leader / Head: landing page | Commission Receivables Team Leader / Head | - |  | Landing page | 12.3 | - | NAV-OP-09_landing.png | Commission Receivables Team Leader / Head: landing page after sign-in | Not started |  | N
| NAV-OP-09 | Commission Receivables Team Leader / Head: menu | Commission Receivables Team Leader / Head | - |  | Menu | 12.3 | - | NAV-OP-09_menu.png | Commission Receivables Team Leader / Head: menu, every group open | Not started |  | N
| NAV-OP-10 | Marketing Collection: landing page | Marketing Collection | - |  | Landing page | 12.3 | - | NAV-OP-10_landing.png | Marketing Collection: landing page after sign-in | Not started |  | N
| NAV-OP-10 | Marketing Collection: menu | Marketing Collection | - |  | Menu | 12.3 | - | NAV-OP-10_menu.png | Marketing Collection: menu, every group open | Not started |  | N
| NAV-OP-11 | Marketing Team Leader / Unit Head (hold approver): landing page | Marketing Team Leader / Unit Head (hold approver) | - |  | Landing page | 12.3 | - | NAV-OP-11_landing.png | Marketing Team Leader / Unit Head (hold approver): landing page after sign-in | Not started |  | N
| NAV-OP-11 | Marketing Team Leader / Unit Head (hold approver): menu | Marketing Team Leader / Unit Head (hold approver) | - |  | Menu | 12.3 | - | NAV-OP-11_menu.png | Marketing Team Leader / Unit Head (hold approver): menu, every group open | Not started |  | N
| NAV-OP-12 | Comptrollership: landing page | Comptrollership | - |  | Landing page | 12.3 | - | NAV-OP-12_landing.png | Comptrollership: landing page after sign-in | Not started |  | N
| NAV-OP-12 | Comptrollership: menu | Comptrollership | - |  | Menu | 12.3 | - | NAV-OP-12_menu.png | Comptrollership: menu, every group open | Not started |  | N
| NAV-OP-13 | Disbursement: landing page | Disbursement | - |  | Landing page | 12.3 | - | NAV-OP-13_landing.png | Disbursement: landing page after sign-in | Not started |  | N
| NAV-OP-13 | Disbursement: menu | Disbursement | - |  | Menu | 12.3 | - | NAV-OP-13_menu.png | Disbursement: menu, every group open | Not started |  | N
| NAV-OP-14 | ACSL Processor (remittance deductions): landing page | ACSL Processor (remittance deductions) | - |  | Landing page | 12.3 | - | NAV-OP-14_landing.png | ACSL Processor (remittance deductions): landing page after sign-in | Not started |  | N
| NAV-OP-14 | ACSL Processor (remittance deductions): menu | ACSL Processor (remittance deductions) | - |  | Menu | 12.3 | - | NAV-OP-14_menu.png | ACSL Processor (remittance deductions): menu, every group open | Not started |  | N
| NAV-OP-15 | ACSL Team Leader (confirms deductions): landing page | ACSL Team Leader (confirms deductions) | - |  | Landing page | 12.3 | - | NAV-OP-15_landing.png | ACSL Team Leader (confirms deductions): landing page after sign-in | Not started |  | N
| NAV-OP-15 | ACSL Team Leader (confirms deductions): menu | ACSL Team Leader (confirms deductions) | - |  | Menu | 12.3 | - | NAV-OP-15_menu.png | ACSL Team Leader (confirms deductions): menu, every group open | Not started |  | N
| NAV-OP-16 | System Administrator: landing page | System Administrator | - |  | Landing page | 12.3 | - | NAV-OP-16_landing.png | System Administrator: landing page after sign-in | Not started |  | N
| NAV-OP-16 | System Administrator: menu | System Administrator | - |  | Menu | 12.3 | - | NAV-OP-16_menu.png | System Administrator: menu, every group open | Not started |  | N
| NAV-OP-17 | Auditor: landing page | Auditor | - |  | Landing page | 12.3 | - | NAV-OP-17_landing.png | Auditor: landing page after sign-in | Not started |  | N
| NAV-OP-17 | Auditor: menu | Auditor | - |  | Menu | 12.3 | - | NAV-OP-17_menu.png | Auditor: menu, every group open | Not started |  | N
| SCR-OP-02 | Invoice Search | Cashier | - |  | Empty list | 13.1.2 | FR-OP-004, FR-OP-005 | SCR-OP-02_empty.png | A search that finds no invoice | Not started |  | N
| SCR-OP-03 | Invoice 360 | Auditor | - |  | Read-only or locked | 13.1.3 | FR-OP-004, FR-OP-005, FR-OP-006, FR-OP-007, FR-OP-061 | SCR-OP-03_auditor.png | Invoice 360 as the Auditor sees it, without the actions | Not started |  | N
| SCR-OP-36 | Disbursement Queue | Disbursement | - |  | Default | 13.3.14 | FR-OP-036, FR-OP-120, FR-OP-121 | SCR-OP-36_actions.png | The row action menu of a payment request, opened from the more button of its row | Not started |  | Y | v2.1-02
| SCR-OP-63 | Report Centre (Operations reports) | Auditor | - |  | Read-only or locked | 13.7.3 | FR-OP-009, FR-OP-028, FR-OP-041, FR-OP-062, FR-OP-080, FR-OP-098, FR-OP-099 | SCR-OP-63_auditor.png | Report Centre as the Auditor sees it: the Operations reports on screen | Not started |  | N
Note on B16: Screen ID The screen of the image, as in the FRS and the deck Mandatory: Yes Format: SCR-, NAV- or DO- and a number Allowed values: Free entry Example: SCR-OP-01
Note on C16: Screen name The title of the screen Mandatory: Yes Format: Text Allowed values: Free entry Example: Operations Home
Note on D16: Persona(s) The personas who see the screen in this state Mandatory: Yes Format: Text Allowed values: Free entry Example: Cashier
Note on E16: Flow The end-to-end flow that shows the image, if any Mandatory: No Format: Flow ID and title Allowed values: Free entry
Note on F16: Step The step of the flow Mandatory: No Format: Whole number Allowed values: A whole number from 1 to 99
Note on G16: State The state of the screen on the image Mandatory: Yes Format: From the list Allowed values: List State of a screen image: 12 values, see Reference lists Example: Default
Note on H16: FRS section The section of the FRS (or handbook) that specifies the screen Mandatory: Yes Format: Section number Allowed values: Free entry Example: 13.1.1
Note on I16: Requirement IDs The functional requirements of the screen Mandatory: No Format: FR-... separated by commas Allowed values: Free entry Example: FR-OP-002, FR-OP-003
Note on J16: Image file The file of the image package (09) Mandatory: Yes Format: <Screen ID>_<state>.png Allowed values: Free entry Example: SCR-OP-01_home.png
Note on K16: What the image shows The caption of the image Mandatory: No Format: Text Allowed values: Free entry Example: Operations Home of a Cashier: the invoice finder and the Cashiering work tiles
Note on L16: UXD status The status of the design of this screen state, kept by the UX Design team Mandatory: Yes Format: From the list Allowed values: Not started, In design, Ready for review, Approved (list UXD status) Example: Not started
Note on M16: UXD comments Comments of the UX Design team on the screen state Mandatory: No Format: Text Allowed values: Free entry
Note on N16: Changed in this issue Y when the image is new or changed in this issue of the set Mandatory: Yes Format: Y or N Allowed values: Y or N Example: N
Note on O16: Change reference The change reference (comment, change request or issue change) that changed the image Mandatory: Conditional: when Changed in this issue is Y Format: Reference Allowed values: Free entry

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | UX screen register: Changed in this issue | Y | Yes
|  | N | No
State of a screen image (UX_STATE) | UX screen register: State | Default
Filled
Validation error
Confirmation with reason
Success message
Empty list
Read-only or locked
Pending approval
Rejected or returned
Document as received
Landing page
Menu
UXD status (UXD_STATUS) | UX screen register: UXD status | Not started
In design
Ready for review
Approved
Templates of this workbook (TEMPLATES) | Questions and comments: Template | UXR UX screen register
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed
Status (STATUS) | Start here: Status | Not started
In progress
Ready for review
Confirmed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100