## Start here
UX screen register BRD-4 Collections
The screen images of the set for the BDOI UX Design team
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-4 Collections (Drop 1)
Version and date |  | Version 2.0, 1 October 2026
For |  | BDOI UX Design team (UXD)
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | Open the sheet UX screen register: one row per screen image of the 07 deck and the 09 image package, with the screen, the personas, the flow and step, the state and the FRS section.
2 | Filter Changed in this issue = Y to see the images that are new or changed in this issue; the change reference names the comment or change request behind the change.
3 | Set the UXD status of each row (Not started, In design, Ready for review, Approved) and write the UXD comments; leave the other columns as issued.
4 | Import the CSV of the image package into the design tool to link each design to its screen image.
5 | Raise questions on the sheet Questions and comments; the project team answers there. At the next issue the UXD status and comments of the unchanged rows are carried over.
The register
Step | ID | Template | What it holds | Kept by | Rows entered | Mandatory cells missing | Status | Open
1 | UXR | UX screen register | 103 screen images of 40 screens; 0 changed in this issue | BDOI UX Design team |  |  | Not started | Open →
Changes in this issue
Change reference |  | What changed |  |  |  |  | Screens
- |  | First issue |  |  |  |  | -
Other sheets
Sheet |  |  | What it holds
Reference lists |  |  | The lists of the drop-downs: states and UXD statuses
Questions and comments |  |  | Questions and comments of the UX Design team, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## UX screen register
UXR UX screen register | [13 empty] | Step 1 of 1
← Back to Start here | Step 1 of 1. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per screen image of BRD-4 Collections (the 07 deck and the 09 image package): the screen, personas, flow and step, state, FRS section and requirements, the image file, and the UXD status and comments of the UX Design team. Changed in this issue marks the images that are new or changed in this issue, with the change reference.
Provided by | BDOI UX Design team (UXD status and comments); iorta TechNXT project team (the other columns)
Due | With each design review; the rows are re-issued with each version of the set
How it is loaded | Kept by the UX Design team; at a new issue the UXD status and comments of the unchanged rows are carried over and the changed rows are flagged
Source | FRS v2.0 and the screens of the SIT environment (seed data)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (UX Design team lead) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | No | Yes | No | Yes | Conditional: when Changed in this issue is Y
Format | SCR-, NAV- or DO- and a number | Text | Text | Flow ID and title | Whole number | From the list | Section number | FR-... separated by commas | <Screen ID>_<state>.png | Text | From the list | Text | Y or N | Reference
Allowed values | Free entry | Free entry | Free entry | Free entry | A whole number from 1 to 99 | List State of a screen image: 12 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Not started, In design, Ready for review, Approved (list UXD status) | Free entry | Y or N | Free entry
What to enter | The screen of the image, as in the FRS and the deck | The title of the screen | The personas who see the screen in this state | The end-to-end flow that shows the image, if any | The step of the flow | The state of the screen on the image | The section of the FRS (or handbook) that specifies the screen | The functional requirements of the screen | The file of the image package (09) | The caption of the image | The status of the design of this screen state, kept by the UX Design team | Comments of the UX Design team on the screen state | Y when the image is new or changed in this issue of the set | The change reference (comment, change request or issue change) that changed the image
Row | Screen ID * | Screen name * | Persona(s) * | Flow | Step | State * | FRS section * | Requirement IDs | Image file * | What the image shows | UXD status * | UXD comments | Changed in this issue * | Change reference
Example – overwrite or delete | SCR-CL-01 | Collections Home | Collection Handler |  |  | Default | 13.1.1 | FR-CL-085 | SCR-CL-01_home.png | Collections Home of the Collection Handler with the work tiles and the aging chart | Not started |  | N
| SCR-CL-01 | Collections Home | Collection Handler | - |  | Default | 13.1.1 | FR-CL-085 | SCR-CL-01_home.png | Collections Home of the Collection Handler with the work tiles and the aging chart | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Team Lead | - |  | Default | 13.1.2 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_list.png | PR Worklist of the Collection Team Lead: open accounts with handler, disposition and status | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Team Lead | - |  | Filled | 13.1.2 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_filters.png | PR Worklist with the Filters panel open | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Handler | - |  | Filled | 13.1.2 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_disposition.png | Record Disposition of a selected account with the check pick-up details | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Team Lead | - |  | Filled | 13.1.2 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_reassign.png | Reassign Accounts dialog for two selected accounts, temporary until an end date | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Handler | - |  | Default | 13.1.3 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_record.png | Collection account: header, facts, actions and the net PR breakdown by component | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Handler | - |  | Read-only or locked | 13.1.3 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_dispositions.png | Dispositions & Efforts tab with the hand-off to Cashiering | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Team Lead | - |  | Read-only or locked | 13.1.3 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_history.png | History tab: assignments and the field changes with From, To, user and source | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Team Lead | - |  | Read-only or locked | 13.1.3 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_locked.png | The account while another user works on it: the editing notice and no actions | Not started |  | N
| SCR-CL-04 | Client View | Collection Team Lead | - |  | Default | 13.1.4 | FR-CL-014 | SCR-CL-04_client.png | Client View: the accounts of a client with the totals of the open ones | Not started |  | N
| SCR-CL-05 | Installment Plans | Collection Handler | - |  | Default | 13.2.1 | FR-CL-040, FR-CL-041 | SCR-CL-05_list.png | Installment Plans: the active plans with their basis, total and paid | Not started |  | N
| SCR-CL-05 | Installment Plans | Collection Handler | - |  | Filled | 13.2.1 | FR-CL-040, FR-CL-041 | SCR-CL-05_new.png | New Installment Plan dialog: installments of one invoice | Not started |  | N
| SCR-CL-06 | Installment Plan | Collection Handler | - |  | Default | 13.2.2 | FR-CL-040, FR-CL-041, FR-CL-042, FR-CL-060 | SCR-CL-06_record.png | Installment Plan: the installments with their coverage, due date, amounts and status | Not started |  | N
| SCR-CL-06 | Installment Plan | Collection Handler | - |  | Default | 13.2.2 | FR-CL-040, FR-CL-041, FR-CL-042, FR-CL-060 | SCR-CL-06_actions.png | The row menu of an installment: Generate SOA and Record Promise | Not started |  | N
| SCR-CL-07 | Installments Due | Collection Handler | - |  | Default | 13.2.3 | FR-CL-041 | SCR-CL-07_list.png | Installments Due: the overdue installments of the live plans | Not started |  | N
| SCR-CL-08 | Promises to Pay | Collection Handler | - |  | Default | 13.2.4 | FR-CL-042, FR-CL-034 | SCR-CL-08_list.png | Promises to Pay: the open promises with the promised date and amount | Not started |  | N
| SCR-CL-08 | Promises to Pay | Collection Handler | - |  | Filled | 13.2.4 | FR-CL-042, FR-CL-034 | SCR-CL-08_new.png | Record Promise to Pay dialog | Not started |  | N
| SCR-CL-08 | Promises to Pay | Collection Handler | - |  | Validation error | 13.2.4 | FR-CL-042, FR-CL-034 | SCR-CL-08_error.png | A promised amount above the outstanding is refused, with the outcome per invoice | Not started |  | N
| SCR-CL-09 | Billing Statements | Collection Handler | - |  | Default | 13.2.5 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-09_list.png | Billing Statements: the statements sent to the clients | Not started |  | N
| SCR-CL-09 | Billing Statements | Collection Handler | - |  | Filled | 13.2.5 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-09_run.png | Billing Run dialog: the due period of the cycles to bill | Not started |  | N
| SCR-CL-10 | Statement of Account | Collection Handler | - |  | Default | 13.2.6 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-10_record.png | Statement of Account with the installments billed and the e-mails sent | Not started |  | N
| SCR-CL-10 | Statement of Account | Collection Handler | - |  | Filled | 13.2.6 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-10_send.png | Send Statement of Account: the e-mail to the client with the protected PDF | Not started |  | N
| SCR-CL-11 | Escalations | Collection Team Lead | - |  | Default | 13.3.1 | FR-CL-051, FR-CL-052, FR-CL-053 | SCR-CL-11_list.png | Escalations with the team lead: by rule or by a user, with the reason and the time in stage | Not started |  | N
| SCR-CL-11 | Escalations | Collection Handler | - |  | Filled | 13.3.1 | FR-CL-051, FR-CL-052, FR-CL-053 | SCR-CL-11_new.png | Escalate Accounts dialog: the invoices, the level and the reason | Not started |  | N
| SCR-CL-12 | Escalation | Collection Team Lead | - |  | Default | 13.3.2 | FR-CL-053 | SCR-CL-12_record.png | Escalation with the team lead: workflow header, actions and the escalated invoices | Not started |  | N
| SCR-CL-12 | Escalation | Collection Team Lead | - |  | Confirmation with reason | 13.3.2 | FR-CL-053 | SCR-CL-12_resolve.png | Resolve Escalation dialog with the resolution, after the escalation is acknowledged | Not started |  | N
| SCR-CL-13 | Escalation Rules | Section Head (Corporate / Retail) | - |  | Pending approval | 13.3.3 | FR-CL-050, FR-CL-051 | SCR-CL-13_list.png | Escalation Rules with their row menu: the rules in force and one waiting for authorization | Not started |  | N
| SCR-CL-13 | Escalation Rules | Section Head (Corporate / Retail) | - |  | Filled | 13.3.3 | FR-CL-050, FR-CL-051 | SCR-CL-13_new.png | New Escalation Rule dialog | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | - |  | Pending approval | 13.4.1 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_list.png | Unapplied Payments awaiting a disposition, with the matched account and the Cashiering status | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | - |  | Filled | 13.4.1 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_apply.png | Request Application: the disposition For Application to Invoice with the invoice number | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | - |  | Validation error | 13.4.1 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_error.png | An invoice number in the wrong format is refused under the field | Not started |  | N
| SCR-CL-15 | Unapplied Payment | Unapplied Payment Handler | - |  | Default | 13.4.2 | FR-CL-070, FR-CL-073, FR-CL-074, FR-CL-076 | SCR-CL-15_record.png | Unapplied payment: the payment and the matched account | Not started |  | N
| SCR-CL-15 | Unapplied Payment | Unapplied Payment Handler | - |  | Read-only or locked | 13.4.2 | FR-CL-070, FR-CL-073, FR-CL-074, FR-CL-076 | SCR-CL-15_history.png | History of an unapplied payment with the dispositions and the request to Cashiering | Not started |  | N
| SCR-CL-16 | Requests to Cashiering | Unapplied Payment Handler | - |  | Default | 13.4.3 | FR-CL-074, FR-CL-077 | SCR-CL-16_list.png | Requests to Cashiering: the open requests with the Cashiering reference | Not started |  | N
| SCR-CL-17 | Assignments | Collection Team Lead | - |  | Default | 13.5.1 | FR-CL-020, FR-CL-021 | SCR-CL-17_list.png | Assignments: the default assignment rules with their row menu, and Reassign by Criteria | Not started |  | N
| SCR-CL-17 | Assignments | Collection Team Lead | - |  | Filled | 13.5.1 | FR-CL-020, FR-CL-021 | SCR-CL-17_preview.png | Reassign by Criteria: the accounts of a handler found by the preview | Not started |  | N
| SCR-CL-17 | Assignments | Collection Team Lead | - |  | Filled | 13.5.1 | FR-CL-020, FR-CL-021 | SCR-CL-17_new.png | New Assignment Rule dialog | Not started |  | N
| SCR-CL-18 | Collections Files | Section Head (Corporate / Retail) | - |  | Default | 13.5.2 | FR-CL-080, FR-CL-081, FR-CL-082, FR-CL-083, FR-CL-084 | SCR-CL-18_list.png | Collections Files: the daily, weekly and monthly files with their availability | Not started |  | N
| SCR-CL-18 | Collections Files | Section Head (Corporate / Retail) | - |  | Filled | 13.5.2 | FR-CL-080, FR-CL-081, FR-CL-082, FR-CL-083, FR-CL-084 | SCR-CL-18_generate.png | Generate Files dialog of the set-up users | Not started |  | N
| SCR-CL-19 | Collections Setup | Section Head (Corporate / Retail) | - |  | Default | 13.5.3 | FR-CL-003, FR-CL-012, FR-CL-030, FR-CL-072 | SCR-CL-19_record.png | Collections Setup: the parameters and the disposition rules | Not started |  | N
| SCR-CL-19 | Collections Setup | Section Head (Corporate / Retail) | - |  | Filled | 13.5.3 | FR-CL-003, FR-CL-012, FR-CL-030, FR-CL-072 | SCR-CL-19_change.png | Change Parameter dialog of the minimal balance threshold | Not started |  | N
| SCR-CL-19 | Collections Setup | Section Head (Corporate / Retail) | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 1 | Success message | 14.1 | FR-CL-003, FR-CL-012, FR-CL-030, FR-CL-072 | SCR-CL-19_wt-a-step-01.png | WT-A step 1: Clicks Refresh Worklist Now on Collections Setup | Not started |  | N
| SCR-CL-01 | Collections Home | Collection Handler | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 2 | Default | 14.1 | FR-CL-085 | SCR-CL-01_wt-a-step-02.png | WT-A step 2: Opens Collections Home | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Handler | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 3 | Default | 14.1 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_wt-a-step-03.png | WT-A step 3: Opens the PR Worklist with Only mine ticked | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Handler | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 4 | Success message | 14.1 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_wt-a-step-04.png | WT-A step 4: Opens the account and clicks Log Effort: Phone call to the client's finance officer | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Handler | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 5 | Success message | 14.1 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_wt-a-step-05.png | WT-A step 5: Clicks Record Disposition, chooses For check pick-up and enters the pick-up date, address, contact person and check amount | Not started |  | N
| SCR-OP-17 | Check Pick-up | Cashier (read access and exports) | WT-A A new outstanding account from the refresh of the worklist to the check pick-up in Cashiering | 6 | Default | 14.1 | FR-OP-017 | SCR-OP-17_wt-a-step-06.png | WT-A step 6: Opens Check Pick-up in Cashiering | Not started |  | N
| SCR-CL-08 | Promises to Pay | Collection Handler | WT-B A promise to pay, the escalation of the account and its resolution | 1 | Success message | 14.2 | FR-CL-042, FR-CL-034 | SCR-CL-08_wt-b-step-01.png | WT-B step 1: Clicks Record Promise and enters the invoice, the promised payment date in ten days and half of the outstanding | Not started |  | N
| SCR-CL-11 | Escalations | Collection Handler | WT-B A promise to pay, the escalation of the account and its resolution | 2 | Success message | 14.2 | FR-CL-051, FR-CL-052, FR-CL-053 | SCR-CL-11_wt-b-step-02.png | WT-B step 2: Clicks Escalate Accounts and enters the invoice, Team Lead and the reason Credit term extension refused by the insurer | Not started |  | N
| SCR-CL-12 | Escalation | Collection Team Lead | WT-B A promise to pay, the escalation of the account and its resolution | 3 | Success message | 14.2 | FR-CL-053 | SCR-CL-12_wt-b-step-03.png | WT-B step 3: Opens the escalation from With Team Lead and clicks Acknowledge | Not started |  | N
| SCR-CL-12 | Escalation | Collection Team Lead | WT-B A promise to pay, the escalation of the account and its resolution | 4 | Success message | 14.2 | FR-CL-053 | SCR-CL-12_wt-b-step-04.png | WT-B step 4: Clicks Resolve and gives the resolution | Not started |  | N
| SCR-CL-13 | Escalation Rules | Authorizer of master data | WT-B A promise to pay, the escalation of the account and its resolution | 5 | Success message | 14.2 | FR-CL-050, FR-CL-051 | SCR-CL-13_wt-b-step-05.png | WT-B step 5: Opens Escalation Rules and, from the row menu of CLX-AMOUNT-1M, authorizes the rule made by the Business Administrator | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | WT-C An unapplied payment applied to an invoice at the collector's request | 1 | Success message | 14.3 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_wt-c-step-01.png | WT-C step 1: Selects the payment, clicks Request Application and enters the invoice number | Not started |  | N
| SCR-CL-16 | Requests to Cashiering | Unapplied Payment Handler | WT-C An unapplied payment applied to an invoice at the collector's request | 2 | Pending approval | 14.3 | FR-CL-074, FR-CL-077 | SCR-CL-16_wt-c-step-02.png | WT-C step 2: Opens Requests to Cashiering | Not started |  | N
| SCR-OP-13 | Incoming Requests | Cashier (read access and exports) | WT-C An unapplied payment applied to an invoice at the collector's request | 3 | Success message | 14.3 | FR-OP-022, FR-OP-130 | SCR-OP-13_wt-c-step-03.png | WT-C step 3: Opens Incoming Requests, selects the collector request and clicks Accept Request with Submit the disposition now | Not started |  | N
| SCR-CL-16 | Requests to Cashiering | Unapplied Payment Handler | WT-C An unapplied payment applied to an invoice at the collector's request | 4 | Success message | 14.3 | FR-CL-074, FR-CL-077 | SCR-CL-16_wt-c-step-04.png | WT-C step 4: Opens the Executed tab of Requests to Cashiering | Not started |  | N
| SCR-CL-15 | Unapplied Payment | Unapplied Payment Handler | WT-C An unapplied payment applied to an invoice at the collector's request | 5 | Read-only or locked | 14.3 | FR-CL-070, FR-CL-073, FR-CL-074, FR-CL-076 | SCR-CL-15_wt-c-step-05.png | WT-C step 5: Opens the unapplied payment, History tab | Not started |  | N
| SCR-CL-05 | Installment Plans | Collection Handler | WT-D An installment plan and the statement of account of its first cycle | 1 | Success message | 14.4 | FR-CL-040, FR-CL-041 | SCR-CL-05_wt-d-step-01.png | WT-D step 1: Clicks New Installment Plan: installments of one invoice, the invoice, the first due date, 4 installments, Quarterly | Not started |  | N
| SCR-CL-06 | Installment Plan | Collection Handler | WT-D An installment plan and the statement of account of its first cycle | 2 | Success message | 14.4 | FR-CL-040, FR-CL-041, FR-CL-042, FR-CL-060 | SCR-CL-06_wt-d-step-02.png | WT-D step 2: Opens the row menu of cycle 1 and clicks Generate SOA, then the Statements of Account tab | Not started |  | N
| SCR-CL-10 | Statement of Account | Collection Handler | WT-D An installment plan and the statement of account of its first cycle | 3 | Filled | 14.4 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-10_wt-d-step-03.png | WT-D step 3: Opens the statement and clicks Send via Email | Not started |  | N
| SCR-CL-10 | Statement of Account | Collection Handler | WT-D An installment plan and the statement of account of its first cycle | 4 | Success message | 14.4 | FR-CL-060, FR-CL-061, FR-CL-062 | SCR-CL-10_wt-d-step-04.png | WT-D step 4: Clicks Send | Not started |  | N
| SCR-CL-03 | Collection Account | Marketing Account Officer | WT-E Controls and the messages the user sees | 1 | Validation error | 14.5 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_wt-e-step-01.png | WT-E step 1: The account officer records the disposition No / missing policy number on an account | Not started |  | N
| SCR-CL-03 | Collection Account | Collection Team Lead | WT-E Controls and the messages the user sees | 2 | Read-only or locked | 14.5 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_wt-e-step-02.png | WT-E step 2: Opens the account the Collection Handler is working on | Not started |  | N
| SCR-CL-08 | Promises to Pay | Collection Handler | WT-E Controls and the messages the user sees | 3 | Validation error | 14.5 | FR-CL-042, FR-CL-034 | SCR-CL-08_wt-e-step-03.png | WT-E step 3: Records a promise of an amount above the outstanding of the account | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | WT-E Controls and the messages the user sees | 4 | Validation error | 14.5 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_wt-e-step-04.png | WT-E step 4: Requests the application of a payment to an invoice number in the wrong format | Not started |  | N
| DO-01 | Statement of account (SOA) | - | - |  | Document as received | 17.1 | FR-CL-060, FR-CL-061, FR-CL-062 | DO-01_document.png | Statement of account (SOA): first page as generated | Not started |  | N
| DO-02 | Outstanding PR List | - | - |  | Document as received | 17.2 | FR-CL-083, FR-CL-084 | DO-02_document.png | Outstanding PR List: first page as generated | Not started |  | N
| DO-03 | Full Production Report | - | - |  | Document as received | 17.3 | FR-CL-083 | DO-03_document.png | Full Production Report: first page as generated | Not started |  | N
| DO-04 | DP PR for Reversal and PR 2307 for Reversal files | - | - |  | Document as received | 17.4 | FR-CL-080, FR-CL-081, FR-CL-082 | DO-04_document.png | DP PR for Reversal and PR 2307 for Reversal files: first page as generated | Not started |  | N
| DO-05 | For Application To Invoice file | - | - |  | Document as received | 17.5 | FR-CL-077 | DO-05_document.png | For Application To Invoice file: first page as generated | Not started |  | N
| NAV-CL-01 | Marketing Account Officer: landing page | Marketing Account Officer | - |  | Landing page | 12.3 | - | NAV-CL-01_landing.png | Marketing Account Officer: landing page after sign-in | Not started |  | N
| NAV-CL-01 | Marketing Account Officer: menu | Marketing Account Officer | - |  | Menu | 12.3 | - | NAV-CL-01_menu.png | Marketing Account Officer: menu, every group open | Not started |  | N
| NAV-CL-02 | Marketing Team Lead: landing page | Marketing Team Lead | - |  | Landing page | 12.3 | - | NAV-CL-02_landing.png | Marketing Team Lead: landing page after sign-in | Not started |  | N
| NAV-CL-02 | Marketing Team Lead: menu | Marketing Team Lead | - |  | Menu | 12.3 | - | NAV-CL-02_menu.png | Marketing Team Lead: menu, every group open | Not started |  | N
| NAV-CL-03 | Marketing Handler: landing page | Marketing Handler | - |  | Landing page | 12.3 | - | NAV-CL-03_landing.png | Marketing Handler: landing page after sign-in | Not started |  | N
| NAV-CL-03 | Marketing Handler: menu | Marketing Handler | - |  | Menu | 12.3 | - | NAV-CL-03_menu.png | Marketing Handler: menu, every group open | Not started |  | N
| NAV-CL-04 | Collection Handler: landing page | Collection Handler | - |  | Landing page | 12.3 | - | NAV-CL-04_landing.png | Collection Handler: landing page after sign-in | Not started |  | N
| NAV-CL-04 | Collection Handler: menu | Collection Handler | - |  | Menu | 12.3 | - | NAV-CL-04_menu.png | Collection Handler: menu, every group open | Not started |  | N
| NAV-CL-05 | Collection Team Lead: landing page | Collection Team Lead | - |  | Landing page | 12.3 | - | NAV-CL-05_landing.png | Collection Team Lead: landing page after sign-in | Not started |  | N
| NAV-CL-05 | Collection Team Lead: menu | Collection Team Lead | - |  | Menu | 12.3 | - | NAV-CL-05_menu.png | Collection Team Lead: menu, every group open | Not started |  | N
| NAV-CL-06 | Section Head (Corporate / Retail): landing page | Section Head (Corporate / Retail) | - |  | Landing page | 12.3 | - | NAV-CL-06_landing.png | Section Head (Corporate / Retail): landing page after sign-in | Not started |  | N
| NAV-CL-06 | Section Head (Corporate / Retail): menu | Section Head (Corporate / Retail) | - |  | Menu | 12.3 | - | NAV-CL-06_menu.png | Section Head (Corporate / Retail): menu, every group open | Not started |  | N
| NAV-CL-07 | Unapplied Payment Handler: landing page | Unapplied Payment Handler | - |  | Landing page | 12.3 | - | NAV-CL-07_landing.png | Unapplied Payment Handler: landing page after sign-in | Not started |  | N
| NAV-CL-07 | Unapplied Payment Handler: menu | Unapplied Payment Handler | - |  | Menu | 12.3 | - | NAV-CL-07_menu.png | Unapplied Payment Handler: menu, every group open | Not started |  | N
| NAV-CL-08 | Processing Unit: landing page | Processing Unit | - |  | Landing page | 12.3 | - | NAV-CL-08_landing.png | Processing Unit: landing page after sign-in | Not started |  | N
| NAV-CL-08 | Processing Unit: menu | Processing Unit | - |  | Menu | 12.3 | - | NAV-CL-08_menu.png | Processing Unit: menu, every group open | Not started |  | N
| NAV-CL-09 | Cashier (read access and exports): landing page | Cashier (read access and exports) | - |  | Landing page | 12.3 | - | NAV-CL-09_landing.png | Cashier (read access and exports): landing page after sign-in | Not started |  | N
| NAV-CL-09 | Cashier (read access and exports): menu | Cashier (read access and exports) | - |  | Menu | 12.3 | - | NAV-CL-09_menu.png | Cashier (read access and exports): menu, every group open | Not started |  | N
| NAV-CL-10 | Disbursement (read access and exports): landing page | Disbursement (read access and exports) | - |  | Landing page | 12.3 | - | NAV-CL-10_landing.png | Disbursement (read access and exports): landing page after sign-in | Not started |  | N
| NAV-CL-10 | Disbursement (read access and exports): menu | Disbursement (read access and exports) | - |  | Menu | 12.3 | - | NAV-CL-10_menu.png | Disbursement (read access and exports): menu, every group open | Not started |  | N
| NAV-CL-11 | Comptrollership (read access): landing page | Comptrollership (read access) | - |  | Landing page | 12.3 | - | NAV-CL-11_landing.png | Comptrollership (read access): landing page after sign-in | Not started |  | N
| NAV-CL-11 | Comptrollership (read access): menu | Comptrollership (read access) | - |  | Menu | 12.3 | - | NAV-CL-11_menu.png | Comptrollership (read access): menu, every group open | Not started |  | N
| NAV-CL-12 | Business Administrator: landing page | Business Administrator | - |  | Landing page | 12.3 | - | NAV-CL-12_landing.png | Business Administrator: landing page after sign-in | Not started |  | N
| NAV-CL-12 | Business Administrator: menu | Business Administrator | - |  | Menu | 12.3 | - | NAV-CL-12_menu.png | Business Administrator: menu, every group open | Not started |  | N
| NAV-CL-13 | System Administrator: landing page | System Administrator | - |  | Landing page | 12.3 | - | NAV-CL-13_landing.png | System Administrator: landing page after sign-in | Not started |  | N
| NAV-CL-13 | System Administrator: menu | System Administrator | - |  | Menu | 12.3 | - | NAV-CL-13_menu.png | System Administrator: menu, every group open | Not started |  | N
| NAV-CL-14 | Auditor: landing page | Auditor | - |  | Landing page | 12.3 | - | NAV-CL-14_landing.png | Auditor: landing page after sign-in | Not started |  | N
| NAV-CL-14 | Auditor: menu | Auditor | - |  | Menu | 12.3 | - | NAV-CL-14_menu.png | Auditor: menu, every group open | Not started |  | N
| SCR-CL-02 | PR Worklist | Collection Team Lead | - |  | Empty list | 13.1.2 | FR-CL-010, FR-CL-011, FR-CL-013, FR-CL-014, FR-CL-015, FR-CL-017, FR-CL-021, FR-CL-031, FR-CL-033, FR-CL-034, FR-CL-084 | SCR-CL-02_empty.png | A search that finds no account | Not started |  | N
| SCR-CL-03 | Collection Account | Auditor | - |  | Read-only or locked | 13.1.3 | FR-CL-002, FR-CL-003, FR-CL-005, FR-CL-016, FR-CL-018, FR-CL-031, FR-CL-032, FR-CL-033, FR-CL-041, FR-CL-043, FR-CL-044 | SCR-CL-03_auditor.png | The collection account as the Auditor sees it, without the actions | Not started |  | N
| SCR-CL-11 | Escalations | Collection Team Lead | - |  | Empty list | 13.3.1 | FR-CL-051, FR-CL-052, FR-CL-053 | SCR-CL-11_empty.png | An escalation tab without escalations | Not started |  | N
| SCR-CL-13 | Escalation Rules | Section Head (Corporate / Retail) | - |  | Default | 13.3.3 | FR-CL-050, FR-CL-051 | SCR-CL-13_actions.png | The row action menu of an escalation rule, opened from the more button of its row | Not started |  | N
| SCR-CL-14 | Unapplied Payments | Unapplied Payment Handler | - |  | Filled | 13.4.1 | FR-CL-070, FR-CL-071, FR-CL-072, FR-CL-073, FR-CL-074, FR-CL-075, FR-CL-076 | SCR-CL-14_filters.png | Unapplied Payments with the Filters panel open | Not started |  | N
Note on B16: Screen ID The screen of the image, as in the FRS and the deck Mandatory: Yes Format: SCR-, NAV- or DO- and a number Allowed values: Free entry Example: SCR-CL-01
Note on C16: Screen name The title of the screen Mandatory: Yes Format: Text Allowed values: Free entry Example: Collections Home
Note on D16: Persona(s) The personas who see the screen in this state Mandatory: Yes Format: Text Allowed values: Free entry Example: Collection Handler
Note on E16: Flow The end-to-end flow that shows the image, if any Mandatory: No Format: Flow ID and title Allowed values: Free entry
Note on F16: Step The step of the flow Mandatory: No Format: Whole number Allowed values: A whole number from 1 to 99
Note on G16: State The state of the screen on the image Mandatory: Yes Format: From the list Allowed values: List State of a screen image: 12 values, see Reference lists Example: Default
Note on H16: FRS section The section of the FRS (or handbook) that specifies the screen Mandatory: Yes Format: Section number Allowed values: Free entry Example: 13.1.1
Note on I16: Requirement IDs The functional requirements of the screen Mandatory: No Format: FR-... separated by commas Allowed values: Free entry Example: FR-CL-085
Note on J16: Image file The file of the image package (09) Mandatory: Yes Format: <Screen ID>_<state>.png Allowed values: Free entry Example: SCR-CL-01_home.png
Note on K16: What the image shows The caption of the image Mandatory: No Format: Text Allowed values: Free entry Example: Collections Home of the Collection Handler with the work tiles and the aging chart
Note on L16: UXD status The status of the design of this screen state, kept by the UX Design team Mandatory: Yes Format: From the list Allowed values: Not started, In design, Ready for review, Approved (list UXD status) Example: Not started
Note on M16: UXD comments Comments of the UX Design team on the screen state Mandatory: No Format: Text Allowed values: Free entry
Note on N16: Changed in this issue Y when the image is new or changed in this issue of the set Mandatory: Yes Format: Y or N Allowed values: Y or N Example: N
Note on O16: Change reference The change reference (comment, change request or issue change) that changed the image Mandatory: Conditional: when Changed in this issue is Y Format: Reference Allowed values: Free entry

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | UX screen register: Changed in this issue | Y | Yes
|  | N | No
State of a screen image (UX_STATE) | UX screen register: State | Default
Filled
Validation error
Confirmation with reason
Success message
Empty list
Read-only or locked
Pending approval
Rejected or returned
Document as received
Landing page
Menu
UXD status (UXD_STATUS) | UX screen register: UXD status | Not started
In design
Ready for review
Approved
Templates of this workbook (TEMPLATES) | Questions and comments: Template | UXR UX screen register
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed
Status (STATUS) | Start here: Status | Not started
In progress
Ready for review
Confirmed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100