## Start here
UX screen register BRD-5 Accounting Disbursement ACSL
The screen images of the set for the BDOI UX Design team
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-5 Accounting Disbursement ACSL (Drop 1)
Version and date |  | Version 2.0, 2 October 2026
For |  | BDOI UX Design team (UXD)
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | Open the sheet UX screen register: one row per screen image of the 07 deck and the 09 image package, with the screen, the personas, the flow and step, the state and the FRS section.
2 | Filter Changed in this issue = Y to see the images that are new or changed in this issue; the change reference names the comment or change request behind the change.
3 | Set the UXD status of each row (Not started, In design, Ready for review, Approved) and write the UXD comments; leave the other columns as issued.
4 | Import the CSV of the image package into the design tool to link each design to its screen image.
5 | Raise questions on the sheet Questions and comments; the project team answers there. At the next issue the UXD status and comments of the unchanged rows are carried over.
The register
Step | ID | Template | What it holds | Kept by | Rows entered | Mandatory cells missing | Status | Open
1 | UXR | UX screen register | 172 screen images of 76 screens; 0 changed in this issue | BDOI UX Design team |  |  | Not started | Open →
Changes in this issue
Change reference |  | What changed |  |  |  |  | Screens
- |  | First issue |  |  |  |  | -
Other sheets
Sheet |  |  | What it holds
Reference lists |  |  | The lists of the drop-downs: states and UXD statuses
Questions and comments |  |  | Questions and comments of the UX Design team, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## UX screen register
UXR UX screen register | [13 empty] | Step 1 of 1
← Back to Start here | Step 1 of 1. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per screen image of BRD-5 Accounting Disbursement ACSL (the 07 deck and the 09 image package): the screen, personas, flow and step, state, FRS section and requirements, the image file, and the UXD status and comments of the UX Design team. Changed in this issue marks the images that are new or changed in this issue, with the change reference.
Provided by | BDOI UX Design team (UXD status and comments); iorta TechNXT project team (the other columns)
Due | With each design review; the rows are re-issued with each version of the set
How it is loaded | Kept by the UX Design team; at a new issue the UXD status and comments of the unchanged rows are carried over and the changed rows are flagged
Source | FRS v2.0 and the screens of the SIT environment (seed data)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (UX Design team lead) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | No | Yes | No | Yes | No | Yes | Conditional: when Changed in this issue is Y
Format | SCR-, NAV- or DO- and a number | Text | Text | Flow ID and title | Whole number | From the list | Section number | FR-... separated by commas | <Screen ID>_<state>.png | Text | From the list | Text | Y or N | Reference
Allowed values | Free entry | Free entry | Free entry | Free entry | A whole number from 1 to 99 | List State of a screen image: 12 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Not started, In design, Ready for review, Approved (list UXD status) | Free entry | Y or N | Free entry
What to enter | The screen of the image, as in the FRS and the deck | The title of the screen | The personas who see the screen in this state | The end-to-end flow that shows the image, if any | The step of the flow | The state of the screen on the image | The section of the FRS (or handbook) that specifies the screen | The functional requirements of the screen | The file of the image package (09) | The caption of the image | The status of the design of this screen state, kept by the UX Design team | Comments of the UX Design team on the screen state | Y when the image is new or changed in this issue of the set | The change reference (comment, change request or issue change) that changed the image
Row | Screen ID * | Screen name * | Persona(s) * | Flow | Step | State * | FRS section * | Requirement IDs | Image file * | What the image shows | UXD status * | UXD comments | Changed in this issue * | Change reference
Example – overwrite or delete | SCR-AC-01 | Journals | GL Team Lead |  |  | Default | 13.1.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_list.png | Journals of the GL Team Lead: vouchers with value date, type, inputter, assignee, authorizer, amount and status | Not started |  | N
| SCR-AC-01 | Journals | GL Team Lead | - |  | Default | 13.1.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_list.png | Journals of the GL Team Lead: vouchers with value date, type, inputter, assignee, authorizer, amount and status | Not started |  | N
| SCR-AC-01 | Journals | GL Team Lead | - |  | Filled | 13.1.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_assign.png | Assign journal(s): the submitted voucher assigned to the user who will post it | Not started |  | N
| SCR-AC-01 | Journals | GL Section Head | - |  | Confirmation with reason | 13.1.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_post.png | Post selected journals: the count, the total debit and the vouchers that are not pending | Not started |  | N
| SCR-AC-02 | New Journal and Edit Journal | GL Officer (FRBS) | - |  | Filled | 13.1.2 | FR-AC-014, FR-AC-032, FR-AC-033, FR-AC-034, FR-AC-035, FR-AC-037 | SCR-AC-02_filled.png | New Journal Voucher: an accrual with its reversal date and two balanced lines | Not started |  | N
| SCR-AC-02 | New Journal and Edit Journal | GL Officer (FRBS) | - |  | Confirmation with reason | 13.1.2 | FR-AC-014, FR-AC-032, FR-AC-033, FR-AC-034, FR-AC-035, FR-AC-037 | SCR-AC-02_confirm.png | Submit journal for posting: the value date, the reversal date, the lines and the totals to confirm | Not started |  | N
| SCR-AC-02 | New Journal and Edit Journal | GL Officer (FRBS) | - |  | Validation error | 13.1.2 | FR-AC-014, FR-AC-032, FR-AC-033, FR-AC-034, FR-AC-035, FR-AC-037 | SCR-AC-02_error.png | An unbalanced voucher: the difference under the lines and the voucher not submitted | Not started |  | N
| SCR-AC-03 | Journal | GL Section Head | - |  | Read-only or locked | 13.1.3 | FR-AC-030, FR-AC-031, FR-AC-035, FR-AC-036, FR-AC-037, FR-AS-024 | SCR-AC-03_posted.png | A posted journal: totals, source, lines and the audit | Not started |  | N
| SCR-AC-03 | Journal | GL Section Head | - |  | Pending approval | 13.1.3 | FR-AC-030, FR-AC-031, FR-AC-035, FR-AC-036, FR-AC-037, FR-AS-024 | SCR-AC-03_pending.png | A journal pending approval as the poster sees it, with Authorize & Post and Return to Maker | Not started |  | N
| SCR-AC-03 | Journal | GL Section Head | - |  | Filled | 13.1.3 | FR-AC-030, FR-AC-031, FR-AC-035, FR-AC-036, FR-AC-037, FR-AS-024 | SCR-AC-03_reverse.png | Reverse journal: the reversal value date and the reason | Not started |  | N
| SCR-AC-04 | Account Inquiry | GL Officer (FRBS) | - |  | Read-only or locked | 13.1.4 | FR-AC-030, FR-AC-014 | SCR-AC-04_statement.png | Account Inquiry: the statement of a bank account with the balances and the posted lines | Not started |  | N
| SCR-AC-05 | Party Statement | ACSL Processor | - |  | Read-only or locked | 13.1.5 | FR-AC-030 | SCR-AC-05_statement.png | Party Statement of an insurer: balances, ageing and the open items | Not started |  | N
| SCR-AC-06 | Chart of Accounts | GL Team Lead | - |  | Default | 13.1.6 | FR-AC-011, FR-AC-013, FR-AC-014, FR-AC-055 | SCR-AC-06_list.png | Chart of Accounts: the account tree with class, tier, sub-ledger, statement line and status | Not started |  | N
| SCR-AC-06 | Chart of Accounts | GL Team Lead | - |  | Filled | 13.1.6 | FR-AC-011, FR-AC-013, FR-AC-014, FR-AC-055 | SCR-AC-06_form.png | New GL account: code, name, short code, class, tier, parent, sub-ledger, negative balance and the posting controls | Not started |  | N
| SCR-AC-07 | Chart Upload | GL Team Lead | - |  | Default | 13.1.7 | FR-AC-012, FR-AC-013 | SCR-AC-07_upload.png | Chart Upload & Numbering: the template, the upload and the uploads before | Not started |  | N
| SCR-AC-07 | Chart Upload | GL Team Lead | - |  | Default | 13.1.7 | FR-AC-012, FR-AC-013 | SCR-AC-07_numbering.png | Numbering Schemes: the separator and the digits of the child accounts of each parent | Not started |  | N
| SCR-AC-08 | Currencies & Rates | GL Section Head | - |  | Default | 13.1.8 | FR-AC-010 | SCR-AC-08_rates.png | Currencies & Exchange Rates with the card Monthly revaluation rates | Not started |  | N
| SCR-AC-09 | Cost-Centre Rules | GL Team Lead | - |  | Default | 13.1.9 | FR-AC-054 | SCR-AC-09_list.png | Cost-Centre Rules: priority, the criteria, the cost centre and the status | Not started |  | N
| SCR-AC-09 | Cost-Centre Rules | GL Team Lead | - |  | Filled | 13.1.9 | FR-AC-054 | SCR-AC-09_form.png | Add cost-centre rule: priority, criteria and the cost centre | Not started |  | N
| SCR-AC-10 | Financial Periods | GL Team Lead | - |  | Default | 13.2.1 | FR-AC-040, FR-AC-041 | SCR-AC-10_list.png | Financial Periods: the periods of the fiscal year with their status, last change and reason | Not started |  | N
| SCR-AC-11 | GL Close & Cut-Off | GL Team Lead | - |  | Default | 13.2.2 | FR-AC-040, FR-AC-042 | SCR-AC-11_close.png | GL Close & Cut-Off: the close settings and the scheduled and past closes | Not started |  | N
| SCR-AC-11 | GL Close & Cut-Off | GL Team Lead | - |  | Filled | 13.2.2 | FR-AC-040, FR-AC-042 | SCR-AC-11_schedule.png | Schedule month-end close: the period and the date and time of the close | Not started |  | N
| SCR-AC-11 | GL Close & Cut-Off | GL Team Lead | - |  | Read-only or locked | 13.2.2 | FR-AC-040, FR-AC-042 | SCR-AC-11_books.png | Broking Books Cut-Off: the books of each period, closed and reopened | Not started |  | N
| SCR-AC-12 | Period-End & Year-End | GL Team Lead | - |  | Default | 13.2.3 | FR-AC-040, FR-AC-041 | SCR-AC-12_period.png | Period-End: the closing checklist of the month with the result of each control | Not started |  | N
| SCR-AC-12 | Period-End & Year-End | GL Team Lead | - |  | Default | 13.2.3 | FR-AC-040, FR-AC-041 | SCR-AC-12_year.png | Year-End: the pre-close checklist and the closing entries preview | Not started |  | N
| SCR-AC-13 | FX Revaluation | GL Team Lead | - |  | Default | 13.2.4 | FR-AC-043, FR-AC-010 | SCR-AC-13_preview.png | FX Revaluation: the period, the preview of the balances revalued and the runs | Not started |  | N
| SCR-AC-14 | Bank Statement Layouts | Accountant (bank reconciliation) | - |  | Default | 13.2.5 | FR-AC-050 | SCR-AC-14_list.png | Bank Statement Layouts: the layout of each bank account and its cheque matching | Not started |  | N
| SCR-AC-14 | Bank Statement Layouts | Accountant (bank reconciliation) | - |  | Filled | 13.2.5 | FR-AC-050 | SCR-AC-14_form.png | Statement layout: the bank account and the columns of its file | Not started |  | N
| SCR-AC-15 | Bank Statements | Accountant (bank reconciliation) | - |  | Default | 13.2.6 | FR-AC-050 | SCR-AC-15_list.png | Bank Statements: the import of a statement and the statements imported | Not started |  | N
| SCR-AC-16 | Bank Reconciliation | Accountant (bank reconciliation) | - |  | Default | 13.2.7 | FR-AC-050, FR-AC-051 | SCR-AC-16_match.png | Bank Reconciliation, Match workbench: book entries and bank lines not reconciled | Not started |  | N
| SCR-AC-16 | Bank Reconciliation | Accountant (bank reconciliation) | - |  | Read-only or locked | 13.2.7 | FR-AC-050, FR-AC-051 | SCR-AC-16_brs.png | Reconciliation statement: balances and the reconciling items | Not started |  | N
| SCR-AC-17 | Report Centre | GL Officer (FRBS) | - |  | Default | 13.3.1 | FR-AC-020, FR-AC-022, FR-AS-001, FR-DS-080, FR-PQ-012 | SCR-AC-17_list.png | Report Centre: the reports by category and My report batches | Not started |  | N
| SCR-AC-17 | Report Centre | GL Officer (FRBS) | - |  | Filled | 13.3.1 | FR-AC-020, FR-AC-022, FR-AS-001, FR-DS-080, FR-PQ-012 | SCR-AC-17_batch.png | Report batch: the reports chosen, the dates and the output | Not started |  | N
| SCR-AC-18 | Report | GL Officer (FRBS) | - |  | Default | 13.3.2 | FR-AC-020, FR-AC-021, FR-AC-023, FR-AC-051, FR-AS-005 | SCR-AC-18_params.png | A report before it is run: its parameters, the print options and the export formats | Not started |  | N
| SCR-AC-18 | Report | GL Officer (FRBS) | - |  | Read-only or locked | 13.3.2 | FR-AC-020, FR-AC-021, FR-AC-023, FR-AC-051, FR-AS-005 | SCR-AC-18_result.png | The report run on screen with the column filters and the export buttons | Not started |  | N
| SCR-AC-19 | Report Pack | GL Officer (FRBS) | - |  | Default | 13.3.3 | FR-AC-060, FR-AC-062 | SCR-AC-19_pack.png | Report Pack: the groups of Appendix A with their reports and formats | Not started |  | N
| SCR-AC-20 | Account Schedules | GL Officer (FRBS) | - |  | Default | 13.3.4 | FR-AC-061 | SCR-AC-20_run.png | Account Schedules: a schedule run for the month with its figures | Not started |  | N
| SCR-AC-20 | Account Schedules | GL Team Lead | - |  | Default | 13.3.4 | FR-AC-061 | SCR-AC-20_definitions.png | Account Schedules, Definitions: family, accounts, figures and layout | Not started |  | N
| SCR-AC-21 | Service Fee Runs | GL Officer (FRBS) | - |  | Default | 13.3.5 | FR-AC-052 | SCR-AC-21_list.png | Service Fee Runs: the runs with their period, invoices, service fee, approver and status | Not started |  | N
| SCR-AC-21 | Service Fee Runs | GL Officer (FRBS) | - |  | Filled | 13.3.5 | FR-AC-052 | SCR-AC-21_compute.png | Compute Service Fee: the period of full payment | Not started |  | N
| SCR-AC-22 | Service Fee Run | GL Team Lead | - |  | Default | 13.3.6 | FR-AC-052, FR-AC-053 | SCR-AC-22_run.png | A service-fee run sent for payment: the lines per recipient with the payout and the tags | Not started |  | N
| SCR-AC-22 | Service Fee Run | GL Team Lead | - |  | Read-only or locked | 13.3.6 | FR-AC-052, FR-AC-053 | SCR-AC-22_invoices.png | The invoices of the run with the commission, withholding tax, base and service fee | Not started |  | N
| SCR-AC-23 | Service Fee Rates | GL Team Lead | - |  | Default | 13.3.7 | FR-AC-052 | SCR-AC-23_rates.png | Service Fee Rates and Recipients: the rates per segment and the recipients per sales unit | Not started |  | N
| SCR-AC-23 | Service Fee Rates | GL Team Lead | - |  | Filled | 13.3.7 | FR-AC-052 | SCR-AC-23_new-rate.png | New Service-Fee Rate: segment, market segments, rate and effective dates | Not started |  | N
| SCR-AC-24 | BIR Forms & Books | GL Officer (FRBS) | - |  | Default | 13.3.8 | FR-AC-063 | SCR-AC-24_outputs.png | BIR Forms and Books: the period and the returns, alphalists and books | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Disbursement Processor | - |  | Default | 13.4.1 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_requests.png | Disbursement Workbench: the counts and the system requests received | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Disbursement Processor | - |  | Default | 13.4.1 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_request.png | Payment Request: source, payee, type, amount and purpose, with Create Voucher and Return to Source | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Disbursement Approver | - |  | Pending approval | 13.4.1 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_approval.png | For Approval: the vouchers waiting for the approver, selected for Approve Selected | Not started |  | N
| SCR-AC-26 | Encode Payment Request | Disbursement Processor | - |  | Filled | 13.4.2 | FR-DS-023 | SCR-AC-26_filled.png | Encode Payment Request: a supplier payment with its expense account and cost centre | Not started |  | N
| SCR-AC-26 | Encode Payment Request | Disbursement Processor | - |  | Validation error | 13.4.2 | FR-DS-023 | SCR-AC-26_error.png | The mandatory fields named under each field | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Processor | - |  | Default | 13.4.3 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_details.png | A voucher in process: the header, the workflow and the terms of the Details tab | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Processor | - |  | Default | 13.4.3 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_entry.png | Entry tab: the proforma entry from the rule, its totals and the expense allocation | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Processor | - |  | Read-only or locked | 13.4.3 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_instrument.png | Instrument tab of a check: status, amount, released to and the status history | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Processor | - |  | Read-only or locked | 13.4.3 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_tags.png | OR / AR and CWT tab: the receipts and certificates tagged on the voucher | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Approver | - |  | Confirmation with reason | 13.4.3 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_approve.png | Approve and Post: the entry posted and the instrument issued on confirmation | Not started |  | N
| SCR-AC-28 | Payees | Disbursement Team Leader | - |  | Default | 13.4.4 | FR-DS-010, FR-DS-012, FR-DS-014 | SCR-AC-28_list.png | Payees: the active payees with class, default mode, primary account and source | Not started |  | N
| SCR-AC-28 | Payees | Disbursement Team Leader | - |  | Default | 13.4.4 | FR-DS-010, FR-DS-012, FR-DS-014 | SCR-AC-28_requests.png | Payee Requests: the requests to create a payee, with Create Payee and Close | Not started |  | N
| SCR-AC-29 | Payee | Disbursement Team Leader | - |  | Default | 13.4.5 | FR-DS-010, FR-DS-011, FR-DS-013 | SCR-AC-29_payee.png | An active payee: details, allowed modes and bank accounts | Not started |  | N
| SCR-AC-29 | Payee | Disbursement Team Leader | - |  | Filled | 13.4.5 | FR-DS-010, FR-DS-011, FR-DS-013 | SCR-AC-29_new.png | New Payee: the payee saved as a draft and submitted for authorisation | Not started |  | N
| SCR-AC-30 | Disbursement Uploads | Disbursement Team Leader | - |  | Default | 13.4.6 | FR-DS-014, FR-DS-024, FR-DS-053 | SCR-AC-30_upload.png | Disbursement Uploads: the upload types, the template and the upload | Not started |  | N
| SCR-AC-31 | Disbursement End of Day | Disbursement Team Leader | - |  | Default | 13.4.7 | FR-DS-060, FR-DS-061, FR-DS-062, FR-DS-063, FR-DS-081 | SCR-AC-31_runs.png | End of Day: the runs with their vouchers, checks, credits, forms and confirmations, and the outputs of a run | Not started |  | N
| SCR-AC-31 | Disbursement End of Day | Disbursement Team Leader | - |  | Filled | 13.4.7 | FR-DS-060, FR-DS-061, FR-DS-062, FR-DS-063, FR-DS-081 | SCR-AC-31_run.png | Run End of Day: the business date | Not started |  | N
| SCR-AC-32 | Account Funding | Disbursement Team Leader | - |  | Default | 13.4.8 | FR-DS-064 | SCR-AC-32_list.png | Account Funding: the transfers with their accounts, value date, amount, requester and status | Not started |  | N
| SCR-AC-33 | Funding Request | Disbursement Team Leader | - |  | Read-only or locked | 13.4.9 | FR-DS-064 | SCR-AC-33_approved.png | An approved funding: the transfer and the workflow history of maker, verifier and two approvers | Not started |  | N
| SCR-AC-33 | Funding Request | Disbursement Team Leader | - |  | Filled | 13.4.9 | FR-DS-064 | SCR-AC-33_new.png | New Funding Request: from and to accounts, amount, value date and purpose | Not started |  | N
| SCR-AC-34 | Bank Accounts and Checks | Disbursement Approver | - |  | Default | 13.4.10 | FR-DS-070, FR-DS-071 | SCR-AC-34_banks.png | Bank Accounts and Checks: the paying accounts and the check series of an account | Not started |  | N
| SCR-AC-34 | Bank Accounts and Checks | Disbursement Team Leader | - |  | Filled | 13.4.10 | FR-DS-070, FR-DS-071 | SCR-AC-34_series.png | Add Series: the first and last check numbers of a new check book | Not started |  | N
| SCR-AC-35 | Employees | Business Administrator | - |  | Default | 13.4.11 | FR-DS-037 | SCR-AC-35_list.png | Employees: number, name, branch, cost centre, position, hire date and status | Not started |  | N
| SCR-AC-36 | Certificates Received | Disbursement Processor | - |  | Default | 13.4.12 | FR-DS-057 | SCR-AC-36_list.png | Certificates Received: the BIR 2307 certificates of the insurers with the journal posted | Not started |  | N
| SCR-AC-37 | BIR Form 2307 | Disbursement Processor | - |  | Default | 13.4.13 | FR-DS-058 | SCR-AC-37_list.png | BIR Form 2307: the generation of a quarter, the batches and the certificate register | Not started |  | N
| SCR-AC-38 | Disbursement Reports | Disbursement Processor | - |  | Default | 13.4.14 | FR-DS-080, FR-DS-081, FR-DS-082, FR-DS-083, FR-DS-092 | SCR-AC-38_list.png | Disbursement Reports: the payment, control and end-of-day reports | Not started |  | N
| SCR-AC-39 | Requests Home | Marketing Reviewer | - |  | Default | 13.5.1 | FR-PQ-001, FR-PQ-008, FR-PQ-009, FR-PQ-012 | SCR-AC-39_list.png | Refund & Cash Advance Requests: the requests by stage with kind, payee, amount, disbursement and status | Not started |  | N
| SCR-AC-39 | Requests Home | Marketing Approver | - |  | Pending approval | 13.5.1 | FR-PQ-001, FR-PQ-008, FR-PQ-009, FR-PQ-012 | SCR-AC-39_approve.png | For Approval: the requests selected for Approve Selected | Not started |  | N
| SCR-AC-40 | New Refund Request | Marketing Processor (AO) | - |  | Filled | 13.5.2 | FR-PQ-003, FR-PQ-014, FR-PQ-016 | SCR-AC-40_filled.png | New Refund Request: the request, the credit to the client's account and the account to refund | Not started |  | N
| SCR-AC-40 | New Refund Request | Marketing Processor (AO) | - |  | Validation error | 13.5.2 | FR-PQ-003, FR-PQ-014, FR-PQ-016 | SCR-AC-40_error.png | An AR number already in another refund request: the request is refused | Not started |  | N
| SCR-AC-41 | New Cash Advance | Marketing Processor (AO) | - |  | Filled | 13.5.3 | FR-PQ-004 | SCR-AC-41_filled.png | New Cash Advance: the employee, amount and purpose, paid by credit to the employee's account | Not started |  | N
| SCR-AC-42 | Cancel a Check | Marketing Processor (AO) | - |  | Default | 13.5.4 | FR-PQ-011 | SCR-AC-42_form.png | Cancel a Disbursed Check: the paid request, the check and the reason | Not started |  | N
| SCR-AC-43 | Request | Marketing Processor (AO) | - |  | Default | 13.5.5 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_details.png | A refund request: header, workflow and the accounts to refund | Not started |  | N
| SCR-AC-43 | Request | Marketing Processor (AO) | - |  | Read-only or locked | 13.5.5 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_disbursement.png | Disbursement tab: the voucher of the refund and its status in Disbursement | Not started |  | N
| SCR-AC-43 | Request | Marketing Reviewer | - |  | Filled | 13.5.5 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_assign.png | Assign the request to the Marketing user who prepares it | Not started |  | N
| SCR-AC-44 | Liquidation Accounts | Marketing Reviewer | - |  | Default | 13.5.6 | FR-PQ-017 | SCR-AC-44_list.png | Liquidation Accounts: the GL account of each expense category | Not started |  | N
| SCR-AC-45 | ACSL Cases | ACSL Team Leader | - |  | Default | 13.6.1 | FR-AS-010 | SCR-AC-45_list.png | ACSL Cases: the cases by stage with type, subject, invoice, amount, requester and status | Not started |  | N
| SCR-AC-45 | ACSL Cases | ACSL Team Leader | - |  | Filled | 13.6.1 | FR-AS-010 | SCR-AC-45_new.png | Open a Case: type, invoice, AR or OR number, subject and details | Not started |  | N
| SCR-AC-46 | ACSL Case | ACSL Processor | - |  | Default | 13.6.2 | FR-AS-010, FR-AS-011, FR-AS-012, FR-AS-013, FR-AS-026, FR-DS-093 | SCR-AC-46_case.png | An ACSL case under investigation: the request, the findings and the actions | Not started |  | N
| SCR-AC-46 | ACSL Case | ACSL Processor | - |  | Read-only or locked | 13.6.2 | FR-AS-010, FR-AS-011, FR-AS-012, FR-AS-013, FR-AS-026, FR-DS-093 | SCR-AC-46_family.png | Invoice Family Cases: the cases of the same root invoice | Not started |  | N
| SCR-AC-47 | Correction Entries | ACSL Team Leader | - |  | Default | 13.6.3 | FR-AS-020 | SCR-AC-47_list.png | Correction Entries: the corrections by stage with kind, invoice, journal, raiser and status | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Processor | - |  | Default | 13.6.4 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_draft.png | A correction in draft: the posted lines of the invoice family and the correction lines | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Head (approver) | - |  | Read-only or locked | 13.6.4 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_posted.png | A posted correction with its journal | Not started |  | N
| SCR-AC-49 | Insurer SOA Reconciliation | ACSL Processor | - |  | Default | 13.6.5 | FR-AS-002, FR-AS-003 | SCR-AC-49_list.png | Insurer SOA Reconciliation: the statements uploaded with their results | Not started |  | N
| SCR-AC-49 | Insurer SOA Reconciliation | ACSL Processor | - |  | Filled | 13.6.5 | FR-AS-002, FR-AS-003 | SCR-AC-49_upload.png | Upload an Insurer SOA: the insurer, the period and the statement file | Not started |  | N
| SCR-AC-50 | Insurer SOA | ACSL Processor | - |  | Default | 13.6.6 | FR-AS-003 | SCR-AC-50_results.png | An insurer SOA reconciled: the counts and the lines with their result and variances | Not started |  | N
| SCR-AC-50 | Insurer SOA | ACSL Processor | - |  | Read-only or locked | 13.6.6 | FR-AS-003 | SCR-AC-50_log.png | Upload Log: the rows of the file and those that failed with their error | Not started |  | N
| SCR-AC-51 | GL-SL Reconciliation | ACSL Team Leader | - |  | Default | 13.6.7 | FR-AS-004 | SCR-AC-51_runs.png | GL-SL Reconciliation: the runs and the balances of the last run | Not started |  | N
| SCR-AC-02 | New Journal and Edit Journal | GL Officer (FRBS) | WT-A A manual accrual from the voucher to its posting and automatic reversal | 1 | Pending approval | 14.1 | FR-AC-014, FR-AC-032, FR-AC-033, FR-AC-034, FR-AC-035, FR-AC-037 | SCR-AC-02_wt-a-step-01.png | WT-A step 1: Enters an accrual on New Journal (value date today, Reverse on the first day of next month, a debit to the expense with its cost centre and a credit to accrued expenses), clicks Save & Submit and confirms | Not started |  | N
| SCR-AC-01 | Journals | GL Team Lead | WT-A A manual accrual from the voucher to its posting and automatic reversal | 2 | Success message | 14.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_wt-a-step-02.png | WT-A step 2: Selects the voucher on Journals, clicks Assign and chooses the GL Section Head | Not started |  | N
| SCR-AC-01 | Journals | GL Section Head | WT-A A manual accrual from the voucher to its posting and automatic reversal | 3 | Success message | 14.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_wt-a-step-03.png | WT-A step 3: Chooses Assigned to me, selects the voucher, clicks Post Selected and confirms | Not started |  | N
| SCR-AC-03 | Journal | GL Section Head | WT-A A manual accrual from the voucher to its posting and automatic reversal | 4 | Read-only or locked | 14.1 | FR-AC-030, FR-AC-031, FR-AC-035, FR-AC-036, FR-AC-037, FR-AS-024 | SCR-AC-03_wt-a-step-04.png | WT-A step 4: Opens the journal | Not started |  | N
| SCR-AC-04 | Account Inquiry | GL Officer (FRBS) | WT-A A manual accrual from the voucher to its posting and automatic reversal | 5 | Read-only or locked | 14.1 | FR-AC-030, FR-AC-014 | SCR-AC-04_wt-a-step-05.png | WT-A step 5: Opens Account Inquiry for the expense account of the month | Not started |  | N
| SCR-AC-40 | New Refund Request | Marketing Processor (AO) | WT-B A client refund from the Refund Request Form to the payment | 1 | Success message | 14.2 | FR-PQ-003, FR-PQ-014, FR-PQ-016 | SCR-AC-40_wt-b-step-01.png | WT-B step 1: Fills in New Refund Request (segment, reference, purpose, credit to the client's account) with one account to refund (AR number, client, assured, amount, reason Overpayment) and clicks Save Request | Not started |  | N
| SCR-AC-43 | Request | Marketing Processor (AO) | WT-B A client refund from the Refund Request Form to the payment | 2 | Success message | 14.2 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_wt-b-step-02.png | WT-B step 2: Clicks Submit for Review and confirms | Not started |  | N
| SCR-AC-43 | Request | Marketing Reviewer | WT-B A client refund from the Refund Request Form to the payment | 3 | Success message | 14.2 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_wt-b-step-03.png | WT-B step 3: Opens the request and clicks Endorse for Approval | Not started |  | N
| SCR-AC-43 | Request | Marketing Approver | WT-B A client refund from the Refund Request Form to the payment | 4 | Success message | 14.2 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_wt-b-step-04.png | WT-B step 4: Clicks Approve and Send | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Disbursement Processor | WT-B A client refund from the Refund Request Form to the payment | 5 | Default | 14.2 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_wt-b-step-05.png | WT-B step 5: Opens For Approval on the Disbursement Workbench | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Processor | WT-B A client refund from the Refund Request Form to the payment | 6 | Pending approval | 14.2 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_wt-b-step-06.png | WT-B step 6: Opens the voucher | Not started |  | N
| SCR-AC-27 | Disbursement Voucher | Disbursement Approver | WT-B A client refund from the Refund Request Form to the payment | 7 | Success message | 14.2 | FR-DS-025, FR-DS-030, FR-DS-031, FR-DS-032, FR-DS-033, FR-DS-034, FR-DS-035, FR-DS-036, FR-DS-040, FR-DS-041, FR-DS-042, FR-DS-043, FR-DS-044, FR-DS-050, FR-DS-051, FR-DS-052, FR-DS-054, FR-DS-055, FR-DS-056, FR-DS-057, FR-DS-062, FR-DS-063 | SCR-AC-27_wt-b-step-07.png | WT-B step 7: Clicks Approve and Post and confirms | Not started |  | N
| SCR-AC-43 | Request | Marketing Processor (AO) | WT-B A client refund from the Refund Request Form to the payment | 8 | Read-only or locked | 14.2 | FR-PQ-001, FR-PQ-005, FR-PQ-006, FR-PQ-007, FR-PQ-008, FR-PQ-009, FR-PQ-010, FR-PQ-012, FR-PQ-013, FR-PQ-015, FR-PQ-017 | SCR-AC-43_wt-b-step-08.png | WT-B step 8: Opens the Disbursement tab of the request | Not started |  | N
| SCR-AC-49 | Insurer SOA Reconciliation | ACSL Processor | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 1 | Success message | 14.3 | FR-AS-002, FR-AS-003 | SCR-AC-49_wt-c-step-01.png | WT-C step 1: Clicks Upload SOA, chooses the insurer, the period and the statement file, and clicks Upload and Reconcile | Not started |  | N
| SCR-AC-50 | Insurer SOA | ACSL Processor | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 2 | Default | 14.3 | FR-AS-003 | SCR-AC-50_wt-c-step-02.png | WT-C step 2: Opens the upload | Not started |  | N
| SCR-AC-45 | ACSL Cases | ACSL Team Leader | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 3 | Success message | 14.3 | FR-AS-010 | SCR-AC-45_wt-c-step-03.png | WT-C step 3: Clicks Open a Case: investigation of the invoice with a variance | Not started |  | N
| SCR-AC-46 | ACSL Case | ACSL Team Leader | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 4 | Success message | 14.3 | FR-AS-010, FR-AS-011, FR-AS-012, FR-AS-013, FR-AS-026, FR-DS-093 | SCR-AC-46_wt-c-step-04.png | WT-C step 4: Opens the case and assigns it to the ACSL Processor | Not started |  | N
| SCR-AC-46 | ACSL Case | ACSL Processor | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 5 | Success message | 14.3 | FR-AS-010, FR-AS-011, FR-AS-012, FR-AS-013, FR-AS-026, FR-DS-093 | SCR-AC-46_wt-c-step-05.png | WT-C step 5: Clicks Start Investigation, records the findings and clicks Raise Correction (posting to a wrong GL account) | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Team Leader | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 6 | Success message | 14.3 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_wt-c-step-06.png | WT-C step 6: Assigns the correction to the ACSL Processor as its preparer | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Processor | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 7 | Success message | 14.3 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_wt-c-step-07.png | WT-C step 7: Picks the wrong line among the posted lines of the invoice family, clicks Correct with the right account, saves the lines and clicks Submit for Review | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Team Leader | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 8 | Success message | 14.3 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_wt-c-step-08.png | WT-C step 8: Clicks Endorse for Approval | Not started |  | N
| SCR-AC-48 | Correction Entry | ACSL Head (approver) | WT-C An insurer's statement of account reconciled and a wrong posting corrected | 9 | Success message | 14.3 | FR-AS-020, FR-AS-021, FR-AS-022, FR-AS-023, FR-AS-024 | SCR-AC-48_wt-c-step-09.png | WT-C step 9: Clicks Approve and Post and confirms | Not started |  | N
| SCR-AC-08 | Currencies & Rates | GL Section Head | WT-D Month end: the revaluation rate, the revaluation, the GL close and the service fee | 1 | Success message | 14.4 | FR-AC-010 | SCR-AC-08_wt-d-step-01.png | WT-D step 1: Enters the month-end rate of USD for the previous month on Monthly revaluation rates and clicks Save Rate | Not started |  | N
| SCR-AC-13 | FX Revaluation | GL Team Lead | WT-D Month end: the revaluation rate, the revaluation, the GL close and the service fee | 2 | Success message | 14.4 | FR-AC-043, FR-AC-010 | SCR-AC-13_wt-d-step-02.png | WT-D step 2: Chooses the previous month, checks the preview and clicks Post revaluation | Not started |  | N
| SCR-AC-11 | GL Close & Cut-Off | GL Team Lead | WT-D Month end: the revaluation rate, the revaluation, the GL close and the service fee | 3 | Success message | 14.4 | FR-AC-040, FR-AC-042 | SCR-AC-11_wt-d-step-03.png | WT-D step 3: Clicks Schedule Close for the previous month at the proposed date and time | Not started |  | N
| SCR-AC-11 | GL Close & Cut-Off | GL Team Lead | WT-D Month end: the revaluation rate, the revaluation, the GL close and the service fee | 4 | Read-only or locked | 14.4 | FR-AC-040, FR-AC-042 | SCR-AC-11_wt-d-step-04.png | WT-D step 4: Opens Broking Books Cut-Off | Not started |  | N
| SCR-AC-22 | Service Fee Run | GL Officer (FRBS) | WT-D Month end: the revaluation rate, the revaluation, the GL close and the service fee | 5 | Success message | 14.4 | FR-AC-052, FR-AC-053 | SCR-AC-22_wt-d-step-05.png | WT-D step 5: Opens the service-fee run of the month and tags a line Released with the date the recipient was credited | Not started |  | N
| SCR-AC-02 | New Journal and Edit Journal | GL Officer (FRBS) | WT-E Controls and the messages the user sees | 1 | Validation error | 14.5 | FR-AC-014, FR-AC-032, FR-AC-033, FR-AC-034, FR-AC-035, FR-AC-037 | SCR-AC-02_wt-e-step-01.png | WT-E step 1: Enters a voucher whose debit and credit differ | Not started |  | N
| SCR-AC-40 | New Refund Request | Marketing Processor (AO) | WT-E Controls and the messages the user sees | 2 | Validation error | 14.5 | FR-PQ-003, FR-PQ-014, FR-PQ-016 | SCR-AC-40_wt-e-step-02.png | WT-E step 2: Raises a refund with the AR of the refund of walkthrough B | Not started |  | N
| SCR-AC-49 | Insurer SOA Reconciliation | ACSL Processor | WT-E Controls and the messages the user sees | 3 | Validation error | 14.5 | FR-AS-002, FR-AS-003 | SCR-AC-49_wt-e-step-03.png | WT-E step 3: Uploads the statement of walkthrough C again | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Disbursement Processor | WT-E Controls and the messages the user sees | 4 | Default | 14.5 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_wt-e-step-04.png | WT-E step 4: Encodes a payment request for a payee code that is not maintained | Not started |  | N
| DO-01 | Disbursement voucher | - | - |  | Document as received | 17.1 | FR-DS-030, FR-DS-062 | DO-01_document.png | Disbursement voucher: first page as generated | Not started |  | N
| DO-02 | Authority to Debit (bank form) | - | - |  | Document as received | 17.2 | FR-DS-034, FR-DS-035 | DO-02_document.png | Authority to Debit (bank form): first page as generated | Not started |  | N
| DO-03 | Direct Credit Transaction File (DCTF) | - | - |  | Document as received | 17.3 | FR-DS-061 | DO-03_document.png | Direct Credit Transaction File (DCTF): first page as generated | Not started |  | N
| DO-04 | Refund Request Form (RRF) | - | - |  | Document as received | 17.4 | FR-PQ-003 | DO-04_document.png | Refund Request Form (RRF): first page as generated | Not started |  | N
| DO-05 | BIR Form 2307 (certificate of creditable tax withheld at source) | - | - |  | Document as received | 17.5 | FR-DS-058 | DO-05_document.png | BIR Form 2307 (certificate of creditable tax withheld at source): first page as generated | Not started |  | N
| DO-06 | Insurer SOA reconciliation report | - | - |  | Document as received | 17.6 | FR-AS-003 | DO-06_document.png | Insurer SOA reconciliation report: first page as generated | Not started |  | N
| NAV-AC-01 | GL Officer (FRBS): landing page | GL Officer (FRBS) | - |  | Landing page | 12.3 | - | NAV-AC-01_landing.png | GL Officer (FRBS): landing page after sign-in | Not started |  | N
| NAV-AC-01 | GL Officer (FRBS): menu | GL Officer (FRBS) | - |  | Menu | 12.3 | - | NAV-AC-01_menu.png | GL Officer (FRBS): menu, every group open | Not started |  | N
| NAV-AC-02 | GL Team Lead: landing page | GL Team Lead | - |  | Landing page | 12.3 | - | NAV-AC-02_landing.png | GL Team Lead: landing page after sign-in | Not started |  | N
| NAV-AC-02 | GL Team Lead: menu | GL Team Lead | - |  | Menu | 12.3 | - | NAV-AC-02_menu.png | GL Team Lead: menu, every group open | Not started |  | N
| NAV-AC-03 | GL Section Head: landing page | GL Section Head | - |  | Landing page | 12.3 | - | NAV-AC-03_landing.png | GL Section Head: landing page after sign-in | Not started |  | N
| NAV-AC-03 | GL Section Head: menu | GL Section Head | - |  | Menu | 12.3 | - | NAV-AC-03_menu.png | GL Section Head: menu, every group open | Not started |  | N
| NAV-AC-04 | Accountant (bank reconciliation): landing page | Accountant (bank reconciliation) | - |  | Landing page | 12.3 | - | NAV-AC-04_landing.png | Accountant (bank reconciliation): landing page after sign-in | Not started |  | N
| NAV-AC-04 | Accountant (bank reconciliation): menu | Accountant (bank reconciliation) | - |  | Menu | 12.3 | - | NAV-AC-04_menu.png | Accountant (bank reconciliation): menu, every group open | Not started |  | N
| NAV-AC-05 | Comptrollership administrator (masters and rules): landing page | Comptrollership administrator (masters and rules) | - |  | Landing page | 12.3 | - | NAV-AC-05_landing.png | Comptrollership administrator (masters and rules): landing page after sign-in | Not started |  | N
| NAV-AC-05 | Comptrollership administrator (masters and rules): menu | Comptrollership administrator (masters and rules) | - |  | Menu | 12.3 | - | NAV-AC-05_menu.png | Comptrollership administrator (masters and rules): menu, every group open | Not started |  | N
| NAV-AC-06 | Disbursement Processor: landing page | Disbursement Processor | - |  | Landing page | 12.3 | - | NAV-AC-06_landing.png | Disbursement Processor: landing page after sign-in | Not started |  | N
| NAV-AC-06 | Disbursement Processor: menu | Disbursement Processor | - |  | Menu | 12.3 | - | NAV-AC-06_menu.png | Disbursement Processor: menu, every group open | Not started |  | N
| NAV-AC-07 | Disbursement Team Leader: landing page | Disbursement Team Leader | - |  | Landing page | 12.3 | - | NAV-AC-07_landing.png | Disbursement Team Leader: landing page after sign-in | Not started |  | N
| NAV-AC-07 | Disbursement Team Leader: menu | Disbursement Team Leader | - |  | Menu | 12.3 | - | NAV-AC-07_menu.png | Disbursement Team Leader: menu, every group open | Not started |  | N
| NAV-AC-08 | Disbursement Approver: landing page | Disbursement Approver | - |  | Landing page | 12.3 | - | NAV-AC-08_landing.png | Disbursement Approver: landing page after sign-in | Not started |  | N
| NAV-AC-08 | Disbursement Approver: menu | Disbursement Approver | - |  | Menu | 12.3 | - | NAV-AC-08_menu.png | Disbursement Approver: menu, every group open | Not started |  | N
| NAV-AC-09 | Marketing Processor (AO): landing page | Marketing Processor (AO) | - |  | Landing page | 12.3 | - | NAV-AC-09_landing.png | Marketing Processor (AO): landing page after sign-in | Not started |  | N
| NAV-AC-09 | Marketing Processor (AO): menu | Marketing Processor (AO) | - |  | Menu | 12.3 | - | NAV-AC-09_menu.png | Marketing Processor (AO): menu, every group open | Not started |  | N
| NAV-AC-10 | Marketing Reviewer: landing page | Marketing Reviewer | - |  | Landing page | 12.3 | - | NAV-AC-10_landing.png | Marketing Reviewer: landing page after sign-in | Not started |  | N
| NAV-AC-10 | Marketing Reviewer: menu | Marketing Reviewer | - |  | Menu | 12.3 | - | NAV-AC-10_menu.png | Marketing Reviewer: menu, every group open | Not started |  | N
| NAV-AC-11 | Marketing Approver: landing page | Marketing Approver | - |  | Landing page | 12.3 | - | NAV-AC-11_landing.png | Marketing Approver: landing page after sign-in | Not started |  | N
| NAV-AC-11 | Marketing Approver: menu | Marketing Approver | - |  | Menu | 12.3 | - | NAV-AC-11_menu.png | Marketing Approver: menu, every group open | Not started |  | N
| NAV-AC-12 | Human Resources Approver: landing page | Human Resources Approver | - |  | Landing page | 12.3 | - | NAV-AC-12_landing.png | Human Resources Approver: landing page after sign-in | Not started |  | N
| NAV-AC-12 | Human Resources Approver: menu | Human Resources Approver | - |  | Menu | 12.3 | - | NAV-AC-12_menu.png | Human Resources Approver: menu, every group open | Not started |  | N
| NAV-AC-13 | ACSL Processor: landing page | ACSL Processor | - |  | Landing page | 12.3 | - | NAV-AC-13_landing.png | ACSL Processor: landing page after sign-in | Not started |  | N
| NAV-AC-13 | ACSL Processor: menu | ACSL Processor | - |  | Menu | 12.3 | - | NAV-AC-13_menu.png | ACSL Processor: menu, every group open | Not started |  | N
| NAV-AC-14 | ACSL Team Leader: landing page | ACSL Team Leader | - |  | Landing page | 12.3 | - | NAV-AC-14_landing.png | ACSL Team Leader: landing page after sign-in | Not started |  | N
| NAV-AC-14 | ACSL Team Leader: menu | ACSL Team Leader | - |  | Menu | 12.3 | - | NAV-AC-14_menu.png | ACSL Team Leader: menu, every group open | Not started |  | N
| NAV-AC-15 | ACSL Head (approver): landing page | ACSL Head (approver) | - |  | Landing page | 12.3 | - | NAV-AC-15_landing.png | ACSL Head (approver): landing page after sign-in | Not started |  | N
| NAV-AC-15 | ACSL Head (approver): menu | ACSL Head (approver) | - |  | Menu | 12.3 | - | NAV-AC-15_menu.png | ACSL Head (approver): menu, every group open | Not started |  | N
| NAV-AC-16 | Comptrollership (read access): landing page | Comptrollership (read access) | - |  | Landing page | 12.3 | - | NAV-AC-16_landing.png | Comptrollership (read access): landing page after sign-in | Not started |  | N
| NAV-AC-16 | Comptrollership (read access): menu | Comptrollership (read access) | - |  | Menu | 12.3 | - | NAV-AC-16_menu.png | Comptrollership (read access): menu, every group open | Not started |  | N
| NAV-AC-17 | Business Administrator: landing page | Business Administrator | - |  | Landing page | 12.3 | - | NAV-AC-17_landing.png | Business Administrator: landing page after sign-in | Not started |  | N
| NAV-AC-17 | Business Administrator: menu | Business Administrator | - |  | Menu | 12.3 | - | NAV-AC-17_menu.png | Business Administrator: menu, every group open | Not started |  | N
| NAV-AC-18 | System Administrator: landing page | System Administrator | - |  | Landing page | 12.3 | - | NAV-AC-18_landing.png | System Administrator: landing page after sign-in | Not started |  | N
| NAV-AC-18 | System Administrator: menu | System Administrator | - |  | Menu | 12.3 | - | NAV-AC-18_menu.png | System Administrator: menu, every group open | Not started |  | N
| NAV-AC-19 | Auditor: landing page | Auditor | - |  | Landing page | 12.3 | - | NAV-AC-19_landing.png | Auditor: landing page after sign-in | Not started |  | N
| NAV-AC-19 | Auditor: menu | Auditor | - |  | Menu | 12.3 | - | NAV-AC-19_menu.png | Auditor: menu, every group open | Not started |  | N
| SCR-AC-01 | Journals | GL Team Lead | - |  | Empty list | 13.1.1 | FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036 | SCR-AC-01_empty.png | A search that finds no journal | Not started |  | N
| SCR-AC-25 | Disbursement Workbench | Auditor | - |  | Read-only or locked | 13.4.1 | FR-DS-020, FR-DS-021, FR-DS-022, FR-DS-025, FR-DS-040, FR-DS-041, FR-DS-045 | SCR-AC-25_auditor.png | The Disbursement Workbench as the Auditor sees it, without Encode Request | Not started |  | N
| SCR-AC-28 | Payees | Disbursement Team Leader | - |  | Default | 13.4.4 | FR-DS-010, FR-DS-012, FR-DS-014 | SCR-AC-28_actions.png | The row action menu of a payee request, opened from the more button of its row | Not started |  | N
| SCR-AC-39 | Requests Home | Marketing Reviewer | - |  | Filled | 13.5.1 | FR-PQ-001, FR-PQ-008, FR-PQ-009, FR-PQ-012 | SCR-AC-39_filters.png | Requests Home with the Filters panel open | Not started |  | N
| SCR-AC-45 | ACSL Cases | ACSL Team Leader | - |  | Empty list | 13.6.1 | FR-AS-010 | SCR-AC-45_empty.png | A case tab without cases | Not started |  | N
Note on B16: Screen ID The screen of the image, as in the FRS and the deck Mandatory: Yes Format: SCR-, NAV- or DO- and a number Allowed values: Free entry Example: SCR-AC-01
Note on C16: Screen name The title of the screen Mandatory: Yes Format: Text Allowed values: Free entry Example: Journals
Note on D16: Persona(s) The personas who see the screen in this state Mandatory: Yes Format: Text Allowed values: Free entry Example: GL Team Lead
Note on E16: Flow The end-to-end flow that shows the image, if any Mandatory: No Format: Flow ID and title Allowed values: Free entry
Note on F16: Step The step of the flow Mandatory: No Format: Whole number Allowed values: A whole number from 1 to 99
Note on G16: State The state of the screen on the image Mandatory: Yes Format: From the list Allowed values: List State of a screen image: 12 values, see Reference lists Example: Default
Note on H16: FRS section The section of the FRS (or handbook) that specifies the screen Mandatory: Yes Format: Section number Allowed values: Free entry Example: 13.1.1
Note on I16: Requirement IDs The functional requirements of the screen Mandatory: No Format: FR-... separated by commas Allowed values: Free entry Example: FR-AC-030, FR-AC-031, FR-AC-033, FR-AC-036
Note on J16: Image file The file of the image package (09) Mandatory: Yes Format: <Screen ID>_<state>.png Allowed values: Free entry Example: SCR-AC-01_list.png
Note on K16: What the image shows The caption of the image Mandatory: No Format: Text Allowed values: Free entry Example: Journals of the GL Team Lead: vouchers with value date, type, inputter, assignee, authorizer, amount and status
Note on L16: UXD status The status of the design of this screen state, kept by the UX Design team Mandatory: Yes Format: From the list Allowed values: Not started, In design, Ready for review, Approved (list UXD status) Example: Not started
Note on M16: UXD comments Comments of the UX Design team on the screen state Mandatory: No Format: Text Allowed values: Free entry
Note on N16: Changed in this issue Y when the image is new or changed in this issue of the set Mandatory: Yes Format: Y or N Allowed values: Y or N Example: N
Note on O16: Change reference The change reference (comment, change request or issue change) that changed the image Mandatory: Conditional: when Changed in this issue is Y Format: Reference Allowed values: Free entry

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | UX screen register: Changed in this issue | Y | Yes
|  | N | No
State of a screen image (UX_STATE) | UX screen register: State | Default
Filled
Validation error
Confirmation with reason
Success message
Empty list
Read-only or locked
Pending approval
Rejected or returned
Document as received
Landing page
Menu
UXD status (UXD_STATUS) | UX screen register: UXD status | Not started
In design
Ready for review
Approved
Templates of this workbook (TEMPLATES) | Questions and comments: Template | UXR UX screen register
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed
Status (STATUS) | Start here: Status | Not started
In progress
Ready for review
Confirmed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100