## Cover
CHANGE CONTROL
Change Request Register
BRD-02 Operations Cashiering - after the sign-off of the FRS v3.3
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
How to use | Raise -> assess -> approve -> schedule -> test -> close (FRS Appendix T) | 6
Register | Candidate changes known at v3.3 (status Candidate - for decision) and new requests | 21
Impact assessment form | Impact assessment form | 12
Decisions log | One row per observation of Appendix R, for the decision of the Business Unit | 83
Legend
Closed
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
How to use | Step | Step of the process
How to use | What happens
How to use | Who
How to use | Record in this workbook
Register | CR No. | Change request number
Register | Date raised | dd-Mmm-yyyy
Register | Raised by | Name and role
Register | BRD ID | BRD requirement
Register | FRS reference | FR item or appendix
Register | Description | The change
Register | Reason | Why
Register | Type | Kind of change | Beyond the BRD, Added by BDOI's FRS, Proposal for best practice, Correction
Register | Impact on scope
Register | Impact on schedule
Register | Impact on cost
Register | Impact on other BRDs
Register | Impact on tests
Register | Priority |  | High, Medium, Low
Register | Status |  | Candidate - for decision, Raised, Assessed, Approved, Rejected, Scheduled, In test, Closed
Register | Decision | Decision of the approvers
Register | Approved by
Register | Decision date
Register | Target drop
Register | Linked test cases | Test cases of the Test Cases and Traceability workbook
Impact assessment form | Field | Part of the assessment
Impact assessment form | Assessment | Filled in by the project
Impact assessment form | Assessed by | Name
Decisions log | Appendix R No. | Row of Appendix R of the FRS v3.3
Decisions log | Section
Decisions log | Topic
Decisions log | Proposed in the FRS
Decisions log | Decision by
Decisions log | Decision | Adopt proposal / Keep BDOI text / Other
Decisions log | Decided by (name)
Decisions log | Date
Decisions log | CR No. (if a change follows)
Decisions log | Status |  | Open, Configurable – BDOI to confirm the setting, Decided, Withdrawn

## How to use
How to use
Raise -> assess -> approve -> schedule -> test -> close (FRS Appendix T)
Step | What happens | Who | Record in this workbook
1 Raise | The change is written with the BRD ID, the FR item or appendix concerned, the reason and the business priority | Any signatory or the Cashiering Process Owner | Register: new row, status Raised
2 Assess | Impact on scope, schedule, cost (mandays), the other BRDs (interfaces of Appendix N), the test cases and the training | iorta TechNXT Project Team with the System Analyst (BDO ITG) | Impact assessment form; status Assessed
3 Approve | Decision by the owners of every BRD touched; a change to an entry or a tax rule also by Comptrollership; a change to an interface also by BDOI IT | Business owner; Cashiering Process Owner; Comptrollership; BDOI IT | Decision, approved by, date; status Approved or Rejected
4 Schedule | The change is given a drop and a version of this FRS (3.3, 3.4 and so on) | Project managers | Target drop; status Scheduled
5 Test | The test cases linked to the change are updated and run | Test lead; Business Unit testers | Linked test cases; result
6 Close | The new version of the FRS and of the workbooks is issued with the change marked | System Analyst (BDO ITG) | Status Closed

## Register
Register
Candidate changes known at v3.3 (status Candidate - for decision) and new requests
CR No. | Date raised | Raised by | BRD ID | FRS reference | Description | Reason | Type | Impact on scope | Impact on schedule | Impact on cost | Impact on other BRDs | Impact on tests | Priority | Status | Decision | Approved by | Decision date | Target drop | Linked test cases
CR-CSH-001 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.001 | FRS.CSH.02.05 | Posting step for every AR and OR: Created record, request number, submit for posting, poster's list, return; number generated at posting | BDOI's FRS adds a second user to every issuance; the BRD does not ask for it (Appendix R, C1) | Added by BDOI's FRS | Receive Payment, Receipts, dashboard | Drop 1 | To assess | None | Posting cases | High | Candidate - for decision |  |  |  |  | TC-OP-002.1-01, TC-OP-002.2-01, TC-OP-002.3-01, TC-OP-010.1-01, TC-OP-010.2-01
CR-CSH-002 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.001 | FRS.CSH.02.01.02 | Entry type, bank account and receipting branch on the AR: Fields of BDOI's FRS.CSH.02.01.02 with maintained lists | Each receipt debits the bank account chosen | Added by BDOI's FRS | Receive Payment | Drop 1 | To assess | Accounting (BRD-5) | Create AR cases | High | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.01.02-AC01, TC-FRS-CSH.02.01.02-AC02, TC-FRS-CSH.02.01.02-AC03, TC-FRS-CSH.02.01.02-AC04, TC-OP-011.4-01
CR-CSH-003 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.020 | FRS.CSH.05.01.08 | Legacy numbers as match keys: QPS, ISYS, Ebix, PN and Loan Application Number matched on Priority 1 and 2 | Payments of migrated accounts quote the legacy numbers | Added by BDOI's FRS | Matching | Drop 1 | To assess | BRD-13 Data Migration | Matching cases | High | Candidate - for decision |  |  |  |  | TC-FRS-CSH.05.01.08-AC01, TC-FRS-CSH.05.01.08-AC02, TC-OP-018.1-01, TC-OP-018.1-02, TC-OP-018.2-01
CR-CSH-004 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.008 | FRS.CSH.05.01.09 | Direct Credit file as identification of payments: Priority 1 match with the payment record; Invalid BP filename, Invalid Transaction Number, Duplicate | Appendix R, C8 | Added by BDOI's FRS | Payment Uploads | Drop 1 | To assess | None | Direct Credit cases | High | Candidate - for decision |  |  |  |  | TC-OP-015.4-01, TC-OP-015.4-02, TC-OP-015.1-01, TC-OP-015.2-01, TC-OP-015.3-01
CR-CSH-005 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.012 | FRS.CSH.03.01.08 | Cancellation of a remitted AR to AR Insurer Refund: Remitted / not remitted branches; OR cancellation to Commission Receivable | Appendix R, C9 | Added by BDOI's FRS | Receipt cancellation | Drop 1 | To assess | Remittance; Accounting | Cancellation cases | High | Candidate - for decision |  |  |  |  | TC-FRS-CSH.03.01.08-AC01, TC-FRS-CSH.03.01.08-AC02, TC-FRS-CSH.03.01.08-AC03, TC-FRS-CSH.03.01.08-AC04, TC-OP-002.1-01
CR-CSH-006 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.004 | FRS.CSH.04.01 | Reinstatement of an issued receipt: Partial by account; Unapplied, AR Insurer Refund, AP Unapplied Commission records | Appendix R, C2, C14 | Added by BDOI's FRS | Receipt reinstatement; Unapplied | Drop 1 | To assess | Commission Receivables | Reinstatement cases | High | Candidate - for decision |  |  |  |  | TC-FRS-CSH.04.01.01-AC01, TC-OP-002.1-01, TC-OP-002.2-01, TC-OP-002.3-01, TC-OP-014.1-01
CR-CSH-007 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.007 | FRS.CSH.07.01.01 | Automatic OR at the Disbursement approval: OR generated once Disbursement approves the insurer settlement | Appendix R, C12 | Added by BDOI's FRS | Commission ORs | Drop 1 | To assess | Disbursement (BRD-5); Remittance | Automatic OR cases | High | Candidate - for decision |  |  |  |  | TC-FRS-CSH.07.01.01-AC01, TC-OP-021.3-01, TC-OP-021.1-01, TC-OP-021.1-02, TC-OP-021.2-01
CR-CSH-008 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.008 | FRS.CSH.05.01.04 | MFT intake of the OBPCS and PMS files: Files received via MFT checked and processed; alert on a refused file | BDOI's List of Integrations | Added by BDOI's FRS | Payment Uploads | Drop 1 | To assess | BDOI IT | Upload cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.05.01.04-AC01, TC-FRS-CSH.05.01.04-AC02, TC-OP-015.4-01, TC-OP-015.4-02, TC-OP-015.1-01
CR-CSH-009 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.008 | FRS.CSH.05.01.05 | File name and header total checks; several files per upload: Name conventions, 50 MB, header count and total | BDOI's FRS.CSH.05.01.03 to .06 | Added by BDOI's FRS | Payment Uploads | Drop 1 | To assess | None | Upload cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.05.01.05-AC01, TC-FRS-CSH.05.01.05-AC02, TC-FRS-CSH.05.01.05-AC03, TC-OP-008.1-01, TC-OP-008.2-01
CR-CSH-010 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.019 | FRS.CSH.02.04.07 | Acknowledgement certificate number and REPRINT mark: Certificate number per printed receipt; REPRINT on every later print; ZIP of PDFs | BDOI's FRS.CSH.02.04 | Added by BDOI's FRS | Batch Print; AR / OR forms | Drop 1 | To assess | None | Printing cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.04.07-AC01, TC-OP-025.3-01, TC-OP-025.3-02, TC-OP-025.1-01, TC-OP-025.2-01
CR-CSH-011 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.019 | FRS.CSH.02.06 | AR and OR forms of BDOI and their template set-up: BDOI's sample AR and OR body; template maintained by MBS with approval | Appendix R, C16, C17 | Added by BDOI's FRS | Document templates | Drop 1 | To assess | None | Form cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.06.01-AC01, TC-OP-025.3-01, TC-OP-025.3-02, TC-OP-025.1-01, TC-OP-025.2-01
CR-CSH-012 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.002 | FRS.CSH.02.02.08 | OR settling a Valid for Collection SOA or a Fee Policy invoice: Selection of what the OR settles | BDOI's FRS.CSH.02.02.08 | Added by BDOI's FRS | Issue Official Receipt | Drop 1 | To assess | Commission Receivables | OR cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.02.08-AC01, TC-OP-012.1-01, TC-OP-012.2-01, TC-OP-012.2-02
CR-CSH-013 | 09-Oct-2026 | iorta TechNXT Project Team | BRQID.003 | FRS.CSH.01.03.02 | Dashboard amounts per receipt type and status: Count and amount per item of BDOI's dashboard | BDOI's FRS.CSH.01.03.02 | Added by BDOI's FRS | Cashiering Workbench | Drop 1 | To assess | None | Dashboard cases | Low | Candidate - for decision |  |  |  |  | TC-FRS-CSH.01.03.02-AC01, TC-FRS-CSH.01.03.02-AC02, TC-FRS-CSH.01.03.02-AC03, TC-OP-003.4-01, TC-OP-003.1-01
CR-CSH-014 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.019 | FRS.CSH.02.04.07 | Certificate number convention: AC_<branch>_<MMYYYY>_<sequence> until BDOI gives its convention | Proposal of version 3.2 | Beyond the BRD | Batch Print | Drop 1 | Low | None | Printing cases | Low | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.04.07-AC01, TC-OP-025.3-01, TC-OP-025.3-02, TC-OP-025.1-01, TC-OP-025.2-01
CR-CSH-015 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.001 | FRS.CSH.02.01.16 | Cashier's day-end list: Records of the day with totals per payment type and bank account | Proposal of version 3.2 | Beyond the BRD | Receipts | Drop 1 | Low | None | - | Low | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.01.16-AC01, TC-OP-011.4-01, TC-OP-011.4-02, TC-OP-011.4-03, TC-OP-011.4-04
CR-CSH-016 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.025 | FRS.CSH.06.02.02 | Done tab of the Unapplied list: Completed dispositions shown in their own tab | Proposal of version 3.2 | Beyond the BRD | Unapplied Payments | Drop 1 | None | None | - | Low | Candidate - for decision |  |  |  |  | TC-FRS-CSH.06.02.02-AC01, TC-FRS-CSH.06.02.02-AC02, TC-OP-022.4-01, TC-OP-022.1-01, TC-OP-022.2-01
CR-CSH-017 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.023 | FRS.CSH.09.02.19 | Five reports added to BDOI's list: PDC Warehousing, Priority Posted Accounts, Payment Reversals, AR Outstanding with Ageing, Payment Batch Run Report | Reports of the BRD annex not in BDOI's list | Beyond the BRD | Report Centre | Drop 1 | Low | None | Report cases | Low | Candidate - for decision |  |  |  |  | TC-FRS-CSH.09.02.19-AC01, TC-OP-016.1-01, TC-OP-016.2-01, TC-OP-016.2-02, TC-OP-016.3-01
CR-CSH-018 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.002 | FRS.CSH.02.02.10 | Invoice under the Ease of Paying Taxes Act: Document name, form and series of the income receipts | RA 11976 (Appendix R) | Proposal for best practice | OR form | Drop 1 | To assess | Accounting (BRD-5) | OR cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.02.02.10-AC01, TC-FRS-CSH.02.02.10-AC02, TC-OP-012.1-01, TC-OP-012.2-01, TC-OP-012.2-02
CR-CSH-019 | 09-Oct-2026 | iorta TechNXT Project Team | CSHID.016 | FRS.CSH.05.01.06 | Excess formula of BDOI's FRS corrected: Excess = Paid Amount - (Outstanding - PR 2307) | Slip in BDOI's FRS (Appendix R.2) | Correction | Application | Drop 1 | None | None | Application cases | Medium | Candidate - for decision |  |  |  |  | TC-FRS-CSH.05.01.06-AC01, TC-FRS-CSH.05.01.06-AC02, TC-OP-008.1-01, TC-OP-008.2-01, TC-OP-008.3-01
CR-CSH-101 | 11-Oct-2026 | iorta TechNXT Project Team | Not in BRD | Appendix J (time rules); FRS.CSH.02.05, FRS.CSH.03.01, FRS.CSH.04.01, FRS.CSH.06.02; FRS Appendix W.2 | Time rules of the Cashiering stages: overdue marker and reminder | Records waiting for posting or approval are visible on the dashboard but nothing marks them late; a time rule per stage with a marker and a reminder keeps receipts issued the same day. | Beyond the BRD | Partial in BrokerVerse OOTB; the effort covers the missing part only: time rules, overdue marker and reminder for the Cashiering stages. | Within the drop if approved | 6.5 md (BIBS_CR_BRD-02_Effort_Estimate_v1.0.xlsx) | BDOI to confirm the times (Appendix R, Appendix S) | Update the linked test cases | Medium | Candidate - for decision |  |  |  |  | TC-OP-002.1-01, TC-OP-002.2-01, TC-OP-002.3-01, TC-OP-010.1-01, TC-OP-010.2-01
CR-CSH-102 | 11-Oct-2026 | iorta TechNXT Project Team | Not in BRD | Appendix G (channel of each notice); FRS Appendix W.2 | Each user chooses an e-mail copy of the Cashiering notices | Team Leaders who post from branches want the notices also by e-mail; the choice per user and per notice avoids e-mail floods. | Beyond the BRD | Partial in BrokerVerse OOTB; the effort is that of the missing part (per-user, per-notice e-mail choice). | Within the drop if approved | 3.5 md (BIBS_CR_BRD-02_Effort_Estimate_v1.0.xlsx) | E-mail channel of BDOI | Test cases to add | Low | Candidate - for decision

## Impact assessment form
Impact assessment form
Purpose | The assessment of one change request before the decision.
Who fills it in | iorta TechNXT Project Team with the System Analyst (BDO ITG)
How it is used | Copied for each change; its conclusion goes to the Register.
Due | Within 5 working days of the request.
Depends on | Register
Mandatory: Mandatory * | Mandatory * | Optional
Format: Text | Text | Text
Allowed values: Free text | Free text | Free text
What to enter: Part of the assessment | Filled in by the project | Name
Field * | Assessment * | Assessed by
Example – overwrite or delete: CR No. | CR-CSH-001 | Project analyst
CR No.
Summary of the change
BRD IDs and FR items affected
Screens, messages, e-mails affected
Other BRDs affected
Effort (mandays)
Schedule impact (drop)
Cost
Test cases to add or change
Training and documents
Risks
Recommendation

## Decisions log
Decisions log
One row per observation of Appendix R, for the decision of the Business Unit
Appendix R No. | Section | Topic | Proposed in the FRS | Decision by | Decision | Decided by (name) | Date | CR No. (if a change follows) | Status
R-01 (C1) | R.1 | Posting step for AR / OR issuance (maker-checker) | Issue at save for counter, file and PDC payments, so the client gets the AR at once and the series is used in order; give the TL a daily review list. If BDOI keeps the posting step, make it a configurable approval per receipt type (for example manual ORs only). Proposed behaviour: “Issue AR and Apply” issues the AR from the branch series, applies the payment and opens the receipt; ORs likewise. Available as a setting: Setting of the receipts that need the posting step: AR and OR (BDOI's reading) by default; blank issues the number at save. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-02 (C2) | R.1 | Meaning of reinstatement | Both, under one Reinstate action with the BRD's reasons: “Due to Cancellation” and bounced check restore a cancelled receipt; mis-application and withholding tax adjustment reverse the application of an issued receipt for re-application. Proposed behaviour: Reinstate a cancelled receipt in full or in part; the reinstated amount is applied to the encoded invoice. Reversal of an issued receipt's application is the payment reversal of Incoming Requests. Available as a setting: Setting of what Reinstate does: issued receipts (BDOI's reading), cancelled receipts, or both (by default). | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-03 (C3) | R.1 | Numbers of creation, cancellation and reinstatement records | Adopt BDOI's prefixes with the year (for example CN-AR-2026-000001); the numbering is configuration. Proposed behaviour: Cancellation CAN-yyyy-n and reinstatement RIN-yyyy-n (014). Available as a setting: Setting of the record number format: prefix, type and sequence by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-04 (C5) | R.1 | Minimal balance threshold | Keep 10.00 as in the BRD unless BDOI decides otherwise; it is a parameter. Proposed behaviour: Default 10.00 for premium and excess, configurable. Available as a setting: Setting of the minimal balance threshold: 10.00 by default (BRD). | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-05 (C6) | R.1 | Application hierarchy | Keep FST as its own component after LGT (it is booked on fire policies); apply check payments before cash payments on the same invoice on the same day. Proposed behaviour: DST, VAT, LGT, FST, other charges, basic premium; check before cash open. Available as a setting: Setting of the order of the payments of one posting run: checks before cash by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-06 (C7) | R.1 | Check holding period | Accept the check when it is presented (a post-dated check goes to the PDC warehouse); keep the holding period for remittance only. Proposed behaviour: No check-date validation at receipt; 3 banking days before the payment is remitted (RMTID.017). Available as a setting: Settings of the check date rule (on) and of the holding period (4 working days). | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-07 (C8) | R.1 | Direct Credit file | Adopt BDOI's reading: the file identifies unmatched payments already receipted, so no second AR; new money arrives through the other channels. Proposed behaviour: Every Direct Credit row is a new payment with its own AR. Available as a setting: Setting of the reading of the Direct Credit file: identification of payments already received (BDOI's reading) by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-08 (C9) | R.1 | Cancellation of a remitted AR | Adopt BDOI's rule; it matches how our Adjustment FRs handle remitted premium (AR Insurer). Proposed behaviour: Every application is reversed and the invoices are outstanding again. Available as a setting: Setting of the cancellation of a remitted AR: AR insurer refund (BDOI's reading) by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-09 (C10) | R.1 | Commission Schedule with failed or unmatched lines | Line-level processing as BRQID.006 asks, with the exceptions listed; partial payments allowed and shown as such. Proposed behaviour: Valid lines are staged and issued; failed lines stay staged with their reason. Available as a setting: Setting of the commission schedule with failed or unmatched lines: valid lines processed (BRD) by default; whole file refused available. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-10 (C11) | R.1 | One OR per commission schedule or per insurer and certificate | One OR per insurer / payee and certificate per schedule or batch, as CSHID.007 states. Proposed behaviour: One OR per insurer, certificate and payment for Collection details; one OR per remittance batch. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-11 (C12) | R.1 | When the remittance OR is generated | Comptrollership decides the point at which the commission OR is issued; moving it to the Disbursement approval is a change to the system. Proposed behaviour: The commission OR is issued when the Remittance TL approves the batch. Available as a setting: Setting of the point the settlement OR is issued: at the approval of Disbursement (BDOI's reading) by default; at the remittance approval available. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-12 (C13) | R.1 | Who works the unapplied payments | Keep Cashiering ownership with requests from Collections, as the BRD-4 Collections FRS specifies; give Marketing read access to the items of its unit. Proposed behaviour: The Cashier assigns and the Cashiering TL approves; Collections asks through Incoming Requests (BRD-4). Available as a setting: Setting of what Marketing users see in the unapplied payment list: their marketing unit (BDOI's reading) by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-13 (C14) | R.1 | AP Unapplied Commission and AR Insurer Refund as unapplied types | Add AP Unapplied Commission for reversed ORs; keep AR Insurer as a receivable, shown on the list for information. Proposed behaviour: AR Insurer is a receivable from the insurer set up by Adjustment; no AP Unapplied Commission. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-14 (C15) | R.1 | Post-dated checks | Keep the the system warehouse (BRD); load it from the PMS list, so PMS stays the source of the checks. Proposed behaviour: Checks are warehoused in the system with a PDCW number and matured by the daily run. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-15 (C16) | R.1 | AR form and signature | Adopt BDOI's forms. Proposed behaviour: The AR / OR PDF has a Cashier signature line; layout draft (this FRS). | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-16 (C18) | R.1 | File size limit | Set 50 MB. Proposed behaviour: Not stated; the system accepts files up to 25 MB. Available as a setting: Size limit per payment file type: 50 MB by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-17 (C20) | R.1 | Exchange rate for USD receipts | One rate from the Comptrollership table; reversals at the rate of the original receipt. Proposed behaviour: Comptrollership BOOK rate with 2 decimals at the receipt date; cancellation and reinstatement at the receipt's rate. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-18 (C21) | R.1 | Cancellation reasons | Keep the BRD list (it is a maintained list); add the check-payment restriction if BDOI wants it. Proposed behaviour: The BRD lists in four groups, including Check not picked-up, Negative VAT, Discount not applied, PDC retrieval / replacement, Bounced or returned check, Error printing. Available as a setting: List of the cancellation reasons allowed for a check payment, by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-19 (C22) | R.1 | Partial reinstatement | By account, with the amount per account shown. Proposed behaviour: Partial reinstatement by amount. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-20 (C23) | R.1 | Encoded reinstatement fields | Keep them, defaulted from the receipt. Proposed behaviour: Invoice, AR / OR no., assured / payor, amount, Account Officer, Unit Head, Team Leader (premium); not required for a bounced check. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-21 (C24) | R.1 | Device for access | Enforce it through BDO's network and device policy if required; no change to the screens. Proposed behaviour: Log-in from a browser; responsive screens. Available as a setting: Setting of the device restriction: off by default for SIT; on with the company networks and the device header of BDOI IT. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-22 (C25) | R.1 | Remarks and bank account mandatory on the AR | Bank account mandatory (defaulted by currency as BDOI proposes); remarks optional. Proposed behaviour: Neither field exists on Receive Payment. Available as a setting: Setting of the remarks of an AR: mandatory by default. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-23 (C26) | R.1 | PR 2307 base and tag | Tag per account, defaulted from the client; Comptrollership states the base of the 2% (basic or gross premium); the system keeps the share applied as a parameter. Proposed behaviour: 2% CWT client flag; 98% of the premium applied. Available as a setting: Setting of the base of the PR 2307: the premium amount by default; the basic premium available. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-24 (C28) | R.1 | Applied Premium report scope | All applications, with a filter on the source (manual, file, PDC). Proposed behaviour: CSH-APPLIED-PREM lists every applied premium payment. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-25 (C29) | R.1 | Who uploads the channel files | Both documents propose the business uploads; record the change against the BRD. Proposed behaviour: The Cashier uploads. | Cashiering Process Owner; System Analyst (BDO ITG) |  |  |  |  | Open
R-26 (C4) | R.2 | AR / OR number format and acknowledgement certificate number | BDOI to give one format per receipt kind; the system sets it as the series prefix and range without a change. Available as a setting: Settings of the AR and OR number format (prefix, year, branch indicator, sequence) and of the certificate number (AC, branch, month and year, sequence). | System Analyst (BDO ITG) |  |  |  |  | Configurable – BDOI to confirm the setting
R-27 (C17) | R.2 | Note on the AR | BDOI to choose; the text is part of the form. | System Analyst (BDO ITG) |  |  |  |  | Open
R-28 (C19) | R.2 | File formats | Keep one layout per channel as configuration; BDOI to confirm each layout with the channel owner. | System Analyst (BDO ITG) |  |  |  |  | Open
R-29 (C27) | R.2 | Sample Billspayment file | BDOI to supply one real file of each channel for the layouts of Annex C. | System Analyst (BDO ITG) |  |  |  |  | Open
R-30 | R.2 | Excess amount formula | The excess is Paid Amount – (Outstanding Balance – PR 2307), that is Paid Amount – Outstanding Balance + PR 2307. Example: outstanding 10,200.00, PR 2307 200.00, paid 10,100.00: applied 10,000.00, excess 100.00 (the formula as written gives -300.00). | System Analyst (BDO ITG); Comptrollership |  |  |  |  | Open
R-31 | R.2 | Duplicate and missing item numbers | Renumber in the next BDOI revision; this version refers to the second FRS.CSH.03.01.05 as "FRS.CSH.03.01.05 (Reason for Cancellation)" and keeps BDOI's numbers otherwise. | System Analyst (BDO ITG) |  |  |  |  | Open
R-32 | R.2 | Tabs quoted in the mapping | Read the mapping row with the four tabs of FRS.CSH.06.02.02. | System Analyst (BDO ITG) |  |  |  |  | Open
R-33 | R.2 | Rule of the Cancelled Acknowledgement Receipts report | Extract all cancelled AR within the covered period (AR status = Cancelled, as the next line says). | System Analyst (BDO ITG) |  |  |  |  | Open
R-34 | R.2 | Cross-reference to batch printing | The reference is FRS.CSH.02.04 (Batch Printing); FRS.CSH.02.03 is the number series. | System Analyst (BDO ITG) |  |  |  |  | Open
R-35 | R.2 | Status of the record in a depleted series | The record keeps its status For Posting and the poster sees the message; read "Created" as "unchanged". | System Analyst (BDO ITG) |  |  |  |  | Open
R-36 | R.2 | Status shown in the reinstatement posting list | The AR / OR number status stays Issued; the Reinstatement Record Status is For Posting. | System Analyst (BDO ITG) |  |  |  |  | Open
R-37 | R.2 | Record number of the returned reinstatement list | Reinstatement Record Number. | System Analyst (BDO ITG) |  |  |  |  | Open
R-38 | R.2 | Drafting notes left in the text | Remove the notes and question marks in the next BDOI revision; the certificate convention is proposed in FRS.CSH.02.04.07 and the template is Appendix A. | System Analyst (BDO ITG) |  |  |  |  | Open
R-39 | R.2 | Typing errors | Unapplied Premium Minimal Balance; "Do you wish to continue"; Aging (Per Date Booked). | System Analyst (BDO ITG) |  |  |  |  | Open
R-40 | R.2 | Version of record | This version is numbered 3.2 after the file name; BDO ITG confirms the numbering of record. | System Analyst (BDO ITG) |  |  |  |  | Open
R-41 (BRQID.001) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.01.01, FRS.CSH.01.02. BDOI's row was blank; the log-in is specified in FRS.CSH.01.01 and FRS.CSH.01.02 (FRS.OPS.001, FRS.OPS.002). | System Analyst (BDO ITG) |  |  |  |  | Open
R-42 (BRQID.002) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.01.02, FRS.OPS.002.04, FRS.OPS.002.05. BDOI's row was blank; access by profile is in FRS.CSH.01.02; permissions per action and segregation of duties added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-43 (BRQID.003) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.01.03, FRS.CSH.01.03.05, FRS.CSH.10.01.02. BDOI's row was blank; the dashboard and the main navigation are in FRS.CSH.01.03; the links to the applications it integrates with added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-44 (BRQID.004) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.10.01, FRS.CSH.06.03. BDOI's row was blank; the List of Integrations names two interfaces; FRS.CSH.10.01 and Appendix N give every interface of Cashiering. | System Analyst (BDO ITG) |  |  |  |  | Open
R-45 (BRQID.005) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.05.01, FRS.CSH.10.02. BDOI's row was blank; the files received via MFT are in FRS.CSH.05.01.04; the flow-in runs added in FRS.CSH.10.02. | System Analyst (BDO ITG) |  |  |  |  | Open
R-46 (BRQID.006) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.05.01, FRS.CSH.05.01.13, FRS.CSH.10.03, FRS.CSH.09.02.23. BDOI's row was blank; partial failures and the run report are in FRS.CSH.05.01.06 and .12; batch runs added in FRS.CSH.10.03. | System Analyst (BDO ITG) |  |  |  |  | Open
R-47 (BRQID.007) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.08.01, FRS.CSH.08.02, FRS.CSH.02.05.10. BDOI's row was blank; remittance and payment details are in the Account Record Inquiry (FRS.CSH.08.01); the payment history of each account added in FRS.CSH.08.02. | System Analyst (BDO ITG) |  |  |  |  | Open
R-48 (CSHID.001) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.01.15, FRS.CSH.02.01.16, FRS.CSH.03.01.11, FRS.CSH.04.01.12. AR Insurance, the cashier's day-end list and the notices of the cancellation and reinstatement records added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-49 (CSHID.002) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.02.10, FRS.CSH.02.06. Taxes on ORs and the OR template added to the mapping. | System Analyst (BDO ITG) |  |  |  |  | Open
R-50 (CSHID.003) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.03.01.06. The validation of the reason (FRS.CSH.03.01.06) named. | System Analyst (BDO ITG) |  |  |  |  | Open
R-51 (CSHID.005) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.04.01.06. The information of CSHID.005 is captured in FRS.CSH.04.01.06. | System Analyst (BDO ITG) |  |  |  |  | Open
R-52 (CSHID.006) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.03.06, FRS.CSH.02.05.08. The AR / OR number assignment (FRS.CSH.02.05.08) and the series in use at go-live added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-53 (CSHID.007) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.14, FRS.CSH.07.01.05. The application of the OR payment and the list of commission ORs added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-54 (CSHID.008) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.05.02, FRS.CSH.05.01.13. The post-dated check warehouse of CSHID.008 (system number, repository, list) added as FRS.CSH.05.02. | System Analyst (BDO ITG) |  |  |  |  | Open
R-55 (CSHID.010) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.08.01.04. The search log of CSHID.010 added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-56 (CSHID.011) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.08.03, FRS.CSH.02.01.14. BDOI's row was blank; the audit trail is stated in each FR item; FRS.CSH.08.03 added for the AR and OR audit trail. | System Analyst (BDO ITG) |  |  |  |  | Open
R-57 (CSHID.012) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.03.01.09. GL posting of the cancellation (FRS.CSH.03.01.09) named; entries in Appendix I. | System Analyst (BDO ITG) |  |  |  |  | Open
R-58 (CSHID.013) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.04.01.10. GL posting of the reinstatement (FRS.CSH.04.01.10) named; entries in Appendix I. | System Analyst (BDO ITG) |  |  |  |  | Open
R-59 (CSHID.014) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.15. GL posting (FRS.CSH.02.05.15) named; entries in Appendix I. | System Analyst (BDO ITG) |  |  |  |  | Open
R-60 (CSHID.015) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.09. The depleted-series check (FRS.CSH.02.05.09) named. | System Analyst (BDO ITG) |  |  |  |  | Open
R-61 (CSHID.016) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.12, FRS.CSH.06.01.08. The minimal balance item (FRS.CSH.02.05.12) named; minimal balances kept out of the Unapplied list. | System Analyst (BDO ITG) |  |  |  |  | Open
R-62 (CSHID.017) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.09.01.05. Reports on a schedule added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-63 (CSHID.019) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.04.17. Copy label added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-64 (CSHID.020) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.05.03, FRS.CSH.05.04, FRS.CSH.02.01.02. Pre-booked payments and the payment confirmation to New Business added; matching at the counter in FRS.CSH.02.01.02. | System Analyst (BDO ITG) |  |  |  |  | Open
R-65 (CSHID.021) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.01.15. The non-premium payments of insurers (AR Insurance) are received in FRS.CSH.02.01; FRS.CSH.02.01.15 added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-66 (CSHID.022) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.11. The hierarchy (FRS.CSH.02.05.11) named. | System Analyst (BDO ITG) |  |  |  |  | Open
R-67 (CSHID.023) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.09.02, FRS.CSH.02.06.04. The report requirements (FRS.CSH.09.02) and the Certification of Payment added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-68 (CSHID.024) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.06.02, FRS.CSH.06.03. The disposition types (FRS.CSH.06.02) and the requests of other modules (FRS.CSH.06.03) added. | System Analyst (BDO ITG) |  |  |  |  | Open
R-69 (MKTID.013) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.02.05.13. BDOI maps the row to the Commission Receivable FRS ("Com rec"); the PR 2307 kept outstanding at payment is in FRS.CSH.02.05.13; the reversal itself is outside this FRS (Appendix R). | System Analyst (BDO ITG) |  |  |  |  | Open
R-70 (DBMID.001) | R.3 | Mapping extended | Added in v3.2: FRS.CSH.10.01. BDOI maps the row to the Commission Receivable FRS ("Com rec"); the hand-over to Disbursement is an interface of FRS.CSH.10.01; the receipt and release of the certificates is outside this FRS (Appendix R). | System Analyst (BDO ITG) |  |  |  |  | Open
R-71 | R.3 | BRD IDs added | Three rows added with the BRD text and the reason of the removal, so that every BRD ID of the Cashiering scope is accounted for. | System Analyst (BDO ITG) |  |  |  |  | Open
R-72 | R.4 | Official receipts and the Ease of Paying Taxes Act | Under the Ease of Paying Taxes Act (Republic Act 11976) and its revenue regulations, the invoice is the primary document for the sale of services and the official receipt a supplementary document. Comptrollership (Tax) confirms whether BDOI's income receipts are issued as invoices and the wording of the OR form and footer; the series and forms follow the BIR registration of BDOI. | Comptrollership (Tax) |  |  |  |  | Open
R-73 | R.4 | Value added tax and withholding tax printed on the OR | Print the gross amount, the VAT and the withholding tax of each OR line (FRS.CSH.02.02.10), as the BIR invoicing rules require for a VAT-registered seller. | Comptrollership (Tax); MBS |  |  |  |  | Open
R-74 | R.4 | Insurance Profit Share and Contingent Profit Commission | Keep CPC as the value of the list and add "Insurance Profit Share" if it is a different income; the list is maintained (Appendix H). | Cashiering Process Owner; Comptrollership |  |  |  |  | Open
R-75 | R.4 | Owner of MKTID.013 and DBMID.001 | Specify them in the FRS of Commission Receivables as BDOI maps them, or in the FRS of Marketing Collection and Disbursement; Cashiering keeps the PR 2307 outstanding at payment (FRS.CSH.02.05.13). | Product Owner; BDO ITG |  |  |  |  | Open
R-76 | R.4 | Notices by e-mail | The notices of Appendix G are given in the system (bell); the system sends no e-mail of Cashiering today except the failed batch run. An e-mail copy of the approval notices is a point for decision (Appendix S). | Cashiering Process Owner |  |  |  |  | Open
R-77 | R.4 | Messages of the system that carry a BRD reference | Some messages of the system end with the BRD ID (for example "Official receipts are issued by Head Office only (CSHID.006)", Appendix F); the texts of this FRS are without it. The wording of every message is confirmed through the requirements collection workbook (sheet Messages to confirm) and the system texts aligned. | Cashiering Process Owner |  |  |  |  | Open
R-78 | R.4 | Bank deposit of the day's collections | The deposit slip of the day's cash and checks is kept in the Accounting (Receivables) module of BIBS; the Daily Cash Reconciliation report gives the receipts per bank account. Whether the cashier prepares the deposit slip in Cashiering is a point for decision (Appendix S). | Cashiering Process Owner; Comptrollership |  |  |  |  | Open
R-79 | R.4 | Legacy numbers of the migrated accounts | The legacy numbers are loaded with the migrated accounts (Appendix P, BRD-13 Data Migration), so that the payments quoting them are matched (FRS.CSH.05.01.08). | Data Migration lead; Cashiering Process Owner |  |  |  |  | Open
R-80 | R.4 | Control totals of the Bills Payment file | Check the detail records against the header count and total and refuse a file that differs (FRS.CSH.05.01.06). | Cashiering Process Owner; BDOI IT (OBPCS) |  |  |  |  | Open
R-81 | R.4 | Address and VAT TIN of the forms | Taken from the company record, as on the sample AR (FRS.CSH.02.06.02). | MBS |  |  |  |  | Open
R-82 | R.4 | Approval and posting times | Proposed: AR / OR creation records posted the same business day; cancellation and reinstatement records within 1 working day; dispositions within 2 working days; overdue records shown on the dashboard (Appendix J). | Cashiering Process Owner |  |  |  |  | Open
R-83 | R.4 | Proposals beyond the BRD text | Items added in this version that go beyond the BRD text and are proposals for decision: certificate number convention (FRS.CSH.02.04.07), day-end list (FRS.CSH.02.01.16), copy label kept (FRS.CSH.02.04.17), Done tab (FRS.CSH.06.02.02), five added reports (FRS.CSH.09.02.19 to .23); each is a candidate change in the Change Request Register. | Product Owner |  |  |  |  | Open

## Lists
Type | Priority | Status | Status
Beyond the BRD | High | Candidate - for decision | Open
Added by BDOI's FRS | Medium | Raised | Configurable – BDOI to confirm the setting
Proposal for best practice | Low | Assessed | Decided
Correction |  | Approved | Withdrawn
Rejected
Scheduled
In test
Closed