## Cover
UAT USERS
Business Unit Walkthrough Users
BRD-03 Product Maintenance – who signs in for the walkthrough
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-03
Version | 1.0
Date | 9 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | The users of BRD-03 for the Business Unit walkthrough, with their sign-in IDs | 12
Walkthrough script | The walkthrough of BRD-03 step by step, with the sign-in ID of each step | 36
Legend
Passed
Failed
Blocked
Environment: BIBS DEV environment: https://dev.brokerverse.cloud.
Passwords: Issued separately by the iorta TechNXT Project Team; no password is written in this workbook.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona | Business role in the FRS
Users | Name | User name
Users | Sign-in ID | User ID in the BIBS DEV environment
Users | Role / group profile | Group profile of the user
Users | Company / branch / unit | Where the user belongs
Users | What the user does in the walkthrough | Responsibilities
Users | Menu path to start | Where the user starts
Users | Product Maintenance menus the user should see | Entries of the menu
Users | Walkthrough steps | Steps of the script
Users | Limits or data scope | Approval limits and data scope
Users | Environment | Where to sign in
Users | Password | How the password is issued
Users | Remarks | Remarks
Walkthrough script | Step | Step number
Walkthrough script | Walkthrough | Walkthrough
Walkthrough script | Persona | Who acts
Walkthrough script | Sign-in ID | User ID
Walkthrough script | Action | What the user does
Walkthrough script | Expected result | What the user sees
Walkthrough script | Result | Result | Not run, Passed, Failed, Blocked
Walkthrough script | Done by | Name
Walkthrough script | Date | dd-MMM-yyyy
Walkthrough script | Remarks | Remarks

## Users
Users
The users of BRD-03 for the Business Unit walkthrough, with their sign-in IDs
Persona | Name | Sign-in ID | Role / group profile | Company / branch / unit | What the user does in the walkthrough | Menu path to start | Product Maintenance menus the user should see | Walkthrough steps | Limits or data scope | Environment | Password | Remarks
MBS | Monica Business Services | mbs | Marketing Business Services and System Support | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing Business Services | Sets up package versions; maintains incentive criteria and product masters; views archived packages | Client & Policy › Product Maintenance › Coverages & Clauses | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation | WT-A.1, WT-A.15, WT-A.16, WT-B.9, WT-B.10, WT-B.12 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
MBS | Marco Business Services | mbs2 | Marketing Business Services and System Support | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing Business Services | Sets up package versions; maintains incentive criteria and product masters; views archived packages | Client & Policy › Product Maintenance › Product Maintenance Home | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation | Not in a walkthrough step | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team | Second MBS user, for the four-eyes set-up of package versions
Marketing AO | Aileen Account Officer | ao | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Creates and submits package requests; views packages | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Deactivation Requests, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Premium Calculator | WT-A.3, WT-A.21, WT-A.22, WT-A.24, WT-B.1, WT-B.2 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
Marketing TL / TH / UH | Marites Marketing Lead | mkttl | Marketing Team Leader / Head (approver) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Approves package requests; reviews terms of client-specific packages; views reports | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Premium Calculator | WT-A.4, WT-B.3 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
TSU Team Lead | Teresa TSU Lead | tsulead | TSU Team Lead | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Technical Support Unit | Reviews and recommends requests; approves quotation slips (or a co-officer); negotiates | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, TSU Workbench, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Coverages & Clauses, Incentive Criteria | WT-A.5, WT-A.8, WT-B.4, WT-B.5 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team | Also holds: Technical Support Unit
TSU Team Head / Head | Tomas TSU Head | tsuhead | TSU Team Head / Head | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Technical Support Unit | Approves requests; releases terms to Marketing; validates package versions | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, TSU Workbench, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Validation Queue, Coverages & Clauses, Incentive Criteria | WT-A.6, WT-A.12, WT-A.17, WT-B.11 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
TSU Officer | Teodoro TSU Analyst | tsu | Technical Support Unit | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Technical Support Unit | Creates requests; prepares quotation slips; keys in insurer responses; prepares requirements and advisories; monitors expiry | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, TSU Workbench, Package Expiry, Deactivation Requests, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Premium Calculator | WT-A.7, WT-A.9, WT-A.10, WT-A.11, WT-A.13, WT-A.20, WT-B.6, WT-B.8 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
ManCom | Manuel ManCom Member | mancom | Management Committee | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Management Committee | Signs off package requirements | Client & Policy › Product Maintenance › Package Requests | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Deactivation Requests, Audit Logs, Products, Coverages & Clauses, Incentive Criteria | WT-A.14, WT-B.7 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
Business Administrator | Bea Business Admin | badmin | Business Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Business Administration | Validates package versions; authorises product masters, incentive criteria and rate exceptions | Client & Policy › Product Maintenance › Coverages & Clauses | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Validation Queue, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation | WT-A.2, WT-A.18 | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
New Business Approver | Andres Approver | approver | Approver (requests, workload) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / New Business | Approves the new insurer record and the master records used by the package | Client & Policy › Product Maintenance › Insurers | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Deactivation Requests, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation, Premium Calculator | WT-A.19, WT-A.23 | Authorisation limit PHP 5,000,000.00; All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | admin | System Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / IT - System Administration | Maintains parameters, lists of values and roles (section 9); read access to Product Maintenance | Setup & Administration › Broking Setup › Lists of Values | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Deactivation Requests, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation | Not in a walkthrough step | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | auditor | Auditor | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Internal Audit | Read access to packages, archive and reports | Client & Policy › Product Maintenance › Product Maintenance Home | Product Maintenance › Product Maintenance Home, Product Maintenance Dashboard, Package Requests, Package Expiry, Deactivation Requests, Product Master Transfers, Placement Update Reports, Audit Logs, Products, Coverages & Clauses, Incentive Criteria, Insurers, Rates & Taxes, Sales Organisation, Premium Calculator | Not in a walkthrough step | All companies and branches | BIBS DEV environment: https://dev.brokerverse.cloud | Issued separately by the iorta TechNXT Project Team

## Walkthrough script
Walkthrough script
The walkthrough of BRD-03 step by step, with the sign-in ID of each step
Step | Walkthrough | Persona | Sign-in ID | Action | Expected result | Result | Done by | Date | Remarks
WT-A.1 | WT-A A new package from the request to its first New Business quotation | MBS | mbs | Opens Coverages & Clauses › Clause Library, clicks New Clause, enters the code FLEET_REPAIR, kind, line Motor, title, effective date and wording, and clicks Save for Authorization | Toast: Clause FLEET_REPAIR saved – pending authorization; the row shows Pending Authorization | Not run
WT-A.2 | WT-A A new package from the request to its first New Business quotation | Business Administrator | badmin | Opens the Clause Library and clicks Authorize on FLEET_REPAIR | Toast: FLEET_REPAIR authorized; the status is Active | Not run
WT-A.3 | WT-A A new package from the request to its first New Business quotation | Marketing AO | ao | Opens Package Requests › New Package Request, chooses New package and Generic programme, enters Motor Fleet Plus, line Motor, cover type Comprehensive, reason New programme for a market segment, the segments, the requested coverages, rate 1.20%, minimum premium and package dates, ticks Mabuhay General Insurance Corp. and Luzon Assurance Co., and clicks Submit for Approval | Toast: PKR-yyyy-nnnnnn submitted for Marketing approval; the request opens in For Marketing approval | Not run
WT-A.4 | WT-A A new package from the request to its first New Business quotation | Marketing TL / TH / UH | mkttl | Opens the request from the For Approval tab and clicks Approve and send to TSU | The stage becomes For TSU review; the history lists the approval | Not run
WT-A.5 | WT-A A new package from the request to its first New Business quotation | TSU Team Lead | tsulead | Clicks Recommend for approval, writes the recommendation and clicks Recommend | The TSU recommendation shows on the Details tab; the stage becomes For TSU Head approval | Not run
WT-A.6 | WT-A A new package from the request to its first New Business quotation | TSU Team Head / Head | tsuhead | Reads the recommendation and clicks Approve for negotiation | The stage becomes Insurer negotiation; round 1 is opened with the two target insurers | Not run
WT-A.7 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Opens the Negotiation tab, adds a note to the insurers and clicks Submit for Approval | Toast: PQS-yyyy-nnnnnn submitted for approval; round 1 shows For approval | Not run
WT-A.8 | WT-A A new package from the request to its first New Business quotation | TSU Team Lead | tsulead | Clicks Approve and Send on round 1 | Toast: PQS-yyyy-nnnnnn sent to 2 insurer(s); both responses show Pending; the E-mails tab lists the slip and password e-mails | Not run
WT-A.9 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Clicks Key In for each insurer, enters the outcome, rate, minimum premium and deductibles, attaches the insurer's reply and clicks Save Terms | Toast: Terms of <insurer> saved; the responses show Approved with changes and Counter-proposal with their rates | Not run
WT-A.10 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Clicks Terms final, ticks the offer of Mabuhay General Insurance Corp. and clicks Make Terms Final | The stage becomes Negotiated terms review; the chosen insurer shows in the header | Not run
WT-A.11 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Opens the Comparative tab | The round 1 comparison with the Lowest rate tag and the current audit master in Stored outputs | Not run
WT-A.12 | WT-A A new package from the request to its first New Business quotation | TSU Team Head / Head | tsuhead | Clicks Proceed to requirements (generic package) | The stage becomes Requirements preparation | Not run
WT-A.13 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Enters the computation basis, clicks Save Requirements, downloads the Package Slip, uploads the signed slip on the Documents tab as Package slip (signed), clicks Submit requirements for ManCom sign-off, then on the Routing & Approvals tab ticks the ManCom member and the President and clicks Send for ManCom Approval | The checklist reads The requirements pack is complete.; the stage becomes For ManCom sign-off; the ManCom Approval table lists the member Pending Approval and the President Waiting for the others | Not run
WT-A.14 | WT-A A new package from the request to its first New Business quotation | ManCom | mancom | The ManCom member reviews the proposed terms and clicks Approve on the Routing & Approvals tab; the President, asked once the member approved, clicks Approve | The ManCom Approval table shows both Approved; ManCom decisions lists MC-PKR-yyyy-nnnnnn Signed; the slips show Locked; the stage becomes With MBS for set-up (forwarding automatic) | Not run
WT-A.15 | WT-A A new package from the request to its first New Business quotation | MBS | mbs | Clicks Set up package version, enters the risk code MTR30 and the product name, and clicks Set Up Version | Toast: Version 1 set up; the Set-up tab shows MTR30 version 1; the stage becomes Package version for validation | Not run
WT-A.16 | WT-A A new package from the request to its first New Business quotation | MBS | mbs | Clicks Open Version Editor, adds the clause FLEET_REPAIR on the insurer terms, saves and clicks Submit for Validation | Toast: Version 1 submitted for validation; the version shows For validation | Not run
WT-A.17 | WT-A A new package from the request to its first New Business quotation | TSU Team Head / Head | tsuhead | Opens the version from the Validation Queue, ticks the five checklist items and clicks Validate and Release | Toast: Version 1 released; the Validation card shows the result Passed, the validator, the date, the test premium and the checks with their figures | Not run
WT-A.18 | WT-A A new package from the request to its first New Business quotation | Business Administrator | badmin | Opens Insurers › Mabuhay General Insurance Corp., clicks Add rate, chooses MTR30, 15% from today and clicks Save for Authorization | Toast: Commission rate saved – pending authorization | Not run
WT-A.19 | WT-A A new package from the request to its first New Business quotation | New Business Approver | approver | Opens the insurer and clicks Authorize on the new commission rate | The rate for MTR30 shows Active | Not run
WT-A.20 | WT-A A new package from the request to its first New Business quotation | TSU Officer | tsu | Opens the Advisories tab of the released request, checks that both supporting documents are Attached and clicks Send Advisory | Toast: Advisory sent; the advisory shows Sent with the date; Marketing users receive the notice | Not run
WT-A.21 | WT-A A new package from the request to its first New Business quotation | Marketing AO | ao | Opens Premium Calculator, chooses MTR30 and Mabuhay General Insurance Corp., enters a vehicle value and clicks Calculate | Priced on package version 1 (effective <date>, scheme rate 1.2%) with every charge and the commission | Not run
WT-A.22 | WT-A A new package from the request to its first New Business quotation | Marketing AO | ao | Creates a New Business quotation of MTR30 for the seed client with an item rate of 1.10%, opens it and clicks Request Rate Exception with the reason | The rate scheme panel shows the exception pending approval | Not run
WT-A.23 | WT-A A new package from the request to its first New Business quotation | New Business Approver | approver | Opens My Approvals, clicks the rate exception of the quotation, compares the requested rate with the scheme in force on the exception record, clicks Approve, writes the comment and confirms | Toast: Rate exception RSE-yyyy-nnnnnn approved; the record shows Approved with the approver, the date and the comment; the Account Officer receives the notice | Not run
WT-A.24 | WT-A A new package from the request to its first New Business quotation | Marketing AO | ao | Opens the quotation again after the approval | The Rate Exceptions table lists the exception Approved; the quotation can be submitted for review | Not run
WT-B.1 | WT-B Returns and refusals, and the messages the user sees | Marketing AO | ao | Opens New Package Request and clicks Save Draft without the name, line and reason | Under the fields: Enter the package or programme name; Select the product line; Select the reason. Nothing is saved | Not run
WT-B.2 | WT-B Returns and refusals, and the messages the user sees | Marketing AO | ao | Completes the header only and clicks Submit for Approval | The hint Before submitting, complete the requested terms (coverages or sections); at least one target insurer; the package end date, and the refusal Complete the request: ... with its reference | Not run
WT-B.3 | WT-B Returns and refusals, and the messages the user sees | Marketing TL / TH / UH | mkttl | Creates and submits a request himself, then clicks Approve and send to TSU on it | A package request is approved by someone other than its maker | Not run
WT-B.4 | WT-B Returns and refusals, and the messages the user sees | TSU Team Lead | tsulead | Opens PKR-2026-900002 and clicks Return to requester, chooses the reason and writes what is missing | The stage becomes Draft request; the requester receives the workflow notice with the comment | Not run
WT-B.5 | WT-B Returns and refusals, and the messages the user sees | TSU Team Lead | tsulead | Prepares and submits a slip himself, then clicks Approve and Send on it | The quotation slip is approved by a TL or a co-officer | Not run
WT-B.6 | WT-B Returns and refusals, and the messages the user sees | TSU Officer | tsu | Opens PKR-2026-900003 and clicks Terms final while Luzon Assurance is still pending in round 2 | Every insurer of round 2 needs an outcome before the terms are final (1 pending) | Not run
WT-B.7 | WT-B Returns and refusals, and the messages the user sees | ManCom | mancom | Opens PKR-2026-900004 and clicks Return to TSU with the reason | The stage becomes Requirements preparation; ManCom decisions lists the return | Not run
WT-B.8 | WT-B Returns and refusals, and the messages the user sees | TSU Officer | tsu | Clicks Submit requirements for ManCom sign-off before uploading the signed package slip | The checklist lists the missing signed package slip; the refusal Complete the requirements: ... | Not run
WT-B.9 | WT-B Returns and refusals, and the messages the user sees | MBS | mbs | Opens PKR-2026-900005 and clicks Return incomplete requirements to TSU with the reason | The stage becomes Requirements preparation | Not run
WT-B.10 | WT-B Returns and refusals, and the messages the user sees | MBS | mbs | Opens MTR12 version 2, clears the minimum premium and sets an effective date before today, then clicks Submit for Validation | Toast Correct the highlighted fields; under the fields Enter the minimum premium and The effective date cannot be before today | Not run
WT-B.11 | WT-B Returns and refusals, and the messages the user sees | TSU Team Head / Head | tsuhead | Opens the submitted MTR12 version 2 and clicks Return to MBS with the reason | Toast: Version 2 returned to MBS | Not run
WT-B.12 | WT-B Returns and refusals, and the messages the user sees | MBS | mbs | Opens MTR12 version 2 | The banner Returned by the validator: <reason> above the tabs; the draft can be corrected and submitted again | Not run

## Lists
Walkthrough script: Result
Not run
Passed
Failed
Blocked