## Cover
CHANGE CONTROL
Change Request Register
Operations Cashiering; goes with the FRS Operations Cashiering v3.4
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | Change requests of BRD-02 Operations Cashiering. | 2
Decision Log | Decision Log | 2
Legend
Open
Closed
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | CR
Register | Title
Register | Status v1.1 |  | Open, Withdrawn, Closed, Approved, Rejected
Register | Reference
Register | Man-days
Register | Note
Decision Log | Date
Decision Log | Item
Decision Log | Decision

## Register
Register
Change requests of BRD-02 Operations Cashiering.
CR | Title | Status v1.1 | Reference | Man-days | Note
CR-CSH-101 | Time rules of the Cashiering stages: overdue marker and reminder | Open | BR-CSH-02 | 6.5 | Not in the BRD; not delivered; BDOI approves or rejects.
CR-CSH-102 | Each user chooses an e-mail copy of the Cashiering notices | Open | FRS.CSH.10.04.03 | 3.5 | Not in the BRD; delivered; BDOI approves or asks for removal.

## Decision Log
Decision Log
Change Request Register – BIBS – BDOI Broker System
Date | Item | Decision
11 Oct 2026 | Register v1.0 | Two change requests (CR-CSH-101, CR-CSH-102) and two BRD items to deliver (D-CSH-01, D-CSH-02) after the product owner review.
16 Oct 2026 | Register v1.1 | Aligned with the FRS v3.4: D-CSH-01 and D-CSH-02 are BRD requirements stated in FRS.CSH.10.03.01 and FRS.CSH.01.03.04 and leave the register; CR-CSH-102 is delivered (for approval or removal); CR-CSH-101 is not delivered (for approval or rejection).

## Lists
Status v1.1
Open
Withdrawn
Closed
Approved
Rejected