## Cover
REQUIREMENTS COLLECTION
Business Unit Requirements Collection
Operations Cashiering; goes with the FRS Operations Cashiering v3.4
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Inputs | Open questions, dependencies and settings of the FRS Operations Cashiering v3.4. | 36
Legend
Open
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Requirements Collection, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Inputs | No.
Inputs | What BDOI provides or decides
Inputs | Owner
Inputs | Needed by
Inputs | Status |  | Open, Received, Confirmed
Inputs | Answer

## Inputs
Inputs
Open questions, dependencies and settings of the FRS Operations Cashiering v3.4.
No. | What BDOI provides or decides | Owner | Needed by | Status | Answer
Q-CSH-01 | Minimal balance: 10.00 (BRD CSHID.016, setting) or -1.00 to 1.00 (BDOI's FRS)? | Comptrollership | 30 Nov 2026 | Open
Q-CSH-02 | Reinstatement: restore a cancelled receipt, reverse an issued one, or both (setting BOTH)? | Cashiering Process Owner | 30 Nov 2026 | Open
Q-CSH-03 | Direct Credit file: identify payments already received (setting IDENTIFY) or new payments? | Cashiering Process Owner; BDO IT | 30 Nov 2026 | Open
Q-CSH-04 | Settlement OR: at Disbursement approval (setting) or at Remittance approval? | Comptrollership | 30 Nov 2026 | Open
Q-CSH-05 | AR and OR number formats and the acknowledgement certificate format registered with the BIR. | Comptrollership | 30 Nov 2026 | Open
Q-CSH-06 | List and addresses of the applications outside BIBS to link from the dashboard (BRQID.003). | BDO IT | 30 Nov 2026 | Open
Q-CSH-07 | Check Pick-up (CSHID.009 removed): remove the screen from the Cashier profiles at go-live? | Cashiering Process Owner | 30 Nov 2026 | Open
Q-CSH-08 | AR and OR Forms: MBS holds no group profile with the form permission; who maintains and approves the forms? | Product Owner, Operations | 30 Nov 2026 | Open
Q-CSH-09 | Approve or remove CR-CSH-102 (e-mail copy of the notices), which is delivered; approve or reject CR-CSH-101 (time rules). | Product Owner, Operations | 30 Nov 2026 | Open
Q-CSH-10 | Note printed on the AR: "Official receipt to be issued by the insurance company" or "Invoice to be issued by the insurance company"? | Comptrollership | 30 Nov 2026 | Open
D-CSH-01 | BDO IT gives the MFT folders and the OBPCS and PMS file schedules (ICD IF-CSH-01, IF-CSH-02). | BDOI IT | Before SIT | Open
D-CSH-02 | BDOI gives one real file of each payment channel to confirm the layouts (ICD IF-CSH-03). | BDOI | Before SIT | Open
D-CSH-03 | Comptrollership gives the GL accounts of the bank accounts and the rate of the day. | BDOI | Before SIT | Open
D-CSH-04 | Data Migration loads the open accounts, unapplied payments and receipt series in use before go-live. | BDOI | Before SIT | Open
D-CSH-05 | BDOI gives the BIR-registered formats of the AR and OR numbers and of the certificate number. | BDOI | Before SIT | Open
P-01 | Confirm the value of: CASH_POSTING_STEP_RECEIPTS: receipt kinds issued at posting (default AR,OR) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-02 | Confirm the value of: CASH_RECEIPT_NO_FORMAT: format of a new series (default {PREFIX}-{YEAR}-{BRANCH}-{SEQ}) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-03 | Confirm the value of: CASH_RECORD_NO_FORMAT: format of the record numbers (default {PREFIX}-{TYPE}-{SEQ}) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-04 | Confirm the value of: CASH_CERTIFICATE_NO_FORMAT: acknowledgement certificate number (default AC_{BRANCH}_{MMYYYY}_{SEQ}) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-05 | Confirm the value of: CASH_MAX_PAID_AMOUNT: highest paid amount of a record (default 1,000,000,000.00) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-06 | Confirm the value of: CASH_AR_REMARKS_REQUIRED: remarks required (default Y) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-07 | Confirm the value of: CASH_CHECK_DATE_RULE / CASH_CHECK_HOLDING_DAYS (default ON / 4) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-08 | Confirm the value of: CASH_CHECK_BEFORE_CASH: checks applied before cash (default Y) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-09 | Confirm the value of: CASH_PR2307_BASE: base of the PR 2307 (default PREMIUM) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-10 | Confirm the value of: Minimal balance rules: premium, excess, commission (default 10.00 / 10.00 / 10.00 (commission inactive)) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-11 | Confirm the value of: CASH_CHECK_CANCEL_REASONS: reasons allowed for a check (default Four check reasons) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-12 | Confirm the value of: CASH_REMITTED_CANCELLATION: cancellation of a remitted AR (default AR_INSURER_REFUND) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-13 | Confirm the value of: CASH_REINSTATEMENT_SCOPE: what Reinstate does (default BOTH) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-14 | Confirm the value of: CASH_DIRECT_CREDIT_MODE: Direct Credit file (default IDENTIFY) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-15 | Confirm the value of: CASH_COMMISSION_SCHEDULE_MODE (default LINE_LEVEL) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-16 | Confirm the value of: CASH_MFT_COMPANY_CODE: company of the MFT files (default (first company)) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-17 | Confirm the value of: CASH_SETTLEMENT_OR_TRIGGER: when the settlement OR is issued (default DISBURSEMENT_APPROVAL) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-18 | Confirm the value of: CASH_UNAPPLIED_MARKETING_SCOPE (default OWN_UNIT) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-19 | Confirm the value of: CASH_BANK_ACCOUNT / CASH_ON_HAND_ACCOUNT: GL accounts (default (set by Comptrollership)) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-20 | Confirm the value of: CASH_AMOUNT_WORDS_UNITS: words of the amount (default PHP Pesos/Centavos; USD US Dollars/Cents) | BDOI Product Owner, Operations | 30 Nov 2026 | Open
P-21 | Confirm the value of: Ageing threshold of pre-booked payments (alert PREBOOKED_AGEING) (default 5 days) | BDOI Product Owner, Operations | 30 Nov 2026 | Open

## Lists
Status
Open
Received
Confirmed