## Cover
USER ACCEPTANCE
Business Unit Walkthrough Users
Operations Cashiering; goes with the FRS Operations Cashiering v3.4
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.1
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | One walkthrough account per persona of the FRS Operations Cashiering v3.4; the people are fictitious. | 8
Script | The storyboards of the Process and Storyboards v3.4, step by step. | 22
Legend
Pass
Fail
Blocked
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.1. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona
Users | Walkthrough account
Users | Does
Users | Screens
Users | Sign-in
Script | Storyboard
Script | Step
Script | Who
Script | Screen
Script | Does
Script | Sees
Script | Result |  | Not run, Pass, Fail, Blocked

## Users
Users
One walkthrough account per persona of the FRS Operations Cashiering v3.4; the people are fictitious.
Persona | Walkthrough account | Does | Screens | Sign-in
Cashier | Carmela Cashier (Head Office); Benjie Branch Cashier (Cebu) | Receives payments at Head Office or a branch, creates AR and OR records and submits them, raises cancellations and reinstatements, uploads payment files, warehouses post-dated checks, gives dispositions, prints receipts. | Cashiering Dashboard, Create AR/OR, Receipts, Unapplied Payments, Payment Uploads, Batch Print, Day-End List | Issued separately by the iorta TechNXT Project Team
Cashiering Team Leader | Cecilia Cashiering Lead | Posts or returns AR, OR, cancellation and reinstatement records, approves dispositions and requests, maintains receipt series and the Cashiering settings, follows payment files. | Posting, Unapplied Payments, Incoming Requests, Receipt Series, AR and OR Forms, Cashiering Setup, Search Log | Issued separately by the iorta TechNXT Project Team
Marketing Collection | Miguel Marketing Collection | Tags BIR 2307 certificates of 2% CWT clients, follows the unapplied payments of the marketing unit and raises collector requests. | BIR 2307, Unapplied Payment List | Issued separately by the iorta TechNXT Project Team
Disbursement | Dante Disbursement | Receives the refund requests of approved dispositions and approves insurer settlements that trigger the automatic OR. | Disbursement Queue (BRD-05) | Issued separately by the iorta TechNXT Project Team
Top Management Approver | Teresa Top Management | Gives the final approval of unapplied payments reclassified to income. | Unapplied to Income, My Approvals | Issued separately by the iorta TechNXT Project Team
Comptrollership | Consuelo Comptroller | Reads the Cashiering reports and journals. | Report Centre | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | Reads receipts, their history, the search log and the reports. Changes nothing. | Receipts, Search Log, Report Centre | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | Keeps the group profiles and the lists of values. | User Access screens (BRD-11) | Issued separately by the iorta TechNXT Project Team

## Script
Script
The storyboards of the Process and Storyboards v3.4, step by step.
Storyboard | Step | Who | Screen | Does | Sees | Result
SB-01 A premium payment from the counter to the issued AR | 1 | Cashier | Create AR/OR | Opens Create AR/OR, finds the account, enters the payor, Cash, the bank account, the amount and the remarks | The account with its outstanding balance and the preview of the application | Not run
SB-01 A premium payment from the counter to the issued AR | 2 | Cashier | Cashiering Record | Saves the record and clicks Submit for Posting | Record CR-AR-<n> For Posting; the receipt number is given at posting | Not run
SB-01 A premium payment from the counter to the issued AR | 3 | Cashiering Team Leader | Posting | Opens Posting | The record among the AR/OR records for posting | Not run
SB-01 A premium payment from the counter to the issued AR | 4 | Cashiering Team Leader | Cashiering Record | Opens the record and clicks Post | The confirmation: the AR will be issued, payments applied, any excess in the Unapplied list | Not run
SB-01 A premium payment from the counter to the issued AR | 5 | Cashiering Team Leader | Cashiering Record | Confirms | AR/OR Issued with the AR number | Not run
SB-01 A premium payment from the counter to the issued AR | 6 | Cashier | Receipt | Opens the AR | The AR Issued with its application by component | Not run
SB-01 A premium payment from the counter to the issued AR | 7 | Cashier | Batch Print | Opens Batch Print | The AR in the print queue | Not run
SB-02 A service fee OR at Head Office | 1 | Cashier | Create AR/OR | Opens Create OR, chooses Service Fee, the insurer, Check with its date, the amount and the VAT | The OR record with the payment type Check and the VAT | Not run
SB-02 A service fee OR at Head Office | 2 | Cashiering Team Leader | Cashiering Record | Opens the submitted record and posts it | AR/OR Issued with the OR number of the Head Office series | Not run
SB-02 A service fee OR at Head Office | 3 | Cashier | Receipt | Opens the OR | The OR Issued with its gross amount, VAT and lines | Not run
SB-03 A Bills Payment file from upload to matching | 1 | Cashier | Payment Uploads | Chooses Bills Payment and the file | The file chosen with its type, ready to upload | Not run
SB-03 A Bills Payment file from upload to matching | 2 | Cashier | Payment Files | Opens Payment Files | The file Processed with its counts per result | Not run
SB-03 A Bills Payment file from upload to matching | 3 | Cashier | Payment Files | Opens the run report of the file | Each payment with its AR and result | Not run
SB-03 A Bills Payment file from upload to matching | 4 | Cashier | Unapplied Payments | Opens Unapplied Payments | The unmatched payment as Unbooked/Unmatched | Not run
SB-04 An excess payment refunded through Disbursement | 1 | Cashier | Unapplied Payment | Opens the unapplied payment and fills the Refund disposition | The disposition form with the payee and remarks | Not run
SB-04 An excess payment refunded through Disbursement | 2 | Cashier | Unapplied Payment | Submits the disposition | For Approval in the workflow header | Not run
SB-04 An excess payment refunded through Disbursement | 3 | Cashiering Team Leader | Unapplied Payment | Opens it from For Approval and approves | The disposition approved; the refund request sent to Disbursement | Not run
SB-04 An excess payment refunded through Disbursement | 4 | Disbursement | Disbursement Queue | Opens the Disbursement Queue | The refund request to acknowledge | Not run
SB-05 Cancellation of an issued AR | 1 | Cashier | Receipt | Opens the AR, clicks Cancel Receipt and chooses the reason | The cancellation dialog with the reason | Not run
SB-05 Cancellation of an issued AR | 2 | Cashiering Team Leader | Posting | Opens the cancellation records for posting | The cancellation record CN-AR-<n> For Posting | Not run
SB-05 Cancellation of an issued AR | 3 | Cashiering Team Leader | Cashiering Record | Opens the record and posts it | AR/OR Cancelled | Not run
SB-05 Cancellation of an issued AR | 4 | Cashier | Receipt | Opens the AR | The AR Cancelled with its cancellation record in the history | Not run

## Lists
Result
Not run
Pass
Fail
Blocked