## Cover
MIGRATION WORKBOOK
Migration Workbook BRD-13 Data Migration
BRD-13 Data Migration – objects and decisions, load templates, code maps, validation rules, data owners, cut-over plan, reconciliation sign-off and the screens, for BU review
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-13
Version | 2.0
Date | 5 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
How to review | How the business unit reviews this workbook | 7
Object catalogue | One row per legacy data object with the proposed decision and the four criteria of the BRD (BRID 1.1a) | 32
Data owners | Business owner and data steward of every object; BDOI names the people (DMQ01) | 30
Extract planning | What BDOI extracts per object, how much, how far back and by when | 26
Milestones | Milestones used in the Due and Needed-by columns | 7
File rules | Rules of every extract and control file: the delivery rules of the console workbook, then the rules of the migration | 11
Load templates | Who provides what, the steps and the templates in the order they are filled in | 29
R01 Lists of values and MIS val | R01 Lists of values and MIS values: One row per record of Lists of values and MIS values as extracted from QPS, EBIX. Key list_type, code. Sent as the file R01_template.csv (CSV, header row as below) with its control file (row count, count of … | 1
R02 Branches and invoicing bran | R02 Branches and invoicing branches: One row per record of Branches and invoicing branches as extracted from EBIX. Key branch_code. Sent as the file R02_template.csv (CSV, header row as below) with its control file (row count, count of distinct … | 1
R03 Sales organisation (units a | R03 Sales organisation (units and account officers): One row per record of Sales organisation (regions, departments, teams, unit heads, account officers) as extracted from QPS, EBIX. Key record_type, unit_code, ao_user_id. Sent as the file … | 1
R04 Insurers | R04 Insurers: One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code. Sent as the file R04_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys). | 1
R04B Insurer branches | R04B Insurer branches: One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code, branch_code. Sent as the file R04B_template.csv (CSV, header row as below) with its control file (row count, count of distinct … | 1
R05 Product lines, cover types, | R05 Product lines, cover types, products and risk codes: One row per record of Product lines, cover types, products and risk codes as extracted from QPS, EBIX. Key risk_code. Sent as the file R05_template.csv (CSV, header row as below) with its … | 1
R06 Package code map (legacy pa | R06 Package code map (legacy package to BIBS package version): One row per record of Package code map (legacy package and version to BIBS package version) as extracted from QPS (legacy packages); TSU (BIBS package versions). Key … | 1
R07 Commission rates by insurer | R07 Commission rates by insurer and product: One row per record of Commission rates by insurer and product as extracted from QPS, EBIX. Key insurer_code, risk_code, effective_from. Sent as the file R07_template.csv (CSV, header row as below) with … | 1
R08 Chart of accounts mapping | R08 Chart of accounts mapping: One row per record of Chart of accounts mapping (legacy GL account to BIBS account) as extracted from EBIX, ISYS GL. Key legacy_account_code. Sent as the file R08_template.csv (CSV, header row as below) with its … | 1
R09 Payees | R09 Payees: One row per record of Payees as extracted from EBIX, Disbursement files. Key payee_code. Sent as the file R09_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys). | 1
R11 Receipt series in use | R11 Receipt series in use: One row per record of Receipt series in use (AR and OR, ATP and next number) as extracted from EBIX. Key branch_code, kind, prefix. Sent as the file R11_template.csv (CSV, header row as below) with its control file (row … | 1
C01 Client master | C01 Client master: One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no. Sent as the file C01_template.csv (CSV, header row as below) with its control file (row count, count of … | 1
C02 Client addresses and contac | C02 Client addresses and contacts: One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no, record_type, seq_no. Sent as the file C02_template.csv (CSV, header row as below) with its … | 1
C03 Client payout accounts | C03 Client payout accounts: One row per record of Client payout accounts (for refunds) as extracted from EBIX. Key legacy_client_no, account_no. Sent as the file C03_template.csv (CSV, header row as below) with its control file (row count, row … | 1
P01 In-force policy headers | P01 In-force policy headers: One row per record of In-force policy headers as extracted from QPS, EBIX. Key legacy_policy_ref. Sent as the file P01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys … | 1
P01S Policy insurer shares | P01S Policy insurer shares: One row per record of In-force policy headers as extracted from QPS, EBIX. Key legacy_policy_ref, share_seq. Sent as the file P01S_template.csv (CSV, header row as below) with its control file (row count, row count). | 1
F01 Open legacy invoices - head | F01 Open legacy invoices - header: One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key legacy_invoice_no. Sent as the … | 1
F01C Open legacy invoices - com | F01C Open legacy invoices - components and positions: One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key … | 1
F01S Open legacy invoices - ins | F01S Open legacy invoices - insurer shares: One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key legacy_invoice_no … | 1
F02 Unapplied premium payments | F02 Unapplied premium payments (UPP): One row per record of Unapplied premium payments (UPP) with disposition in progress as extracted from EBIX, CMS. Key legacy_upp_ref. Sent as the file F02_template.csv (CSV, header row as below) with its control … | 1
F03 Open collection state | F03 Open collection state: One row per record of Open collection state (dispositions, promises to pay, installment plans, collector assignments) as extracted from CMS. Key legacy_invoice_no, record_type, seq_no. Sent as the file F03_template.csv … | 1
F04 Remittance in flight | F04 Remittance in flight: One row per record of Remittance in flight (batches not yet paid, holds, special remittances) as extracted from EBIX. Key legacy_batch_no, legacy_invoice_no. Sent as the file F04_template.csv (CSV, header row as below) … | 1
F06 PDCs, check pick-ups and re | F06 PDCs, check pick-ups and refunds in process: One row per record of PDCs in the warehouse, check pick-ups and refunds in process as extracted from EBIX. Key record_type, reference. Sent as the file F06_template.csv (CSV, header row as below) … | 1
G01 GL opening trial balance | G01 GL opening trial balance: One row per record of GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) as extracted from EBIX GL, ISYS GL. Key tb_version, branch_code, currency, legacy_account_code … | 1
P03 Renewal advices already sen | P03 Renewal advices already sent before go-live (RA-sent file): One row per record of Renewal advices already sent before go-live (RA-sent file) as extracted from Excel RA trackers of the Renewal processing team. Key legacy_policy_ref. Sent as the … | 1
H01 Archive records (closed tra | H01 Archive records (closed transactions and history): One row per record of Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) as extracted from EBIX, QPS, ISYS. Key record_type … | 1
H02 Archive documents index | H02 Archive documents index: One row per record of Legacy documents (policies, SOAs, ORs, certificates, letters) as extracted from File shares, EBIX. Key record_type, legacy_key, file_name. Sent as the file H02_template.csv (CSV, header row as … | 1
G03 FY2027 true-up - legacy adj | G03 FY2027 true-up - legacy adjustment journal lines after the freeze: One row per record of FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) as extracted from EBIX GL, ISYS GL; FY2027 … | 1
G03D FY2027 true-up - open-item | G03D FY2027 true-up - open-item detail of the lines on legacy control accounts: One row per record of FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) as extracted from EBIX GL, ISYS GL … | 1
Reference lists | Every list of allowed values used by the drop-downs (code and label) | 139
Control file | The control file sent with every data file (<data file name>.ctl.csv): one row per measure | 12
Control example | Example control file of F01C (made-up values) | 7
Control totals | Control totals per layout; the tie-out sheet of reconciliation levels L1 to L3 in each run | 116
Code maps | Code map sets of the Migration Console (BRID 3.1): one per domain, versioned and approved by the business owner | 34
Code map template | Columns of a code map version as exported and imported in Excel on the Code Maps screen (the columns source_system to remarks; illustrative rows) | 11
Validation rules | Data-quality rules applied to every staged row (Layouts and Rules, Data-Quality Rules). Thresholds: master data 0.5 percent rejected or waived; financial objects none | 54
Masking | Personal data masked when a file is received in any environment other than production | 31
Cut-over tasks | The production cut-over plan from T-30 to the close of the opening-balance adjustments | 95
Cut-over roles | Owner roles of the task plan | 16
Cut-over calendar | Relative days on the calendar of the proposed go-live (DMQ25, DMQ39) | 26
Go-no-go checkpoints | Go / no-go checkpoints and their criteria | 35
Freeze windows | Freeze windows of the legacy systems and of BIBS | 6
Rollback | Rollback procedure (only on NO-GO, before the point of no return) | 8
Communication | Communication plan of the cut-over | 12
Hypercare | Hypercare roster and exit criteria | 17
Decommissioning | Checklist per legacy system and for the legacy context (BRID 12.1; DMQ27) | 31
Reconciliation sign-off | Reconciliation and acceptance of every object with a load template: what each level proves and who signs (Handbook Part C) | 23
Open decisions | Decisions of BDOI that the migration waits for, with the date each is needed by | 42
Proposed rules | Proposed business rules and clarifications for confirmation (Handbook chapter of the same name) | 28
Screen standards | Elements and standards shared by every screen (workflow stepper and history, pills, dates, uploads, messages, notifications); described once, not repeated per screen | 9
Screen catalogue | One row per Data Migration screen | 20
Field register | Every field and list column of every screen | 190
Actions | Every action (button) of every screen | 87
Business rules | The business rules stated on the screens | 68
Messages | Every validation, error, warning and confirmation message | 216
Notifications | In-app notifications and e-mails | 10
Menu by persona | What each Data Migration persona sees in the sidebar (from the role grants) | 437
Cross-BRD contract | What Data Migration takes from and hands to the other BRDs and systems; a change is a change request | 12
Comments log | Questions, corrections and change requests raised during the review, with the answer | 50
Meeting minutes | Minutes of the review sessions | 3
Version history | Versions of this release set (a revision after review is v2.1; after sign-off, a change request) | 1
Sign-off certificate | By signing, the signatories confirm the BRD-13 Data Migration – Business Sign-off Pack v2.0: its content, screens and navigation are frozen; the screenshots use fictitious seed data; later changes go through the Change Management Register | 17
Legend
Accept | The row is correct as specified
Change requested | The row must change: describe the change in BU comment
Comment | A remark that does not change the row
Issued on 05-Oct-2026 with the Data Migration Handbook v2.0. The load template sheets are the layouts of the Migration Console column for column, each with its guide above the header row; the sheet Load templates lists them in load order. The console exports the same templates (Layouts and Rules).
Fill in the BU review columns (on a load template sheet, the BU review rows above each column) and, on the Proposed rules sheet, the BDOI decision. After sign-off the objects, decisions, layouts, screens and rules are frozen; later changes go through the Change Management Register.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Migration Workbook BRD-13 Data Migration, version 2.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
How to review | Step | Step number
How to review | How to review | Instruction
Object catalogue | Object | Data object code
Object catalogue | Data object | What the object holds
Object catalogue | Category | Reference, Client, Policy, Open item, GL, History
Object catalogue | Decision (proposed) | Migrate, Carry forward, Conditional, Archive or Excluded; the business owner confirms at gate G1 | Migrate, Carry forward, Conditional, Archive, Excluded
Object catalogue | Rationale | Why this decision
Object catalogue | Day-1 need | Needed in BIBS on the first business day
Object catalogue | Compliance need | Must be kept for compliance or audit
Object catalogue | Archive option | Read-only legacy or the BIBS archive is enough
Object catalogue | Data trust | High, Medium or Low, before cleansing
Object catalogue | Condition | Condition of a conditional object
Object catalogue | Source system | Legacy system(s) that hold the object
Object catalogue | Templates | Load templates of the object (sheets of this workbook)
Object catalogue | Where it lands in BIBS | The BIBS records the object becomes
Object catalogue | Load order | Lower loads first
Object catalogue | Loads after | Objects that must be accepted first
Object catalogue | BRD | BRD requirement
Object catalogue | Open decisions | Decisions that affect the object
Object catalogue | BU review | Business unit decision on the row | Accept, Change requested, Comment
Object catalogue | BU comment | What should change, or the comment
Object catalogue | Reviewer | Name of the BU reviewer
Object catalogue | Review date | Date of the review (dd-mmm-yyyy)
Data owners | Object | Data object code
Data owners | Data object | What the object holds
Data owners | Business owner (proposed) | Signs the decision (G1), the code maps (G2) and the acceptance (G6)
Data owners | Data steward (proposed) | Prepares the code maps, resolves data-quality issues, fixes records at source
Data owners | Named business owner | Name given by BDOI
Data owners | Named data steward | Name given by BDOI
Data owners | BU review | Business unit decision on the row | Accept, Change requested, Comment
Data owners | BU comment | What should change, or the comment
Data owners | Reviewer | Name of the BU reviewer
Data owners | Review date | Date of the review (dd-mmm-yyyy)
Extract planning | Object | Data object code
Extract planning | Data object | What the object holds
Extract planning | Volume (BDOI to fill) | Row count per source system at the last extract
Extract planning | Planning bound | Known bound from the BRDs
Extract planning | History depth | Which records and how far back
Extract planning | Delta frequency | Extracts after the first full one
Extract planning | Format | CSV or XLSX, with a control file
Extract planning | Control totals | Measures of the control file
Extract planning | Due | Milestone of the first full extract and of the final one
Extract planning | BU review | Business unit decision on the row | Accept, Change requested, Comment
Extract planning | BU comment | What should change, or the comment
Extract planning | Reviewer | Name of the BU reviewer
Extract planning | Review date | Date of the review (dd-mmm-yyyy)
Milestones | Milestone | Milestone ID
Milestones | What is due | Content of the milestone
Milestones | When | Date
File rules | Topic | Topic of the rule
File rules | Rule | What every extract file follows
File rules | BU review | Business unit decision on the row | Accept, Change requested, Comment
File rules | BU comment | What should change, or the comment
File rules | Reviewer | Name of the BU reviewer
File rules | Review date | Date of the review (dd-mmm-yyyy)
Control file | No. | Column position
Control file | Column | Column name of the control-file template
Control file | What it holds | Content
Control file | Mandatory | Y, N or C (conditional)
Control file | Format | How the value is written
Control file | Example | A made-up example
Control example | object | Object code of the data file
Control example | layout | Layout (template) code
Control example | source_system | Source system: EBIX, QPS, ISYS, CMS or EXCEL
Control example | data_file | Name of the data file the control file belongs to
Control example | as_of | Date and time the data represents
Control example | extracted_at | When the extract ran
Control example | extracted_by | BDOI IT user who ran the extract
Control example | measure | Kind of control: ROW_COUNT, HASH_TOTAL, AMOUNT_TOTAL or SHA256
Control example | column_name | Column the measure applies to
Control example | currency | Currency of an AMOUNT_TOTAL
Control example | filter | Optional filter of the measure
Control example | value | Value of the measure
Control totals | Layout | Layout code
Control totals | Object | Data object
Control totals | Measure | Control measure | ROW_COUNT, HASH_TOTAL, AMOUNT_TOTAL, SHA256
Control totals | Column | Column the measure applies to
Control totals | Currency | Per currency or not
Control totals | How it is computed | Computation
Control totals | Value from BDOI | From the control file
Control totals | Value in BIBS | Received, staged or loaded value (Reconciliation Summary)
Control totals | Difference | BDOI value minus BIBS value
Control totals | Status | Matched, Break or Explained | MATCHED, BREAK, EXPLAINED
Code maps | Code map | Code map set
Code maps | What is mapped | Legacy codes mapped
Code maps | BIBS values | The BIBS values the codes map to
Code maps | Used by layouts | Layouts whose columns use the set
Code maps | Approves (G2) | Business owner who approves each version
Code maps | Prepares | Data steward who prepares the entries
Code maps | First approved version due | Milestone
Code maps | BU review | Business unit decision on the row | Accept, Change requested, Comment
Code maps | BU comment | What should change, or the comment
Code maps | Reviewer | Name of the BU reviewer
Code maps | Review date | Date of the review (dd-mmm-yyyy)
Code map template | Code map | Code map set; the console exports one sheet per set, named after it
Code map template | source_system | Legacy system of the code | EBIX, QPS, ISYS, CMS, EXCEL
Code map template | legacy_code | Code as stored in legacy
Code map template | legacy_description | Description in legacy
Code map template | qualifier | Attribute that splits one legacy code into several BIBS values (package code map: RISK_CODE, INSURER or SI_BAND); empty otherwise
Code map template | qualifier_value | Value of the qualifier (a code, or a from-to amount band)
Code map template | action | MAP to a BIBS value, DEFAULT to the default of the set, REJECT the rows, CREATE a new BIBS value | MAP, DEFAULT, REJECT, CREATE
Code map template | target_code | BIBS value; mandatory for MAP and CREATE
Code map template | remarks | Reason for DEFAULT, REJECT or CREATE; condition of a conditional entry
Code map template | Rows using it | From the profiling of the extracts (not part of the file)
Validation rules | Rule | Rule ID shown with each issue
Validation rules | Layouts | Layouts checked
Validation rules | Columns | Columns checked
Validation rules | Kind | Kind of rule
Validation rules | Rule | What is checked
Validation rules | Severity | Error: the row is not loaded; Warning: loaded and reported
Validation rules | Message | Message of the issue; {name} is filled in
Validation rules | Fixed by | Who corrects a failing row
Validation rules | BU review | Business unit decision on the row | Accept, Change requested, Comment
Validation rules | BU comment | What should change, or the comment
Validation rules | Reviewer | Name of the BU reviewer
Validation rules | Review date | Date of the review (dd-mmm-yyyy)
Masking | Layout | Layout code
Masking | Column | Column masked
Masking | Masking outside production | How the value is replaced (the same value every time)
Masking | BU review | Business unit decision on the row | Accept, Change requested, Comment
Masking | BU comment | What should change, or the comment
Masking | Reviewer | Name of the BU reviewer
Masking | Review date | Date of the review (dd-mmm-yyyy)
Cut-over tasks | Task | Task ID
Cut-over tasks | Phase | Phase of the cut-over
Cut-over tasks | Day | Day relative to go-live (T)
Cut-over tasks | Start (PHT) | Planned start
Cut-over tasks | Task | What is done
Cut-over tasks | Owner | Accountable role (sheet Cut-over roles)
Cut-over tasks | Hours | Planned elapsed hours
Cut-over tasks | After | Tasks that must be complete first
Cut-over tasks | Verification | How completion is proven
Cut-over tasks | Checkpoint | Go / no-go checkpoint or milestone
Cut-over tasks | Assignee (name) | Named person
Cut-over tasks | Status | Task status | NOT STARTED, IN PROGRESS, DONE, BLOCKED, N/A
Cut-over tasks | BU review | Business unit decision on the row | Accept, Change requested, Comment
Cut-over tasks | BU comment | What should change, or the comment
Cut-over tasks | Reviewer | Name of the BU reviewer
Cut-over tasks | Review date | Date of the review (dd-mmm-yyyy)
Cut-over roles | Code | Owner code of the task plan
Cut-over roles | Role | Role
Cut-over roles | Organisation | Organisation
Cut-over roles | Name and phone (to fill) | Named person
Cut-over calendar | Day | Day relative to go-live (T)
Cut-over calendar | Date (T = 3-Jan-2028) | Date for the proposed go-live
Cut-over calendar | Note | Holiday or year-end note
Go-no-go checkpoints | Checkpoint | Checkpoint
Go-no-go checkpoints | When | Day and time
Go-no-go checkpoints | Decision | What is decided
Go-no-go checkpoints | No. | Criterion number
Go-no-go checkpoints | Criterion | Criterion that must be met
Go-no-go checkpoints | Measured value | Value at the decision
Go-no-go checkpoints | Met | Y or N | Y, N
Go-no-go checkpoints | BU review | Business unit decision on the row | Accept, Change requested, Comment
Go-no-go checkpoints | BU comment | What should change, or the comment
Go-no-go checkpoints | Reviewer | Name of the BU reviewer
Go-no-go checkpoints | Review date | Date of the review (dd-mmm-yyyy)
Freeze windows | Freeze | What is frozen
Freeze windows | From | Start
Freeze windows | Until | End
Freeze windows | Scope | What may not change
Freeze windows | Exception route | How an urgent change is handled
Freeze windows | BU review | Business unit decision on the row | Accept, Change requested, Comment
Freeze windows | BU comment | What should change, or the comment
Freeze windows | Reviewer | Name of the BU reviewer
Freeze windows | Review date | Date of the review (dd-mmm-yyyy)
Rollback | Step | Step
Rollback | Name | Step name
Rollback | Action | What is done
Rollback | Owner | Role
Rollback | Done at | Date and time
Rollback | BU review | Business unit decision on the row | Accept, Change requested, Comment
Rollback | BU comment | What should change, or the comment
Rollback | Reviewer | Name of the BU reviewer
Rollback | Review date | Date of the review (dd-mmm-yyyy)
Communication | No. | Item
Communication | Message | What is said
Communication | Audience | Who receives it
Communication | Channel | How
Communication | When | Day
Communication | Owner | Role
Communication | Sent on | Date
Hypercare | Function | Support function
Hypercare | Who | Team
Hypercare | Coverage | Hours
Hypercare | Escalates to | Escalation
Hypercare | Names and phone (to fill) | Named people
Decommissioning | Legacy system | System or the legacy context
Decommissioning | No. | Criterion
Decommissioning | Criterion | Criterion
Decommissioning | Evidence | Report, log or sign-off
Decommissioning | Signed by and date | Signer
Decommissioning | Status | Status | OPEN, DONE, N/A
Decommissioning | BU review | Business unit decision on the row | Accept, Change requested, Comment
Decommissioning | BU comment | What should change, or the comment
Decommissioning | Reviewer | Name of the BU reviewer
Decommissioning | Review date | Date of the review (dd-mmm-yyyy)
Reconciliation sign-off | Object | Data object
Reconciliation sign-off | Data object | What the object holds
Reconciliation sign-off | L1 counts | What the count level compares
Reconciliation sign-off | L2 amounts | What the amount level compares
Reconciliation sign-off | L3 hash totals | What the hash level compares
Reconciliation sign-off | L4 fields | What the field level compares
Reconciliation sign-off | L5 or business check | GL level of the financial objects, or the business check
Reconciliation sign-off | Business verification sample (G6) | What the data owner checks on the BIBS screens
Reconciliation sign-off | Signs G5 | Reconciliation approver (Comptrollership for financial objects)
Reconciliation sign-off | Run | Trial migration 1 to 4, dress rehearsal or production | Trial migration 1, Trial migration 2, Trial migration 3, Trial migration 4, Dress rehearsal, Production
Reconciliation sign-off | Result | Matched, or explained with approval | Matched, Explained, Break
Reconciliation sign-off | G5 signed by and date | Reconciliation approver
Reconciliation sign-off | G6 signed by and date | Data owner and Data Migration Lead
Reconciliation sign-off | BU review | Business unit decision on the row | Accept, Change requested, Comment
Reconciliation sign-off | BU comment | What should change, or the comment
Reconciliation sign-off | Reviewer | Name of the BU reviewer
Reconciliation sign-off | Review date | Date of the review (dd-mmm-yyyy)
Open decisions | ID | Question (DMQnn) or register ID (DCR-nnn)
Open decisions | Register | Item of the BRD discrepancy and clarification register
Open decisions | Topic | Subject
Open decisions | Decision needed | What BDOI decides
Open decisions | What waits for it | Objects, gates or dates that wait for the answer
Open decisions | Needed by | Milestone and date
Open decisions | BDOI owner | Who answers
Open decisions | Status | Open, Partly answered, Answered, or Recommended (answered with a recommendation that BDOI still confirms) | OPEN, PARTIAL, ANSWERED, RECOMMENDED
Open decisions | Answer | BDOI answer and date
Proposed rules | Ref | Proposal reference
Proposed rules | Topic | Subject
Proposed rules | Proposed rule | The rule proposed by the project team
Proposed rules | Reason | Why it is proposed
Proposed rules | Decision requested | What BDOI is asked to decide
Proposed rules | Open decisions | Decisions it answers
Proposed rules | Needed by | Date
Proposed rules | BDOI decision | Agree, Agree with change, Disagree or Need more information | Agree, Agree with change, Disagree, Need more information
Proposed rules | Change or comment | The change asked for, or the comment
Proposed rules | Decided by | Name and unit
Proposed rules | Decided on | Date of the decision (dd-mmm-yyyy)
Screen standards | No. | Row number
Screen standards | Element | Element shared by the Data Migration screens
Screen standards | What the user sees and does | Behaviour of the element on every screen
Screen standards | BU review | Business unit decision on the row | Accept, Change requested, Comment
Screen standards | BU comment | What should change, or the comment
Screen standards | Reviewer | Name of the BU reviewer
Screen standards | Review date | Date of the review (dd-mmm-yyyy)
Screen catalogue | Screen ID | Screen identifier used in the Data Migration Handbook
Screen catalogue | Area | Process area
Screen catalogue | Screen | Screen name as in the menu or page title
Screen catalogue | Menu path | Where the screen is in the sidebar (› separates the levels)
Screen catalogue | Personas | Roles that can open the screen (from the role grants)
Screen catalogue | Permission | Permission(s) that open the screen
Screen catalogue | Purpose | What the screen is for
Screen catalogue | Other entry points | How the user reaches it from other screens
Screen catalogue | Expected outcome | What is achieved on the screen
Screen catalogue | FRs | Functional requirements of the Data Migration Handbook
Screen catalogue | Test cases | Test cases of the test plan on this screen
Screen catalogue | Screenshots | Screenshots of the screen in the Data Migration Handbook
Screen catalogue | Fields | Number of fields and columns
Screen catalogue | Actions | Number of actions
Screen catalogue | BU review | Business unit decision on the row | Accept, Change requested, Comment
Screen catalogue | BU comment | What should change, or the comment
Screen catalogue | Reviewer | Name of the BU reviewer
Screen catalogue | Review date | Date of the review (dd-mmm-yyyy)
Field register | Screen ID | Screen identifier
Field register | Screen | Screen name
Field register | No. | Field number = callout number on the screenshot
Field register | Section | Card, tab, step or dialog of the field
Field register | Field | Label as shown on screen
Field register | Type | Text, Date, Drop-down, Check box, Column, ...
Field register | Length / format | Length, format, allowed values
Field register | Mandatory | Y, N or the condition that makes it mandatory
Field register | Source / list | List of values, master or record the value comes from
Field register | Default | Value proposed by the system
Field register | Editable in | Statuses in which the field can be changed
Field register | Validation rule | Check applied
Field register | Message when it fails | Message shown, exactly as on screen
Field register | BU review | Business unit decision on the row | Accept, Change requested, Comment
Field register | BU comment | What should change, or the comment
Field register | Reviewer | Name of the BU reviewer
Field register | Review date | Date of the review (dd-mmm-yyyy)
Actions | Screen ID | Screen identifier
Actions | Screen | Screen name
Actions | Button | Button or link as shown
Actions | Who | Permission or role that sees it
Actions | Enabled when | Condition for the button to be offered
Actions | What happens | Effect of the action
Actions | Resulting status | Status after the action
Actions | Notification | Notice or e-mail sent
Business rules | Rule ID | Rule identifier in this workbook
Business rules | Screen ID | Screen where the rule applies
Business rules | Screen | Screen name
Business rules | Business rule | The proposed business rule
Business rules | FRs | Functional requirements that state the rule
Business rules | BU review | Business unit decision on the row | Accept, Change requested, Comment
Business rules | BU comment | What should change, or the comment
Business rules | Reviewer | Name of the BU reviewer
Business rules | Review date | Date of the review (dd-mmm-yyyy)
Messages | Message ID | Message identifier in this set
Messages | Where it appears | Screen or dialog that shows it
Messages | Shown by | Screen (checked as you type), Server (checked on save or action) or Upload row
Messages | Code (not shown) | Identifies the message for the project team and support; not shown on the screen
Messages | Message | Exact text; <name> is filled in by the system
Messages | Type | Validation, Error, Warning, Confirmation or Information | Validation, Error, Warning, Confirmation, Information
Messages | What the user does | The correction or next step
Messages | BU review | Business unit decision on the row | Accept, Change requested, Comment
Messages | BU comment | What should change, or the comment
Messages | Reviewer | Name of the BU reviewer
Messages | Review date | Date of the review (dd-mmm-yyyy)
Notifications | ID | Notification identifier
Notifications | Channel | In-app, E-mail or Alert inbox
Notifications | Trigger | What causes it
Notifications | Recipient | Who receives it
Notifications | Template and text | Subject / title and body
Notifications | Content | Attachments and data
Notifications | Screen | Where it is raised or opened
Notifications | FRs | Functional requirements
Menu by persona | Persona | Persona name
Menu by persona | Group | Sidebar group
Menu by persona | Section | Sidebar section
Menu by persona | Screen | Menu entry
Menu by persona | BRD | BRD that owns the screen
Menu by persona | Data Migration | Yes for a screen of this set
Cross-BRD contract | ID | Contract line
Cross-BRD contract | BRD or system | Other BRD or external system
Cross-BRD contract | Direction | In: taken by Data Migration; Out: handed over
Cross-BRD contract | What | Data or function exchanged
Cross-BRD contract | When and how | Trigger and mechanism
Cross-BRD contract | Owner of the data | Who maintains it
Cross-BRD contract | Screens | Data Migration screens concerned
Cross-BRD contract | FRs | Functional requirements
Comments log | ID | Comment identifier
Comments log | Raised by | Name and unit of the reviewer
Comments log | Date | Date raised
Comments log | Page / screen | Data Migration Handbook page or section, screen ID or workbook row
Comments log | Template | Load template (sheet) the question is about, if any
Comments log | Column | Column of the template, if any
Comments log | Type | Clarification, Correction or Change request | Clarification, Correction, Change request
Comments log | Comment | The question, the correction or the change asked for
Comments log | Response | Answer of the project team; for a change request, its register number
Comments log | Status | Open, Answered or Closed | Open, Answered, Closed
Comments log | Closed on | Date closed
Meeting minutes | Date | Date of the session
Meeting minutes | Session | Walkthrough, Q&A or sign-off meeting
Meeting minutes | Planned | Planned date and length
Meeting minutes | Attendees | Names and units
Meeting minutes | Discussion | Points discussed
Meeting minutes | Decisions | Decisions taken
Meeting minutes | Actions | Actions, with the comment IDs
Meeting minutes | Owner | Owner of the actions
Meeting minutes | Due date | Due date of the actions
Version history | Version | Version of the release set
Version history | Date | Date of issue
Version history | Author | Prepared by
Version history | Change | What changed; for a revision, the comment IDs answered
Version history | Rows changed | Sheets and rows changed
Sign-off certificate | Capacity | Prepared by, Input provided by, Reviewed by or Approved by, as on the BRD approval sheet
Sign-off certificate | Role | Signatory role
Sign-off certificate | Organisation | Organisation
Sign-off certificate | Confirms | What the signatory confirms by signing
Sign-off certificate | On the BRD approval sheet | Where the role signs the BRD (BRD-13 approval pages p.15-16 (draft V0.01, not yet signed))
Sign-off certificate | Name | Name of the signatory
Sign-off certificate | Decision | Approved, Approved with comments or Not approved | Approved, Approved with comments, Not approved
Sign-off certificate | Comments | Conditions of the approval
Sign-off certificate | Signature | Signature
Sign-off certificate | Date | Date of the decision

## How to review
How to review
How the business unit reviews this workbook
Step | How to review
1 | Read the Handbook part of your role with the screenshots, or walk through the Migration Console on the SIT environment during the sessions of the Start Here guide.
2 | On the sheets of your objects (Object catalogue, Data owners, Extract planning, Code maps, Validation rules, Reconciliation sign-off) and on the screen sheets, set BU review to Accept, Change requested or Comment for each row you review, and write the change in BU comment. On a load template sheet the BU review and BU comment rows sit above each column.
3 | On the Proposed rules sheet, record the BDOI decision (Agree, Agree with change, Disagree, Need more information), the change asked for, who decided and the date.
4 | Put your name in Reviewer and the date in Review date. Leave the other columns unchanged.
5 | The sheet Load templates lists the load templates in load order with a link to each. A load template sheet is the layout of the Migration Console column for column, with the guide of each column (Mandatory, Format, Allowed values, What to enter, the check when loaded) directly above the header row; the console exports the same templates (Layouts and Rules, Load Templates Workbook).
6 | Return the workbook to the iorta TechNXT project team by the date of the Start Here guide. Every Change requested row is answered in the Comments log before sign-off.
7 | Questions and change requests go to the Comments log, with the load template and the column when they concern one; the project team answers each one there. On the Sign-off certificate sheet, each signatory records the decision and the date. The screenshots use fictitious seed data.

## Object catalogue
Object catalogue
One row per legacy data object with the proposed decision and the four criteria of the BRD (BRID 1.1a)
Object | Data object | Category | Decision (proposed) | Rationale | Day-1 need | Compliance need | Archive option | Data trust | Condition | Source system | Templates | Where it lands in BIBS | Load order | Loads after | BRD | Open decisions | BU review | BU comment | Reviewer | Review date
R01 | Lists of values and MIS values | Reference | Migrate | Every coded field of clients, policies and open items needs its BIBS value on Day 1 (BRID 3.1). Legacy values are mapped to BIBS values; missing values are created through the LOV master with maker-checker. | Yes | No | No | Medium |  | QPS, EBIX | R01 | Lists of Values (maker-checker); MIS field catalogue | 1 | - | BRID 3.1 | DMQ08
R02 | Branches and invoicing branches | Reference | Migrate | Branch codes are mapped only; BIBS branches are configured by Comptrollership before the load. | Yes | No | No | Medium |  | EBIX | R02 | Branches (check only, code map BRANCH) | 1 | - | BRID 3.1 | DMQ08
R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Reference | Migrate | Clients, policies and open items carry the AO and unit; MIS reporting and Collections assignment need them on Day 1. | Yes | No | No | Medium |  | QPS, EBIX | R03 | Sales organisation: sales units and account officers | 2 | R02 | BRID 3.1 | DMQ08
R04 | Insurers and insurer branches | Reference | Migrate | Every open invoice, header and remittance position is owed to or by an insurer. | Yes | No | No | Medium |  | QPS, EBIX | R04, R04B | Insurers and insurer branches (insurer and party records) | 2 | - | BRID 3.1 | DMQ08
R05 | Product lines, cover types, products and risk codes | Reference | Migrate | The risk code decides the premium components, taxes and commission of every open invoice and header. | Yes | No | No | Medium |  | QPS, EBIX | R05 | Product catalogue: product lines, cover types and products | 3 | - | BRID 3.1 | DMQ08
R06 | Package code map (legacy package and version to BIBS package version) | Reference | Migrate | Packages are remapped at sanitation in Renewal, not at migration intake (DMQ36, answered 26-Sep-2026). The migration loads the package code map as reference data only; the Renewal package check uses it and sends unmapped packages to the Exception bucket, worked by the Renewal processing team. The BIBS packages themselves are maintained by TSU in Product Maintenance (BRD-3) and are not migrated. | Yes | No | No | Medium |  | QPS (legacy packages); TSU (BIBS package versions) | R06 | Renewal package map, used by the package check of the Renewal sanitation | 3 | - | BRID 3.1, 12.1 | DMQ08, DMQ36
R07 | Commission rates by insurer and product | Reference | Migrate | Endorsements and renewals of legacy policies compute commission from the rate table. | Yes | No | No | Medium |  | QPS, EBIX | R07 | Commission rates of the product catalogue | 3 | R04 | BRID 3.1 | DMQ30
R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Reference | Migrate | The GL opening trial balance (G01) is loaded through this map; legacy control accounts are mapped to Migration Clearing. | Yes | No | No | Medium |  | EBIX, ISYS GL | R08 | GL account code map to the BIBS chart of accounts (chart configured by Comptrollership) | 3 | - | BRID 5.1-8.1; AQ01 | DMQ18
R09 | Payees | Reference | Conditional | Payees are loaded through the payee migration upload of Disbursement; in scope if BDOI confirms (AQ11, DMQ30). | Yes | No | No | Medium | Loaded through the payee registration of Disbursement if BDOI confirms (DMQ30). | EBIX, Disbursement files | R09 | Payees (party and payee records, loaded by the payee migration) | 4 | - | AQ11 | DMQ30
R10 | Users and roles | Reference | Excluded | Users are created through User Access requests and approvals (BRD-11); legacy user IDs are only mapped (user code map) so that the AO, handler and collector fields resolve. | No | No | Yes | Medium |  | QPS, EBIX | - | None (code map USER only) | - | - | BRD-11 | DMQ30
R11 | Receipt series in use (AR and OR, ATP and next number) | Reference | Carry forward | Receipts issued in BIBS after go-live must continue the BIR-authorised series without gap or overlap. | Yes | No | No | Medium |  | EBIX | R11 | Receipt series of Cashiering | 4 | R02 | BRID 6.1 | DMQ14
C01 | Client master (individual and corporate) | Client | Migrate | Marketing, Operations and Renewal must find and use clients on Day 1 without re-encoding (BRID 2.1); clients are deduplicated before load. Umbrella BRD p.43 asks for clients "2020 to present" and daily client batches (DCR-173). | Yes | No | No | Medium |  | QPS, EBIX, CMS | C01, C02 | Client master, registered as migrated clients | 5 | R01,R02,R03 | BRID 2.1 | DMQ04, DMQ05, DMQ06, DCR-173
C03 | Client payout accounts (for refunds) | Client | Migrate | Refunds of legacy UPP (BRID 5.4) need the client's payout account. | Yes | No | No | Medium |  | EBIX | C03 | Client payout accounts | 6 | C01 | BRID 5.4 | DMQ17
C04 | KYC documents and IDs | Client | Archive | Documents stay retrievable for audit; BIBS keeps the KYC status and review date on the client (DMQ07 may change this to MIGRATE). | No | Yes | Yes | Medium |  | QPS, file shares | H02 | BIBS archive (legacy document attachments) | 16 | - | BRID 11.1 | DMQ07, DMQ24
C05 | Screening results and risk ratings | Client | Excluded | One full screening run after the client load gives current results (BRD-10); legacy results are archived with the client history. | No | No | Yes | Medium |  | Excel, Compliance | - | None (a full periodic screening run after C01) | - | - | BRID 2.1 | DMQ06
P01 | In-force policy headers | Policy | Conditional | Needed to locate active coverage, to endorse legacy invoices (BRID 9) and to renew in BIBS (BRID 12.1); the scope condition is decided by BDOI (DMQ09). Whatever it is, every policy expiring from T to 31-May-2028 and every renewal term booked in legacy that starts on or after T are in scope, because the go-live renewal extraction works only from the headers (DMQ37). The legacy package is kept as given; it is remapped at Renewal sanitation (DMQ36). | Yes | No | No | Medium | Needed to locate active coverage, to endorse legacy invoices and to renew in BIBS; the scope condition is decided by BDOI. Whatever it is, every policy expiring from T to 31-May-2028 and every renewal term booked in legacy that starts on or after T are in scope, because the go-live renewal extraction works only from the headers. The legacy package is kept as given; it is remapped at Renewal sanitation. | QPS, EBIX | P01, P01S | Accounts, imported as legacy policy headers | 7 | C01,R04,R05 | BRID 4.1 | DMQ09, DMQ22, DMQ36, DMQ37
P02 | Expired policies and policy history | Policy | Archive | History is not converted (BRD p.3); kept for inquiry. | No | Yes | Yes | Medium |  | QPS, EBIX | H01 | BIBS archive, record type POLICY | 16 | - | BRID 11.1 | DMQ24
P03 | Renewal advices already sent before go-live (RA-sent file) | Policy | Migrate | The January-May 2028 expiries are processed in BIBS after go-live from a go-live extraction of the migrated headers (DMQ37, answered 26-Sep-2026); no renewal candidate is carried. The RAs already sent by hand before go-live, kept in the Excel trackers of the Renewal processing team (DMQ38), are loaded as a small reference file so that BIBS does not send them again. | Yes | No | No | Medium |  | Excel RA trackers of the Renewal processing team | P03 | Renewal Advices already sent, given to Renewal with the policy header in the go-live extraction | 13 | P01 | BRID 12.1 | DMQ26, DMQ37, DMQ38
P04 | Submitted-policy masterlists | Policy | Conditional | Loaded through the masterlist upload of Submitted Policies if BDOI confirms (SP SQ16, DMQ30); the layout is issued with that module. | Yes | No | No | Medium | Loaded through the policy registration of Submitted Policies if BDOI confirms (DMQ30); the layout is issued with the Submitted Policies set. | Excel | - | Submitted Policies masterlist (migration upload) | 14 | - | BRIDSP-33 | DMQ30
P05 | Employee Benefits programmes | Policy | Conditional | Loaded through the programme upload of Employee Benefits if BDOI confirms (DMQ30); the layout is issued with that module. | Yes | No | No | Medium | Loaded through the programme set-up of Employee Benefits if BDOI confirms (DMQ30); the layout is issued with the Employee Benefits set. | EBIX | - | Employee Benefits programmes (programme load) | 14 | - | BRD-8 | DMQ30
F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Open item | Carry forward | Receivables and payables open at cutover must be collected, remitted, reversed and endorsed in BIBS (BRID 5.1-10.1). | Yes | No | No | Medium |  | EBIX, QPS | F01, F01S, F01C | Operations invoice ledger (invoices, insurer shares, components) with an opening accounting entry on the legacy sub-ledgers | 8 | C01,R04,R05,P01 | BRID 5.2, 6.1-6.4, 7.1, 7.2, 8.1, 9.1-9.3, 10.1 | DMQ10, DMQ11, DMQ12, DMQ13, DMQ35
F02 | Unapplied premium payments (UPP) with disposition in progress | Open item | Carry forward | Unapplied cash must not be lost after cutover (BRID 5.1); it is applied, refunded or reclassified in BIBS. | Yes | No | No | Medium |  | EBIX, CMS | F02 | Cashiering unapplied payments, as migrated items, with an opening accounting entry | 9 | C01 | BRID 5.1-5.5, 6.3, 6.4 | DMQ14, DMQ15, DMQ16
F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | Open item | Carry forward | Collectors continue their follow-up without re-keying (CQ07); only the open state is carried, history is archived (DMQ34). | Yes | No | No | Medium |  | CMS | F03 | Legacy follow-up of the Collections worklist items | 10 | F01 | CQ07 | DMQ34
F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Open item | Conditional | Proposal - complete legacy batches before the freeze; carry only holds and special remittances that cannot complete (DMQ21). | Yes | No | No | Medium | Proposal - complete legacy batches before the freeze; carry only holds and special remittances that cannot complete. | EBIX | F04 | Remittance holds and special remittances | 11 | F01 | BRID 8.1 | DMQ21
F05 | DP billing in process and DP commission receivable | Open item | Carry forward | Carried inside F01 (dp_flag and the COMMISSION components of direct-payment invoices); no separate file. | Yes | No | No | Medium |  | EBIX, Operations files | - | Part of F01; Commission DP list | 8 | - | BRID 7.1 | DMQ19
F06 | PDCs in the warehouse, check pick-ups and refunds in process | Open item | Conditional | Proposal - carry PDCs in the warehouse; complete pick-ups and refunds in legacy before the freeze where possible (DMQ33). | Yes | No | No | Medium | Proposal - carry PDCs in the warehouse; complete pick-ups and refunds in legacy before the freeze where possible. | EBIX | F06 | Cashiering PDC warehouse and check pick-up | 11 | C01 | BRID 5.1 | DMQ33
F07 | Open claims | Open item | Conditional | Loaded through the Claims migration if BDOI decides (CLQ14, DMQ30); closed claims are archived. | Yes | No | No | Medium | Loaded through the claim registration of Claims if BDOI decides (DMQ30); closed claims are archived. | EBIX, ISYS | - | Claims, through the claims migration | 14 | - | CLQ14 | DMQ30
G01 | GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) | GL | Migrate | At the year-end go-live (DMQ39, option A recommended) the BIBS GL opens from the preliminary December 2027 TB - balance-sheet accounts only, the FY2027 net result to retained earnings, legacy control-account lines to Migration Clearing, which the F01 and F02 opening entries clear to 0.00. The opening is provisional; at each true-up the legacy TB after the adjustments is sent again as reconciliation input (G03). | Yes | No | No | Medium |  | EBIX GL, ISYS GL | G01 | General ledger journals of type OPENING (value date 1-Jan-2028); at a true-up, reconciliation input only | 12 | R08,F01,F02 | BRID 1.1b, 5.1-8.1 | DMQ18, DMQ25, DMQ35, DMQ39
G02 | GL history (journals and balances before cutover) | History | Archive | Kept for audit; BIBS starts from the opening trial balance. | No | Yes | Yes | Medium |  | EBIX GL, ISYS GL | H01 | BIBS archive, record type GL journal | 16 | - | BRID 11.1 | DMQ24
G03 | FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) | GL | Migrate | The legacy GL stays open after the freeze only for the FY2027 closing and audit adjustments of Comptrollership (DMQ39). Each adjustment reaches BIBS as a controlled opening-balance adjustment journal in the opening period - after the legacy year-end close and after the audited FS - with approvals, cut-off controls and a reconciliation to the legacy TB. | Yes | No | No | Medium |  | EBIX GL, ISYS GL; FY2027 adjustment register of Comptrollership | G03, G03D | General ledger journals of type OPENING (reference MIG-TU-<n>); opening adjustments of the legacy open items and unapplied payments | 17 | G01 | BRID 1.1b, 5.1-8.1 | DMQ18, DMQ39
H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | History | Archive | History stays in read-only legacy or the BIBS archive with logged access (BRID 11.1). | No | Yes | Yes | Medium |  | EBIX, QPS, ISYS | H01 | BIBS archive (Legacy Inquiry) | 16 | - | BRID 11.1 | DMQ24, DMQ27
H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | History | Archive | Documents are kept with their archive record and a checksum. | No | Yes | Yes | Medium |  | File shares, EBIX | H02 | Legacy documents attached to the archive records | 16 | - | BRID 11.1 | DMQ24

## Data owners
Data owners
Business owner and data steward of every object; BDOI names the people (DMQ01)
Object | Data object | Business owner (proposed) | Data steward (proposed) | Named business owner | Named data steward | BU review | BU comment | Reviewer | Review date
R01 | Lists of values and MIS values | Product Owner, Marketing Business System (MBS) | MBS data steward (to name)
R02 | Branches and invoicing branches | Head, Comptrollership | Comptrollership data steward (to name)
R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Heads, Retail and Corporate Marketing | Marketing data steward (to name)
R04 | Insurers and insurer branches | Head, Operations | Operations data steward (to name)
R05 | Product lines, cover types, products and risk codes | Product Owner, MBS | MBS data steward (to name)
R06 | Package code map (legacy package and version to BIBS package version) | Product Owner, MBS (approves); TSU (prepares) | TSU (to name)
R07 | Commission rates by insurer and product | Head, Operations | Operations data steward (to name)
R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Head, Comptrollership; Product Owner FRBS and ACSL | Comptrollership data steward (to name)
R09 | Payees | Product Owner, Comptrollership - Disbursement | Disbursement data steward (to name)
R11 | Receipt series in use (AR and OR, ATP and next number) | Operations - Financial Transactions | Cashiering data steward (to name)
C01 | Client master (individual and corporate) | Product Owner, MBS; Heads, Retail and Corporate Marketing | Marketing data steward (to name)
C03 | Client payout accounts (for refunds) | Product Owner, Comptrollership - Disbursement | Disbursement data steward (to name)
C04 | KYC documents and IDs | Compliance | Compliance data steward (to name)
P01 | In-force policy headers | Head, Operations | Operations data steward (to name)
P02 | Expired policies and policy history | Head, Operations | Operations data steward (to name)
P03 | Renewal advices already sent before go-live (RA-sent file) | Head of the Renewal processing team | Renewal processing team - makers (corrections) and checkers (resubmission approval)
P04 | Submitted-policy masterlists | CBG and Non-CBG Marketing (Submitted Policies) | Submitted Policies data steward (to name)
P05 | Employee Benefits programmes | Head, Employee Benefits | EB data steward (to name)
F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Operations - Financial Transactions; Head, Comptrollership | Operations data steward (to name)
F02 | Unapplied premium payments (UPP) with disposition in progress | Operations - Financial Transactions | Cashiering data steward (to name)
F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | Head, Operations (Collections) | Collections data steward (to name)
F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Operations - Remittance | Remittance data steward (to name)
F05 | DP billing in process and DP commission receivable | Operations - Financial Transactions | Operations data steward (to name)
F06 | PDCs in the warehouse, check pick-ups and refunds in process | Operations - Cashiering | Cashiering data steward (to name)
F07 | Open claims | Unit Head, Claims, RI and TU | Claims data steward (to name)
G01 | GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) | Head, Comptrollership | Comptrollership data steward (to name)
G02 | GL history (journals and balances before cutover) | Head, Comptrollership | Comptrollership data steward (to name)
G03 | FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) | Head, Comptrollership | Comptrollership GL lead (prepares each true-up)
H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | Audit / Compliance; legacy system owners | Compliance data steward (to name)
H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | Audit / Compliance | Compliance data steward (to name)

## Extract planning
Extract planning
What BDOI extracts per object, how much, how far back and by when
Object | Data object | Volume (BDOI to fill) | Planning bound | History depth | Delta frequency | Format | Control totals | Due | BU review | BU comment | Reviewer | Review date
R01 | Lists of values and MIS values |  | A few thousand values | Current values and values used by any migrated record | None after the map freeze (T-7 days); changes by change request and a new map version | CSV | Row count; count of distinct (list_type, code) | M3 (29 Jan 2027)
R02 | Branches and invoicing branches |  | Under 100 | Current | None | CSV | Row count | M3 (29 Jan 2027)
R03 | Sales organisation (regions, departments, teams, unit heads, account officers) |  | About 600 AOs (485 Marketing users, BRD-3) | Current, plus inactive AOs referenced by open items | Weekly until the freeze | CSV | Row count per record type | M3 (29 Jan 2027)
R04 | Insurers and insurer branches |  | Under 100 insurers | Active insurers, and inactive insurers with open items | None | CSV | Row count per file | M3 (29 Jan 2027)
R05 | Product lines, cover types, products and risk codes |  | A few hundred codes | Current, plus codes used by in-force policies and open items | None | CSV | Row count | M3 (29 Jan 2027)
R06 | Package code map (legacy package and version to BIBS package version) |  | Under 200 legacy packages | Legacy packages of in-force policies | New map versions until the map freeze (T-7 days) | XLSX or CSV | Row count; count of distinct (legacy_package_code, legacy_package_version) | M5 (18 Jun 2027); final at T-7
R07 | Commission rates by insurer and product |  | Insurers x products | Rates effective at cutover and later | None | CSV | Row count | M3 (29 Jan 2027)
R08 | Chart of accounts mapping (legacy GL account to BIBS account) |  | A few thousand accounts | Current chart | None | XLSX or CSV | Row count | M3 (29 Jan 2027)
R09 | Payees |  | To supply | Active payees | None | CSV | Row count | M3 (29 Jan 2027)
R11 | Receipt series in use (AR and OR, ATP and next number) |  | One per branch and kind | Series in use at the freeze | Final values at the freeze (T-3) | CSV | Row count | M3 (29 Jan 2027); final at T-3
C01 | Client master (individual and corporate) |  | Loaders sized for 1,000,000 rows | Clients from 2020 to present (umbrella p.43); filter per DMQ05 | Daily new and changed clients from T-14 days until the freeze | CSV | Row count; count of distinct legacy_client_no | M3 (29 Jan 2027); deltas daily from T-14 days
C03 | Client payout accounts (for refunds) |  | To supply | Active accounts | None | CSV | Row count | M3 (29 Jan 2027)
C04 | KYC documents and IDs |  | To supply | Per retention | None | CSV index plus files | Row count; SHA-256 per file | Before decommissioning
P01 | In-force policy headers |  | 250,000-310,000 renewable accounts a year (umbrella p.44-45) | Policies in force at T (DMQ09); at least every expiry from T to 31-May-2028 and every booked renewal term starting on or after T | Single load after the freeze | CSV | Row count; sum of sum_insured and gross_premium per currency; count of distinct legacy_policy_ref | M3 (29 Jan 2027); final at T-2
P02 | Expired policies and policy history |  | To supply | Per retention (5 years online, 15 years archive, umbrella p.45) | None | CSV | Row count and hash total per record type | Before decommissioning
P03 | Renewal advices already sent before go-live (RA-sent file) |  | Small - at most the January-May 2028 expiries with an RA sent before go-live | RAs sent before go-live for expiries from T to 31-May-2028 | One file in every trial migration; final file with the RAs sent up to T-5; resubmissions of corrected rows until T-1 12:00 | XLSX template (P03_template.xlsx) or CSV | Row count; count of distinct legacy_policy_ref; sum of proposed_premium per currency | M4 (9 Apr 2027) (Trial migration 1); final at T-5
F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares |  | Loaders sized for 500,000 rows | Every invoice with any open component at T (DMQ10) | Single load after the freeze | CSV with control file | Row count per file; sums per component, bucket and currency; count of distinct legacy_invoice_no | M3 (29 Jan 2027); final at T-2
F02 | Unapplied premium payments (UPP) with disposition in progress |  | To supply | Every UPP item with a balance at T | Single load after the freeze | CSV with control file | Row count; sums of amount and balance per currency; count of distinct legacy_upp_ref | M3 (29 Jan 2027); final at T-2
F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) |  | 1,200 dispositions a day (umbrella p.42) | Open items only | Single load after the freeze | CSV | Row count; sum of promise_amount per currency | M3 (29 Jan 2027); final at T-2
F04 | Remittance in flight (batches not yet paid, holds, special remittances) |  | To supply | Open at T | Single load after the freeze | CSV | Row count; sum of amount per currency | M3 (29 Jan 2027); final at T-2
F06 | PDCs in the warehouse, check pick-ups and refunds in process |  | To supply | Open at T | Single load after the freeze | CSV | Row count; sum of amount per currency and record type | M3 (29 Jan 2027); final at T-2
G01 | GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) |  | A few thousand lines | Preliminary December 2027 TB after the last legacy EOD; the legacy TB at each true-up | Single load after the freeze; one TB per true-up (about 18-Jan-2028 and after the audited FS) | XLSX or CSV with control file | Row count; total debit and total credit per branch and currency (must be equal) | M3 (29 Jan 2027); final at T-2; at each true-up
G02 | GL history (journals and balances before cutover) |  | To supply | Per retention | None | CSV | Row count and debit / credit totals per period | Before decommissioning
G03 | FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) |  | Tens to a few hundred journal lines per true-up | Legacy journals posted after the freeze, dated in FY2027 | One set per true-up (true-up 1 about 18-Jan-2028; final after the audited FS, about March-April 2028) | XLSX or CSV with control file | Row count; debit and credit totals per branch and currency; count of distinct legacy_journal_no | T+16 (true-up 1); T+92 (final)
H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) |  | To supply | Per retention (5 years online, 15 years archive, umbrella p.45) | None | CSV | Row count, amount totals and hash total per record type | Before decommissioning
H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) |  | To supply | Per retention | None | CSV index plus files | Row count; SHA-256 per file | Before decommissioning

## Milestones
Milestones
Milestones used in the Due and Needed-by columns
Milestone | What is due | When
M0 | Business sign-off set issued to BDOI (release set v2.0, with the BDOI answers to DMQ36-DMQ39) | 5 Oct 2026
M1 | Scope-shaping decisions (answers that change the migration functions) | 16 Oct 2026
M2 | Owners, stewards, keys and remaining business rules; object decisions signed (gate G1); layouts frozen, version 1 (G2 part 1) - end of requirements and mapping | 30 Oct 2026
M3 | First full extracts in the templates, with control files and volumes (profiling, performance sizing) | 29 Jan 2027
M4 | Extracts for Trial migration 1 (SIT migration starts); reference data and clients first | 9 Apr 2027
M5 | Code maps approved for Trial migration 2 (G2), including the package code map | 18 Jun 2027
M6 | Cut-over date and window, fallback and decommissioning criteria agreed; Comptrollership confirms the year-end option A (DMQ39) | 1 Oct 2027

## File rules
File rules
Rules of every extract and control file: the delivery rules of the console workbook, then the rules of the migration
Topic | Rule | BU review | BU comment | Reviewer | Review date
File name | <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.xlsx or .csv, for example F01C_EBIX_20271231_01.xlsx: the layout code, the source system, the as-of date and the sequence of the day
One file per | Layout, source system and extract; an object with several layouts sends one file per layout with the same as-of date
Excel | The load template of the console, uploaded as it is: its guide rows and example row are skipped and the sheet of the layout is read; a workbook of several layouts is uploaded once per layout, named after that layout. A plain workbook has the header in row 1 of its first sheet, no merged cells, no formulas
CSV | For large extracts: UTF-8 without byte order mark, comma separator, double quotes around values that hold a comma, a quote or a line break, one header row with the column names exactly as in the template
Values | Dates as Excel dates or yyyy-MM-dd; timestamps yyyy-MM-dd HH:mm:ss (Philippine time); amounts with a dot decimal, 2 decimals, no thousands separator, minus sign for negatives; currency ISO 4217; codes exactly as stored in the legacy system; blank means no value
Control file | <data file name>.ctl.xlsx or .ctl.csv in the control layout: the row count, the hash total of the key column, the total of each amount column per currency and the SHA-256 of the data file, one row per measure
Delivery | Upload the data file and its control file together on the Extracts screen of the Migration Console; never by e-mail
Checks | A file whose checksum, header, row count, amount totals or hash total does not agree with its control file is rejected with the reason; nothing of it is loaded
Personal data | Production extracts are loaded only in production. Every other environment receives masked data: names, addresses, TIN, ID, account and phone numbers, e-mail addresses and birth dates are masked when the file is received. Staged rows and files are deleted within 5 days of the batch sign-off
Layout changes | A layout is frozen at gate G2. A file whose header does not match the layout in force is rejected. A change of layout is a new layout version agreed with the Data Migration Lead
Load template workbook of P03 | The Renewal processing team may send the RA-sent file in the load template workbook of layout P03 exported by the Migration Console (the template sheet with the guide rows Mandatory, Format, Allowed values and What to enter directly above the header row, and the Lists sheet with the allowed values); the CSV template is also accepted

## Load templates
Load templates – start here
The extract layouts in force, in load order, each with its sheet
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Release set |  | BRD-13 Data Migration (Drop 0, Setup and Data Migration)
Version and date |  | Version 2.0, 5 October 2026
Owner |  | Program Manager, Business Project Services (Data Migration)
Due |  | Per object: the Due of the index (milestones on the sheet Milestones)
How to fill in this workbook
1 | The index below lists the load templates in load order: reference data first, then clients, policies, open items, the general ledger and the archive. Each template has a sheet of its own, named as in the workbook the Migration Console exports (Layouts and Rules); the extracts are sent as CSV files with their control file (sheets File rules and Control file).
2 | On a template sheet, the header block says what one row holds, who provides it, when it is due and how it is loaded; above each column the guide gives Mandatory, Format (type and length), Allowed values or the code map, What to enter and the check applied when the file is loaded. The header row is the header row of the file; * marks a mandatory column.
3 | Review each column: set BU review (Accept, Change requested or Comment) and write the change in BU comment, in the two rows above the guide; record your name and the date in Reviewed by and Review date.
4 | The grey example row is made up. Test rows may be entered under it for the review: the drop-downs offer the allowed values (sheet Reference lists) and a mandatory cell left empty turns red.
5 | Set the Status of each template in the index. Questions go to the Comments log with the template and the column.
Load templates in load order
Step | Layout | Object | Content | Provided by | Due | Decision | Loads after | Columns | Mandatory | Key | File | Rows entered | Mandatory cells missing | Status | Open
1 | R01 | R01 | Lists of values and MIS values | MBS data steward (to name); approved by Product Owner, Marketing Business System (MBS); extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | - | 8 | 4 | list_type, code | R01_template.csv |  |  | Not started | Open →
2 | R02 | R02 | Branches and invoicing branches | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | - | 5 | 4 | branch_code | R02_template.csv |  |  | Not started | Open →
3 | R03 | R03 | Sales organisation (units and account officers) | Marketing data steward (to name); approved by Heads, Retail and Corporate Marketing; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | R02 | 11 | 3 | record_type, unit_code, ao_user_id | R03_template.csv |  |  | Not started | Open →
4 | R04 | R04 | Insurers | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | - | 10 | 3 | insurer_code | R04_template.csv |  |  | Not started | Open →
5 | R04B | R04 | Insurer branches | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | R04 | 7 | 4 | insurer_code, branch_code | R04B_template.csv |  |  | Not started | Open →
6 | R05 | R05 | Product lines, cover types, products and risk codes | MBS data steward (to name); approved by Product Owner, MBS; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | - | 9 | 4 | risk_code | R05_template.csv |  |  | Not started | Open →
7 | R06 | R06 | Package code map (legacy package to BIBS package version) | TSU (to name); approved by Product Owner, MBS (approves); TSU (prepares); extracted by BDOI IT | M5 (18 Jun 2027); final at T-7 | Migrate | - | 8 | 4 | legacy_package_code, legacy_package_version, qualifier, qualifier_value | R06_template.csv |  |  | Not started | Open →
8 | R07 | R07 | Commission rates by insurer and product | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | R04, R04B | 5 | 4 | insurer_code, risk_code, effective_from | R07_template.csv |  |  | Not started | Open →
9 | R08 | R08 | Chart of accounts mapping | Comptrollership data steward (to name); approved by Head, Comptrollership; Product Owner FRBS and ACSL; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | - | 8 | 4 | legacy_account_code | R08_template.csv |  |  | Not started | Open →
10 | R09 | R09 | Payees | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT | M3 (29 Jan 2027) | Conditional | - | 11 | 6 | payee_code | R09_template.csv |  |  | Not started | Open →
11 | R11 | R11 | Receipt series in use | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT | M3 (29 Jan 2027); final at T-3 | Carry forward | R02 | 8 | 7 | branch_code, kind, prefix | R11_template.csv |  |  | Not started | Open →
12 | C01 | C01 | Client master | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT | M3 (29 Jan 2027); deltas daily from T-14 days | Migrate | R01, R02, R03 | 36 | 6 | legacy_client_no | C01_template.csv |  |  | Not started | Open →
13 | C02 | C01 | Client addresses and contacts | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT | M3 (29 Jan 2027); deltas daily from T-14 days | Migrate | C01, R01, R02, R03 | 13 | 4 | legacy_client_no, record_type, seq_no | C02_template.csv |  |  | Not started | Open →
14 | C03 | C03 | Client payout accounts | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT | M3 (29 Jan 2027) | Migrate | C01, C02 | 6 | 4 | legacy_client_no, account_no | C03_template.csv |  |  | Not started | Open →
15 | P01 | P01 | In-force policy headers | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Conditional | C01, C02, R04, R04B, R05 | 31 | 20 | legacy_policy_ref | P01_template.csv |  |  | Not started | Open →
16 | P01S | P01 | Policy insurer shares | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Conditional | P01, C01, C02, R04, R04B, R05 | 6 | 5 | legacy_policy_ref, share_seq | P01S_template.csv |  |  | Not started | Open →
17 | F01 | F01 | Open legacy invoices - header | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Carry forward | C01, C02, R04, R04B, R05, P01, P01S | 38 | 24 | legacy_invoice_no | F01_template.csv |  |  | Not started | Open →
18 | F01C | F01 | Open legacy invoices - components and positions | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Carry forward | F01, C01, C02, R04, R04B, R05, P01, P01S | 8 | 8 | legacy_invoice_no, component | F01C_template.csv |  |  | Not started | Open →
19 | F01S | F01 | Open legacy invoices - insurer shares | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Carry forward | F01, C01, C02, R04, R04B, R05, P01, P01S | 5 | 5 | legacy_invoice_no, share_seq | F01S_template.csv |  |  | Not started | Open →
20 | F02 | F02 | Unapplied premium payments (UPP) | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Carry forward | C01, C02 | 21 | 11 | legacy_upp_ref | F02_template.csv |  |  | Not started | Open →
21 | F03 | F03 | Open collection state | Collections data steward (to name); approved by Head, Operations (Collections); extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Carry forward | F01, F01S, F01C | 12 | 3 | legacy_invoice_no, record_type, seq_no | F03_template.csv |  |  | Not started | Open →
22 | F04 | F04 | Remittance in flight | Remittance data steward (to name); approved by Operations - Remittance; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Conditional | F01, F01S, F01C | 10 | 6 | legacy_batch_no, legacy_invoice_no | F04_template.csv |  |  | Not started | Open →
23 | F06 | F06 | PDCs, check pick-ups and refunds in process | Cashiering data steward (to name); approved by Operations - Cashiering; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2 | Conditional | C01, C02 | 14 | 6 | record_type, reference | F06_template.csv |  |  | Not started | Open →
24 | G01 | G01 | GL opening trial balance | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT | M3 (29 Jan 2027); final at T-2; at each true-up | Migrate | R08, F01, F01S, F01C, F02 | 11 | 9 | tb_version, branch_code, currency, legacy_account_code, cost_center | G01_template.csv |  |  | Not started | Open →
25 | P03 | P03 | Renewal advices already sent before go-live (RA-sent file) | Renewal processing team - makers (corrections) and checkers (resubmission approval); approved by Head of the Renewal processing team; extracted by BDOI IT | M4 (9 Apr 2027) (Trial migration 1); final at T-5 | Migrate | P01, P01S | 13 | 6 | legacy_policy_ref | P03_template.csv |  |  | Not started | Open →
26 | H01 | H01 | Archive records (closed transactions and history) | Compliance data steward (to name); approved by Audit / Compliance; legacy system owners; extracted by BDOI IT | Before decommissioning | Archive | - | 15 | 3 | record_type, legacy_key | H01_template.csv |  |  | Not started | Open →
27 | H02 | H02 | Archive documents index | Compliance data steward (to name); approved by Audit / Compliance; extracted by BDOI IT | Before decommissioning | Archive | - | 8 | 6 | record_type, legacy_key, file_name | H02_template.csv |  |  | Not started | Open →
28 | G03 | G03 | FY2027 true-up - legacy adjustment journal lines after the freeze | Comptrollership GL lead (prepares each true-up); approved by Head, Comptrollership; extracted by BDOI IT | T+16 (true-up 1); T+92 (final) | Migrate | G01 | 19 | 17 | legacy_journal_no, line_no | G03_template.csv |  |  | Not started | Open →
29 | G03D | G03 | FY2027 true-up - open-item detail of the lines on legacy control accounts | Comptrollership GL lead (prepares each true-up); approved by Head, Comptrollership; extracted by BDOI IT | T+16 (true-up 1); T+92 (final) | Migrate | G03, G01 | 10 | 10 | legacy_journal_no, line_no, item_ref, component | G03D_template.csv |  |  | Not started | Open →
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## R01 Lists of values and MIS val
R01 Lists of values and MIS values | [7 empty] | Step 1 of 29
← Back to Load templates | Step 1 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Lists of values and MIS values as extracted from QPS, EBIX. Key list_type, code. Sent as the file R01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | MBS data steward (to name); approved by Product Owner, Marketing Business System (MBS); extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R01 (Migrate), layout R01 version 1, through the Migration Console; lands in: Lists of Values (maker-checker); MIS field catalogue
Source | QPS, EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Known list name | Unique per list_type | Not blank | Parent exists in the file | Y or N | Valid date | Not before effective_from | 0 or more
Mandatory | Yes | Yes | Yes | No | Yes | No | No | No
Format | Code, up to 40; Upper case | Code, up to 40; As stored in legacy | Text, up to 200; Free text | Code, up to 40 | Flag, up to 1; Y or N | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Integer, up to 9; Digits
Allowed values | Legacy list names; one code map set LOV:<list> or MIS:<field> per list | Free entry, up to 40 characters | Free entry, up to 200 characters | Codes of the same file | Y or N | Free entry | Free entry | A whole number
What to enter | Legacy name of the list (for example MARKET_SEGMENT, BUSINESS_ORIGIN, CUSTOMER_SEGMENT, REGION, AREA, DEPARTMENT, ACCOUNT_TYPE, ID_TYPE, NATIONALITY) | Legacy value code | Legacy value description | Code of the parent value for hierarchical lists (area under region) | Value in use in legacy | First day the value is valid | Last day the value is valid | Number of legacy records that use the value (helps the mapping)
Row | list_type * | code * | description * | parent_code | active_flag * | effective_from | effective_to | used_count
Example – overwrite or delete | MARKET_SEGMENT | CBG | Consumer Banking Group | NCR | Y | 2020-01-01 |  | 1520
Note on B19: list_type Legacy name of the list (for example MARKET_SEGMENT, BUSINESS_ORIGIN, CUSTOMER_SEGMENT, REGION, AREA, DEPARTMENT, ACCOUNT_TYPE, ID_TYPE, NATIONALITY) Mandatory: Yes Format: Code, up to 40; Upper case Allowed values: Legacy list names; one code map set LOV:<list> or MIS:<field> per list Example: MARKET_SEGMENT
Note on C19: code Legacy value code Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: CBG
Note on D19: description Legacy value description Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Consumer Banking Group
Note on E19: parent_code Code of the parent value for hierarchical lists (area under region) Mandatory: No Format: Code, up to 40 Allowed values: Codes of the same file Example: NCR
Note on F19: active_flag Value in use in legacy Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on G19: effective_from First day the value is valid Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2020-01-01
Note on H19: effective_to Last day the value is valid Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry
Note on I19: used_count Number of legacy records that use the value (helps the mapping) Mandatory: No Format: Integer, up to 9; Digits Allowed values: A whole number Example: 1520

## R02 Branches and invoicing bran
R02 Branches and invoicing branches | [5 empty] | Step 2 of 29
← Back to Load templates | Step 2 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Branches and invoicing branches as extracted from EBIX. Key branch_code. Sent as the file R02_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R02 (Migrate), layout R02 version 1, through the Migration Console; lands in: Branches (check only, code map BRANCH)
Source | EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique | Not blank | Y or N | - | Y or N
Mandatory | Yes | Yes | Yes | No | Yes
Format | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Flag, up to 1; Y or N | Text, up to 80; Free text | Flag, up to 1; Y or N
Allowed values | Free entry, up to 20 characters | Free entry, up to 120 characters | Y or N | Free entry, up to 80 characters | Y or N
What to enter | Legacy branch code | Branch name | Branch issues invoices and receipts | City of the branch | Branch active in legacy
Row | branch_code * | branch_name * | invoicing_branch_flag * | city | active_flag *
Example – overwrite or delete | MKT01 | Makati Head Office | Y | Makati City | Y
Note on B19: branch_code Legacy branch code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MKT01
Note on C19: branch_name Branch name Mandatory: Yes Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Makati Head Office
Note on D19: invoicing_branch_flag Branch issues invoices and receipts Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on E19: city City of the branch Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Makati City
Note on F19: active_flag Branch active in legacy Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## R03 Sales organisation (units a
R03 Sales organisation (units and account officers) | [10 empty] | Step 3 of 29
← Back to Load templates | Step 3 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per record of Sales organisation (regions, departments, teams, unit heads, account officers) as extracted from QPS, EBIX. Key record_type, unit_code, ao_user_id. Sent as the file R03_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Marketing data steward (to name); approved by Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R03 (Migrate), layout R03 version 1, through the Migration Console; lands in: Sales organisation: sales units and account officers
Source | QPS, EBIX
Depends on | R02 Branches and invoicing branches →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list | Exists as a TEAM row for AO rows | Mandatory for REGION, DEPARTMENT, TEAM | Mandatory for DEPARTMENT and TEAM; parent exists | Mapped in USER | Mapped | Mandatory for AO rows; mapped in USER | Unique | Mandatory for AO rows | Mapped | Y or N
Mandatory | Yes | Yes | Conditional: Mandatory for REGION, DEPARTMENT, TEAM | Conditional: Mandatory for DEPARTMENT and TEAM; parent exists | No | No | Conditional: Mandatory for AO rows; mapped in USER | No | Conditional: Mandatory for AO rows | No | Yes
Format | Code, up to 12; Upper case | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Code, up to 20; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Code, up to 20; As stored in legacy | Flag, up to 1; Y or N
Allowed values | REGION, DEPARTMENT, TEAM, AO (list R03 record_type) | Free entry, up to 20 characters | Free entry, up to 120 characters | unit_code values of the file | The legacy code; mapped by the code map USER (sheet Code maps) | The legacy code; mapped by the code map COST_CENTER (sheet Code maps) | The legacy code; mapped by the code map USER (sheet Code maps) | The legacy code; mapped by the code map AO (sheet Code maps) | Free entry, up to 120 characters | The legacy code; mapped by the code map BRANCH (sheet Code maps) | Y or N
What to enter | Kind of row | Legacy code of the unit (for an AO row, the team of the AO) | Unit name | Code of the parent unit (department of a team, region of a department) | Legacy user ID of the unit head | Cost centre of the unit | Legacy user ID of the account officer | Legacy AO code if different from the user ID | AO full name | Branch of the unit or AO | Unit or AO active
Row | record_type * | unit_code * | unit_name | parent_unit_code | unit_head_user_id | cost_center | ao_user_id | ao_code | ao_name | branch_code | active_flag *
Example – overwrite or delete | TEAM | T-RET-07 | Retail Team 7 | D-RET | jdelacruz | 4100 | mreyes | AO0457 | Maria Reyes | MKT01 | Y
Note on B19: record_type Kind of row Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: REGION, DEPARTMENT, TEAM, AO (list R03 record_type) Example: TEAM
Note on C19: unit_code Legacy code of the unit (for an AO row, the team of the AO) Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: T-RET-07
Note on D19: unit_name Unit name Mandatory: Conditional: Mandatory for REGION, DEPARTMENT, TEAM Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Retail Team 7
Note on E19: parent_unit_code Code of the parent unit (department of a team, region of a department) Mandatory: Conditional: Mandatory for DEPARTMENT and TEAM; parent exists Format: Code, up to 20; As stored in legacy Allowed values: unit_code values of the file Example: D-RET
Note on F19: unit_head_user_id Legacy user ID of the unit head Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: jdelacruz
Note on G19: cost_center Cost centre of the unit Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (sheet Code maps) Example: 4100
Note on H19: ao_user_id Legacy user ID of the account officer Mandatory: Conditional: Mandatory for AO rows; mapped in USER Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: mreyes
Note on I19: ao_code Legacy AO code if different from the user ID Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map AO (sheet Code maps) Example: AO0457
Note on J19: ao_name AO full name Mandatory: Conditional: Mandatory for AO rows Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Maria Reyes
Note on K19: branch_code Branch of the unit or AO Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on L19: active_flag Unit or AO active Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## R04 Insurers
R04 Insurers | [9 empty] | Step 4 of 29
← Back to Load templates | Step 4 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code. Sent as the file R04_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R04 (Migrate), layout R04 version 1, through the Migration Console; lands in: Insurers and insurer branches (insurer and party records)
Source | QPS, EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique | Not blank | - | 9 to 12 digits | - | - | Valid date | Valid e-mail addresses | 0 to 365 | Mapped
Mandatory | Yes | Yes | No | No | No | No | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Text, up to 200; Free text | Text, up to 40; Free text | Text, up to 20; 000-000-000-000 | Text, up to 300; Free text | Text, up to 40; Free text | Date, up to 10; yyyy-MM-dd | Text, up to 500; name@domain;name@domain | Integer, up to 3; Digits | Code, up to 20; As stored in legacy
Allowed values | Free entry, up to 30 characters | Free entry, up to 200 characters | Free entry, up to 40 characters | Free entry, up to 20 characters | Free entry, up to 300 characters | Free entry, up to 40 characters | Free entry | Free entry, up to 500 characters | A whole number | The legacy code; mapped by the code map STATUS:INSURER (sheet Code maps)
What to enter | Legacy insurer code | Registered name | Short name | Tax identification number | Registered address | Insurance Commission accreditation number | End of accreditation | E-mail address(es) for placement, separated by semicolons | Credit term in days | Insurer status in legacy
Row | insurer_code * | insurer_name * | short_name | tin | address | accreditation_no | accredited_until | placement_email | default_credit_days | status *
Example – overwrite or delete | MAL | Malayan Insurance Co., Inc. | Malayan | 000-123-456-000 | 500 Quintin Paredes St., Manila | IC-2025-0123 | 2028-06-30 | placement@insurer.example | 60 | ACTIVE
Note on B19: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: MAL
Note on C19: insurer_name Registered name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Malayan Insurance Co., Inc.
Note on D19: short_name Short name Mandatory: No Format: Text, up to 40; Free text Allowed values: Free entry, up to 40 characters Example: Malayan
Note on E19: tin Tax identification number Mandatory: No Format: Text, up to 20; 000-000-000-000 Allowed values: Free entry, up to 20 characters Example: 000-123-456-000
Note on F19: address Registered address Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 500 Quintin Paredes St., Manila
Note on G19: accreditation_no Insurance Commission accreditation number Mandatory: No Format: Text, up to 40; Free text Allowed values: Free entry, up to 40 characters Example: IC-2025-0123
Note on H19: accredited_until End of accreditation Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-06-30
Note on I19: placement_email E-mail address(es) for placement, separated by semicolons Mandatory: No Format: Text, up to 500; name@domain;name@domain Allowed values: Free entry, up to 500 characters Example: placement@insurer.example
Note on J19: default_credit_days Credit term in days Mandatory: No Format: Integer, up to 3; Digits Allowed values: A whole number Example: 60
Note on K19: status Insurer status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:INSURER (sheet Code maps) Example: ACTIVE

## R04B Insurer branches
R04B Insurer branches | [6 empty] | Step 5 of 29
← Back to Load templates | Step 5 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code, branch_code. Sent as the file R04B_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R04 (Migrate), layout R04B version 1, through the Migration Console; lands in: Insurers and insurer branches (insurer and party records)
Source | QPS, EBIX
Depends on | R04 Insurers →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in R04 | Unique per insurer | Not blank | - | 0 to 5 | Valid e-mail | Mapped
Mandatory | Yes | Yes | Yes | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Text, up to 80; Free text | Decimal, up to 9,4; Dot decimal | Text, up to 120; name@domain | Code, up to 20; As stored in legacy
Allowed values | The legacy code; mapped by the code map INSURER (sheet Code maps) | Free entry, up to 20 characters | Free entry, up to 120 characters | Free entry, up to 80 characters | A number | Free entry, up to 120 characters | The legacy code; mapped by the code map STATUS:INSURER (sheet Code maps)
What to enter | Legacy insurer code | Legacy insurer branch code | Branch name | City | Local government tax rate of the branch location, in percent | Branch placement e-mail | Branch status
Row | insurer_code * | branch_code * | branch_name * | city | lgt_rate | placement_email | status *
Example – overwrite or delete | MAL | MAL-CEB | Malayan Cebu | Cebu City | 0.75 | cebu@insurer.example | ACTIVE
Note on B19: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on C19: branch_code Legacy insurer branch code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MAL-CEB
Note on D19: branch_name Branch name Mandatory: Yes Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Malayan Cebu
Note on E19: city City Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Cebu City
Note on F19: lgt_rate Local government tax rate of the branch location, in percent Mandatory: No Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 0.75
Note on G19: placement_email Branch placement e-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: cebu@insurer.example
Note on H19: status Branch status Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:INSURER (sheet Code maps) Example: ACTIVE

## R05 Product lines, cover types,
R05 Product lines, cover types, products and risk codes | [8 empty] | Step 6 of 29
← Back to Load templates | Step 6 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | One row per record of Product lines, cover types, products and risk codes as extracted from QPS, EBIX. Key risk_code. Sent as the file R05_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | MBS data steward (to name); approved by Product Owner, MBS; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R05 (Migrate), layout R05 version 1, through the Migration Console; lands in: Product catalogue: product lines, cover types and products
Source | QPS, EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Mapped | - | Mapped | Unique | Not blank | Y or N | Each mapped | Mapped | 0 or more
Mandatory | Yes | No | No | Yes | Yes | No | No | Yes | No
Format | Code, up to 30; As stored in legacy | Text, up to 120; Free text | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 200; Free text | Flag, up to 1; Y or N | Text, up to 300; CODE;CODE | Code, up to 20; As stored in legacy | Integer, up to 9; Digits
Allowed values | The legacy code; mapped by the code map LINE (sheet Code maps) | Free entry, up to 120 characters | The legacy code; mapped by the code map COVER_TYPE (sheet Code maps) | Free entry, up to 20 characters | Free entry, up to 200 characters | Y or N | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) | The legacy code; mapped by the code map STATUS:PRODUCT (sheet Code maps) | A whole number
What to enter | Legacy line of business | Line name | Legacy cover type | Legacy risk code / product code | Product / risk name | Sold as a package | Segments that may use the product, separated by semicolons | Status in legacy | Open invoices and in-force policies using the code (helps the mapping)
Row | line_code * | line_name | cover_type_code | risk_code * | risk_name * | packaged_flag | market_segments | status * | open_item_count
Example – overwrite or delete | MOTOR | Motor Car | COMP | MC-PC-COMP | Private Car Own Damage and Theft | N | CBG;RETAIL | ACTIVE | 4211
Note on B19: line_code Legacy line of business Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map LINE (sheet Code maps) Example: MOTOR
Note on C19: line_name Line name Mandatory: No Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Motor Car
Note on D19: cover_type_code Legacy cover type Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map COVER_TYPE (sheet Code maps) Example: COMP
Note on E19: risk_code Legacy risk code / product code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MC-PC-COMP
Note on F19: risk_name Product / risk name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Private Car Own Damage and Theft
Note on G19: packaged_flag Sold as a package Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on H19: market_segments Segments that may use the product, separated by semicolons Mandatory: No Format: Text, up to 300; CODE;CODE Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) Example: CBG;RETAIL
Note on I19: status Status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:PRODUCT (sheet Code maps) Example: ACTIVE
Note on J19: open_item_count Open invoices and in-force policies using the code (helps the mapping) Mandatory: No Format: Integer, up to 9; Digits Allowed values: A whole number Example: 4211

## R06 Package code map (legacy pa
R06 Package code map (legacy package to BIBS package version) | [7 empty] | Step 7 of 29
← Back to Load templates | Step 7 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Package code map (legacy package and version to BIBS package version) as extracted from QPS (legacy packages); TSU (BIBS package versions). Key legacy_package_code, legacy_package_version, qualifier, qualifier_value. Sent as the file R06_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | TSU (to name); approved by Product Owner, MBS (approves); TSU (prepares); extracted by BDOI IT
Due | M5 (18 Jun 2027); final at T-7
How it is loaded | Data migration object R06 (Migrate), layout R06 version 1, through the Migration Console; lands in: Renewal package map, used by the package check of the Renewal sanitation
Source | QPS (legacy packages); TSU (BIBS package versions)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in the legacy package list | 0 or more | Not blank | In the list; one qualifier per entry | Mandatory with a qualifier; bands of one legacy package do not overlap | In the list | Mandatory for MAP; active in Product Maintenance | -
Mandatory | Yes | Yes | Yes | No | Conditional: Mandatory with a qualifier; bands of one legacy package do not overlap | Yes | Conditional: Mandatory for MAP; active in Product Maintenance | No
Format | Code, up to 20; As stored in legacy | Integer, up to 4; Digits | Text, up to 200; Free text | Code, up to 20; Upper case | Text, up to 60; Code, or from-to amounts with a dot decimal | Code, up to 6; Upper case | Code, up to 40; As in BIBS | Text, up to 250; Free text
Allowed values | Free entry, up to 20 characters | A whole number | Free entry, up to 200 characters | RISK_CODE, INSURER, SI_BAND (list R06 qualifier) | Free entry, up to 60 characters | MAP, REJECT (list R06 action) | Active package versions in Product Maintenance | Free entry, up to 250 characters
What to enter | Legacy package code | Version of the legacy package | Package name in legacy | Attribute that splits one legacy package into several BIBS packages | Value of the qualifier (risk code, insurer code, or sum-insured band as from-to) | MAP to a BIBS package version, or REJECT (no BIBS package) | BIBS package version maintained by TSU | Why the entry maps as it does
Row | legacy_package_code * | legacy_package_version * | legacy_package_name * | qualifier | qualifier_value | action * | bibs_package_version | remarks
Example – overwrite or delete | PKG-MC-PRIV | 3 | Private Car Package 2027 | SI_BAND | 0.00-2000000.00 | MAP | MC-PRIVATE-STD v1 | Sum insured up to 2,000,000.00
Note on B19: legacy_package_code Legacy package code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: PKG-MC-PRIV
Note on C19: legacy_package_version Version of the legacy package Mandatory: Yes Format: Integer, up to 4; Digits Allowed values: A whole number Example: 3
Note on D19: legacy_package_name Package name in legacy Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Private Car Package 2027
Note on E19: qualifier Attribute that splits one legacy package into several BIBS packages Mandatory: No Format: Code, up to 20; Upper case Allowed values: RISK_CODE, INSURER, SI_BAND (list R06 qualifier) Example: SI_BAND
Note on F19: qualifier_value Value of the qualifier (risk code, insurer code, or sum-insured band as from-to) Mandatory: Conditional: Mandatory with a qualifier; bands of one legacy package do not overlap Format: Text, up to 60; Code, or from-to amounts with a dot decimal Allowed values: Free entry, up to 60 characters Example: 0.00-2000000.00
Note on G19: action MAP to a BIBS package version, or REJECT (no BIBS package) Mandatory: Yes Format: Code, up to 6; Upper case Allowed values: MAP, REJECT (list R06 action) Example: MAP
Note on H19: bibs_package_version BIBS package version maintained by TSU Mandatory: Conditional: Mandatory for MAP; active in Product Maintenance Format: Code, up to 40; As in BIBS Allowed values: Active package versions in Product Maintenance Example: MC-PRIVATE-STD v1
Note on I19: remarks Why the entry maps as it does Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Sum insured up to 2,000,000.00

## R07 Commission rates by insurer
R07 Commission rates by insurer and product | [5 empty] | Step 8 of 29
← Back to Load templates | Step 8 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Commission rates by insurer and product as extracted from QPS, EBIX. Key insurer_code, risk_code, effective_from. Sent as the file R07_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R07 (Migrate), layout R07 version 1, through the Migration Console; lands in: Commission rates of the product catalogue
Source | QPS, EBIX
Depends on | R04 Insurers → |  | R04B Insurer branches →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Mapped | Mapped | 0 to 100 | Valid date | No overlap for the same insurer and product
Mandatory | Yes | Yes | Yes | Yes | No
Format | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Decimal, up to 9,4; Dot decimal | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd
Allowed values | The legacy code; mapped by the code map INSURER (sheet Code maps) | The legacy code; mapped by the code map PRODUCT (sheet Code maps) | A number | Free entry | Free entry
What to enter | Legacy insurer code | Legacy product / risk code | Commission rate in percent | Rate valid from | Rate valid to
Row | insurer_code * | risk_code * | rate_pct * | effective_from * | effective_to
Example – overwrite or delete | MAL | MC-PC-COMP | 20 | 2026-01-01
Note on B19: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on C19: risk_code Legacy product / risk code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map PRODUCT (sheet Code maps) Example: MC-PC-COMP
Note on D19: rate_pct Commission rate in percent Mandatory: Yes Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 20.0000
Note on E19: effective_from Rate valid from Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2026-01-01
Note on F19: effective_to Rate valid to Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry

## R08 Chart of accounts mapping
R08 Chart of accounts mapping | [7 empty] | Step 9 of 29
← Back to Load templates | Step 9 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Chart of accounts mapping (legacy GL account to BIBS account) as extracted from EBIX, ISYS GL. Key legacy_account_code. Sent as the file R08_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; Product Owner FRBS and ACSL; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R08 (Migrate), layout R08 version 1, through the Migration Console; lands in: GL account code map to the BIBS chart of accounts (chart configured by Comptrollership)
Source | EBIX, ISYS GL
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique | Not blank | In the list | In the list | In the list | Mandatory when legacy_control_type is NONE; exists and active in BIBS | Y or N | -
Mandatory | Yes | Yes | Yes | Yes | No | Conditional: Mandatory when legacy_control_type is NONE; exists and active in BIBS | No | No
Format | Code, up to 30; As stored in legacy | Text, up to 200; Free text | Code, up to 12; Upper case | Code, up to 2; Upper case | Code, up to 20; Upper case | Code, up to 30; As in the BIBS chart | Flag, up to 1; Y or N | Text, up to 300; Free text
Allowed values | Free entry, up to 30 characters | Free entry, up to 200 characters | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list R08 account_type) | DR, CR (list R08 normal_balance) | List R08 legacy_control_type: 8 values, see Reference lists | Account codes of the BIBS chart of accounts | Y or N | Free entry, up to 300 characters
What to enter | Legacy GL account code | Legacy account name | Account type | Normal balance side | Marks the legacy control accounts whose balance F01 or F02 carries in detail | BIBS account the legacy account maps to (filled by Comptrollership) | Balances are kept per branch | Mapping remarks
Row | legacy_account_code * | legacy_account_name * | account_type * | normal_balance * | legacy_control_type | bibs_account_code | branch_specific_flag | remarks
Example – overwrite or delete | 1101-02 | Cash in Bank - BDO Makati | ASSET | DR | NONE | X102.03 (illustrative code, not in use) | Y | Merged with 1201-01
Note on B19: legacy_account_code Legacy GL account code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: 1101-02
Note on C19: legacy_account_name Legacy account name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Cash in Bank - BDO Makati
Note on D19: account_type Account type Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list R08 account_type) Example: ASSET
Note on E19: normal_balance Normal balance side Mandatory: Yes Format: Code, up to 2; Upper case Allowed values: DR, CR (list R08 normal_balance) Example: DR
Note on F19: legacy_control_type Marks the legacy control accounts whose balance F01 or F02 carries in detail Mandatory: No Format: Code, up to 20; Upper case Allowed values: List R08 legacy_control_type: 8 values, see Reference lists Example: NONE
Note on G19: bibs_account_code BIBS account the legacy account maps to (filled by Comptrollership) Mandatory: Conditional: Mandatory when legacy_control_type is NONE; exists and active in BIBS Format: Code, up to 30; As in the BIBS chart Allowed values: Account codes of the BIBS chart of accounts Example: X102.03 (illustrative code, not in use)
Note on H19: branch_specific_flag Balances are kept per branch Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on I19: remarks Mapping remarks Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: Merged with 1201-01

## R09 Payees
R09 Payees | [10 empty] | Step 10 of 29
← Back to Load templates | Step 10 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per record of Payees as extracted from EBIX, Disbursement files. Key payee_code. Sent as the file R09_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object R09 (Conditional), layout R09 version 1, through the Migration Console; lands in: Payees (party and payee records, loaded by the payee migration)
Source | EBIX, Disbursement files
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique | In the list | Not blank | - | Valid e-mail | 9 to 12 digits | One of allowed_modes | CTA | Valid code | Mapped | Mandatory for CTA
Mandatory | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes | No | Conditional: Mandatory for CTA
Format | Code, up to 30; As stored in legacy | Code, up to 20; Upper case | Text, up to 250; Free text | Text, up to 300; Free text | Text, up to 120; name@domain | Text, up to 20; 000-000-000-000 | Code, up to 20; Upper case | Text, up to 100; MODE\ | Code, up to 3; Upper case | Text, up to 120; Free text | Text, up to 40; Digits
Allowed values | Free entry, up to 30 characters | LOV PAYEE_CLASS | Free entry, up to 250 characters | Free entry, up to 300 characters | Free entry, up to 120 characters | Free entry, up to 20 characters | List R09 default_mode: 7 values, see Reference lists | Same list as default_mode | ISO 4217 | The legacy code; mapped by the code map BANK (sheet Code maps) | Free entry, up to 40 characters
What to enter | Legacy payee code | Payee class | Payee name | Address | E-mail for payment advices | Tax identification number | Default payment mode | Allowed payment modes separated by a vertical bar | Currency | Bank of the payee account | Payee account number
Row | payee_code * | payee_class * | name * | address | email | tin | default_mode * | allowed_modes * | currency * | bank | account_no
Example – overwrite or delete | SUP-0001 | SUPPLIER | Acme Office Supply | Makati City | ap@acme.example | 123-456-789-000 | CHECK | MODE | PHP | BDO Unibank | 001234567890
Note on B19: payee_code Legacy payee code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: SUP-0001
Note on C19: payee_class Payee class Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: LOV PAYEE_CLASS Example: SUPPLIER
Note on D19: name Payee name Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Acme Office Supply
Note on E19: address Address Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: Makati City
Note on F19: email E-mail for payment advices Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: ap@acme.example
Note on G19: tin Tax identification number Mandatory: No Format: Text, up to 20; 000-000-000-000 Allowed values: Free entry, up to 20 characters Example: 123-456-789-000
Note on H19: default_mode Default payment mode Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: List R09 default_mode: 7 values, see Reference lists Example: CHECK
Note on I19: allowed_modes Allowed payment modes separated by a vertical bar Mandatory: Yes Format: Text, up to 100; MODE\ Allowed values: Same list as default_mode Example: MODE
Note on J19: currency Currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on K19: bank Bank of the payee account Mandatory: No Format: Text, up to 120; Free text Allowed values: The legacy code; mapped by the code map BANK (sheet Code maps) Example: BDO Unibank
Note on L19: account_no Payee account number Mandatory: Conditional: Mandatory for CTA Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 001234567890

## R11 Receipt series in use
R11 Receipt series in use | [7 empty] | Step 11 of 29
← Back to Load templates | Step 11 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Receipt series in use (AR and OR, ATP and next number) as extracted from EBIX. Key branch_code, kind, prefix. Sent as the file R11_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-3
How it is loaded | Data migration object R11 (Carry forward), layout R11 version 1, through the Migration Console; lands in: Receipt series of Cashiering
Source | EBIX
Depends on | R02 Branches and invoicing branches →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Mapped | In the list | Not blank | Unique per branch and kind | Less than to_no | More than from_no | Between from_no and to_no
Mandatory | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes
Format | Code, up to 20; As stored in legacy | Code, up to 2; Upper case | Text, up to 40; As printed | Text, up to 20; As printed | Integer, up to 12; Digits | Integer, up to 12; Digits | Integer, up to 12; Digits | Integer, up to 12; Digits
Allowed values | The legacy code; mapped by the code map BRANCH (sheet Code maps) | AR, OR (list R11 kind) | Free entry, up to 40 characters | Free entry, up to 20 characters | A whole number | A whole number | A whole number | A whole number
What to enter | Issuing branch | Receipt kind | BIR Authority to Print number | Series prefix | First number of the series | Last number of the series | Last number issued in legacy at the freeze | Next number BIBS issues
Row | branch_code * | kind * | atp_no * | prefix | from_no * | to_no * | last_used_no * | next_no *
Example – overwrite or delete | MKT01 | AR | ATP-OCN-2025-000123 | AR-MKT | 100001 | 150000 | 131245 | 131246
Note on B19: branch_code Issuing branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on C19: kind Receipt kind Mandatory: Yes Format: Code, up to 2; Upper case Allowed values: AR, OR (list R11 kind) Example: AR
Note on D19: atp_no BIR Authority to Print number Mandatory: Yes Format: Text, up to 40; As printed Allowed values: Free entry, up to 40 characters Example: ATP-OCN-2025-000123
Note on E19: prefix Series prefix Mandatory: No Format: Text, up to 20; As printed Allowed values: Free entry, up to 20 characters Example: AR-MKT
Note on F19: from_no First number of the series Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 100001
Note on G19: to_no Last number of the series Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 150000
Note on H19: last_used_no Last number issued in legacy at the freeze Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 131245
Note on I19: next_no Next number BIBS issues Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 131246

## C01 Client master
C01 Client master | [35 empty] | Step 12 of 29
← Back to Load templates | Step 12 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [34 empty] | Ask a question →
Purpose | One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no. Sent as the file C01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027); deltas daily from T-14 days
How it is loaded | Data migration object C01 (Migrate), layout C01 version 1, through the Migration Console; lands in: Client master, registered as migrated clients
Source | QPS, EBIX, CMS
Depends on | R01 Lists of values and MIS values → |  | R02 Branches and invoicing branches → |  | R03 Sales organisation (units and account officers) →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique in the file | In the list | Mandatory for I | Mandatory for I | - | - | Mandatory for C | - | Mandatory for I; not in the future; age 0 to 120 | 9 to 12 digits; duplicate key K1 | Mapped | Mandatory when id_type is given; duplicate key K2 | Y or N | Duplicate key K5 if agreed | Mapped | Mapped | Mapped | Mapped | Mapped | Mapped in USER | Mapped | Mapped | Valid e-mail; soft key K6 | PH mobile format; soft key K6 | - | - | - | - | 4 digits | Mapped | Not in the future | Valid date | Mapped | Mapped | Valid date | Valid timestamp
Mandatory | Yes | Yes | Conditional: Mandatory for I | Conditional: Mandatory for I | No | No | Conditional: Mandatory for C | No | Conditional: Mandatory for I; not in the future; age 0 to 120 | No | No | Conditional: Mandatory when id_type is given; duplicate key K2 | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 1; Upper case | Text, up to 100; Free text | Text, up to 100; Free text | Text, up to 100; Free text | Text, up to 20; Free text | Text, up to 200; Free text | Text, up to 60; As registered | Date, up to 10; yyyy-MM-dd | Text, up to 20; 000-000-000-000 | Code, up to 40; As stored in legacy | Text, up to 60; As printed | Flag, up to 1; Y or N | Text, up to 40; Digits | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; name@domain | Text, up to 30; 09xxxxxxxxx or +639xxxxxxxxx | Text, up to 30; Free text | Text, up to 300; Free text | Text, up to 80; Free text | Text, up to 80; Free text | Text, up to 10; 4 digits | Code, up to 20; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Date, up to 10; yyyy-MM-dd | Timestamp, up to 19; yyyy-MM-dd HH:mm:ss
Allowed values | Free entry, up to 30 characters | I, C (list C01 client_type) | Free entry, up to 100 characters | Free entry, up to 100 characters | Free entry, up to 100 characters | Free entry, up to 20 characters | Free entry, up to 200 characters | Free entry, up to 60 characters | Free entry | Free entry, up to 20 characters | The legacy code; mapped by the code map LOV:ID_TYPE (sheet Code maps) | Free entry, up to 60 characters | Y or N | Free entry, up to 40 characters | The legacy code; mapped by the code map LOV:NATIONALITY (sheet Code maps) | The legacy code; mapped by the code map LOV:SOURCE_OF_FUNDS (sheet Code maps) | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) | The legacy code; mapped by the code map MIS:CUSTOMER_SEGMENT (sheet Code maps) | The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (sheet Code maps) | The legacy code; mapped by the code map USER (sheet Code maps) | The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) | The legacy code; mapped by the code map BRANCH (sheet Code maps) | Free entry, up to 120 characters | Free entry, up to 30 characters | Free entry, up to 30 characters | Free entry, up to 300 characters | Free entry, up to 80 characters | Free entry, up to 80 characters | Free entry, up to 10 characters | The legacy code; mapped by the code map STATUS:KYC (sheet Code maps) | Free entry | Free entry | The legacy code; mapped by the code map LOV:KYC_RISK_RATING (sheet Code maps) | The legacy code; mapped by the code map STATUS:CLIENT (sheet Code maps) | Free entry | Free entry
What to enter | Client number in the source system | Individual or corporate | Last name (individual) | First name (individual) | Middle name | Name suffix | Registered name (corporate) | SEC or DTI registration number (corporate) | Birth date (individual) | Tax identification number | Government ID type | Government ID number | BDO bank client | BDO customer information file number | Nationality | Source of funds | Market segment | Customer segment (MIS) | Business origin (MIS) | Account officer | Sales unit of the client | Servicing branch | Primary e-mail | Primary mobile number | Landline | Primary street address | City / municipality | Province | Postal code | KYC status in legacy | Date KYC was verified | Next KYC review date | KYC risk rating | Client status in legacy | Date the client was created in legacy | Last change in legacy (survivorship and deltas)
Row | legacy_client_no * | client_type * | last_name | first_name | middle_name | suffix | corporate_name | registration_no | birth_date | tin | id_type | id_number | bank_client_flag | bank_cif | nationality | source_of_funds | market_segment * | customer_segment | business_origin | ao_user_id | sales_unit_code | branch_code | email | mobile | phone | address_line | city | province | postal_code | kyc_status | kyc_verified_date | kyc_review_due | risk_rating | client_status * | created_date * | last_updated *
Example – overwrite or delete | Q-0012345 | I | Reyes | Ana | Cruz | Jr. | Acme Trading Corp. | CS201912345 | 1990-04-15 | 123-456-789-000 | PASSPORT | P1234567A | Y | 1234567890 | FILIPINO | SALARY | CBG | AFFLUENT | BANK_REFERRAL | mreyes | T-RET-07 | MKT01 | ana.reyes@example.ph | 09171234567 | (02) 8123 4567 | 12 Rizal St., Brgy. San Antonio | Pasig | Metro Manila | 1600 | COMPLETE | 2024-03-11 | 2028-03-11 | STANDARD | ACTIVE | 2021-07-02 | 2026-08-30 14:22:05
Note on B19: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: Q-0012345
Note on C19: client_type Individual or corporate Mandatory: Yes Format: Code, up to 1; Upper case Allowed values: I, C (list C01 client_type) Example: I
Note on D19: last_name Last name (individual) Mandatory: Conditional: Mandatory for I Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Reyes
Note on E19: first_name First name (individual) Mandatory: Conditional: Mandatory for I Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Ana
Note on F19: middle_name Middle name Mandatory: No Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Cruz
Note on G19: suffix Name suffix Mandatory: No Format: Text, up to 20; Free text Allowed values: Free entry, up to 20 characters Example: Jr.
Note on H19: corporate_name Registered name (corporate) Mandatory: Conditional: Mandatory for C Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Acme Trading Corp.
Note on I19: registration_no SEC or DTI registration number (corporate) Mandatory: No Format: Text, up to 60; As registered Allowed values: Free entry, up to 60 characters Example: CS201912345
Note on J19: birth_date Birth date (individual) Mandatory: Conditional: Mandatory for I; not in the future; age 0 to 120 Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 1990-04-15
Note on K19: tin Tax identification number Mandatory: No Format: Text, up to 20; 000-000-000-000 Allowed values: Free entry, up to 20 characters Example: 123-456-789-000
Note on L19: id_type Government ID type Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:ID_TYPE (sheet Code maps) Example: PASSPORT
Note on M19: id_number Government ID number Mandatory: Conditional: Mandatory when id_type is given; duplicate key K2 Format: Text, up to 60; As printed Allowed values: Free entry, up to 60 characters Example: P1234567A
Note on N19: bank_client_flag BDO bank client Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on O19: bank_cif BDO customer information file number Mandatory: No Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 1234567890
Note on P19: nationality Nationality Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:NATIONALITY (sheet Code maps) Example: FILIPINO
Note on Q19: source_of_funds Source of funds Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:SOURCE_OF_FUNDS (sheet Code maps) Example: SALARY
Note on R19: market_segment Market segment Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) Example: CBG
Note on S19: customer_segment Customer segment (MIS) Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map MIS:CUSTOMER_SEGMENT (sheet Code maps) Example: AFFLUENT
Note on T19: business_origin Business origin (MIS) Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (sheet Code maps) Example: BANK_REFERRAL
Note on U19: ao_user_id Account officer Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: mreyes
Note on V19: sales_unit_code Sales unit of the client Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) Example: T-RET-07
Note on W19: branch_code Servicing branch Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on X19: email Primary e-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: ana.reyes@example.ph
Note on Y19: mobile Primary mobile number Mandatory: No Format: Text, up to 30; 09xxxxxxxxx or +639xxxxxxxxx Allowed values: Free entry, up to 30 characters Example: 09171234567
Note on Z19: phone Landline Mandatory: No Format: Text, up to 30; Free text Allowed values: Free entry, up to 30 characters Example: (02) 8123 4567
Note on AA19: address_line Primary street address Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 12 Rizal St., Brgy. San Antonio
Note on AB19: city City / municipality Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Pasig
Note on AC19: province Province Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Metro Manila
Note on AD19: postal_code Postal code Mandatory: No Format: Text, up to 10; 4 digits Allowed values: Free entry, up to 10 characters Example: 1600
Note on AE19: kyc_status KYC status in legacy Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:KYC (sheet Code maps) Example: COMPLETE
Note on AF19: kyc_verified_date Date KYC was verified Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2024-03-11
Note on AG19: kyc_review_due Next KYC review date Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-03-11
Note on AH19: risk_rating KYC risk rating Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:KYC_RISK_RATING (sheet Code maps) Example: STANDARD
Note on AI19: client_status Client status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:CLIENT (sheet Code maps) Example: ACTIVE
Note on AJ19: created_date Date the client was created in legacy Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2021-07-02
Note on AK19: last_updated Last change in legacy (survivorship and deltas) Mandatory: Yes Format: Timestamp, up to 19; yyyy-MM-dd HH:mm:ss Allowed values: Free entry Example: 2026-08-30 14:22:05

## C02 Client addresses and contac
C02 Client addresses and contacts | [12 empty] | Step 13 of 29
← Back to Load templates | Step 13 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [11 empty] | Ask a question →
Purpose | One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no, record_type, seq_no. Sent as the file C02_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027); deltas daily from T-14 days
How it is loaded | Data migration object C01 (Migrate), layout C02 version 1, through the Migration Console; lands in: Client master, registered as migrated clients
Source | QPS, EBIX, CMS
Depends on | C01 Client master → |  | R01 Lists of values and MIS values → |  | R02 Branches and invoicing branches → | R03 Sales organisation (units and account officers) →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in C01 of the same source | In the list | Unique per client and record type | Mandatory for ADDRESS | Mandatory for ADDRESS | - | - | 4 digits | Mandatory for CONTACT | - | Valid e-mail | PH mobile format | One primary ADDRESS per client
Mandatory | Yes | Yes | Yes | Conditional: Mandatory for ADDRESS | Conditional: Mandatory for ADDRESS | No | No | No | Conditional: Mandatory for CONTACT | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 10; Upper case | Integer, up to 3; Digits | Code, up to 12; Upper case | Text, up to 300; Free text | Text, up to 80; Free text | Text, up to 80; Free text | Text, up to 10; 4 digits | Text, up to 200; Free text | Text, up to 60; Free text | Text, up to 120; name@domain | Text, up to 30; 09xxxxxxxxx | Flag, up to 1; Y or N
Allowed values | legacy_client_no of C01 | ADDRESS, CONTACT (list C02 record_type) | A whole number | HOME, BUSINESS, MAILING, BILLING (list C02 address_type) | Free entry, up to 300 characters | Free entry, up to 80 characters | Free entry, up to 80 characters | Free entry, up to 10 characters | Free entry, up to 200 characters | Free entry, up to 60 characters | Free entry, up to 120 characters | Free entry, up to 30 characters | Y or N
What to enter | Client number in the source system | Address or contact person | Sequence within the client and record type | Kind of address | Street address | City / municipality | Province | Postal code | Contact person (corporate clients) | Role of the contact | E-mail | Mobile number | Primary address or contact
Row | legacy_client_no * | record_type * | seq_no * | address_type | address_line | city | province | postal_code | contact_name | contact_role | email | mobile | primary_flag *
Example – overwrite or delete | Q-0012345 | ADDRESS | 1 | MAILING | 12 Rizal St., Brgy. San Antonio | Pasig | Metro Manila | 1600 | Jose Santos | HR Manager | jose.santos@acme.example | 09181234567 | Y
Note on B19: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on C19: record_type Address or contact person Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: ADDRESS, CONTACT (list C02 record_type) Example: ADDRESS
Note on D19: seq_no Sequence within the client and record type Mandatory: Yes Format: Integer, up to 3; Digits Allowed values: A whole number Example: 1
Note on E19: address_type Kind of address Mandatory: Conditional: Mandatory for ADDRESS Format: Code, up to 12; Upper case Allowed values: HOME, BUSINESS, MAILING, BILLING (list C02 address_type) Example: MAILING
Note on F19: address_line Street address Mandatory: Conditional: Mandatory for ADDRESS Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 12 Rizal St., Brgy. San Antonio
Note on G19: city City / municipality Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Pasig
Note on H19: province Province Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Metro Manila
Note on I19: postal_code Postal code Mandatory: No Format: Text, up to 10; 4 digits Allowed values: Free entry, up to 10 characters Example: 1600
Note on J19: contact_name Contact person (corporate clients) Mandatory: Conditional: Mandatory for CONTACT Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Jose Santos
Note on K19: contact_role Role of the contact Mandatory: No Format: Text, up to 60; Free text Allowed values: Free entry, up to 60 characters Example: HR Manager
Note on L19: email E-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: jose.santos@acme.example
Note on M19: mobile Mobile number Mandatory: No Format: Text, up to 30; 09xxxxxxxxx Allowed values: Free entry, up to 30 characters Example: 09181234567
Note on N19: primary_flag Primary address or contact Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## C03 Client payout accounts
C03 Client payout accounts | [5 empty] | Step 14 of 29
← Back to Load templates | Step 14 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Client payout accounts (for refunds) as extracted from EBIX. Key legacy_client_no, account_no. Sent as the file C03_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Data migration object C03 (Migrate), layout C03 version 1, through the Migration Console; lands in: Client payout accounts
Source | EBIX
Depends on | C01 Client master → |  | C02 Client addresses and contacts →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Client loaded | In the list | Not blank | Mandatory for CTA; mapped | Mandatory for CTA | Y or N
Mandatory | Yes | Yes | Yes | Conditional: Mandatory for CTA; mapped | Conditional: Mandatory for CTA | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 10; Upper case | Text, up to 250; Free text | Code, up to 30; As stored in legacy | Text, up to 40; Digits | Flag, up to 1; Y or N
Allowed values | legacy_client_no of C01 | CTA, CHECK (list C03 mode) | Free entry, up to 250 characters | The legacy code; mapped by the code map BANK (sheet Code maps) | Free entry, up to 40 characters | Y or N
What to enter | Client number in the source system | Payout mode | Name on the account or check | Bank of the account | Account number | Account in use
Row | legacy_client_no * | mode * | payee_name * | bank_code | account_no | active_flag *
Example – overwrite or delete | E-0098765 | CTA | Ana C. Reyes | BDO | 001234567890 | Y
Note on B19: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: E-0098765
Note on C19: mode Payout mode Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: CTA, CHECK (list C03 mode) Example: CTA
Note on D19: payee_name Name on the account or check Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on E19: bank_code Bank of the account Mandatory: Conditional: Mandatory for CTA; mapped Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map BANK (sheet Code maps) Example: BDO
Note on F19: account_no Account number Mandatory: Conditional: Mandatory for CTA Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 001234567890
Note on G19: active_flag Account in use Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## P01 In-force policy headers
P01 In-force policy headers | [30 empty] | Step 15 of 29
← Back to Load templates | Step 15 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [29 empty] | Ask a question →
Purpose | One row per record of In-force policy headers as extracted from QPS, EBIX. Key legacy_policy_ref. Sent as the file P01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: sum_insured, gross_premium, net_premium).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object P01 (Conditional), layout P01 version 1, through the Migration Console; lands in: Accounts, imported as legacy policy headers
Source | QPS, EBIX
Depends on | C01 Client master → |  | C02 Client addresses and contacts → |  | R04 Insurers → |  | R04B Insurer branches → |  | R05 Product lines, cover types, products and risk codes →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique in the file | Not blank | 0 or more | Not blank | Client loaded | Not blank | Mapped | Mandatory for packaged policies; not mapped at load | Mandatory with package_code | Mapped; consistent with risk_code | Mapped | In the list | Mapped to an in-force status | Valid date | After inception_date; on or after the cutover date; every expiry to 31-May-2028 present (go-live renewal extraction) | Valid code | 0 or more | 0 or more | Not below net_premium | 0 to 100 | In the list | - | - | Mapped | Y or N | Mapped in USER | Mapped | Mapped | Mapped | Mapped | -
Mandatory | Yes | Yes | No | Yes | Yes | Yes | Yes | Conditional: Mandatory for packaged policies; not mapped at load | Conditional: Mandatory with package_code | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Yes | Yes | Yes | Yes | No | No
Format | Code, up to 60; <cover no.>-<version> | Text, up to 40; As stored in legacy | Integer, up to 4; Digits | Text, up to 60; As issued | Code, up to 30; As stored in legacy | Text, up to 250; Free text | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Integer, up to 4; Digits | Code, up to 30; As stored in legacy | Code, up to 30; As stored in legacy | Code, up to 2; Upper case | Code, up to 20; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Decimal, up to 9,4; Dot decimal | Code, up to 20; Upper case | Text, up to 500; PN;PN | Text, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Flag, up to 1; Y or N | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Text, up to 300; Free text
Allowed values | Free entry, up to 60 characters | Free entry, up to 40 characters | A whole number | Free entry, up to 60 characters | legacy_client_no of C01 | Free entry, up to 250 characters | The legacy code; mapped by the code map PRODUCT (sheet Code maps) | Free entry, up to 20 characters | A whole number | The legacy code; mapped by the code map LINE (sheet Code maps) | The legacy code; mapped by the code map COVER_TYPE (sheet Code maps) | NB, RB (list P01 business_type) | The legacy code; mapped by the code map STATUS:POLICY (sheet Code maps) | Free entry | Free entry | ISO 4217 | A number | A number | A number | A number | VIA_BDOI, DIRECT (list P01 payment_arrangement) | Free entry, up to 500 characters | Free entry, up to 40 characters | The legacy code; mapped by the code map BANK (sheet Code maps) | Y or N | The legacy code; mapped by the code map USER (sheet Code maps) | The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) | The legacy code; mapped by the code map BRANCH (sheet Code maps) | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) | The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (sheet Code maps) | Free entry, up to 300 characters
What to enter | Unique legacy reference of the policy term (cover no. and version, or policy reference) | Legacy cover number | Legacy cover version | Insurer policy number | Client number of the assured | Assured name as on the policy | Product / risk code | Legacy package of a packaged policy | Version of the legacy package | Line of business | Cover type | New business or renewal | Status of the term in legacy | Period from | Period to | Policy currency | Total sum insured | Basic premium | Gross premium including taxes and charges | Commission rate in percent | Premium paid through BDOI or directly to the insurer | Loan promissory note numbers, separated by semicolons | Loan application number | Mortgagee | Free first year | Account officer | Sales team | Branch | Market segment | Business origin / channel | Short risk description (vehicle, location)
Row | legacy_policy_ref * | cover_no * | cover_version | policy_no * | legacy_client_no * | assured_name * | risk_code * | package_code | package_version | line_code * | cover_type_code | business_type * | policy_status * | inception_date * | expiry_date * | currency * | sum_insured * | net_premium * | gross_premium * | commission_rate_pct | payment_arrangement * | pn_nos | loan_application_no | mortgagee_bank | ffy_flag | ao_user_id * | sales_unit_code * | branch_code * | market_segment * | source_channel | risk_description
Example – overwrite or delete | C-2026-004512-01 | C-2026-004512 | 1 | MC-PC-26-0012345 | Q-0012345 | Ana C. Reyes | MC-PC-COMP | PKG-MC-PRIV | 3 | MOTOR | COMP | RB | ISSUED | 2027-03-15 | 2028-03-15 | PHP | 950000 | 21375 | 25946.25 | 20 | VIA_BDOI | PN-2019-000123 | LA-2019-5566 | BDO | N | mreyes | T-RET-07 | MKT01 | CBG | BANK_REFERRAL | 2022 Toyota Vios ABC 1234
Note on B19: legacy_policy_ref Unique legacy reference of the policy term (cover no. and version, or policy reference) Mandatory: Yes Format: Code, up to 60; <cover no.>-<version> Allowed values: Free entry, up to 60 characters Example: C-2026-004512-01
Note on C19: cover_no Legacy cover number Mandatory: Yes Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: C-2026-004512
Note on D19: cover_version Legacy cover version Mandatory: No Format: Integer, up to 4; Digits Allowed values: A whole number Example: 1
Note on E19: policy_no Insurer policy number Mandatory: Yes Format: Text, up to 60; As issued Allowed values: Free entry, up to 60 characters Example: MC-PC-26-0012345
Note on F19: legacy_client_no Client number of the assured Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on G19: assured_name Assured name as on the policy Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on H19: risk_code Product / risk code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map PRODUCT (sheet Code maps) Example: MC-PC-COMP
Note on I19: package_code Legacy package of a packaged policy Mandatory: Conditional: Mandatory for packaged policies; not mapped at load Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: PKG-MC-PRIV
Note on J19: package_version Version of the legacy package Mandatory: Conditional: Mandatory with package_code Format: Integer, up to 4; Digits Allowed values: A whole number Example: 3
Note on K19: line_code Line of business Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map LINE (sheet Code maps) Example: MOTOR
Note on L19: cover_type_code Cover type Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map COVER_TYPE (sheet Code maps) Example: COMP
Note on M19: business_type New business or renewal Mandatory: Yes Format: Code, up to 2; Upper case Allowed values: NB, RB (list P01 business_type) Example: RB
Note on N19: policy_status Status of the term in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:POLICY (sheet Code maps) Example: ISSUED
Note on O19: inception_date Period from Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-03-15
Note on P19: expiry_date Period to Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-03-15
Note on Q19: currency Policy currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on R19: sum_insured Total sum insured Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 950000.00
Note on S19: net_premium Basic premium Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 21375.00
Note on T19: gross_premium Gross premium including taxes and charges Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 25946.25
Note on U19: commission_rate_pct Commission rate in percent Mandatory: No Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 20.0000
Note on V19: payment_arrangement Premium paid through BDOI or directly to the insurer Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: VIA_BDOI, DIRECT (list P01 payment_arrangement) Example: VIA_BDOI
Note on W19: pn_nos Loan promissory note numbers, separated by semicolons Mandatory: No Format: Text, up to 500; PN;PN Allowed values: Free entry, up to 500 characters Example: PN-2019-000123
Note on X19: loan_application_no Loan application number Mandatory: No Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: LA-2019-5566
Note on Y19: mortgagee_bank Mortgagee Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map BANK (sheet Code maps) Example: BDO
Note on Z19: ffy_flag Free first year Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on AA19: ao_user_id Account officer Mandatory: Yes Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: mreyes
Note on AB19: sales_unit_code Sales team Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) Example: T-RET-07
Note on AC19: branch_code Branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on AD19: market_segment Market segment Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) Example: CBG
Note on AE19: source_channel Business origin / channel Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (sheet Code maps) Example: BANK_REFERRAL
Note on AF19: risk_description Short risk description (vehicle, location) Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 2022 Toyota Vios ABC 1234

## P01S Policy insurer shares
P01S Policy insurer shares | [5 empty] | Step 16 of 29
← Back to Load templates | Step 16 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of In-force policy headers as extracted from QPS, EBIX. Key legacy_policy_ref, share_seq. Sent as the file P01S_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object P01 (Conditional), layout P01S version 1, through the Migration Console; lands in: Accounts, imported as legacy policy headers
Source | QPS, EBIX
Depends on | P01 In-force policy headers → |  | C01 Client master → |  | C02 Client addresses and contacts →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in P01 | Unique per policy | Mapped | Mapped | Above 0; shares of a policy add to 100 | One lead per policy
Mandatory | Yes | Yes | Yes | No | Yes | Yes
Format | Code, up to 60; As in P01 | Integer, up to 2; Digits | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Decimal, up to 9,4; Dot decimal | Flag, up to 1; Y or N
Allowed values | legacy_policy_ref of P01 | A whole number | The legacy code; mapped by the code map INSURER (sheet Code maps) | The legacy code; mapped by the code map INSURER_BRANCH (sheet Code maps) | A number | Y or N
What to enter | Legacy reference of the policy term | Sequence of the insurer | Insurer | Insurer branch | Share in percent | Lead insurer
Row | legacy_policy_ref * | share_seq * | insurer_code * | insurer_branch_code | share_pct * | lead_flag *
Example – overwrite or delete | C-2026-004512-01 | 1 | MAL | MAL-CEB | 100 | Y
Note on B19: legacy_policy_ref Legacy reference of the policy term Mandatory: Yes Format: Code, up to 60; As in P01 Allowed values: legacy_policy_ref of P01 Example: C-2026-004512-01
Note on C19: share_seq Sequence of the insurer Mandatory: Yes Format: Integer, up to 2; Digits Allowed values: A whole number Example: 1
Note on D19: insurer_code Insurer Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on E19: insurer_branch_code Insurer branch Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER_BRANCH (sheet Code maps) Example: MAL-CEB
Note on F19: share_pct Share in percent Mandatory: Yes Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 100.0000
Note on G19: lead_flag Lead insurer Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## F01 Open legacy invoices - head
F01 Open legacy invoices - header | [37 empty] | Step 17 of 29
← Back to Load templates | Step 17 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [36 empty] | Ask a question →
Purpose | One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key legacy_invoice_no. Sent as the file F01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: gross_premium, commission, vat_on_commission).
Provided by | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F01 (Carry forward), layout F01 version 1, through the Migration Console; lands in: Operations invoice ledger (invoices, insurer shares, components) with an opening accounting entry on the legacy sub-ledgers
Source | EBIX, QPS
Depends on | C01 Client master → |  | C02 Client addresses and contacts → |  | R04 Insurers → |  | R04B Insurer branches → |  | R05 Product lines, cover types, products and risk codes → |  | P01 In-force policy headers → |  | P01S Policy insurer shares →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique across EBIX and QPS | In the list | Mandatory for ENDORSEMENT_PLUS, ENDORSEMENT_MINUS and CANCELLATION; parent in the file or loaded | - | Mandatory when P01 is in scope; exists in P01 | Not blank | 1 or more | Client loaded | Not blank | - | Valid code | Mandatory when currency is not PHP | Before the cutover date | Before the cutover date | Valid date | Valid date | On or after inception_date | Mapped | Mapped | Mapped | Mapped in USER | Mapped | Mapped | Mapped | - |  |  |  | 0 to 100 | 0 to commission | 0 to vat_on_commission | Y or N | Y or N | Y or N | Y or N | - | Not after the freeze | -
Mandatory | Yes | Yes | Conditional: Mandatory for ENDORSEMENT_PLUS, ENDORSEMENT_MINUS and CANCELLATION; parent in the file or loaded | No | Conditional: Mandatory when P01 is in scope; exists in P01 | Yes | No | Yes | Yes | No | Yes | Conditional: Mandatory when currency is not PHP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | No | No | No | No | No
Format | Code, up to 40; EBIX I######## | Code, up to 20; Upper case | Code, up to 40; As stored in legacy | Text, up to 40; As stored in legacy | Code, up to 60; As in P01 | Text, up to 60; As issued | Integer, up to 2; Digits | Code, up to 30; As stored in legacy | Text, up to 250; Free text | Text, up to 250; Free text | Code, up to 3; Upper case | Decimal, up to 12,6; Dot decimal | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 20; As stored in legacy | Code, up to 30; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 500; PN;PN | Amount, up to 19,2; Dot decimal, 2 decimals; minus for return invoices | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Decimal, up to 9,4; Dot decimal | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Flag, up to 1; Y or N | Flag, up to 1; Y or N | Flag, up to 1; Y or N | Flag, up to 1; Y or N | Text, up to 40; As printed | Date, up to 10; yyyy-MM-dd | Text, up to 500; Free text
Allowed values | Free entry, up to 40 characters | BOOKING, ENDORSEMENT_PLUS, ENDORSEMENT_MINUS, CANCELLATION (list F01 invoice_kind) | legacy_invoice_no values | Free entry, up to 40 characters | legacy_policy_ref of P01 | Free entry, up to 60 characters | A whole number | legacy_client_no of C01 | Free entry, up to 250 characters | Free entry, up to 250 characters | ISO 4217 | A number | Free entry | Free entry | Free entry | Free entry | Free entry | The legacy code; mapped by the code map PRODUCT (sheet Code maps) | The legacy code; mapped by the code map LINE (sheet Code maps) | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) | The legacy code; mapped by the code map USER (sheet Code maps) | The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) | The legacy code; mapped by the code map BRANCH (sheet Code maps) | The legacy code; mapped by the code map COST_CENTER (sheet Code maps) | Free entry, up to 500 characters | A number | A number | A number | A number | A number | A number | Y or N | Y or N | Y or N | Y or N | Free entry, up to 40 characters | Free entry | Free entry, up to 500 characters
What to enter | Invoice number in the source system | Kind of invoice | Original invoice of an endorsement or cancellation invoice | Legacy endorsement number | Legacy reference of the policy term | Insurer policy number | Year of a multi-year policy | Client number of the assured | Assured name on the invoice | Payor if not the assured | Invoice currency | Exchange rate used at booking (foreign currency) | Legacy booking date | Invoice date | Due date | Period from | Period to | Product / risk code | Line of business | Market segment | Account officer | Sales team | Invoicing branch | Cost centre | Loan PN numbers, separated by semicolons | Gross premium of the invoice (sum of the six premium components) | Commission of the invoice | VAT on commission | Withholding tax rate on commission, in percent | Commission already realised (recognised as income) in legacy | Output VAT on commission still deferred | Direct-payment invoice (premium paid to the insurer) | Client withholds 2% (BIR 2307) | Counts for incentive programmes | Remittance on hold in legacy | Legacy service invoice issued for the commission | Date of the last payment applied in legacy | Legacy remarks
Row | legacy_invoice_no * | invoice_kind * | parent_invoice_no | endorsement_no | legacy_policy_ref | policy_no * | policy_year | legacy_client_no * | assured_name * | payor_name | currency * | booking_fx_rate | booking_date * | invoice_date * | due_date * | inception_date * | expiry_date * | risk_code * | line_code * | market_segment * | ao_user_id * | sales_unit_code * | branch_code * | cost_center | pn_nos | gross_premium * | commission * | vat_on_commission * | wtax_rate_pct * | commission_realised * | deferred_vat_open | dp_flag * | cwt_flag * | incentive_eligible_flag | hold_flag | legacy_service_invoice_no | last_payment_date | remarks
Example – overwrite or delete | I00123456 | BOOKING | I00119876 | END-2026-0456 | C-2026-004512-01 | MC-PC-26-0012345 | 1 | Q-0012345 | Ana C. Reyes | BDO Unibank - Auto Loans | PHP | 56.125 | 2027-03-10 | 2027-03-10 | 2027-04-09 | 2027-03-15 | 2028-03-15 | MC-PC-COMP | MOTOR | CBG | mreyes | T-RET-07 | MKT01 | 4100 | PN-2019-000123 | 25946.25 | 4275 | 513 | 10 | 1710 | 307.8 | N | N | N | N | SI-000456789 | 2027-05-02 | Balance under dispute
Note on B19: legacy_invoice_no Invoice number in the source system Mandatory: Yes Format: Code, up to 40; EBIX I######## Allowed values: Free entry, up to 40 characters Example: I00123456
Note on C19: invoice_kind Kind of invoice Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: BOOKING, ENDORSEMENT_PLUS, ENDORSEMENT_MINUS, CANCELLATION (list F01 invoice_kind) Example: BOOKING
Note on D19: parent_invoice_no Original invoice of an endorsement or cancellation invoice Mandatory: Conditional: Mandatory for ENDORSEMENT_PLUS, ENDORSEMENT_MINUS and CANCELLATION; parent in the file or loaded Format: Code, up to 40; As stored in legacy Allowed values: legacy_invoice_no values Example: I00119876
Note on E19: endorsement_no Legacy endorsement number Mandatory: No Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: END-2026-0456
Note on F19: legacy_policy_ref Legacy reference of the policy term Mandatory: Conditional: Mandatory when P01 is in scope; exists in P01 Format: Code, up to 60; As in P01 Allowed values: legacy_policy_ref of P01 Example: C-2026-004512-01
Note on G19: policy_no Insurer policy number Mandatory: Yes Format: Text, up to 60; As issued Allowed values: Free entry, up to 60 characters Example: MC-PC-26-0012345
Note on H19: policy_year Year of a multi-year policy Mandatory: No Format: Integer, up to 2; Digits Allowed values: A whole number Example: 1
Note on I19: legacy_client_no Client number of the assured Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on J19: assured_name Assured name on the invoice Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on K19: payor_name Payor if not the assured Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: BDO Unibank - Auto Loans
Note on L19: currency Invoice currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on M19: booking_fx_rate Exchange rate used at booking (foreign currency) Mandatory: Conditional: Mandatory when currency is not PHP Format: Decimal, up to 12,6; Dot decimal Allowed values: A number Example: 56.125000
Note on N19: booking_date Legacy booking date Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-03-10
Note on O19: invoice_date Invoice date Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-03-10
Note on P19: due_date Due date Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-04-09
Note on Q19: inception_date Period from Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-03-15
Note on R19: expiry_date Period to Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-03-15
Note on S19: risk_code Product / risk code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map PRODUCT (sheet Code maps) Example: MC-PC-COMP
Note on T19: line_code Line of business Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map LINE (sheet Code maps) Example: MOTOR
Note on U19: market_segment Market segment Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (sheet Code maps) Example: CBG
Note on V19: ao_user_id Account officer Mandatory: Yes Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: mreyes
Note on W19: sales_unit_code Sales team Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) Example: T-RET-07
Note on X19: branch_code Invoicing branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on Y19: cost_center Cost centre Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (sheet Code maps) Example: 4100
Note on Z19: pn_nos Loan PN numbers, separated by semicolons Mandatory: No Format: Text, up to 500; PN;PN Allowed values: Free entry, up to 500 characters Example: PN-2019-000123
Note on AA19: gross_premium Gross premium of the invoice (sum of the six premium components) Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals; minus for return invoices Allowed values: A number Example: 25946.25
Note on AB19: commission Commission of the invoice Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 4275.00
Note on AC19: vat_on_commission VAT on commission Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 513.00
Note on AD19: wtax_rate_pct Withholding tax rate on commission, in percent Mandatory: Yes Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 10.0000
Note on AE19: commission_realised Commission already realised (recognised as income) in legacy Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 1710.00
Note on AF19: deferred_vat_open Output VAT on commission still deferred Mandatory: No Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 307.80
Note on AG19: dp_flag Direct-payment invoice (premium paid to the insurer) Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on AH19: cwt_flag Client withholds 2% (BIR 2307) Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on AI19: incentive_eligible_flag Counts for incentive programmes Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on AJ19: hold_flag Remittance on hold in legacy Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on AK19: legacy_service_invoice_no Legacy service invoice issued for the commission Mandatory: No Format: Text, up to 40; As printed Allowed values: Free entry, up to 40 characters Example: SI-000456789
Note on AL19: last_payment_date Date of the last payment applied in legacy Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-05-02
Note on AM19: remarks Legacy remarks Mandatory: No Format: Text, up to 500; Free text Allowed values: Free entry, up to 500 characters Example: Balance under dispute

## F01C Open legacy invoices - com
F01C Open legacy invoices - components and positions | [7 empty] | Step 18 of 29
← Back to Load templates | Step 18 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key legacy_invoice_no, component. Sent as the file F01C_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: booked, adjusted, paid, remitted, written_off, open_balance).
Provided by | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F01 (Carry forward), layout F01C version 1, through the Migration Console; lands in: Operations invoice ledger (invoices, insurer shares, components) with an opening accounting entry on the legacy sub-ledgers
Source | EBIX, QPS
Depends on | F01 Open legacy invoices - header → |  | C01 Client master → | C02 Client addresses and contacts → |  | R04 Insurers → |  | R04B Insurer branches →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in F01 | In the list; one row per component and invoice | Same sign as the invoice | - | 0 for DTIP, COMMISSION, COMMISSION_VAT, WTAX | 0 for premium components | - | Premium components and PR2307 = booked + adjusted - paid - written_off; DTIP, COMMISSION, COMMISSION_VAT, WTAX = booked + adjusted - remitted - written_off; within 0 and booked + adjusted
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Code, up to 40; As in F01 | Code, up to 20; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals; minus for return invoices | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals
Allowed values | legacy_invoice_no of F01 | List F01C component: 11 values, see Reference lists | A number | A number | A number | A number | A number | A number
What to enter | Invoice number in the source system | Premium or settlement component | Amount booked in legacy | Net legacy adjustments kept on the same invoice | Paid by the client before cutover (premium components and PR2307) | Settled with the insurer before cutover (DTIP, commission, VAT on commission, WTAX) | Written off or DP-reversed before cutover | Open balance at the freeze
Row | legacy_invoice_no * | component * | booked * | adjusted * | paid * | remitted * | written_off * | open_balance *
Example – overwrite or delete | I00123456 | BASIC | 21375 | 0 | 8550 | 0 | 0 | 12825
Note on B19: legacy_invoice_no Invoice number in the source system Mandatory: Yes Format: Code, up to 40; As in F01 Allowed values: legacy_invoice_no of F01 Example: I00123456
Note on C19: component Premium or settlement component Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: List F01C component: 11 values, see Reference lists Example: BASIC
Note on D19: booked Amount booked in legacy Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals; minus for return invoices Allowed values: A number Example: 21375.00
Note on E19: adjusted Net legacy adjustments kept on the same invoice Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on F19: paid Paid by the client before cutover (premium components and PR2307) Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 8550.00
Note on G19: remitted Settled with the insurer before cutover (DTIP, commission, VAT on commission, WTAX) Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on H19: written_off Written off or DP-reversed before cutover Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on I19: open_balance Open balance at the freeze Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 12825.00

## F01S Open legacy invoices - ins
F01S Open legacy invoices - insurer shares | [5 empty] | Step 19 of 29
← Back to Load templates | Step 19 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares as extracted from EBIX, QPS. Key legacy_invoice_no, share_seq. Sent as the file F01S_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Operations data steward (to name); approved by Operations - Financial Transactions; Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F01 (Carry forward), layout F01S version 1, through the Migration Console; lands in: Operations invoice ledger (invoices, insurer shares, components) with an opening accounting entry on the legacy sub-ledgers
Source | EBIX, QPS
Depends on | F01 Open legacy invoices - header → |  | C01 Client master → |  | C02 Client addresses and contacts →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in F01 | Unique per invoice | Mapped | Above 0 and at most 100; shares of an invoice add to 100 | One lead per invoice
Mandatory | Yes | Yes | Yes | Yes | Yes
Format | Code, up to 40; As in F01 | Integer, up to 2; Digits | Code, up to 30; As stored in legacy | Decimal, up to 9,4; Dot decimal | Flag, up to 1; Y or N
Allowed values | legacy_invoice_no of F01 | A whole number | The legacy code; mapped by the code map INSURER (sheet Code maps) | A number | Y or N
What to enter | Invoice number in the source system | Sequence of the insurer | Insurer | Share in percent | Lead insurer
Row | legacy_invoice_no * | share_seq * | insurer_code * | share_pct * | lead_flag *
Example – overwrite or delete | I00123456 | 1 | MAL | 100 | Y
Note on B19: legacy_invoice_no Invoice number in the source system Mandatory: Yes Format: Code, up to 40; As in F01 Allowed values: legacy_invoice_no of F01 Example: I00123456
Note on C19: share_seq Sequence of the insurer Mandatory: Yes Format: Integer, up to 2; Digits Allowed values: A whole number Example: 1
Note on D19: insurer_code Insurer Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on E19: share_pct Share in percent Mandatory: Yes Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 100.0000
Note on F19: lead_flag Lead insurer Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## F02 Unapplied premium payments
F02 Unapplied premium payments (UPP) | [20 empty] | Step 20 of 29
← Back to Load templates | Step 20 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [19 empty] | Ask a question →
Purpose | One row per record of Unapplied premium payments (UPP) with disposition in progress as extracted from EBIX, CMS. Key legacy_upp_ref. Sent as the file F02_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: amount, balance).
Provided by | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F02 (Carry forward), layout F02 version 1, through the Migration Console; lands in: Cashiering unapplied payments, as migrated items, with an opening accounting entry
Source | EBIX, CMS
Depends on | C01 Client master → |  | C02 Client addresses and contacts →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Unique | Not blank | Before the cutover date | Before the cutover date | In the list | Not blank | Client loaded when given | Valid code | Above 0 | Above 0 and at most amount | Mapped | Mapped | At least one ref_ field is recommended | - | - | - | Mapped | Mapped | Mandatory when disposition_type is given | - | -
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | No | Yes | No | No | No | No | Yes | No | Conditional: Mandatory when disposition_type is given | No | No
Format | Code, up to 40; As stored in legacy | Text, up to 40; As printed | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 20; Upper case | Text, up to 250; Free text | Code, up to 30; As stored in legacy | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 400; NO;NO | Text, up to 400; NO;NO | Text, up to 400; PN;PN | Text, up to 80; As in the payment file | Code, up to 30; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 20; Upper case | Text, up to 500; Free text | Text, up to 250; Free text
Allowed values | Free entry, up to 40 characters | Free entry, up to 40 characters | Free entry | Free entry | List F02 channel: 7 values, see Reference lists | Free entry, up to 250 characters | legacy_client_no of C01 | ISO 4217 | A number | A number | The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) | The legacy code; mapped by the code map BRANCH (sheet Code maps) | Free entry, up to 400 characters | Free entry, up to 400 characters | Free entry, up to 400 characters | Free entry, up to 80 characters | The legacy code; mapped by the code map STATUS:UPP (sheet Code maps) | The legacy code; mapped by the code map DISPOSITION_TYPE (sheet Code maps) | MONITORING, FOR_APPROVAL, IN_PROCESS (list F02 disposition_status) | Free entry, up to 500 characters | Free entry, up to 250 characters
What to enter | UPP reference in the source system | Acknowledgment receipt issued in legacy | AR date | Value date of the cash | Channel of the payment | Payor | Client if identified | Currency | Amount received | Unapplied balance at the freeze | Sales unit | Branch that received the cash | Invoice numbers the payor quoted, separated by semicolons | Cover or policy numbers quoted | PN numbers quoted | Bank or payment file reference | UPP status in legacy | Disposition in progress in legacy | Status of the disposition | Details (target invoice, refund payee, amount) | Legacy remarks
Row | legacy_upp_ref * | legacy_ar_no * | legacy_ar_date * | value_date * | channel * | payor_name * | legacy_client_no | currency * | amount * | balance * | sales_unit_code | branch_code * | ref_invoice_nos | ref_cover_nos | ref_pn_nos | ref_bank_reference | legacy_status * | disposition_type | disposition_status | disposition_details | remarks
Example – overwrite or delete | UPP-2026-004321 | AR-MKT-131002 | 2026-07-14 | 2026-07-14 | DIRECT_CREDIT | Ana C. Reyes | Q-0012345 | PHP | 5000 | 5000 | T-RET-07 | MKT01 | I00123456 | C-2026-004512 | PN-2019-000123 | DC20260714-000981 | FOR_MONITORING | REFUND | FOR_APPROVAL | Refund to CTA 001234567890 | Client to confirm invoice
Note on B19: legacy_upp_ref UPP reference in the source system Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: UPP-2026-004321
Note on C19: legacy_ar_no Acknowledgment receipt issued in legacy Mandatory: Yes Format: Text, up to 40; As printed Allowed values: Free entry, up to 40 characters Example: AR-MKT-131002
Note on D19: legacy_ar_date AR date Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2026-07-14
Note on E19: value_date Value date of the cash Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2026-07-14
Note on F19: channel Channel of the payment Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: List F02 channel: 7 values, see Reference lists Example: DIRECT_CREDIT
Note on G19: payor_name Payor Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on H19: legacy_client_no Client if identified Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on I19: currency Currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on J19: amount Amount received Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 5000.00
Note on K19: balance Unapplied balance at the freeze Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 5000.00
Note on L19: sales_unit_code Sales unit Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map SALES_UNIT (sheet Code maps) Example: T-RET-07
Note on M19: branch_code Branch that received the cash Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on N19: ref_invoice_nos Invoice numbers the payor quoted, separated by semicolons Mandatory: No Format: Text, up to 400; NO;NO Allowed values: Free entry, up to 400 characters Example: I00123456
Note on O19: ref_cover_nos Cover or policy numbers quoted Mandatory: No Format: Text, up to 400; NO;NO Allowed values: Free entry, up to 400 characters Example: C-2026-004512
Note on P19: ref_pn_nos PN numbers quoted Mandatory: No Format: Text, up to 400; PN;PN Allowed values: Free entry, up to 400 characters Example: PN-2019-000123
Note on Q19: ref_bank_reference Bank or payment file reference Mandatory: No Format: Text, up to 80; As in the payment file Allowed values: Free entry, up to 80 characters Example: DC20260714-000981
Note on R19: legacy_status UPP status in legacy Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:UPP (sheet Code maps) Example: FOR_MONITORING
Note on S19: disposition_type Disposition in progress in legacy Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map DISPOSITION_TYPE (sheet Code maps) Example: REFUND
Note on T19: disposition_status Status of the disposition Mandatory: Conditional: Mandatory when disposition_type is given Format: Code, up to 20; Upper case Allowed values: MONITORING, FOR_APPROVAL, IN_PROCESS (list F02 disposition_status) Example: FOR_APPROVAL
Note on U19: disposition_details Details (target invoice, refund payee, amount) Mandatory: No Format: Text, up to 500; Free text Allowed values: Free entry, up to 500 characters Example: Refund to CTA 001234567890
Note on V19: remarks Legacy remarks Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Client to confirm invoice

## F03 Open collection state
F03 Open collection state | [11 empty] | Step 21 of 29
← Back to Load templates | Step 21 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [10 empty] | Ask a question →
Purpose | One row per record of Open collection state (dispositions, promises to pay, installment plans, collector assignments) as extracted from CMS. Key legacy_invoice_no, record_type, seq_no. Sent as the file F03_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: promise_amount, installment_amount).
Provided by | Collections data steward (to name); approved by Head, Operations (Collections); extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F03 (Carry forward), layout F03 version 1, through the Migration Console; lands in: Legacy follow-up of the Collections worklist items
Source | CMS
Depends on | F01 Open legacy invoices - header → |  | F01S Open legacy invoices - insurer shares → |  | F01C Open legacy invoices - components and positions →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in F01 | In the list | Unique per invoice and record type | Mandatory for DISPOSITION; mapped | Mandatory for DISPOSITION | Mandatory for PROMISE | Mandatory for PROMISE; at most the open PR | Mandatory for INSTALLMENT | Mandatory for INSTALLMENT | Mandatory for INSTALLMENT | Mandatory for ASSIGNMENT; mapped | -
Mandatory | Yes | Yes | Yes | Conditional: Mandatory for DISPOSITION; mapped | Conditional: Mandatory for DISPOSITION | Conditional: Mandatory for PROMISE | Conditional: Mandatory for PROMISE; at most the open PR | Conditional: Mandatory for INSTALLMENT | Conditional: Mandatory for INSTALLMENT | Conditional: Mandatory for INSTALLMENT | Conditional: Mandatory for ASSIGNMENT; mapped | No
Format | Code, up to 40; As in F01 | Code, up to 12; Upper case | Integer, up to 3; Digits | Code, up to 40; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Amount, up to 19,2; Dot decimal, 2 decimals | Integer, up to 3; Digits | Date, up to 10; yyyy-MM-dd | Amount, up to 19,2; Dot decimal, 2 decimals | Code, up to 50; As stored in legacy | Text, up to 500; Free text
Allowed values | legacy_invoice_no of F01 | DISPOSITION, PROMISE, INSTALLMENT, ASSIGNMENT (list F03 record_type) | A whole number | The legacy code; mapped by the code map DISPOSITION_CLX (sheet Code maps) | Free entry | Free entry | A number | A whole number | Free entry | A number | The legacy code; mapped by the code map USER (sheet Code maps) | Free entry, up to 500 characters
What to enter | Invoice the follow-up belongs to | Kind of row | Sequence within the invoice and record type | Latest disposition | Date of the disposition | Promised payment date | Promised amount | Installment number | Installment due date | Installment amount | Assigned collector | Collector remarks
Row | legacy_invoice_no * | record_type * | seq_no * | disposition_code | disposition_date | promise_date | promise_amount | installment_no | installment_due | installment_amount | collector_user_id | remarks
Example – overwrite or delete | I00123456 | PROMISE | 1 | PTP | 2027-12-20 | 2028-01-14 | 6000 | 2 | 2028-01-15 | 3000 | jgarcia | Client will pay after salary
Note on B19: legacy_invoice_no Invoice the follow-up belongs to Mandatory: Yes Format: Code, up to 40; As in F01 Allowed values: legacy_invoice_no of F01 Example: I00123456
Note on C19: record_type Kind of row Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: DISPOSITION, PROMISE, INSTALLMENT, ASSIGNMENT (list F03 record_type) Example: PROMISE
Note on D19: seq_no Sequence within the invoice and record type Mandatory: Yes Format: Integer, up to 3; Digits Allowed values: A whole number Example: 1
Note on E19: disposition_code Latest disposition Mandatory: Conditional: Mandatory for DISPOSITION; mapped Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map DISPOSITION_CLX (sheet Code maps) Example: PTP
Note on F19: disposition_date Date of the disposition Mandatory: Conditional: Mandatory for DISPOSITION Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-12-20
Note on G19: promise_date Promised payment date Mandatory: Conditional: Mandatory for PROMISE Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-01-14
Note on H19: promise_amount Promised amount Mandatory: Conditional: Mandatory for PROMISE; at most the open PR Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 6000.00
Note on I19: installment_no Installment number Mandatory: Conditional: Mandatory for INSTALLMENT Format: Integer, up to 3; Digits Allowed values: A whole number Example: 2
Note on J19: installment_due Installment due date Mandatory: Conditional: Mandatory for INSTALLMENT Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-01-15
Note on K19: installment_amount Installment amount Mandatory: Conditional: Mandatory for INSTALLMENT Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 3000.00
Note on L19: collector_user_id Assigned collector Mandatory: Conditional: Mandatory for ASSIGNMENT; mapped Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: jgarcia
Note on M19: remarks Collector remarks Mandatory: No Format: Text, up to 500; Free text Allowed values: Free entry, up to 500 characters Example: Client will pay after salary

## F04 Remittance in flight
F04 Remittance in flight | [9 empty] | Step 22 of 29
← Back to Load templates | Step 22 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | One row per record of Remittance in flight (batches not yet paid, holds, special remittances) as extracted from EBIX. Key legacy_batch_no, legacy_invoice_no. Sent as the file F04_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: amount).
Provided by | Remittance data steward (to name); approved by Operations - Remittance; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F04 (Conditional), layout F04 version 1, through the Migration Console; lands in: Remittance holds and special remittances
Source | EBIX
Depends on | F01 Open legacy invoices - header → |  | F01S Open legacy invoices - insurer shares → |  | F01C Open legacy invoices - components and positions →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list | Mandatory for BATCH and SPECIAL | Mapped | Exists in F01 | Valid code | At most the open DTIP | Mapped | Mandatory for HOLD | Valid date | Mapped
Mandatory | Yes | Conditional: Mandatory for BATCH and SPECIAL | Yes | Yes | Yes | Yes | Yes | Conditional: Mandatory for HOLD | No | No
Format | Code, up to 10; Upper case | Text, up to 40; As stored in legacy | Code, up to 30; As stored in legacy | Code, up to 40; As in F01 | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Code, up to 30; As stored in legacy | Text, up to 250; Free text | Date, up to 10; yyyy-MM-dd | Code, up to 50; As stored in legacy
Allowed values | HOLD, SPECIAL, BATCH (list F04 record_type) | Free entry, up to 40 characters | The legacy code; mapped by the code map INSURER (sheet Code maps) | legacy_invoice_no of F01 | ISO 4217 | A number | The legacy code; mapped by the code map STATUS:REMITTANCE (sheet Code maps) | Free entry, up to 250 characters | Free entry | The legacy code; mapped by the code map USER (sheet Code maps)
What to enter | Kind of row | Legacy remittance batch number (BATCH, SPECIAL) | Insurer | Invoice of the line | Currency | Amount held or to remit | Status in legacy | Reason of the hold | End of the hold | Requester
Row | record_type * | legacy_batch_no | insurer_code * | legacy_invoice_no * | currency * | amount * | status * | hold_reason | hold_until | requested_by_user_id
Example – overwrite or delete | HOLD | RB-2026-0877 | MAL | I00123456 | PHP | 21671.25 | ON_HOLD | Pending negative endorsement | 2028-01-31 | rtan
Note on B19: record_type Kind of row Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: HOLD, SPECIAL, BATCH (list F04 record_type) Example: HOLD
Note on C19: legacy_batch_no Legacy remittance batch number (BATCH, SPECIAL) Mandatory: Conditional: Mandatory for BATCH and SPECIAL Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: RB-2026-0877
Note on D19: insurer_code Insurer Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on E19: legacy_invoice_no Invoice of the line Mandatory: Yes Format: Code, up to 40; As in F01 Allowed values: legacy_invoice_no of F01 Example: I00123456
Note on F19: currency Currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on G19: amount Amount held or to remit Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 21671.25
Note on H19: status Status in legacy Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:REMITTANCE (sheet Code maps) Example: ON_HOLD
Note on I19: hold_reason Reason of the hold Mandatory: Conditional: Mandatory for HOLD Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Pending negative endorsement
Note on J19: hold_until End of the hold Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-01-31
Note on K19: requested_by_user_id Requester Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: rtan

## F06 PDCs, check pick-ups and re
F06 PDCs, check pick-ups and refunds in process | [13 empty] | Step 23 of 29
← Back to Load templates | Step 23 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per record of PDCs in the warehouse, check pick-ups and refunds in process as extracted from EBIX. Key record_type, reference. Sent as the file F06_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: amount).
Provided by | Cashiering data steward (to name); approved by Operations - Cashiering; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2
How it is loaded | Data migration object F06 (Conditional), layout F06 version 1, through the Migration Console; lands in: Cashiering PDC warehouse and check pick-up
Source | EBIX
Depends on | C01 Client master → |  | C02 Client addresses and contacts →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list | Unique per record type | Mandatory for PDC | Mandatory for PDC and PICKUP | Mandatory for PDC; mapped | - | Mandatory for PDC | Valid code | Above 0 | Client loaded when given | Not blank | Exists in F01 when given | Mapped | -
Mandatory | Yes | Yes | Conditional: Mandatory for PDC | Conditional: Mandatory for PDC and PICKUP | Conditional: Mandatory for PDC; mapped | No | Conditional: Mandatory for PDC | Yes | Yes | No | Yes | No | Yes | No
Format | Code, up to 10; Upper case | Text, up to 80; As stored in legacy | Text, up to 30; As stored in legacy | Text, up to 40; Digits | Code, up to 30; As stored in legacy | Text, up to 60; Free text | Date, up to 10; yyyy-MM-dd | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Code, up to 30; As stored in legacy | Text, up to 250; Free text | Code, up to 40; As in F01 | Code, up to 20; As stored in legacy | Text, up to 250; Free text
Allowed values | PDC, PICKUP, REFUND (list F06 record_type) | Free entry, up to 80 characters | Free entry, up to 30 characters | Free entry, up to 40 characters | The legacy code; mapped by the code map BANK (sheet Code maps) | Free entry, up to 60 characters | Free entry | ISO 4217 | A number | legacy_client_no of C01 | Free entry, up to 250 characters | legacy_invoice_no of F01 | The legacy code; mapped by the code map STATUS:PDC (sheet Code maps) | Free entry, up to 250 characters
What to enter | Kind of item | Legacy reference of the item | PDC warehouse number | Check number | Drawee bank | Drawee branch | Check date or maturity date | Currency | Amount | Client | Payor | Invoice the item pays or refunds | Status in legacy | Remarks
Row | record_type * | reference * | warehouse_no | check_no | bank_code | check_branch | check_date | currency * | amount * | legacy_client_no | payor_name * | legacy_invoice_no | status * | remarks
Example – overwrite or delete | PDC | PDC-2026-000345 | WH-02 | 0004567 | BPI | BPI Ortigas | 2028-01-15 | PHP | 6000 | Q-0012345 | Ana C. Reyes | I00123456 | WAREHOUSED | Replacement check expected
Note on B19: record_type Kind of item Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: PDC, PICKUP, REFUND (list F06 record_type) Example: PDC
Note on C19: reference Legacy reference of the item Mandatory: Yes Format: Text, up to 80; As stored in legacy Allowed values: Free entry, up to 80 characters Example: PDC-2026-000345
Note on D19: warehouse_no PDC warehouse number Mandatory: Conditional: Mandatory for PDC Format: Text, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: WH-02
Note on E19: check_no Check number Mandatory: Conditional: Mandatory for PDC and PICKUP Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 0004567
Note on F19: bank_code Drawee bank Mandatory: Conditional: Mandatory for PDC; mapped Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map BANK (sheet Code maps) Example: BPI
Note on G19: check_branch Drawee branch Mandatory: No Format: Text, up to 60; Free text Allowed values: Free entry, up to 60 characters Example: BPI Ortigas
Note on H19: check_date Check date or maturity date Mandatory: Conditional: Mandatory for PDC Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-01-15
Note on I19: currency Currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on J19: amount Amount Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 6000.00
Note on K19: legacy_client_no Client Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on L19: payor_name Payor Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on M19: legacy_invoice_no Invoice the item pays or refunds Mandatory: No Format: Code, up to 40; As in F01 Allowed values: legacy_invoice_no of F01 Example: I00123456
Note on N19: status Status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:PDC (sheet Code maps) Example: WAREHOUSED
Note on O19: remarks Remarks Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Replacement check expected

## G01 GL opening trial balance
G01 GL opening trial balance | [10 empty] | Step 24 of 29
← Back to Load templates | Step 24 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per record of GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) as extracted from EBIX GL, ISYS GL. Key tb_version, branch_code, currency, legacy_account_code, cost_center. Sent as the file G01_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: debit_fc, credit_fc, debit_php, credit_php).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2; at each true-up
How it is loaded | Data migration object G01 (Migrate), layout G01 version 1, through the Migration Console; lands in: General ledger journals of type OPENING (value date 1-Jan-2028); at a true-up, reconciliation input only
Source | EBIX GL, ISYS GL
Depends on | R08 Chart of accounts mapping → |  | F01 Open legacy invoices - header → |  | F01S Open legacy invoices - insurer shares → | F01C Open legacy invoices - components and positions → |  | F02 Unapplied premium payments (UPP) →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list; one version per file | One date in the file | Mapped | Valid code | Mapped | Mapped | 0 or more; debit or credit, not both | 0 or more | 0 or more | 0 or more | Mandatory when currency is not PHP
Mandatory | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Conditional: Mandatory when currency is not PHP
Format | Code, up to 12; Upper case | Date, up to 10; yyyy-MM-dd | Code, up to 20; As stored in legacy | Code, up to 3; Upper case | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Decimal, up to 12,6; Dot decimal
Allowed values | PROVISIONAL, TU1, TU2, TU3, FINAL (list G01 tb_version) | Free entry | The legacy code; mapped by the code map BRANCH (sheet Code maps) | ISO 4217 | The legacy code; mapped by the code map GL_ACCOUNT (sheet Code maps) | The legacy code; mapped by the code map COST_CENTER (sheet Code maps) | A number | A number | A number | A number | A number
What to enter | Version of the trial balance - PROVISIONAL at cut-over (preliminary December TB), then TU1, TU2... and FINAL (audited) at the true-ups | Trial balance date - 31-Dec-2027 for every version; the version says which adjustments it includes | Branch | Account currency | Legacy account | Cost centre | Debit balance in the account currency | Credit balance in the account currency | Debit balance in PHP | Credit balance in PHP | Rate used for the PHP amount
Row | tb_version * | as_of_date * | branch_code * | currency * | legacy_account_code * | cost_center | debit_fc * | credit_fc * | debit_php * | credit_php * | fx_rate
Example – overwrite or delete | PROVISIONAL | 2027-12-31 | MKT01 | USD | 1101-02 | 4100 | 12500 | 0 | 701562.5 | 0 | 56.125
Note on B19: tb_version Version of the trial balance - PROVISIONAL at cut-over (preliminary December TB), then TU1, TU2... and FINAL (audited) at the true-ups Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: PROVISIONAL, TU1, TU2, TU3, FINAL (list G01 tb_version) Example: PROVISIONAL
Note on C19: as_of_date Trial balance date - 31-Dec-2027 for every version; the version says which adjustments it includes Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-12-31
Note on D19: branch_code Branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on E19: currency Account currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: USD
Note on F19: legacy_account_code Legacy account Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map GL_ACCOUNT (sheet Code maps) Example: 1101-02
Note on G19: cost_center Cost centre Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (sheet Code maps) Example: 4100
Note on H19: debit_fc Debit balance in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 12500.00
Note on I19: credit_fc Credit balance in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on J19: debit_php Debit balance in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 701562.50
Note on K19: credit_php Credit balance in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on L19: fx_rate Rate used for the PHP amount Mandatory: Conditional: Mandatory when currency is not PHP Format: Decimal, up to 12,6; Dot decimal Allowed values: A number Example: 56.125000

## P03 Renewal advices already sen
P03 Renewal advices already sent before go-live (RA-sent file) | [12 empty] | Step 25 of 29
← Back to Load templates | Step 25 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [11 empty] | Ask a question →
Purpose | One row per record of Renewal advices already sent before go-live (RA-sent file) as extracted from Excel RA trackers of the Renewal processing team. Key legacy_policy_ref. Sent as the file P03_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: proposed_premium).
Provided by | Renewal processing team - makers (corrections) and checkers (resubmission approval); approved by Head of the Renewal processing team; extracted by BDOI IT
Due | M4 (9 Apr 2027) (Trial migration 1); final at T-5
How it is loaded | Data migration object P03 (Migrate), layout P03 version 1, through the Migration Console; lands in: Renewal Advices already sent, given to Renewal with the policy header in the go-live extraction
Source | Excel RA trackers of the Renewal processing team
Depends on | P01 In-force policy headers → |  | P01S Policy insurer shares →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Exists in P01 of the same load | Equals the cover of the P01 header | Equals the P01 expiry; from T to 31-May-2028 | Not after the last legacy business day; warning when more than 140 days before expiry | - | In the list | Masked outside production | Mapped | Mandatory with proposed_premium | 0 or more | Mapped in USER | Not blank | -
Mandatory | Yes | Yes | Yes | Yes | No | Yes | No | No | Conditional: Mandatory with proposed_premium | No | No | Yes | No
Format | Code, up to 60; As in P01 | Text, up to 40; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Text, up to 30; As in the tracker | Code, up to 10; Upper case | Text, up to 250; Free text | Code, up to 30; As stored in legacy | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Code, up to 50; As stored in legacy | Text, up to 120; File / sheet | Text, up to 500; Free text
Allowed values | legacy_policy_ref of P01 | Free entry, up to 40 characters | Free entry | Free entry | Free entry, up to 30 characters | EMAIL, COURIER, HAND, OTHER (list P03 ra_channel) | Free entry, up to 250 characters | The legacy code; mapped by the code map INSURER (sheet Code maps) | ISO 4217 | A number | The legacy code; mapped by the code map USER (sheet Code maps) | Free entry, up to 120 characters | Free entry, up to 500 characters
What to enter | Legacy reference of the expiring policy term | Legacy cover number of the expiring term | Expiry of the expiring term | Date the RA was sent | RA reference, if the tracker gives one | How the RA was sent | Recipient (client name or e-mail address) | Insurer quoted on the RA | Currency of the quoted premium | Gross premium quoted on the RA | Renewal processor who sent the RA | Tracker file and sheet the row comes from | Remarks of the processor
Row | legacy_policy_ref * | cover_no * | expiry_date * | ra_sent_date * | ra_ref | ra_channel * | sent_to | proposed_insurer_code | currency | proposed_premium | sent_by_user_id | tracker_name * | remarks
Example – overwrite or delete | C-2027-004512-01 | C-2027-004512 | 2028-01-15 | 2027-11-16 | RA-2027-018833 | EMAIL | ana.reyes@example.com | MAL | PHP | 24650 | mreyes | Retail RA tracker Jan-2028 / MKT01 | Client asked for a quote with higher SI
Note on B19: legacy_policy_ref Legacy reference of the expiring policy term Mandatory: Yes Format: Code, up to 60; As in P01 Allowed values: legacy_policy_ref of P01 Example: C-2027-004512-01
Note on C19: cover_no Legacy cover number of the expiring term Mandatory: Yes Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: C-2027-004512
Note on D19: expiry_date Expiry of the expiring term Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-01-15
Note on E19: ra_sent_date Date the RA was sent Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-11-16
Note on F19: ra_ref RA reference, if the tracker gives one Mandatory: No Format: Text, up to 30; As in the tracker Allowed values: Free entry, up to 30 characters Example: RA-2027-018833
Note on G19: ra_channel How the RA was sent Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: EMAIL, COURIER, HAND, OTHER (list P03 ra_channel) Example: EMAIL
Note on H19: sent_to Recipient (client name or e-mail address) Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: ana.reyes@example.com
Note on I19: proposed_insurer_code Insurer quoted on the RA Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (sheet Code maps) Example: MAL
Note on J19: currency Currency of the quoted premium Mandatory: Conditional: Mandatory with proposed_premium Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on K19: proposed_premium Gross premium quoted on the RA Mandatory: No Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 24650.00
Note on L19: sent_by_user_id Renewal processor who sent the RA Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (sheet Code maps) Example: mreyes
Note on M19: tracker_name Tracker file and sheet the row comes from Mandatory: Yes Format: Text, up to 120; File / sheet Allowed values: Free entry, up to 120 characters Example: Retail RA tracker Jan-2028 / MKT01
Note on N19: remarks Remarks of the processor Mandatory: No Format: Text, up to 500; Free text Allowed values: Free entry, up to 500 characters Example: Client asked for a quote with higher SI

## H01 Archive records (closed tra
H01 Archive records (closed transactions and history) | [14 empty] | Step 26 of 29
← Back to Load templates | Step 26 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [13 empty] | Ask a question →
Purpose | One row per record of Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) as extracted from EBIX, QPS, ISYS. Key record_type, legacy_key. Sent as the file H01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: amount).
Provided by | Compliance data steward (to name); approved by Audit / Compliance; legacy system owners; extracted by BDOI IT
Due | Before decommissioning
How it is loaded | Data migration object H01 (Archive), layout H01 version 1, through the Migration Console; lands in: BIBS archive (Legacy Inquiry)
Source | EBIX, QPS, ISYS
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list | Unique per record type | - | - | - | - | - | - | Valid date | Valid date | Not before period_from | Valid code | - | - | Every pair has a label and a value
Mandatory | Yes | Yes | No | No | No | No | No | No | Yes | No | No | No | No | No | No
Format | Code, up to 20; Upper case | Code, up to 80; As stored in legacy | Code, up to 30; As stored in legacy | Text, up to 250; Free text | Text, up to 60; As stored in legacy | Text, up to 40; As stored in legacy | Text, up to 40; As printed | Text, up to 40; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Text, up to 40; As stored in legacy | Text, up to 20000; Label: value pairs separated by ;
Allowed values | List H01 record_type: 11 values, see Reference lists | Free entry, up to 80 characters | Free entry, up to 30 characters | Free entry, up to 250 characters | Free entry, up to 60 characters | Free entry, up to 40 characters | Free entry, up to 40 characters | Free entry, up to 40 characters | Free entry | Free entry | Free entry | ISO 4217 | A number | Free entry, up to 40 characters | Free entry, up to 20000 characters
What to enter | Kind of record | Unique key of the record in the source | Client number | Client name | Policy or cover number | Invoice number | AR or OR number | Claim number | Date of the record | Period from | Period to | Currency | Main amount of the record | Status in legacy | Other legacy fields of the record, each as a label and its value
Row | record_type * | legacy_key * | legacy_client_no | client_name | policy_no | invoice_no | receipt_no | claim_no | document_date * | period_from | period_to | currency | amount | status | detail_json
Example – overwrite or delete | INVOICE | I00098765 | Q-0012345 | Ana C. Reyes | MC-PC-22-0004567 | I00098765 | AR-MKT-098001 | CL-2023-000456 | 2022-05-10 | 2022-05-15 | 2023-05-15 | PHP | 18450 | PAID_REMITTED | Insurer: MAL; Remitted on: 01-Jul-2022
Note on B19: record_type Kind of record Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: List H01 record_type: 11 values, see Reference lists Example: INVOICE
Note on C19: legacy_key Unique key of the record in the source Mandatory: Yes Format: Code, up to 80; As stored in legacy Allowed values: Free entry, up to 80 characters Example: I00098765
Note on D19: legacy_client_no Client number Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: Q-0012345
Note on E19: client_name Client name Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on F19: policy_no Policy or cover number Mandatory: No Format: Text, up to 60; As stored in legacy Allowed values: Free entry, up to 60 characters Example: MC-PC-22-0004567
Note on G19: invoice_no Invoice number Mandatory: No Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: I00098765
Note on H19: receipt_no AR or OR number Mandatory: No Format: Text, up to 40; As printed Allowed values: Free entry, up to 40 characters Example: AR-MKT-098001
Note on I19: claim_no Claim number Mandatory: No Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: CL-2023-000456
Note on J19: document_date Date of the record Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2022-05-10
Note on K19: period_from Period from Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2022-05-15
Note on L19: period_to Period to Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2023-05-15
Note on M19: currency Currency Mandatory: No Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on N19: amount Main amount of the record Mandatory: No Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 18450.00
Note on O19: status Status in legacy Mandatory: No Format: Text, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: PAID_REMITTED
Note on P19: detail_json Other legacy fields of the record, each as a label and its value Mandatory: No Format: Text, up to 20000; Label: value pairs separated by ; Allowed values: Free entry, up to 20000 characters Example: Insurer: MAL; Remitted on: 01-Jul-2022

## H02 Archive documents index
H02 Archive documents index | [7 empty] | Step 27 of 29
← Back to Load templates | Step 27 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Legacy documents (policies, SOAs, ORs, certificates, letters) as extracted from File shares, EBIX. Key record_type, legacy_key, file_name. Sent as the file H02_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Compliance data steward (to name); approved by Audit / Compliance; extracted by BDOI IT
Due | Before decommissioning
How it is loaded | Data migration object H02 (Archive), layout H02 version 1, through the Migration Console; lands in: Legacy documents attached to the archive records
Source | File shares, EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list | Record exists in H01 or C01 | Mapped | - | Valid date | File present in the transfer
Mandatory | Yes | Yes | Yes | No | No | Yes | Yes | Yes
Format | Code, up to 20; Upper case | Code, up to 80; As in H01 | Code, up to 40; As stored in legacy | Text, up to 60; As printed | Date, up to 10; yyyy-MM-dd | Text, up to 255; name.ext | Integer, up to 12; Digits | Text, up to 64; Lower-case hex
Allowed values | Same list as H01 record_type | legacy_key of H01 | The legacy code; mapped by the code map DOCUMENT_TYPE (sheet Code maps) | Free entry, up to 60 characters | Free entry | Free entry, up to 255 characters | A whole number | Free entry, up to 64 characters
What to enter | Kind of the archive record the document belongs to | Key of the archive record (or legacy_client_no for KYC documents) | Kind of document | Document number (ID number, policy number) | Date of the document | File name in the transfer folder | File size | SHA-256 of the file, 64 hexadecimal characters
Row | record_type * | legacy_key * | document_type * | document_no | document_date | file_name * | file_size_bytes * | sha256 *
Example – overwrite or delete | CLIENT | Q-0012345 | KYC_ID | P1234567A | 2021-07-02 | Q-0012345_KYC_ID_1.pdf | 245760 | 9f86d081884c7d659a2feaa0c55ad015a3bf4f1b2b0b822cd15d6c15b0f00a08
Note on B19: record_type Kind of the archive record the document belongs to Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: Same list as H01 record_type Example: CLIENT
Note on C19: legacy_key Key of the archive record (or legacy_client_no for KYC documents) Mandatory: Yes Format: Code, up to 80; As in H01 Allowed values: legacy_key of H01 Example: Q-0012345
Note on D19: document_type Kind of document Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map DOCUMENT_TYPE (sheet Code maps) Example: KYC_ID
Note on E19: document_no Document number (ID number, policy number) Mandatory: No Format: Text, up to 60; As printed Allowed values: Free entry, up to 60 characters Example: P1234567A
Note on F19: document_date Date of the document Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2021-07-02
Note on G19: file_name File name in the transfer folder Mandatory: Yes Format: Text, up to 255; name.ext Allowed values: Free entry, up to 255 characters Example: Q-0012345_KYC_ID_1.pdf
Note on H19: file_size_bytes File size Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 245760
Note on I19: sha256 SHA-256 of the file, 64 hexadecimal characters Mandatory: Yes Format: Text, up to 64; Lower-case hex Allowed values: Free entry, up to 64 characters Example: 9f86d081884c7d659a2feaa0c55ad015a3bf4f1b2b0b822cd15d6c15b0f00a08

## G03 FY2027 true-up - legacy adj
G03 FY2027 true-up - legacy adjustment journal lines after the freeze | [18 empty] | Step 28 of 29
← Back to Load templates | Step 28 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [17 empty] | Ask a question →
Purpose | One row per record of FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) as extracted from EBIX GL, ISYS GL; FY2027 adjustment register of Comptrollership. Key legacy_journal_no, line_no. Sent as the file G03_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys; amount totals per currency: debit_fc, credit_fc, debit_php, credit_php).
Provided by | Comptrollership GL lead (prepares each true-up); approved by Head, Comptrollership; extracted by BDOI IT
Due | T+16 (true-up 1); T+92 (final)
How it is loaded | Data migration object G03 (Migrate), layout G03 version 1, through the Migration Console; lands in: General ledger journals of type OPENING (reference MIG-TU-<n>); opening adjustments of the legacy open items and unapplied payments
Source | EBIX GL, ISYS GL; FY2027 adjustment register of Comptrollership
Depends on | G01 GL opening trial balance →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | In the list; one true-up per file | In the FY2027 adjustment register | Unique per journal | From 1-Jan-2027 to 31-Dec-2027 | After the freeze (T-3 22:00) | In the list | Exists in the register | Mapped | Valid code | Mapped; a legacy control account needs G03D detail | Mapped | 0 or more; debit or credit, not both | 0 or more | 0 or more; each journal balances per branch and currency | 0 or more | Mandatory when currency is not PHP | Not blank | On the Comptrollership access list | On the access list; not the preparer
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Conditional: Mandatory when currency is not PHP | Yes | Yes | Yes
Format | Code, up to 2; As listed | Code, up to 30; As stored in legacy | Integer, up to 4; Digits | Date, up to 10; yyyy-MM-dd | Timestamp, up to 19; yyyy-MM-dd HH:mm:ss | Code, up to 8; Upper case | Text, up to 20; As in the register | Code, up to 20; As stored in legacy | Code, up to 3; Upper case | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Decimal, up to 12,6; Dot decimal | Text, up to 250; Free text | Text, up to 50; As in legacy | Text, up to 50; As in legacy
Allowed values | 1, 2, 3, F (list G03 trueup_no) | Free entry, up to 30 characters | A whole number | Free entry | Free entry | CLOSING, AUDIT (list G03 adjustment_kind) | Free entry, up to 20 characters | The legacy code; mapped by the code map BRANCH (sheet Code maps) | ISO 4217 | The legacy code; mapped by the code map GL_ACCOUNT (sheet Code maps) | The legacy code; mapped by the code map COST_CENTER (sheet Code maps) | A number | A number | A number | A number | A number | Free entry, up to 250 characters | Free entry, up to 50 characters | Free entry, up to 50 characters
What to enter | True-up number - 1 after the legacy year-end close, 2 and 3 for interim true-ups, F for the final one after the audited FS | Legacy journal voucher number | Line of the legacy journal | Value date of the legacy journal | When the journal was posted in legacy | Year-end closing or audit adjustment | Reference of the journal in the FY2027 adjustment register | Branch | Account currency | Legacy account | Cost centre | Debit in the account currency | Credit in the account currency | Debit in PHP | Credit in PHP | Rate used for the PHP amount | Journal line description | Legacy user who prepared the journal | Legacy user who approved the journal
Row | trueup_no * | legacy_journal_no * | line_no * | legacy_journal_date * | posted_at * | adjustment_kind * | register_ref * | branch_code * | currency * | legacy_account_code * | cost_center | debit_fc * | credit_fc * | debit_php * | credit_php * | fx_rate | description * | prepared_by * | approved_by *
Example – overwrite or delete | 1 | JV-2027-12-0457 | 1 | 2027-12-31 | 2028-01-14 10:22:05 | CLOSING | ADJ-2027-014 | MKT01 | PHP | 5120-01 | 4100 | 80000 | 0 | 80000 | 0 | 56.125 | Accrual of December 2027 professional fees | cmp.jdelacruz | cmp.head
Note on B19: trueup_no True-up number - 1 after the legacy year-end close, 2 and 3 for interim true-ups, F for the final one after the audited FS Mandatory: Yes Format: Code, up to 2; As listed Allowed values: 1, 2, 3, F (list G03 trueup_no) Example: 1
Note on C19: legacy_journal_no Legacy journal voucher number Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: JV-2027-12-0457
Note on D19: line_no Line of the legacy journal Mandatory: Yes Format: Integer, up to 4; Digits Allowed values: A whole number Example: 1
Note on E19: legacy_journal_date Value date of the legacy journal Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-12-31
Note on F19: posted_at When the journal was posted in legacy Mandatory: Yes Format: Timestamp, up to 19; yyyy-MM-dd HH:mm:ss Allowed values: Free entry Example: 2028-01-14 10:22:05
Note on G19: adjustment_kind Year-end closing or audit adjustment Mandatory: Yes Format: Code, up to 8; Upper case Allowed values: CLOSING, AUDIT (list G03 adjustment_kind) Example: CLOSING
Note on H19: register_ref Reference of the journal in the FY2027 adjustment register Mandatory: Yes Format: Text, up to 20; As in the register Allowed values: Free entry, up to 20 characters Example: ADJ-2027-014
Note on I19: branch_code Branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (sheet Code maps) Example: MKT01
Note on J19: currency Account currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on K19: legacy_account_code Legacy account Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map GL_ACCOUNT (sheet Code maps) Example: 5120-01
Note on L19: cost_center Cost centre Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (sheet Code maps) Example: 4100
Note on M19: debit_fc Debit in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 80000.00
Note on N19: credit_fc Credit in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on O19: debit_php Debit in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 80000.00
Note on P19: credit_php Credit in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on Q19: fx_rate Rate used for the PHP amount Mandatory: Conditional: Mandatory when currency is not PHP Format: Decimal, up to 12,6; Dot decimal Allowed values: A number Example: 56.125000
Note on R19: description Journal line description Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Accrual of December 2027 professional fees
Note on S19: prepared_by Legacy user who prepared the journal Mandatory: Yes Format: Text, up to 50; As in legacy Allowed values: Free entry, up to 50 characters Example: cmp.jdelacruz
Note on T19: approved_by Legacy user who approved the journal Mandatory: Yes Format: Text, up to 50; As in legacy Allowed values: Free entry, up to 50 characters Example: cmp.head

## G03D FY2027 true-up - open-item
G03D FY2027 true-up - open-item detail of the lines on legacy control accounts | [9 empty] | Step 29 of 29
← Back to Load templates | Step 29 of 29. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | One row per record of FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) as extracted from EBIX GL, ISYS GL; FY2027 adjustment register of Comptrollership. Key legacy_journal_no, line_no, item_ref, component. Sent as the file G03D_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: amount).
Provided by | Comptrollership GL lead (prepares each true-up); approved by Head, Comptrollership; extracted by BDOI IT
Due | T+16 (true-up 1); T+92 (final)
How it is loaded | Data migration object G03 (Migrate), layout G03D version 1, through the Migration Console; lands in: General ledger journals of type OPENING (reference MIG-TU-<n>); opening adjustments of the legacy open items and unapplied payments
Source | EBIX GL, ISYS GL; FY2027 adjustment register of Comptrollership
Depends on | G03 FY2027 true-up - legacy adjustment journal lines after the freeze → |  | G01 GL opening trial balance →
Progress | Rows entered |  | Mandatory cells missing
Reviewed by (BU reviewer) |  |  | Review date
BU review
BU comment
Check when loaded | Equals the G03 file | Exists in G03 | Exists in G03; the line is on a legacy control account | In the list | Item loaded | In the list | In the list | Equals the item currency | Open balance stays within 0 and booked + adjusted; detail per account equals the G03 line | Not blank
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Code, up to 2; As listed | Code, up to 30; As in G03 | Integer, up to 4; Digits | Code, up to 8; Upper case | Code, up to 40; As in F01 or F02 | Code, up to 20; Upper case | Code, up to 12; Upper case | Code, up to 3; Upper case | Amount, up to 19,2; Dot decimal, 2 decimals | Text, up to 250; Free text
Allowed values | 1, 2, 3, F (list G03D trueup_no) | legacy_journal_no of G03 | line_no of G03 | INVOICE, UPP (list G03D item_kind) | legacy_invoice_no of F01 or legacy_upp_ref of F02 | List G03D component: 14 values, see Reference lists | ADJUSTED, WRITTEN_OFF (list G03D movement) | ISO 4217 | A number | Free entry, up to 250 characters
What to enter | True-up number, as in G03 | Legacy journal of the line | Line of the legacy journal on the legacy control account | Legacy invoice or legacy UPP | Legacy invoice number (F01) or UPP reference (F02) | Component adjusted (UPP for an unapplied item) | Effect on the open item | Currency of the item | Change of the open balance - positive raises it, negative lowers it | Reason or audit finding
Row | trueup_no * | legacy_journal_no * | line_no * | item_kind * | item_ref * | component * | movement * | currency * | amount * | reason *
Example – overwrite or delete | 1 | JV-2028-AUD-0003 | 2 | INVOICE | I00300002 | BASIC | WRITTEN_OFF | PHP | -3000 | Audit finding 7 - uncollectible premium written off
Note on B19: trueup_no True-up number, as in G03 Mandatory: Yes Format: Code, up to 2; As listed Allowed values: 1, 2, 3, F (list G03D trueup_no) Example: 1
Note on C19: legacy_journal_no Legacy journal of the line Mandatory: Yes Format: Code, up to 30; As in G03 Allowed values: legacy_journal_no of G03 Example: JV-2028-AUD-0003
Note on D19: line_no Line of the legacy journal on the legacy control account Mandatory: Yes Format: Integer, up to 4; Digits Allowed values: line_no of G03 Example: 2
Note on E19: item_kind Legacy invoice or legacy UPP Mandatory: Yes Format: Code, up to 8; Upper case Allowed values: INVOICE, UPP (list G03D item_kind) Example: INVOICE
Note on F19: item_ref Legacy invoice number (F01) or UPP reference (F02) Mandatory: Yes Format: Code, up to 40; As in F01 or F02 Allowed values: legacy_invoice_no of F01 or legacy_upp_ref of F02 Example: I00300002
Note on G19: component Component adjusted (UPP for an unapplied item) Mandatory: Yes Format: Code, up to 20; Upper case Allowed values: List G03D component: 14 values, see Reference lists Example: BASIC
Note on H19: movement Effect on the open item Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: ADJUSTED, WRITTEN_OFF (list G03D movement) Example: WRITTEN_OFF
Note on I19: currency Currency of the item Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: PHP
Note on J19: amount Change of the open balance - positive raises it, negative lowers it Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: -3000.00
Note on K19: reason Reason or audit finding Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Audit finding 7 - uncollectible premium written off

## Reference lists
Reference lists
← Back to Load templates | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | R01 Lists of values and MIS val: active_flag R02 Branches and invoicing bran: invoicing_branch_flag R02 Branches and invoicing bran: active_flag R03 Sales organisation (units a: active_flag R05 Product lines, cover types,: packaged_flag R08 Chart of accounts mapping: branch_specific_flag C01 Client master: bank_client_flag C02 Client addresses and contac: primary_flag C03 Client payout accounts: active_flag P01 In-force policy headers: ffy_flag P01S Policy insurer shares: lead_flag F01 Open legacy invoices - head: dp_flag F01 Open legacy invoices - head: cwt_flag F01 Open legacy invoices - head: incentive_eligible_flag F01 Open legacy invoices - head: hold_flag F01S Open legacy invoices - ins: lead_flag | Y | Yes
|  | N | No
BU review (BU_REVIEW) | R01 Lists of values and MIS val: BU review R02 Branches and invoicing bran: BU review R03 Sales organisation (units a: BU review R04 Insurers: BU review R04B Insurer branches: BU review R05 Product lines, cover types,: BU review R06 Package code map (legacy pa: BU review R07 Commission rates by insurer: BU review R08 Chart of accounts mapping: BU review R09 Payees: BU review R11 Receipt series in use: BU review C01 Client master: BU review C02 Client addresses and contac: BU review C03 Client payout accounts: BU review P01 In-force policy headers: BU review P01S Policy insurer shares: BU review F01 Open legacy invoices - head: BU review F01C Open legacy invoices - com: BU review F01S Open legacy invoices - ins: BU review F02 Unapplied premium payments: BU review F03 Open collection state: BU review F04 Remittance in flight: BU review F06 PDCs, check pick-ups and re: BU review G01 GL opening trial balance: BU review P03 Renewal advices already sen: BU review H01 Archive records (closed tra: BU review H02 Archive documents index: BU review G03 FY2027 true-up - legacy adj: BU review G03D FY2027 true-up - open-item: BU review | Accept
Change requested
Comment
R03 record_type (R03_RECORD_TYPE) | R03 Sales organisation (units a: record_type | REGION
DEPARTMENT
TEAM
AO
R06 qualifier (R06_QUALIFIER) | R06 Package code map (legacy pa: qualifier | RISK_CODE
INSURER
SI_BAND
R06 action (R06_ACTION) | R06 Package code map (legacy pa: action | MAP
REJECT
R08 account_type (R08_ACCOUNT_TYPE) | R08 Chart of accounts mapping: account_type | ASSET
LIABILITY
EQUITY
INCOME
EXPENSE
R08 normal_balance (R08_NORMAL_BALANCE) | R08 Chart of accounts mapping: normal_balance | DR
CR
R08 legacy_control_type (R08_LEGACY_CONTROL_TYPE) | R08 Chart of accounts mapping: legacy_control_type | PR
PR2307
DTIP
COMMISSION_REC
UNREALIZED_COMM
DEFERRED_VAT
UPP
NONE
R09 default_mode (R09_DEFAULT_MODE) | R09 Payees: default_mode | CTA
ATD
MC_DD
CREDIT_TICKET
TT
ONLINE_BANKING
CHECK
R11 kind (R11_KIND) | R11 Receipt series in use: kind | AR
OR
C01 client_type (C01_CLIENT_TYPE) | C01 Client master: client_type | I
C
C02 record_type (C02_RECORD_TYPE) | C02 Client addresses and contac: record_type | ADDRESS
CONTACT
C02 address_type (C02_ADDRESS_TYPE) | C02 Client addresses and contac: address_type | HOME
BUSINESS
MAILING
BILLING
C03 mode (C03_MODE) | C03 Client payout accounts: mode | CTA
CHECK
P01 business_type (P01_BUSINESS_TYPE) | P01 In-force policy headers: business_type | NB
RB
P01 payment_arrangement (P01_PAYMENT_ARRANGEMENT) | P01 In-force policy headers: payment_arrangement | VIA_BDOI
DIRECT
P03 ra_channel (P03_RA_CHANNEL) | P03 Renewal advices already sen: ra_channel | EMAIL
COURIER
HAND
OTHER
F01 invoice_kind (F01_INVOICE_KIND) | F01 Open legacy invoices - head: invoice_kind | BOOKING
ENDORSEMENT_PLUS
ENDORSEMENT_MINUS
CANCELLATION
F01C component (F01C_COMPONENT) | F01C Open legacy invoices - com: component | BASIC
DST
PREMIUM_TAX_VAT
LGT
FST
OTHER
DTIP
COMMISSION
COMMISSION_VAT
WTAX
PR2307
F02 channel (F02_CHANNEL) | F02 Unapplied premium payments: channel | OTC
BILLS_PAYMENT
TRADE
CLPC
DIRECT_CREDIT
CHECK
OTHER
F02 disposition_status (F02_DISPOSITION_STATUS) | F02 Unapplied premium payments: disposition_status | MONITORING
FOR_APPROVAL
IN_PROCESS
F03 record_type (F03_RECORD_TYPE) | F03 Open collection state: record_type | DISPOSITION
PROMISE
INSTALLMENT
ASSIGNMENT
F04 record_type (F04_RECORD_TYPE) | F04 Remittance in flight: record_type | HOLD
SPECIAL
BATCH
F06 record_type (F06_RECORD_TYPE) | F06 PDCs, check pick-ups and re: record_type | PDC
PICKUP
REFUND
G01 tb_version (G01_TB_VERSION) | G01 GL opening trial balance: tb_version | PROVISIONAL
TU1
TU2
TU3
FINAL
G03 trueup_no (G03_TRUEUP_NO) | G03 FY2027 true-up - legacy adj: trueup_no | 1
2
3
F
G03 adjustment_kind (G03_ADJUSTMENT_KIND) | G03 FY2027 true-up - legacy adj: adjustment_kind | CLOSING
AUDIT
G03D trueup_no (G03D_TRUEUP_NO) | G03D FY2027 true-up - open-item: trueup_no | 1
2
3
F
G03D item_kind (G03D_ITEM_KIND) | G03D FY2027 true-up - open-item: item_kind | INVOICE
UPP
G03D component (G03D_COMPONENT) | G03D FY2027 true-up - open-item: component | BASIC
DST
PREMIUM_TAX_VAT
LGT
FST
OTHER
DTIP
COMMISSION
COMMISSION_VAT
WTAX
PR2307
UNREALIZED
DEFERRED_VAT
UPP
G03D movement (G03D_MOVEMENT) | G03D FY2027 true-up - open-item: movement | ADJUSTED
WRITTEN_OFF
H01 record_type (H01_RECORD_TYPE) | H01 Archive records (closed tra: record_type | CLIENT
POLICY
INVOICE
RECEIPT
REMITTANCE
ENDORSEMENT
CLAIM
GL_JOURNAL
RENEWAL_ADVICE
LETTER
OTHER
Status (STATUS) | Load templates: Status | Not started
In progress
Ready for review
Confirmed

## Control file
Control file
The control file sent with every data file (<data file name>.ctl.csv): one row per measure
No. | Column | What it holds | Mandatory | Format | Example
1 | object | Object code of the data file | Y | Upper case; matches the file name | F01
2 | layout | Layout (template) code | Y | Upper case; matches the header row | F01C
3 | source_system | Source system: EBIX, QPS, ISYS, CMS or EXCEL | Y | Upper case; matches the file name | EBIX
4 | data_file | Name of the data file the control file belongs to | Y | <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv or .xlsx | F01C_EBIX_20271231_01.csv
5 | as_of | Date and time the data represents | Y | yyyy-MM-dd HH:mm:ss; not earlier than the previous extract of the layout | 2027-12-31 22:00:00
6 | extracted_at | When the extract ran | Y | yyyy-MM-dd HH:mm:ss; after as_of | 2028-01-01 00:40:12
7 | extracted_by | BDOI IT user who ran the extract | Y | Free text | bdoi.it.jramos
8 | measure | Kind of control: ROW_COUNT, HASH_TOTAL, AMOUNT_TOTAL or SHA256 | Y | Upper case | AMOUNT_TOTAL
9 | column_name | Column the measure applies to | C | As in the header; mandatory for HASH_TOTAL and AMOUNT_TOTAL | open_balance
10 | currency | Currency of an AMOUNT_TOTAL | C | ISO 4217; mandatory for AMOUNT_TOTAL | PHP
11 | filter | Optional filter of the measure | N | column=value | component=BASIC
12 | value | Value of the measure | Y | Digits with a dot decimal for amounts; 64 hexadecimal characters for SHA256 | 98450221.40

## Control example
Control example
Example control file of F01C (made-up values)
object | layout | source_system | data_file | as_of | extracted_at | extracted_by | measure | column_name | currency | filter | value
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | ROW_COUNT |  |  |  | 184220
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | HASH_TOTAL | legacy_invoice_no |  |  | 31207
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | AMOUNT_TOTAL | open_balance | PHP | component=BASIC | 98450221.40
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | AMOUNT_TOTAL | open_balance | PHP | component=DTIP | -84120775.15
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | AMOUNT_TOTAL | open_balance | USD | component=BASIC | 412330.00
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | AMOUNT_TOTAL | booked | PHP |  | 1284533.75
F01C | F01C | EBIX | F01C_EBIX_20271231_01.csv | 2027-12-31 22:00:00 | 2028-01-01 00:40:12 | bdoi.it.jramos | SHA256 |  |  |  | 3a7bd3e2360a3d29eea436fcfb7e44c735d117c42d1c1835420b6b9942dd4f1b

## Control totals
Control totals
Control totals per layout; the tie-out sheet of reconciliation levels L1 to L3 in each run
Layout | Object | Measure | Column | Currency | How it is computed | Value from BDOI | Value in BIBS | Difference | Status
R01 | R01 | ROW_COUNT | - | - | Rows of the data file, header excluded
R01 | R01 | HASH_TOTAL | list_type, code | - | Count of distinct keys
R01 | R01 | SHA256 | - | - | SHA-256 of the data file as sent
R02 | R02 | ROW_COUNT | - | - | Rows of the data file, header excluded
R02 | R02 | HASH_TOTAL | branch_code | - | Count of distinct keys
R02 | R02 | SHA256 | - | - | SHA-256 of the data file as sent
R03 | R03 | ROW_COUNT | - | - | Rows of the data file, header excluded
R03 | R03 | HASH_TOTAL | record_type, unit_code, ao_user_id | - | Row count
R03 | R03 | SHA256 | - | - | SHA-256 of the data file as sent
R04 | R04 | ROW_COUNT | - | - | Rows of the data file, header excluded
R04 | R04 | HASH_TOTAL | insurer_code | - | Count of distinct keys
R04 | R04 | SHA256 | - | - | SHA-256 of the data file as sent
R04B | R04 | ROW_COUNT | - | - | Rows of the data file, header excluded
R04B | R04 | HASH_TOTAL | insurer_code, branch_code | - | Count of distinct keys
R04B | R04 | SHA256 | - | - | SHA-256 of the data file as sent
R05 | R05 | ROW_COUNT | - | - | Rows of the data file, header excluded
R05 | R05 | HASH_TOTAL | risk_code | - | Count of distinct keys
R05 | R05 | SHA256 | - | - | SHA-256 of the data file as sent
R06 | R06 | ROW_COUNT | - | - | Rows of the data file, header excluded
R06 | R06 | HASH_TOTAL | legacy_package_code, legacy_package_version | - | Count of distinct keys
R06 | R06 | SHA256 | - | - | SHA-256 of the data file as sent
R07 | R07 | ROW_COUNT | - | - | Rows of the data file, header excluded
R07 | R07 | HASH_TOTAL | insurer_code, risk_code, effective_from | - | Row count
R07 | R07 | SHA256 | - | - | SHA-256 of the data file as sent
R08 | R08 | ROW_COUNT | - | - | Rows of the data file, header excluded
R08 | R08 | HASH_TOTAL | legacy_account_code | - | Count of distinct keys
R08 | R08 | SHA256 | - | - | SHA-256 of the data file as sent
R09 | R09 | ROW_COUNT | - | - | Rows of the data file, header excluded
R09 | R09 | HASH_TOTAL | payee_code | - | Count of distinct keys
R09 | R09 | SHA256 | - | - | SHA-256 of the data file as sent
R11 | R11 | ROW_COUNT | - | - | Rows of the data file, header excluded
R11 | R11 | HASH_TOTAL | branch_code, kind, prefix | - | Row count
R11 | R11 | SHA256 | - | - | SHA-256 of the data file as sent
C01 | C01 | ROW_COUNT | - | - | Rows of the data file, header excluded
C01 | C01 | HASH_TOTAL | legacy_client_no | - | Count of distinct keys
C01 | C01 | SHA256 | - | - | SHA-256 of the data file as sent
C02 | C01 | ROW_COUNT | - | - | Rows of the data file, header excluded
C02 | C01 | HASH_TOTAL | legacy_client_no, record_type, seq_no | - | Row count
C02 | C01 | SHA256 | - | - | SHA-256 of the data file as sent
C03 | C03 | ROW_COUNT | - | - | Rows of the data file, header excluded
C03 | C03 | HASH_TOTAL | legacy_client_no, account_no | - | Row count
C03 | C03 | SHA256 | - | - | SHA-256 of the data file as sent
P01 | P01 | ROW_COUNT | - | - | Rows of the data file, header excluded
P01 | P01 | HASH_TOTAL | legacy_policy_ref | - | Count of distinct keys
P01 | P01 | AMOUNT_TOTAL | sum_insured | Each currency | Sum per currency
P01 | P01 | AMOUNT_TOTAL | gross_premium | Each currency | Sum per currency
P01 | P01 | AMOUNT_TOTAL | net_premium | Each currency | Sum per currency
P01 | P01 | SHA256 | - | - | SHA-256 of the data file as sent
P01S | P01 | ROW_COUNT | - | - | Rows of the data file, header excluded
P01S | P01 | HASH_TOTAL | legacy_policy_ref, share_seq | - | Row count
P01S | P01 | SHA256 | - | - | SHA-256 of the data file as sent
P03 | P03 | ROW_COUNT | - | - | Rows of the data file, header excluded
P03 | P03 | HASH_TOTAL | legacy_policy_ref | - | Count of distinct keys
P03 | P03 | AMOUNT_TOTAL | proposed_premium | Each currency | Sum per currency
P03 | P03 | SHA256 | - | - | SHA-256 of the data file as sent
F01 | F01 | ROW_COUNT | - | - | Rows of the data file, header excluded
F01 | F01 | HASH_TOTAL | legacy_invoice_no | - | Count of distinct keys
F01 | F01 | AMOUNT_TOTAL | gross_premium | Each currency | Sum per currency
F01 | F01 | AMOUNT_TOTAL | commission | Each currency | Sum per currency
F01 | F01 | AMOUNT_TOTAL | vat_on_commission | Each currency | Sum per currency
F01 | F01 | SHA256 | - | - | SHA-256 of the data file as sent
F01S | F01 | ROW_COUNT | - | - | Rows of the data file, header excluded
F01S | F01 | HASH_TOTAL | legacy_invoice_no, share_seq | - | Row count
F01S | F01 | SHA256 | - | - | SHA-256 of the data file as sent
F01C | F01 | ROW_COUNT | - | - | Rows of the data file, header excluded
F01C | F01 | HASH_TOTAL | legacy_invoice_no, component | - | Row count
F01C | F01 | AMOUNT_TOTAL | booked | Each currency | Sum per currency and component
F01C | F01 | AMOUNT_TOTAL | adjusted | Each currency | Sum per currency and component
F01C | F01 | AMOUNT_TOTAL | paid | Each currency | Sum per currency and component
F01C | F01 | AMOUNT_TOTAL | remitted | Each currency | Sum per currency and component
F01C | F01 | AMOUNT_TOTAL | written_off | Each currency | Sum per currency and component
F01C | F01 | AMOUNT_TOTAL | open_balance | Each currency | Sum per currency and component
F01C | F01 | SHA256 | - | - | SHA-256 of the data file as sent
F02 | F02 | ROW_COUNT | - | - | Rows of the data file, header excluded
F02 | F02 | HASH_TOTAL | legacy_upp_ref | - | Count of distinct keys
F02 | F02 | AMOUNT_TOTAL | amount | Each currency | Sum per currency
F02 | F02 | AMOUNT_TOTAL | balance | Each currency | Sum per currency
F02 | F02 | SHA256 | - | - | SHA-256 of the data file as sent
F03 | F03 | ROW_COUNT | - | - | Rows of the data file, header excluded
F03 | F03 | HASH_TOTAL | legacy_invoice_no, record_type, seq_no | - | Row count
F03 | F03 | AMOUNT_TOTAL | promise_amount | Each currency | Sum per currency
F03 | F03 | AMOUNT_TOTAL | installment_amount | Each currency | Sum per currency
F03 | F03 | SHA256 | - | - | SHA-256 of the data file as sent
F04 | F04 | ROW_COUNT | - | - | Rows of the data file, header excluded
F04 | F04 | HASH_TOTAL | legacy_batch_no, legacy_invoice_no | - | Row count
F04 | F04 | AMOUNT_TOTAL | amount | Each currency | Sum per currency
F04 | F04 | SHA256 | - | - | SHA-256 of the data file as sent
F06 | F06 | ROW_COUNT | - | - | Rows of the data file, header excluded
F06 | F06 | HASH_TOTAL | record_type, reference | - | Row count
F06 | F06 | AMOUNT_TOTAL | amount | Each currency | Sum per currency
F06 | F06 | SHA256 | - | - | SHA-256 of the data file as sent
G01 | G01 | ROW_COUNT | - | - | Rows of the data file, header excluded
G01 | G01 | HASH_TOTAL | tb_version, branch_code, currency, legacy_account_code, cost_center | - | Row count
G01 | G01 | AMOUNT_TOTAL | debit_fc | Each currency | Sum per currency
G01 | G01 | AMOUNT_TOTAL | credit_fc | Each currency | Sum per currency
G01 | G01 | AMOUNT_TOTAL | debit_php | Each currency | Sum per currency
G01 | G01 | AMOUNT_TOTAL | credit_php | Each currency | Sum per currency
G01 | G01 | SHA256 | - | - | SHA-256 of the data file as sent
G03 | G03 | ROW_COUNT | - | - | Rows of the data file, header excluded
G03 | G03 | HASH_TOTAL | legacy_journal_no | - | Count of distinct keys
G03 | G03 | AMOUNT_TOTAL | debit_fc | Each currency | Sum per currency
G03 | G03 | AMOUNT_TOTAL | credit_fc | Each currency | Sum per currency
G03 | G03 | AMOUNT_TOTAL | debit_php | Each currency | Sum per currency
G03 | G03 | AMOUNT_TOTAL | credit_php | Each currency | Sum per currency
G03 | G03 | SHA256 | - | - | SHA-256 of the data file as sent
G03D | G03 | ROW_COUNT | - | - | Rows of the data file, header excluded
G03D | G03 | HASH_TOTAL | legacy_journal_no, line_no, item_ref, component | - | Row count
G03D | G03 | AMOUNT_TOTAL | amount | Each currency | Sum per currency
G03D | G03 | SHA256 | - | - | SHA-256 of the data file as sent
H01 | H01 | ROW_COUNT | - | - | Rows of the data file, header excluded
H01 | H01 | HASH_TOTAL | record_type, legacy_key | - | Count of distinct keys
H01 | H01 | AMOUNT_TOTAL | amount | Each currency | Sum per currency
H01 | H01 | SHA256 | - | - | SHA-256 of the data file as sent
H02 | H02 | ROW_COUNT | - | - | Rows of the data file, header excluded
H02 | H02 | HASH_TOTAL | record_type, legacy_key, file_name | - | Row count
H02 | H02 | SHA256 | - | - | SHA-256 of the data file as sent

## Code maps
Code maps
Code map sets of the Migration Console (BRID 3.1): one per domain, versioned and approved by the business owner
Code map | What is mapped | BIBS values | Used by layouts | Approves (G2) | Prepares | First approved version due | BU review | BU comment | Reviewer | Review date
INSURER | Legacy insurer code to BIBS insurer | Insurers | R04, R06, R07, P01S, P03, F01S, F04 | Head, Operations | Operations data steward | M5 (18 Jun 2027)
INSURER_BRANCH | Legacy insurer branch to BIBS insurer branch | Insurer branches | R04B, P01S | Head, Operations | Operations data steward | M5 (18 Jun 2027)
LINE | Legacy line of business to BIBS product line | Product lines | R05, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
COVER_TYPE | Legacy cover type to BIBS cover type | Cover types | R05, P01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
PRODUCT | Legacy product / risk code to BIBS product code | Products and risk codes | R05, R06, R07, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
PACKAGE | Legacy package and version to the BIBS package version maintained by TSU; conditional entries (risk code, insurer, sum-insured band) where one legacy package splits. Loaded as reference data (R06) for | Package versions (Renewal package map) | R06 | Product Owner, MBS (approves) | TSU (prepares) | M5 (18 Jun 2027)
BRANCH | Legacy branch to BIBS branch | Branches | R02, R03, R11, C01, P01, F01, F02, G01, G03 | Head, Comptrollership | Comptrollership data steward | M5 (18 Jun 2027)
SALES_UNIT | Legacy region, department and team to BIBS sales unit | Sales units | R03, C01, P01, F01, F02 | Heads, Retail and Corporate Marketing | Marketing data steward | M5 (18 Jun 2027)
AO | Legacy AO code to BIBS account officer | Account officers | R03 | Heads, Retail and Corporate Marketing | Marketing data steward | M5 (18 Jun 2027)
USER | Legacy user ID to BIBS username (AO, handler, collector, requester) | BIBS users (User Access) | R03, C01, P01, P03, F01, F03, F04 | Unit Head, Analytics and Risk Management | IT security administrator | M5 (18 Jun 2027)
COST_CENTER | Legacy cost centre to BIBS cost centre | Cost centres | R03, F01, G01, G03 | Head, Comptrollership | Comptrollership data steward | M5 (18 Jun 2027)
GL_ACCOUNT | Legacy GL account to BIBS account (legacy control accounts to Migration Clearing; lines on P&L accounts post to retained earnings in the opening and the true-ups) | Chart of accounts | R08, G01, G03 | Head, Comptrollership | Comptrollership data steward | M5 (18 Jun 2027)
BANK | Legacy bank code to BIBS bank list | Bank list | R09, C03, P01, F06 | Product Owner, Comptrollership - Disbursement | Disbursement data steward | M5 (18 Jun 2027)
CURRENCY | Legacy currency code to ISO 4217 | Currencies (ISO 4217) | All amount layouts | Head, Comptrollership | Comptrollership data steward | M5 (18 Jun 2027)
DISPOSITION_TYPE | Legacy UPP disposition types to BIBS disposition types | Cashiering disposition types | F02 | Operations - Financial Transactions | Cashiering data steward | M5 (18 Jun 2027)
DISPOSITION_CLX | Legacy collection dispositions to BIBS collection dispositions | Collections dispositions | F03 | Head, Operations (Collections) | Collections data steward | M5 (18 Jun 2027)
DOCUMENT_TYPE | Legacy document types to archive document types | Document types of the archive | H02 | Compliance | Compliance data steward | Before the first archive load
LOV:CIVIL_STATUS | Legacy values of the list civil status | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:ID_TYPE | Legacy values of the list ID type | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:KYC_RISK_RATING | Legacy values of the list kyc risk rating | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:MARKET_SEGMENT | Legacy values of the list market segment | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:NATIONALITY | Legacy values of the list nationality | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:PAYEE_CLASS | Legacy values of the list payee class | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
LOV:SOURCE_OF_FUNDS | Legacy values of the list source of funds | Lists of values | R01, C01, P01, F01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
MIS:BUSINESS_ORIGIN | Legacy values of the MIS field business origin | MIS fields | R01, C01, P01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
MIS:CUSTOMER_SEGMENT | Legacy values of the MIS field customer segment | MIS fields | R01, C01, P01 | Product Owner, MBS | MBS data steward | M5 (18 Jun 2027)
STATUS:CLIENT | Legacy statuses of client | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:INSURER | Legacy statuses of insurer | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:KYC | Legacy statuses of kyc | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:PDC | Legacy statuses of pdc | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:POLICY | Legacy statuses of policy | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:PRODUCT | Legacy statuses of product | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:REMITTANCE | Legacy statuses of remittance | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)
STATUS:UPP | Legacy statuses of upp | Status of the BIBS record | C01, R04, R05, P01, F02, F04, F06 | Owner of the object | Steward of the object | M5 (18 Jun 2027)

## Code map template
Code map template
Columns of a code map version as exported and imported in Excel on the Code Maps screen (the columns source_system to remarks; illustrative rows)
Code map | source_system | legacy_code | legacy_description | qualifier | qualifier_value | action | target_code | remarks | Rows using it
INSURER | EBIX | MAL | Malayan Insurance Co., Inc. |  |  | MAP | INS-MAL |  | 1,240
INSURER | QPS | 0012 | Malayan Insurance |  |  | MAP | INS-MAL | QPS numeric code of the same insurer | 310
LOV:MARKET_SEGMENT | QPS | CBG | Consumer Banking Group |  |  | MAP | CBG |  | 88,410
LOV:MARKET_SEGMENT | QPS | OLD-RET | Retail (discontinued 2019) |  |  | DEFAULT |  | Segment discontinued; the default of the set applies | 12
PRODUCT | EBIX | MC-PC-COMP | Private Car Own Damage and Theft |  |  | MAP | MCPC01 |  | 41,002
STATUS:UPP | EBIX | FOR_MONITORING | For monitoring |  |  | MAP | MONITORING | Monitoring tab of the Unapplied workbench | 815
USER | QPS | mreyes | Maria Reyes |  |  | MAP | maria.reyes | BIBS user created through User Access | 3,112
MIS:BUSINESS_ORIGIN | QPS | WALKIN | Walk-in |  |  | CREATE | WALK_IN | New MIS value; authorised in the LOV master | 57
PACKAGE | QPS | PKG-MC-PRIV | Private Car Package 2027 | SI_BAND | 0.00-2000000.00 | MAP | MC-PRIVATE-STD v1 | Sum insured up to 2,000,000.00 (DMQ36) | 18,240
PACKAGE | QPS | PKG-MC-PRIV | Private Car Package 2027 | SI_BAND | 2000000.01-999999999.99 | MAP | MC-PRIVATE-HV v1 | Sum insured above 2,000,000.00 (DMQ36) | 1,115
PACKAGE | QPS | PKG-HOME-01 | Home Protect (withdrawn) |  |  | REJECT |  | No BIBS package; at renewal the candidate goes to the Exception bucket (Renewal processing team) | 96

## Validation rules
Validation rules
Data-quality rules applied to every staged row (Layouts and Rules, Data-Quality Rules). Thresholds: master data 0.5 percent rejected or waived; financial objects none
Rule | Layouts | Columns | Kind | Rule | Severity | Message | Fixed by | BU review | BU comment | Reviewer | Review date
DQ-001 | All | Mandatory columns | Mandatory | A column marked Y in the layout has a value; a column marked C has a value when its condition holds | Error - the row is not loaded | {field} is mandatory | BDOI data steward (fix at source)
DQ-002 | All | Date and amount columns | Format | Dates are yyyy-MM-dd; timestamps yyyy-MM-dd HH:mm:ss; amounts have a dot decimal, 2 decimals and no thousands separator | Error - the row is not loaded | {field} {value} is not a valid {type} | BDOI IT (extract)
DQ-003 | All | Coded columns | Code map | Every coded column has an entry in the approved version of its code map set | Error - the row is not loaded | Code {code} of {set} is not mapped | Data Steward (code map)
DQ-004 | All | Key columns | Unique | The legacy key of the layout is unique in the file | Error - the row is not loaded | {key} appears twice | BDOI IT (extract)
DQ-005 | All | Length | Format | No value is longer than the length of the layout | Error - the row is not loaded | {field} is longer than {n} characters | BDOI data steward
DQ-006 | C01 | tin | Format | TIN has 9 to 12 digits after removing separators | Error - the row is not loaded | TIN {value} is not valid | BDOI data steward
DQ-007 | C01 | email, mobile | Format | E-mail and PH mobile follow the client formats of BIBS (09xxxxxxxxx or +639xxxxxxxxx) | Warning - loaded and reported | {field} {value} is not valid; it is loaded blank | BDOI data steward
DQ-008 | C01 | birth_date | Plausibility | Birth date not in the future and age at most 120 years | Error - the row is not loaded | Birth date {value} is not plausible | BDOI data steward
DQ-009 | C01 | client_type, names | Cross-field | Individual has last and first name; corporate has corporate name | Error - the row is not loaded | {field} is mandatory for client type {type} | BDOI data steward
DQ-010 | C01 | All identity keys | Duplicate client | Pairs scoring 90 or more merge automatically; 60 to 89 go to the review queue | Warning - loaded and reported | {n} client pairs are waiting for review | Data Steward (review queue)
DQ-011 | C01 | created_date | Plausibility | Client in scope per (created from 2020, or with an in-force policy or open item) | Warning - loaded and reported | Client {no} is outside the migration scope | Data owner (decision)
DQ-012 | C02 | legacy_client_no | Reference | The client exists in C01 of the same source | Error - the row is not loaded | {parent} {key} is not loaded | BDOI IT (extract)
DQ-013 | C02 | primary_flag | Cross-field | One primary ADDRESS per client | Warning - loaded and reported | Client {no} has {n} primary addresses; the latest is kept | BDOI data steward
DQ-014 | P01 | inception_date, expiry_date | Cross-field | Expiry after inception and on or after the cut-over date | Error - the row is not loaded | The expiry date is before the inception date | BDOI data steward
DQ-015 | P01S | share_pct | Cross-field | Shares of a policy add up to 100 and exactly one lead | Error - the row is not loaded | Insurer shares add up to {x} percent | BDOI data steward
DQ-016 | P01 | legacy_client_no | Reference | The client is loaded (cross-reference of migrated keys) or in the same load | Error - the row is not loaded | {parent} {key} is not loaded | iorta TechNXT (load order) / BDOI (extract)
DQ-017 | P01 | risk_code, line_code | Cross-field | The product belongs to the line (line of the product in the product master) | Error - the row is not loaded | Product {code} is not in line {line} | Data Steward (code map)
DQ-018 | P03 | legacy_policy_ref | Reference | The expiring policy header exists in P01 of the same load | Error - the row is not loaded | Cover {no} has no migrated header | Renewal processing team (maker)
DQ-019 | P03 | expiry_date | Cross-field | Expiry equals the P01 expiry and falls from the cut-over date T to 31-May-2028 (go-live renewal window) | Error - the row is not loaded | Expiry {date} is outside the go-live renewal window or differs from the header | Renewal processing team (maker)
DQ-020 | F01 | legacy_invoice_no | Unique | Invoice number unique across EBIX and QPS; a collision is prefixed with the source system | Warning - loaded and reported | Invoice {no} exists in two source systems; loaded as {source}-{no} | iorta TechNXT (loader)
DQ-021 | F01 | gross_premium | Cross-field | Gross premium = sum of the booked amounts of the six premium components in F01C | Error - the row is not loaded | The premium components add up to {x}; the gross premium is {y} | BDOI IT (extract)
DQ-022 | F01C | open_balance | Balance | Premium components and PR2307 - open = booked + adjusted - paid - written off; DTIP, commission, VAT on commission, WTAX - open = booked + adjusted - remitted - written off | Error - the row is not loaded | The open balance of {component} does not equal booked + adjusted - paid / remitted - written off | BDOI IT (extract)
DQ-023 | F01C | open_balance | Balance | Open balance within 0 and booked + adjusted (same sign as the invoice) | Error - the row is not loaded | The open balance of {component} is outside the booked amount | BDOI data steward
DQ-024 | F01 | every row | Cross-field | At least one component has an open balance | Warning - loaded and reported | Invoice {no} has no open balance | Data owner (decision)
DQ-025 | F01S | share_pct | Cross-field | Shares of an invoice add up to 100 and exactly one lead | Error - the row is not loaded | Insurer shares add up to {x} percent | BDOI data steward
DQ-026 | F01 | parent_invoice_no | Reference | The parent invoice of an endorsement invoice is in the file or loaded | Error - the row is not loaded | {parent} {key} is not loaded | BDOI IT (extract)
DQ-027 | F01 | commission_realised, deferred_vat_open | Balance | Realised commission within 0 and commission; deferred VAT within 0 and VAT on commission | Error - the row is not loaded | {field} is outside 0 and {limit} | BDOI (Comptrollership)
DQ-028 | F01 | due_date | Plausibility | Invoice open more than 5 years | Warning - loaded and reported | Invoice {no} has been open since {date} | Data owner (review)
DQ-029 | F01 | currency, booking_fx_rate | Cross-field | Foreign-currency invoice has a booking rate | Error - the row is not loaded | booking_fx_rate is mandatory for currency {currency} | BDOI IT (extract)
DQ-030 | F02 | balance, amount | Balance | Balance above 0 and at most amount | Error - the row is not loaded | The balance is more than the amount received | BDOI data steward
DQ-031 | F02 | ref_ columns | Plausibility | At least one match reference is given | Warning - loaded and reported | UPP {ref} has no reference to match; it stays for manual disposition | BDOI data steward
DQ-032 | F02 | value_date | Plausibility | UPP older than 2 years | Warning - loaded and reported | UPP {ref} is older than 2 years | Data owner (review; candidate for income reclassification)
DQ-033 | F03 | legacy_invoice_no | Reference | The invoice is in F01 | Error - the row is not loaded | {parent} {key} is not loaded | BDOI IT (extract)
DQ-034 | F03 | promise_amount | Balance | Promise at most the open premium receivable of the invoice | Warning - loaded and reported | Promise {amount} is above the open balance {balance} | BDOI data steward
DQ-035 | F04 | amount | Balance | Hold or special amount at most the open DTIP of the invoice | Error - the row is not loaded | Amount {x} is above the open DTIP {y} | BDOI data steward
DQ-036 | F06 | check_no, bank_code | Unique | Check number and bank unique among PDCs | Error - the row is not loaded | Check {no} of {bank} appears twice | BDOI data steward
DQ-037 | G01 | debit_php, credit_php | Balance | Total debit = total credit per branch and currency | Error - the row is not loaded | The trial balance of {branch} {currency} is out of balance by {x} | BDOI (Comptrollership)
DQ-038 | G01 | debit_fc, credit_fc | Cross-field | A line is debit or credit and not both | Error - the row is not loaded | Line {account} has a debit and a credit | BDOI IT (extract)
DQ-039 | G01 | legacy_account_code | Code map | Every account maps to a BIBS account or to Migration Clearing (legacy control accounts) | Error - the row is not loaded | Account {code} is not mapped | BDOI (Comptrollership)
DQ-040 | G01 with F01 and F02 | control accounts | Balance | Per branch and currency, the trial balance lines of each legacy control account equal the F01 / F02 opening detail (Migration Clearing nets to 0.00) | Error - the row is not loaded | Migration Clearing is {amount} in {branch} {currency}; it must be zero | BDOI (Comptrollership) with iorta
DQ-041 | R11 | next_no | Cross-field | The next number is the last used number + 1 and lies within the series (from and to numbers) | Error - the row is not loaded | Next number {n} is outside the series | BDOI data steward
DQ-042 | R06 | share_pct | Cross-field | Shares of a package version add up to 100 | Error - the row is not loaded | Insurer shares add up to {x} percent | BDOI data steward
DQ-043 | R07 | effective_from, effective_to | Cross-field | No two rates overlap for the same insurer and product | Error - the row is not loaded | Rates of {insurer} {product} overlap | BDOI data steward
DQ-044 | H01 | record_type, legacy_key | Unique | Key unique per record type | Error - the row is not loaded | {key} appears twice | BDOI IT (extract)
DQ-045 | H02 | sha256, file_size_bytes | Format | Checksum and size equal the received file | Error - the row is not loaded | File {name} does not match its checksum | BDOI IT (transfer)
DQ-046 | All | as_of (control file) | Format | The data file agrees with its control file - SHA-256, row count, amount totals, hash total | Error - the row is not loaded | The file has {n} rows; the control file says {m} | BDOI IT (extract)
DQ-047 | P03 | ra_sent_date | Cross-field | The RA date is not after the last legacy business day (T-5) | Error - the row is not loaded | RA date {date} is after the last legacy business day | Renewal processing team (maker)
DQ-048 | P03 | ra_sent_date, expiry_date | Plausibility | The RA date is not more than 140 days before the expiry | Warning - loaded and reported | RA date {date} is more than 140 days before expiry {expiry}; check the tracker | Renewal processing team (checker)
DQ-049 | P03 with P01 | legacy_policy_ref, expiry_date | Reference | Not renewed in legacy already - no P01 term of the same cover starts on this expiry | Error - the row is not loaded | Cover {no} was already renewed in legacy as {ref}; remove the row | Renewal processing team (maker)
DQ-052 | G03 | debit_php, credit_php, debit_fc, credit_fc | Balance | Each legacy journal balances per branch and currency | Error - the row is not loaded | Journal {no} is out of balance by {amount} in {branch} {currency} | BDOI (Comptrollership)
DQ-053 | G03 | legacy_journal_date, posted_at | Cross-field | Journal dated in FY2027 (1-Jan to 31-Dec-2027) and posted in legacy after the freeze (T-3 22:00) | Error - the row is not loaded | Journal {no} is dated {date}, outside FY2027 | BDOI (Comptrollership)
DQ-054 | G03 | register_ref, prepared_by, approved_by | Reference | The journal is in the FY2027 adjustment register; preparer and approver are on the Comptrollership access list and are different users | Error - the row is not loaded | Journal {no} is not in the FY2027 adjustment register | BDOI (Comptrollership)
DQ-055 | G03 with G03D | legacy_account_code, amount | Balance | Per legacy journal line on a legacy control account, the G03D detail adds up to the line (branch and currency) | Error - the row is not loaded | {account} adjustment of {amount} has no matching open-item detail | BDOI (Comptrollership)
DQ-056 | G03D | item_ref, component, amount | Reference | The item is loaded (F01 or F02) and the adjustment keeps its open balance within 0 and booked + adjusted | Error - the row is not loaded | Adjustment of {component} on {item} makes the open balance {amount} | BDOI (Comptrollership)

## Masking
Masking
Personal data masked when a file is received in any environment other than production
Layout | Column | Masking outside production | BU review | BU comment | Reviewer | Review date
C01 | last_name | Substitute last name
C01 | first_name | Substitute first name
C01 | middle_name | Substitute first name
C01 | corporate_name | Substitute company name
C01 | birth_date | Date shifted by up to 30 days
C01 | tin | Digits replaced, length kept
C01 | id_number | Digits replaced, length kept
C01 | bank_cif | Digits replaced, length kept
C01 | email | Substitute e-mail address
C01 | mobile | Digits replaced, length kept
C01 | phone | Digits replaced, length kept
C01 | address_line | Substitute address
C02 | address_line | Substitute address
C02 | contact_name | Substitute name
C02 | email | Substitute e-mail address
C02 | mobile | Digits replaced, length kept
C03 | payee_name | Substitute name
C03 | account_no | Digits replaced, length kept
P01 | assured_name | Substitute name
P03 | sent_to | Substitute name
F01 | assured_name | Substitute name
F01 | payor_name | Substitute name
F02 | payor_name | Substitute name
F06 | payor_name | Substitute name
F06 | check_no | Digits replaced, length kept
R09 | name | Substitute company name
R09 | tin | Digits replaced, length kept
R09 | email | Substitute e-mail address
R09 | address | Substitute address
R09 | account_no | Digits replaced, length kept
H01 | client_name | Substitute name

## Cut-over tasks
Cut-over tasks
The production cut-over plan from T-30 to the close of the opening-balance adjustments
Task | Phase | Day | Start (PHT) | Task | Owner | Hours | After | Verification | Checkpoint | Assignee (name) | Status | BU review | BU comment | Reviewer | Review date
CT-001 | A Readiness | T-30 |  | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed, go-live renewal extraction run) | DML | 4 |  | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |  |  | NOT STARTED
CT-002 | A Readiness | T-30 |  | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25) with Comptrollership's confirmation of the year-end option A (DMQ39); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated; option A confirmed in writing by the Head of Comptrollership |  |  | NOT STARTED
CT-003 | A Readiness | T-29 |  | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |  |  | NOT STARTED
CT-004 | A Readiness | T-28 |  | Freeze the production cutover plan in the Migration Console (plan kind Production cut-over, tasks and owners from this list) | IML | 4 | CT-002 | the Cutover Runbook Status report shows the plan with every task owned |  |  | NOT STARTED
CT-005 | A Readiness | T-28 |  | Production environment ready - the go-live release of BIBS installed; migration parameters set (environment class Production, go-live date T, opening value date 1-Jan-2028, go-live renewal window to 31-May-2028, urgent renewals to 31-Jan-2028); scheduled jobs set | IDO | 8 |  | Deployment record; parameter screen; job list |  |  | NOT STARTED
CT-006 | A Readiness | T-27 |  | Grant the migration roles in production (Data Migration Lead, Data Steward, data owner, Migration Operator, reconciliation approver, go / no-go board), the opening-balance adjustment rights of Comptrollership and the P03 rights of the Renewal processing team (maker and checker) through User Access requests; check the Philippines-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |  |  | NOT STARTED
CT-007 | A Readiness | T-25 |  | Comptrollership sets up in production the legacy control accounts, Migration Clearing, the LG_ accounting rule lines (DMQ18) and the retained earnings account of the opening, through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |  |  | NOT STARTED
CT-008 | A Readiness | T-25 |  | Approve the final code map versions for production (all sets, including the package code map loaded for Renewal); record versions in the plan | OWN | 16 |  | the Code Map Versions report lists one approved version per set |  |  | NOT STARTED
CT-009 | A Readiness | T-24 |  | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |  |  | NOT STARTED
CT-010 | A Readiness | T-21 |  | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-6) |  |  | NOT STARTED
CT-011 | A Readiness | T-21 |  | Legacy December soft close - accruals and cut-offs, bank reconciliations, sub-ledger to GL reconciliations, known year-end adjustments posted - completed by 20 December 2027 (T-14) | COMP | 56 |  | Soft-close checklist signed by the Head of Comptrollership on 20 Dec 2027 |  |  | NOT STARTED
CT-012 | A Readiness | T-20 |  | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Trial migration 3, unmapped codes | STW | 80 |  | Clean-up tracker; counts reduced against Trial migration 3 profiling |  |  | NOT STARTED
CT-013 | A Readiness | T-20 |  | Renewal processing team ready for the January expiries - staffing plan for January (handlers, overtime, back-up) signed; BIBS Renewal training completed; day-1 priority queue worked on the Trial migration 4 and dress-rehearsal data; draft RA-sent file from the Excel trackers validated and its rejects reviewed (maker-checker) | RNW | 16 | CT-009 | Staffing plan signed by the Head of the Renewal processing team; draft P03 validated; rejects corrected and approved |  |  | NOT STARTED
CT-014 | A Readiness | T-18 |  | Secure file drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |  |  | NOT STARTED
CT-015 | A Readiness | T-15 |  | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-013, CT-014 | Decision recorded in the console with the GNG-1 criteria | GNG-1 |  | NOT STARTED
CT-016 | B Pre-load and daily deltas | T-14 | 08:00 | Take a full backup (snapshot) of production before the pre-load | IDO | 1 | CT-015 | Snapshot ID recorded in the plan |  |  | NOT STARTED
CT-017 | B Pre-load and daily deltas | T-14 | 09:00 | Extract and send R01-R08 and R11 (current values; R06 is the package code map prepared by TSU) with control files | BIT | 6 | CT-016 | Files received; intake checks passed (extract status CHECKED) |  |  | NOT STARTED
CT-018 | B Pre-load and daily deltas | T-14 | 15:00 | Validate and load reference data R01-R08 (R06 into the Renewal package map); authorise CREATE values in each master | IOP | 8 | CT-017 | Batches loaded; the Unmapped Legacy Codes report empty for R objects |  |  | NOT STARTED
CT-019 | B Pre-load and daily deltas | T-13 |  | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-018 | the Sign-off Status report shows G6 for R01-R08 |  |  | NOT STARTED
CT-020 | B Pre-load and daily deltas | T-13 |  | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-019 | Batch accepted |  |  | NOT STARTED
CT-021 | B Pre-load and daily deltas | T-12 |  | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-019 | Files CHECKED; counts against the Trial migration 4 volumes within 5 percent |  |  | NOT STARTED
CT-022 | B Pre-load and daily deltas | T-12 |  | Validate clients; run matching; clear the review queue | STW | 24 | CT-021 | Review queue empty; the Client Matching report reviewed |  |  | NOT STARTED
CT-023 | B Pre-load and daily deltas | T-11 |  | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-022 | the Reconciliation Summary report all matched or explained; G6 signed |  |  | NOT STARTED
CT-024 | B Pre-load and daily deltas | T-11 |  | Daily client delta (new and changed clients of the day) from T-11 to T-5 - extract 23:00, load 00:30 (daily client delta job) | BIT | 1 | CT-023 | Delta batch accepted each morning by 07:00 |  |  | NOT STARTED
CT-025 | B Pre-load and daily deltas | T-12 |  | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 |  | List of carried items for F04 agreed by Operations - Remittance |  |  | NOT STARTED
CT-026 | B Pre-load and daily deltas | T-12 |  | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, renewals placed or bound in legacy and not yet booked (booked before the freeze so that the new term migrates as a header), check pick-ups, refunds (DMQ33) | OPS | 40 |  | In-flight list reduced; the rest listed for carry-forward or re-keying |  |  | NOT STARTED
CT-027 | B Pre-load and daily deltas | T-7 |  | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-019 | Freeze notice sent; change log opened |  |  | NOT STARTED
CT-028 | B Pre-load and daily deltas | T-7 |  | Legacy reference-data change freeze in EBIX and QPS (insurers, products, packages, AOs, branches) | BIT | 1 | CT-027 | Maintenance screens locked or change log reviewed daily |  |  | NOT STARTED
CT-029 | B Pre-load and daily deltas | T-7 |  | Dry run of the final extract jobs on the current day's data (timing and control files; P01 covers every expiry to 31-May-2028 and every booked renewal term starting on or after T) | BIT | 6 | CT-017 | Extract timings within the plan; control files correct; P01 dry run checked against the legacy in-force list |  |  | NOT STARTED
CT-030 | B Pre-load and daily deltas | T-5 |  | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-013, CT-023, CT-024, CT-025, CT-026, CT-029 | Decision recorded with the GNG-2 criteria | GNG-2 |  | NOT STARTED
CT-031 | B Pre-load and daily deltas | T-5 |  | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-030 | Communication plan item 7 sent |  |  | NOT STARTED
CT-032 | B Pre-load and daily deltas | T-5 | 17:00 | Last legacy business day - last business transactions; cashiers deposit and close; UPP of the day recorded (30 and 31 December are holidays, DMQ39) | OPS | 3 | CT-030 | Branch close checklist from every branch |  |  | NOT STARTED
CT-033 | B Pre-load and daily deltas | T-5 | 18:00 | Final RA-sent file (P03) compiled from the Excel trackers with the RAs sent up to the last business day (maker); the checker compares it with the trackers and releases it; trackers closed for new RAs | RNW | 3 | CT-032 | File and control file ready; checker's release recorded |  |  | NOT STARTED
CT-034 | B Pre-load and daily deltas | T-5 | 18:00 | Name the Comptrollership users who may post FY2027 closing and audit adjustments in the legacy GL after the freeze; open the FY2027 adjustment register | COMP | 2 | CT-030 | Access list signed by the Head of Comptrollership; register opened |  |  | NOT STARTED
CT-035 | C Legacy freeze and final extracts | T-3 | 20:00 | Last legacy EOD (EBIX, QPS, ISYS, CMS); preliminary December 2027 trial balance run | BIT | 2 | CT-032 | EOD logs complete without error; preliminary TB printed per branch and currency |  |  | NOT STARTED
CT-036 | C Legacy freeze and final extracts | T-3 | 22:00 | Legacy business freeze - EBIX, QPS, CMS business modules set to read-only; batch jobs that post are disabled; legacy GL restricted to the named Comptrollership users and to FY2027 periods (FY2028 periods are not opened in legacy) | BIT | 1 | CT-035, CT-034 | Test posting refused in each business module and by a GL user not on the list; job list shows disabled jobs | FREEZE |  | NOT STARTED
CT-037 | C Legacy freeze and final extracts | T-3 | 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-036 | Last delta batch accepted |  |  | NOT STARTED
CT-038 | C Legacy freeze and final extracts | T-3 | 22:30 | Final extracts after the EOD - P01, P01S, P03 (the RA-sent file of the Renewal processing team), F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 preliminary December TB (version PROVISIONAL) | BIT | 5 | CT-036, CT-033 | Every file and control file in the intake; SHA-256 recorded |  |  | NOT STARTED
CT-039 | C Legacy freeze and final extracts | T-3 | 23:30 | Comptrollership signs the preliminary December trial balance as the provisional opening - balanced per branch and currency, with the FY2027 result per branch and currency | COMP | 2 | CT-035 | Signed TB totals and FY2027 result per branch and currency |  |  | NOT STARTED
CT-040 | D Production load | T-2 | 02:00 | Take the full backup (snapshot) of production - the rollback point | IDO | 1 | CT-037, CT-038 | Snapshot ID and restore test of the snapshot metadata recorded | ROLLBACK POINT |  | NOT STARTED
CT-041 | D Production load | T-2 | 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-040 | Every extract CHECKED; rejected files re-sent within 1 hour |  |  | NOT STARTED
CT-042 | D Production load | T-2 | 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-041 | Error rate within the master threshold; every expiry to 31-May-2028 present against the legacy in-force list; G4 signed by the Data Migration Lead |  |  | NOT STARTED
CT-043 | D Production load | T-2 | 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-042 | the Reconciliation Summary report for P01 matched |  |  | NOT STARTED
CT-044 | D Production load | T-2 | 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-041 | 0 financial errors or owner-approved exclusions with manual-entry plan |  |  | NOT STARTED
CT-045 | D Production load | T-2 | 09:00 | Load open legacy invoices F01 with their opening entries | IOP | 5 | CT-043, CT-044 | Batch loaded without rejects |  |  | NOT STARTED
CT-046 | D Production load | T-2 | 09:00 | Validate and load UPP F02 with their opening entries | IOP | 3 | CT-041, CT-023 | Batch loaded without rejects |  |  | NOT STARTED
CT-047 | D Production load | T-2 | 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-045 | Batches loaded |  |  | NOT STARTED
CT-048 | D Production load | T-2 | 15:00 | Load the provisional GL opening G01 - OPENING journals per branch and currency, value date 1-Jan-2028; balance-sheet lines; FY2027 result to retained earnings; legacy control-account lines to Migration Clearing | IOP | 2 | CT-039, CT-045, CT-046 | Journals posted and flagged PROVISIONAL; balance sheet in BIBS equals the preliminary TB; P&L accounts 0.00 |  |  | NOT STARTED
CT-049 | D Production load | T-2 | 16:00 | Validate and load the RA-sent file P03; send the Rejected Rows report of P03 to the Renewal processing team (maker and checker) | IOP | 2 | CT-043 | Batch loaded, or loaded with rejects; rejection report with correction columns sent |  |  | NOT STARTED
CT-050 | D Production load | T-2 | 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-041 | Next AR / OR numbers = legacy last used + 1 per branch |  |  | NOT STARTED
CT-051 | D Production load | T-2 | 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-047, CT-048 | the Migration Clearing report shows 0.00 per branch and currency |  |  | NOT STARTED
CT-052 | D Production load | T-2 | 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-051 | the Reconciliation Summary report all matched or explained with approval |  |  | NOT STARTED
CT-053 | E Reconciliation, verification and go / no-go | T-1 | 06:00 | Start the full sanction screening run of migrated clients (periodic screening job with the full re-screen option) | IOP | 6 | CT-023 | Run completed; hits in the screening queue for Compliance |  |  | NOT STARTED
CT-054 | E Reconciliation, verification and go / no-go | T-1 | 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-052 | Sample checklists signed; G6 for every Day-1 object |  |  | NOT STARTED
CT-055 | E Reconciliation, verification and go / no-go | T-1 | 08:00 | P03 rejects - the maker corrects each row and prepares the resubmission; the checker approves it by 12:00 (resubmission deadline); the operator loads the rerun batch; rows still rejected are listed for the day-1 queue | RNW | 4 | CT-049 | Resubmission approved by a checker other than the maker; rerun reconciled; list of rows still rejected |  |  | NOT STARTED
CT-056 | E Reconciliation, verification and go / no-go | T-1 | 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-052 | Smoke test checklist passed; no posting left open |  |  | NOT STARTED
CT-057 | E Reconciliation, verification and go / no-go | T-1 | 13:00 | Check jobs, alerts and integrations for Monday (Renewal go-live extraction at T 04:00, payment automatch hourly, payment file uploads, daily Renewal extraction, e-mail) | IDO | 2 | CT-056 | Job schedule and alert routing checked |  |  | NOT STARTED
CT-058 | E Reconciliation, verification and go / no-go | T-1 | 15:00 | Prepare the go / no-go pack - the Go / No-Go report with measured criteria, open issues, sign-off status | IML | 2 | CT-053, CT-054, CT-055, CT-056, CT-057 | Pack circulated to the board by 17:00 |  |  | NOT STARTED
CT-059 | E Reconciliation, verification and go / no-go | T-1 | 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-058 | Decision recorded in the console with every criterion value | GNG-3 |  | NOT STARTED
CT-060 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-059 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |  |  | NOT STARTED
CT-061 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-059 | Communication plan item 8 sent |  |  | NOT STARTED
CT-062 | F Go-live | T | 04:00 | Renewal go-live extraction - a candidate for every migrated header expiring 3-Jan to 31-May-2028 that was not renewed in legacy; priority by expiry date, January expiries flagged URGENT; RAs already sent recorded from P03; extraction check the go-live renewal extraction check | IOP | 2 | CT-061 | the go-live renewal extraction check balances for every month January-May 2028; URGENT count = January headers |  |  | NOT STARTED
CT-063 | F Go-live | T | 06:00 | Enable business logins; confirm legacy business modules stay read-only; legacy links shown in BIBS | IDO | 1 | CT-061 | Log-in test per persona; legacy posting refused |  |  | NOT STARTED
CT-064 | F Go-live | T | 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-063 | Attendance on the bridge |  |  | NOT STARTED
CT-065 | F Go-live | T | 08:00 | BIBS open for business | PM | 0 | CT-064 | First transactions observed in each branch | GO-LIVE |  | NOT STARTED
CT-066 | F Go-live | T | 08:00 | Renewal processing team works the day-1 priority queue - URGENT January expiries first, earliest expiry first; insurer requests and RAs for the expiries without an RA; the tracker is checked first for rows still rejected in P03 | RNW | 10 | CT-062, CT-065 | End-of-day count of URGENT candidates with an RA sent or an insurer request made |  |  | NOT STARTED
CT-067 | F Go-live | T | 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-065 | Run summary; legacy and new postings in the right accounts |  |  | NOT STARTED
CT-068 | F Go-live | T | 12:00 | Midday check - issues, queues, Migration Clearing still 0.00, no legacy business posting | IML | 1 | CT-065 | Midday report to the board |  |  | NOT STARTED
CT-069 | F Go-live | T | 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-068 | Decision recorded | POINT OF NO RETURN |  | NOT STARTED
CT-070 | F Go-live | T | 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-069 | Job run log; CRB lists the day's receipts |  |  | NOT STARTED
CT-071 | G Hypercare and true-up 1 | T+1 |  | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, URGENT January renewals without an RA or insurer request, failed jobs (daily until exit) | IML | 1 | CT-070 | Daily hypercare report |  |  | NOT STARTED
CT-072 | G Hypercare and true-up 1 | T+1 |  | Issue triage twice a day (10:00 and 16:00) with Operations, Comptrollership, Renewal and iorta QA | IQA | 1 | CT-070 | Issue log updated; severity agreed |  |  | NOT STARTED
CT-073 | G Hypercare and true-up 1 | T+2 |  | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-070 | Schedules show legacy invoice numbers; the remittance posts to DTIP - Legacy |  |  | NOT STARTED
CT-074 | G Hypercare and true-up 1 | T+3 |  | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-070 | Worklist counts agree with F03 |  |  | NOT STARTED
CT-075 | G Hypercare and true-up 1 | T+5 |  | Staging purge - staged records and intake files of the signed-off production batches deleted within 5 days (staging purge job) | IDO | 1 | CT-059 | No staged record older than 5 days after sign-off; purge log |  |  | NOT STARTED
CT-076 | G Hypercare and true-up 1 | T+7 |  | Week-1 review with the board - issues, volumes, performance, renewal queue, user feedback | GNG | 2 | CT-071 | Minutes; actions |  |  | NOT STARTED
CT-077 | G Hypercare and true-up 1 | T+10 |  | First daily Renewal extraction that creates new candidates - expiry 1-Jun-2028 on 13-Jan-2028; headers already extracted at go-live are skipped | RNW | 1 | CT-062 | Candidates of 1-Jun-2028 created; no duplicate of a go-live candidate |  |  | NOT STARTED
CT-078 | G Hypercare and true-up 1 | T+10 |  | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-070 | Run report; legacy sub-ledgers reduced by the batch total |  |  | NOT STARTED
CT-079 | G Hypercare and true-up 1 | T+14 |  | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-076 | Criteria status recorded | CHECKPOINT |  | NOT STARTED
CT-080 | G Hypercare and true-up 1 | T+15 |  | Legacy FY2027 year-end close completed by Comptrollership - closing adjustments posted in legacy, each entered in the FY2027 adjustment register | COMP | 8 | CT-036 | Register complete for the close; legacy post-close TB run |  |  | NOT STARTED
CT-081 | G Hypercare and true-up 1 | T+16 |  | Extract for true-up 1 - legacy TB after the close (G01, version TU1), adjustment journal lines since the freeze (G03), open-item detail of the lines on legacy control accounts (G03D), legacy journal listing since the freeze from the audit trail; control files | BIT | 4 | CT-080 | Every file and control file CHECKED |  |  | NOT STARTED
CT-082 | G Hypercare and true-up 1 | T+17 |  | Validate true-up 1 (cut-off, FY2027 dates, register, balance, mapping, open-item detail); the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-081 | Validation without error; true-up 1 submitted |  |  | NOT STARTED
CT-083 | G Hypercare and true-up 1 | T+18 |  | Head of Comptrollership approves true-up 1; BIBS posts the opening-balance adjustment journals MIG-TU-1 (opening journals, value date 1-Jan-2028) and the open-item adjustments | COMP | 2 | CT-082 | Journals posted; approver is not the preparer |  |  | NOT STARTED
CT-084 | G Hypercare and true-up 1 | T+18 |  | Reconcile true-up 1 (the Opening-Balance Adjustment Reconciliation report) - cut-off; movement = legacy TB change = register; BIBS opening = legacy post-close TB; Migration Clearing 0.00; legacy control accounts = sub-ledgers; the Head of Comptrollership signs | COMP | 4 | CT-083 | All checks met; true-up 1 signed |  |  | NOT STARTED
CT-085 | G Hypercare and true-up 1 | T+30 |  | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-079, CT-084 | ACSL reconciliation without difference; FRBS schedules include legacy balances; opening balances include true-up 1 |  |  | NOT STARTED
CT-086 | G Hypercare and true-up 1 | T+30 |  | Hypercare exit decision | GNG | 2 | CT-085 | Exit criteria met; hand-over to production support (L1 / L2 / L3) | HYPERCARE EXIT |  | NOT STARTED
CT-087 | H Final true-up and legacy GL close | T+60 |  | Interim true-up 2 when Comptrollership has posted material FY2027 adjustments since true-up 1 - same steps as true-up 1; skipped when there are none | COMP | 16 | CT-084 | True-up 2 signed, or 'none' recorded by the Head of Comptrollership |  |  | NOT STARTED
CT-088 | H Final true-up and legacy GL close | T+85 |  | Auditor's adjustments agreed and posted in legacy; audited FY2027 financial statements signed (about March-April 2028; the date follows the audit timetable) | COMP | 16 | CT-080 | Audited FS; register complete with the AUDIT adjustments |  |  | NOT STARTED
CT-089 | H Final true-up and legacy GL close | T+92 |  | Extract for the final true-up - legacy audited TB (G01, version FINAL), adjustment lines since the previous true-up (G03), their open-item detail (G03D), legacy journal listing since the freeze; control files | BIT | 4 | CT-087, CT-088 | Every file and control file CHECKED |  |  | NOT STARTED
CT-090 | H Final true-up and legacy GL close | T+95 |  | Validate the final true-up; the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-089 | Validation without error; final true-up submitted |  |  | NOT STARTED
CT-091 | H Final true-up and legacy GL close | T+99 |  | Head of Comptrollership approves the final true-up; January 2028 is reopened for the posting when closed; BIBS posts MIG-TU-F; January is closed again the same day | COMP | 4 | CT-090 | Journals posted; period reopen and close logged with the reason |  |  | NOT STARTED
CT-092 | H Final true-up and legacy GL close | T+99 |  | FY2027 BIR annual returns and the audited FS filed from legacy data by Comptrollership (not a BIBS task; BIBS is the source from FY2028) | COMP | 8 | CT-088 | Filing evidence recorded |  |  | NOT STARTED
CT-093 | H Final true-up and legacy GL close | T+100 |  | Reconcile the final true-up to the audited FY2027 TB (the Opening-Balance Adjustment Reconciliation report); re-run the February and March 2028 balance-sheet reports it changed; the Head of Comptrollership signs and shares the reconciliation with the external auditor | COMP | 8 | CT-091 | All checks met; final true-up signed; reports re-filed |  |  | NOT STARTED
CT-094 | H Final true-up and legacy GL close | T+106 |  | Lock the legacy GL for all users (FY2027 closed in legacy); close the FY2027 adjustment register | BIT | 2 | CT-093 | Test posting refused in the legacy GL; register closed |  |  | NOT STARTED
CT-095 | H Final true-up and legacy GL close | T+120 |  | Close the true-ups - final opening statement signed by the Head of Comptrollership and the Program Manager; opening journals no longer PROVISIONAL; a later FY2027 finding is a prior-period adjustment in BIBS outside the migration | PM | 2 | CT-094 | Closure recorded in the console | TRUE-UP CLOSED |  | NOT STARTED

## Cut-over roles
Cut-over roles
Owner roles of the task plan
Code | Role | Organisation | Name and phone (to fill)
PM | BDOI Program Manager (ESG - Business Project Services) | BDOI
DML | BDOI Data Migration Lead | BDOI
OWN | Data owners (department heads of each object) | BDOI
STW | Data stewards | BDOI
COMP | Comptrollership (reconciliation approver for financial objects) | BDOI
OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI
MKT | Marketing (Retail and Corporate) | BDOI
RNW | Renewal processing team (makers and checkers; Head of the Renewal processing team) | BDOI
CMP | Compliance and Audit | BDOI
BIT | BDOI IT (legacy systems, extracts, network, secure file transfer) | BDOI
GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT
IPM | iorta TechNXT Project Manager | iorta TechNXT
IML | iorta TechNXT Migration Lead (loads, reconciliation, Migration Console) | iorta TechNXT
IOP | iorta TechNXT Migration Operator (intake, validation, loads) | iorta TechNXT
IDO | iorta TechNXT infrastructure team (AWS environment, snapshots, access, monitoring) | iorta TechNXT
IQA | iorta TechNXT QA (smoke tests, issue triage) | iorta TechNXT

## Cut-over calendar
Cut-over calendar
Relative days on the calendar of the proposed go-live (DMQ25, DMQ39)
Day | Date (T = 3-Jan-2028) | Note
T-30 | Sat 4 Dec 2027 | Dress rehearsal (15-26 Nov 2027) already done; reserve slot 6-10 Dec 2027 if its exit criteria were missed
T-26 | Wed 8 Dec 2027 | Feast of the Immaculate Conception (special non-working day) - the Comptrollership set-up (CT-007) is planned from T-25
T-21 | Mon 13 Dec 2027 | Communications to branches, insurers and bank channels; legacy December soft close under way
T-20 | Tue 14 Dec 2027 | Renewal processing team readiness - January staffing plan, training, day-1 queue rehearsed
T-15 | Sun 19 Dec 2027 | GNG-1 (board meets on Friday 17 December if preferred)
T-14 | Mon 20 Dec 2027 | December soft close complete; production pre-load of reference data starts
T-12 | Wed 22 Dec 2027 | Client extract; completion drives for remittance batches and in-flight items (moved from T-9, Christmas Day)
T-11 | Thu 23 Dec 2027 | Client load and sign-off; daily client deltas start (moved from T-10, Christmas Eve)
T-10 | Fri 24 Dec 2027 | Christmas Eve (special non-working day) - no task planned
T-9 | Sat 25 Dec 2027 | Christmas Day - no task planned
T-7 | Mon 27 Dec 2027 | Code map freeze; legacy reference-data change freeze
T-5 | Wed 29 Dec 2027 | Last legacy business day; GNG-2 (moved from T-4, Rizal Day); freeze announcement; final RA-sent file; legacy GL access list for FY2027 adjustments
T-4 | Thu 30 Dec 2027 | Rizal Day (regular holiday) - no task planned
T-3 | Fri 31 Dec 2027 | Last day of the year (special non-working day) - last legacy EOD; preliminary December TB; business freeze 22:00; legacy GL restricted to FY2027 adjustments; final extracts
T-2 | Sat 1 Jan 2028 | New Year's Day - production load, provisional GL opening (cut-over team on duty)
T-1 | Sun 2 Jan 2028 | Reconciliation, verification, P03 resubmissions until 12:00, GNG-3 at 18:00
T | Mon 3 Jan 2028 | Renewal go-live extraction 04:00; go-live 08:00; day-1 renewal priority queue; point of no return 18:00
T+10 | Thu 13 Jan 2028 | First daily Renewal extraction of new expiries (1 June 2028)
T+15 | Tue 18 Jan 2028 | Legacy FY2027 year-end close complete
T+18 | Fri 21 Jan 2028 | True-up 1 posted, reconciled and signed
T+30 | Wed 2 Feb 2028 | First month-end close (January 2028) completed; hypercare exit decision
T+60 | Fri 3 Mar 2028 | Interim true-up 2, only when needed
T+85 | Tue 28 Mar 2028 | Audited FY2027 financial statements (about March-April 2028; follows the audit timetable)
T+99 | Tue 11 Apr 2028 | Final true-up posted; FY2027 BIR annual returns filed from legacy
T+106 | Tue 18 Apr 2028 | Legacy GL locked
T+120 | Tue 2 May 2028 | True-ups closed

## Go-no-go checkpoints
Go-no-go checkpoints
Go / no-go checkpoints and their criteria
Checkpoint | When | Decision | No. | Criterion | Measured value | Met | BU review | BU comment | Reviewer | Review date
GNG-1 | T-15 | Start the production pre-load | 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed
GNG-1 | T-15 | Start the production pre-load | 2 | Production environment, roles and PH-only access ready; masking off only in production
GNG-1 | T-15 | Start the production pre-load | 3 | Legacy control accounts, Migration Clearing and the legacy accounting rules approved in production (DMQ18)
GNG-1 | T-15 | Start the production pre-load | 4 | Code map versions for production approved
GNG-1 | T-15 | Start the production pre-load | 5 | Transfer path (secure file drop or console) tested
GNG-1 | T-15 | Start the production pre-load | 6 | December soft close on track for 20 December 2027
GNG-1 | T-15 | Start the production pre-load | 7 | Renewal processing team ready - January staffing plan signed, training done, day-1 queue rehearsed
GNG-1 | T-15 | Start the production pre-load | 8 | No open Critical issue of the migration or of a Day-1 module
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 2 | Client review queue empty
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 3 | Final extract jobs timed within the window (dry run)
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 4 | In-flight items and remittance batches closed or listed for carry-forward
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 5 | P01 dry run covers every expiry to 31 May 2028 and every renewal term booked in legacy starting on or after T
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 6 | Draft RA-sent file validated; its rejects reviewed by the Renewal processing team
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 7 | Comptrollership access list for the legacy GL after the freeze named
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 8 | Communications sent; branches and insurers informed
GNG-3 | T-1 18:00 | Go live on T | 1 | Every Day-1 object at G6 (100 percent)
GNG-3 | T-1 18:00 | Go live on T | 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object
GNG-3 | T-1 18:00 | Go live on T | 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan
GNG-3 | T-1 18:00 | Go live on T | 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency
GNG-3 | T-1 18:00 | Go live on T | 5 | Migration Clearing - 0.00 per branch and currency
GNG-3 | T-1 18:00 | Go live on T | 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00
GNG-3 | T-1 18:00 | Go live on T | 7 | Client review queue empty; screening run complete
GNG-3 | T-1 18:00 | Go live on T | 8 | Business smoke test passed
GNG-3 | T-1 18:00 | Go live on T | 9 | Rollback point (snapshot) taken and verified
GNG-3 | T-1 18:00 | Go live on T | 10 | Hypercare roster and support channels in place
GNG-3 | T-1 18:00 | Go live on T | 11 | Preliminary December TB signed as the provisional opening; legacy GL restricted to the named FY2027 adjustment users
GNG-3 | T-1 18:00 | Go live on T | 12 | Headers of every expiry to 31 May 2028 loaded; RA-sent file loaded; Renewal January staffing plan confirmed
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 1 | No Critical issue that stops receipts, payment application, remittance or booking
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 2 | Migration Clearing still 0.00; no posting in legacy since the freeze
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 3 | Every branch has transacted in BIBS
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 1 | Final true-up reconciled to the audited FY2027 TB and signed by the Head of Comptrollership
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 2 | Legacy GL locked for all users; FY2027 adjustment register closed
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 3 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers after the final true-up
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 4 | Opening journals no longer marked PROVISIONAL

## Freeze windows
Freeze windows
Freeze windows of the legacy systems and of BIBS
Freeze | From | Until | Scope | Exception route | BU review | BU comment | Reviewer | Review date
Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects
Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live
Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings of the business modules of EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements; GL journals other than the FY2027 adjustments | None; an urgent item is recorded on paper and keyed in BIBS on T
Legacy GL (FY2027 adjustments) | T-3 22:00 | Legacy GL lock (T+106) | Only FY2027 closing and audit adjustments, by the Comptrollership users on the signed access list; FY2028 periods never opened in legacy; no new business | Each journal in the FY2027 adjustment register; it reaches BIBS in the next true-up
BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board
BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical issue approved by the go / no-go board

## Rollback
Rollback
Rollback procedure (only on NO-GO, before the point of no return)
Step | Name | Action | Owner | Done at | BU review | BU comment | Reviewer | Review date
RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG
RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (payment automatch, payment file uploads, Renewal extraction, e-mail dispatch). | IDO
RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with the Cutover Runbook Status report and the Operations reports for re-keying in legacy. | IML
RB-4 | Restore | Restore production to the rollback-point backup (CT-037); restore the stored attachments of the same time; verify the restore (record counts of the key records, application start). | IDO
RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; lift the GL restriction; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT
RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS
RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM
RB-8 | Review | Within 2 business days - root cause, new go-live date, which trial migrations to repeat; purge the production staging of the failed cutover within 5 days. | PM

## Communication
Communication
Communication plan of the cut-over
No. | Message | Audience | Channel | When | Owner | Sent on
1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM
2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS
3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML
4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM
5 | Renewals of the January-May 2028 expiries are processed in BIBS from go-live, January expiries first; RAs already sent are not sent again; RAs sent up to 29 December go in the trackers | Renewal processing team, Retail and Corporate Marketing, branches | E-mail from the Head of the Renewal processing team; team briefing | T-21 | RNW
6 | Legacy GL after the freeze - FY2027 closing and audit adjustments only, by named users; true-up timetable to April 2028 | Comptrollership, external auditor, BDOI IT | Memo from the Head of Comptrollership | T-21 | COMP
7 | Last legacy business day T-5 (29 December); legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items over the holidays | All users, branches, insurers | E-mail; branch notice | T-5 | PM
8 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM
9 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM
10 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM
11 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM
12 | True-ups closed; legacy GL locked | Comptrollership, external auditor, Program Manager | Memo | T+120 | COMP

## Hypercare
Hypercare
Hypercare roster and exit criteria
Function | Who | Coverage | Escalates to | Names and phone (to fill)
Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager
Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager
Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager
Infrastructure | iorta TechNXT infrastructure team | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager
Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead
Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end; true-ups T+15 to T+120 | Head, Comptrollership
Renewal processing team | Head of the Renewal processing team; makers and checkers | 08:00-20:00 T to T+10 on the day-1 queue; P03 resubmissions on T-2 and T-1 | Program Manager
Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head
Service desk (L1) | BDOI service desk | Service hours | BDOI IT head
Exit criterion 1 | No open Critical or High issue; Medium issues have an agreed fix date
Exit criterion 2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days
Exit criterion 3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference
Exit criterion 4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident
Exit criterion 5 | Staging and extract files of production purged within 5 days of sign-off (purge log)
Exit criterion 6 | True-up 1 posted, reconciled and signed
Exit criterion 7 | Every URGENT January renewal has an RA sent or an insurer request made
Exit criterion 8 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted

## Decommissioning
Decommissioning
Checklist per legacy system and for the legacy context (BRID 12.1; DMQ27)
Legacy system | No. | Criterion | Evidence | Signed by and date | Status | BU review | BU comment | Reviewer | Review date
EBIX | 1 | Final extracts reconciled - F01, F02, F03, F04, F06, G01 and C01 signed off |  |  | OPEN
EBIX | 2 | Final true-up reconciled - final true-up signed against the audited FY2027 TB; legacy GL locked |  |  | OPEN
EBIX | 3 | Archive reconciled - archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |  |  | OPEN
EBIX | 4 | Legacy Inquiry verified - by Audit / Compliance on samples of each record type |  |  | OPEN
EBIX | 5 | No open item needs the system - no open legacy invoice or legacy UPP needs an EBIX document; the legacy context in BIBS may still be open |  |  | OPEN
EBIX | 6 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |  |  | OPEN
EBIX | 7 | Access logs archived - read-only access logs exported to the archive |  |  | OPEN
EBIX | 8 | Retention covered - production backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |  |  | OPEN
EBIX | 9 | Owners signed - EBIX system owner, Compliance and Comptrollership |  |  | OPEN
QPS | 1 | Final extracts reconciled - C01, P01, P03 and the R objects signed off |  |  | OPEN
QPS | 2 | No open item needs the system - last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |  |  | OPEN
QPS | 3 | Archive reconciled - archive objects of QPS loaded and reconciled |  |  | OPEN
QPS | 4 | Legacy Inquiry verified - by Audit / Compliance |  |  | OPEN
QPS | 5 | Access logs archived - read-only access logs exported to the archive |  |  | OPEN
QPS | 6 | Retention covered - production backup retained per DMQ27 |  |  | OPEN
QPS | 7 | Owners signed - QPS system owner, Compliance and the Heads of Marketing |  |  | OPEN
ISYS | 1 | No open item needs the system - claims and ACSL reports and the Marketing Diary replaced by BIBS reports |  |  | OPEN
ISYS | 2 | Archive reconciled - GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |  |  | OPEN
ISYS | 3 | Final true-up reconciled - ISYS GL lines of the final true-up signed; ISYS GL locked |  |  | OPEN
ISYS | 4 | Owners signed - ISYS system owner, Claims and Comptrollership |  |  | OPEN
CMS | 1 | Final extracts reconciled - collection state F03 and UPP F02 reconciled and signed off |  |  | OPEN
CMS | 2 | Archive reconciled - disposition history archived (H01) if required by DMQ34 |  |  | OPEN
CMS | 3 | Owners signed - Head of Operations (Collections) and BDOI IT |  |  | OPEN
Excel masterlists and file shares | 1 | Final extracts reconciled - submitted-policy masterlists migrated (P04) or archived |  |  | OPEN
Excel masterlists and file shares | 2 | Archive reconciled - KYC documents and legacy documents (C04, H02) archived with checksums |  |  | OPEN
Excel masterlists and file shares | 3 | Retention covered - folders set to read-only, then removed per the retention decision |  |  | OPEN
Excel masterlists and file shares | 4 | Owners signed - owning department and Compliance |  |  | OPEN
Legacy context in BIBS | 1 | No open legacy invoice - every legacy invoice paid, reversed, written off or reclassified |  |  | OPEN
Legacy context in BIBS | 2 | No legacy UPP balance - every legacy UPP applied, refunded or reclassified |  |  | OPEN
Legacy context in BIBS | 3 | Legacy accounts at zero - legacy control accounts and Migration Clearing at 0.00 |  |  | OPEN
Legacy context in BIBS | 4 | Chart decision recorded - Comptrollership decides whether the legacy accounts are closed in the chart |  |  | OPEN

## Reconciliation sign-off
Reconciliation sign-off
Reconciliation and acceptance of every object with a load template: what each level proves and who signs (Handbook Part C)
Object | Data object | L1 counts | L2 amounts | L3 hash totals | L4 fields | L5 or business check | Business verification sample (G6) | Signs G5 | Run | Result | G5 signed by and date | G6 signed by and date | BU review | BU comment | Reviewer | Review date
R01 | Lists of values and MIS values | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Product Owner, Marketing Business System (MBS)
R02 | Branches and invoicing branches | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Head, Comptrollership
R03 | Sales organisation (regions, departments, teams, unit heads, account officers) | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Heads, Retail and Corporate Marketing
R04 | Insurers and insurer branches | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Head, Operations
R05 | Product lines, cover types, products and risk codes | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Product Owner, MBS
R06 | Package code map (legacy package and version to BIBS package version) | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Product Owner, MBS (approves); TSU (prepares)
R07 | Commission rates by insurer and product | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Head, Operations
R08 | Chart of accounts mapping (legacy GL account to BIBS account) | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Head, Comptrollership; Product Owner FRBS and ACSL
R09 | Payees | Payees received and loaded | - | Distinct payee codes | All loaded fields | Payee list in Disbursement | 20 random payees. Checked: name, TIN, bank and account on the payee record (status Draft until submitted by Disbursement) | Product Owner, Comptrollership - Disbursement
R11 | Receipt series in use (AR and OR, ATP and next number) | Values received, mapped, created, rejected; package code map entries | - | Distinct keys | Created values (name, status, dates); package code map entries in the Renewal package map | Unmapped-code report empty; every value created in BIBS authorised in its master; the package code map entries in the Renewal package map equal the approved version | Every value created in BIBS; 10 mapped values per code map set; every legacy package with more than one BIBS target; every receipt series. Checked: value, description and status in the master; the package entries of each split in the Renewal package map; next AR / OR number = legacy last used + 1 | Operations - Financial Transactions
C01 | Client master (individual and corporate) | Legacy clients received, clusters, merged, new, loaded; payout accounts received and loaded | - | Distinct legacy client numbers = key cross-reference entries | Identity, contact, segment and KYC fields of the surviving record; payout account fields | Client review queue empty; each legacy number resolves to one BIBS client | 30 random clients per source system; 20 merged clusters; 10 decisions of the review queue; 10 corporate clients. Checked: client search by legacy number; name, identity, contacts, segment, AO, KYC status and review date; the cluster shows every legacy number | Product Owner, MBS; Heads, Retail and Corporate Marketing
C03 | Client payout accounts (for refunds) | Legacy clients received, clusters, merged, new, loaded; payout accounts received and loaded | - | Distinct legacy client numbers = key cross-reference entries | Identity, contact, segment and KYC fields of the surviving record; payout account fields | Client review queue empty; each legacy number resolves to one BIBS client | 30 random clients per source system; 20 merged clusters; 10 decisions of the review queue; 10 corporate clients. Checked: client search by legacy number; name, identity, contacts, segment, AO, KYC status and review date; the cluster shows every legacy number | Product Owner, Comptrollership - Disbursement
P01 | In-force policy headers | Headers and share rows received and loaded | Sum insured, gross and net premium per currency | Distinct legacy policy references | All header fields and shares | Headers linked to their clients and legacy invoices; P01 against the legacy in-force list for every expiry to 31 May 2028 | 30 random headers; 10 with several insurers; 10 expiring within 140 days. Checked: account search by policy and legacy reference; dates, insurer and shares, sum insured, premium, client link, legacy invoices listed | Head, Operations
P03 | Renewal advices already sent before go-live (RA-sent file) | RA-sent rows received, loaded, rejected; resubmitted rows | Proposed premium per currency | Distinct legacy policy references | RA date, reference, channel, sender, tracker | At go-live, the extraction check per expiry month January-May 2028: headers expiring from T to 31 May 2028 = candidates + renewals booked in legacy; loaded P03 rows = candidates with the RA already sent; every January candidate urgent | 10 rows per tracker; every resubmitted row; at go-live 20 candidates per expiry month January-May 2028. Checked: RA date, reference and channel against the tracker; the candidate shows the RA already sent; January candidates urgent and in expiry-date order | Head of the Renewal processing team
F01 | Open legacy invoices (premium receivable, paid not remitted, commission receivable, PR2307), with components and insurer shares | Invoices, share rows, component rows | Booked, adjusted, paid, remitted, written off and open per component and currency | Distinct invoice numbers | Header fields, shares, every component and bucket | L5: Premium Receivable, PR 2307, DTIP and Commission Receivable (legacy) against the legacy invoices; Migration Clearing 0.00 | 20 largest open balances per currency; 30 random; 10 endorsement or cancellation invoices; 10 direct-payment; 10 with 2307; up to 20 foreign-currency. Checked on Invoice 360: LEGACY badge, source, legacy number, original values, booked / paid / remitted / open per component, shares; the Collections item of an open premium | Head, Comptrollership
F02 | Unapplied premium payments (UPP) with disposition in progress | Unapplied payments received and loaded | Amount and balance per currency | Distinct unapplied payment references | All fields, stage and disposition | L5: Unapplied Collections (legacy) against the migrated balances | 20 largest balances; 20 random; every item with a disposition in progress (up to 30). Checked on the Unapplied workbench: legacy AR, amount, balance, tab, references, disposition | Head, Comptrollership
F03 | Open collection state (dispositions, promises to pay, installment plans, collector assignments) | Rows per record type | Promise, instalment, hold and cheque amounts per currency | Distinct keys | All fields | Worklist items show the carried promises and assignments; holds and cheques visible in Remittance and Cashiering | 20 random rows per object. Checked: the promise and assignment on the Collections item; the hold or special request in Remittance; the cheque in the warehouse list | Head, Operations (Collections)
F04 | Remittance in flight (batches not yet paid, holds, special remittances) | Rows per record type | Promise, instalment, hold and cheque amounts per currency | Distinct keys | All fields | Worklist items show the carried promises and assignments; holds and cheques visible in Remittance and Cashiering | 20 random rows per object. Checked: the promise and assignment on the Collections item; the hold or special request in Remittance; the cheque in the warehouse list | Operations - Remittance
F06 | PDCs in the warehouse, check pick-ups and refunds in process | Rows per record type | Promise, instalment, hold and cheque amounts per currency | Distinct keys | All fields | Worklist items show the carried promises and assignments; holds and cheques visible in Remittance and Cashiering | 20 random rows per object. Checked: the promise and assignment on the Collections item; the hold or special request in Remittance; the cheque in the warehouse list | Operations - Cashiering
G01 | GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) | Trial balance lines | Debit and credit per branch and currency, in currency and in PHP | Lines per branch | Account, branch, currency and amounts per line | Provisional opening: balance sheet in BIBS = preliminary December TB per branch and currency; FY2027 result on retained earnings; P&L accounts 0.00; Migration Clearing 0.00 | Every branch and currency total; the 20 largest account lines; retained earnings per branch. Checked: the BIBS trial balance against the signed preliminary trial balance; P&L accounts at 0.00 | Head, Comptrollership
G03 | FY2027 opening-balance true-ups (legacy adjustment journals after the freeze and their open-item detail) | Journal lines and detail lines per true-up | Debit and credit per branch and currency; detail per account | Distinct legacy journals | Account, branch, currency, amounts; item and component of each detail line | True-up reconciliation: cut-off, movement, balance, Migration Clearing and sub-ledgers, opening period | Every journal of the true-up; every detail line on a legacy control account. Checked: journal inquiry (MIG-TU-n) against the legacy journal and the register; Invoice 360 or the Unapplied workbench for the item adjusted | Head, Comptrollership
H01 | Closed transactions (paid and remitted invoices, receipts, remittances, endorsements, claims, renewal advices, letters) | Records per record type; documents | Amount per record type and currency | Distinct keys per record type; SHA-256 per document | Labelled legacy columns | Samples found in Legacy Inquiry with their documents | 10 records per record type; 10 documents. Checked: Legacy Inquiry search by the legacy key; labelled columns; the document opens and matches its checksum | Audit / Compliance; legacy system owners
H02 | Legacy documents (policies, SOAs, ORs, certificates, letters) | Records per record type; documents | Amount per record type and currency | Distinct keys per record type; SHA-256 per document | Labelled legacy columns | Samples found in Legacy Inquiry with their documents | 10 records per record type; 10 documents. Checked: Legacy Inquiry search by the legacy key; labelled columns; the document opens and matches its checksum | Audit / Compliance

## Open decisions
Open decisions
Decisions of BDOI that the migration waits for, with the date each is needed by
ID | Register | Topic | Decision needed | What waits for it | Needed by | BDOI owner | Status | Answer
DCR-189 | DCR-189 | BRD sign-off | The Data Migration BRD is a draft v0.01 without signatures (p.2, p.15-16); when is it walked through and signed, and by whom | Baseline of this set; Handbook re-issue | M2 (30 Oct 2026) | Program Manager | OPEN
DCR-173 | DCR-173 | Client migration period and daily client batches | Umbrella BRD p.43 asks for a one-time client migration 'from Broker and source, 2020 to present' and daily midday / EOD client batches with a modification report. Confirm the period and filter (DMQ05), the source systems, and that the daily batches run only until the freeze (proposal) and not as a feed after go-live | C01 scope and delta extracts; client migration | M1 (16 Oct 2026) | Product Owner, MBS | OPEN
DMQ01 | DCR-195 | Data object inventory | Confirm the objects, classes and source systems of the register; name the business owner and data steward per object | All objects; gate G1 | M2 (30 Oct 2026) | Program Manager | OPEN
DMQ02 | DCR-192 | Decision rule | Confirm who rates the four criteria, who approves, and the rule that turns ratings into a class (proposal in Handbook Part A, the decision gate) | Gate G1 | M2 (30 Oct 2026) | Program Manager | OPEN
DMQ03 | DCR-195 | Source systems | Confirm the systems in scope (EBIX, QPS, ISYS, CMS, Excel) and the system of record per object where two hold it | All layouts | M1 (16 Oct 2026) | BDOI IT | OPEN
DMQ04 | - | Client dedupe keys | Agreed keys (is the bank CIF a key?), survivorship per field, who reviews doubtful matches and within what time | C01 matching | M2 (30 Oct 2026) | Product Owner, MBS | OPEN
DMQ05 | - | Client scope | All clients since 2020, or only those with an in-force policy, open item or activity since a date; prospects; corporate contacts | C01 volumes; filter | M2 (30 Oct 2026) | Product Owner, MBS | PARTIAL
DMQ06 | DCR-208 | Screening of migrated clients | One full screening run after the load instead of per client; legacy results archived | C01 load; cutover task CT-050 | M2 (30 Oct 2026) | Compliance | OPEN
DMQ07 | - | KYC documents | Migrate as attachments or archive; KYC status and review dates | C04, H02 | M2 (30 Oct 2026) | Compliance | OPEN
DMQ08 | - | Code map owners | Owner and signer per map set; MIS fields required | Gate G2; all map sets | M2 (30 Oct 2026) | Product Owner, MBS | OPEN
DMQ09 | DCR-194 | In-force header condition | All in-force policies, or only those with open legacy invoices or that may be endorsed or claimed; the header fields | P01, P01S; endorsements BRID 9 | M1 (16 Oct 2026) | Head, Operations | OPEN
DMQ10 | - | Legacy invoice scope | Which invoices carry forward (open PR, paid not remitted, open commission, open PR2307); zero-balance invoices of in-force policies for endorsement; history depth | F01 | M1 (16 Oct 2026) | Operations - Financial Transactions | OPEN
DMQ11 | DCR-207 | Invoice numbers | Are EBIX and QPS invoice numbers unique across both systems; QPS invoice format | F01 keys; payment matching | M1 (16 Oct 2026) | BDOI IT | OPEN
DMQ12 | DCR-207 | Components and shares | Can legacy give open balances per component and per insurer share; if not which split rule | F01C | M1 (16 Oct 2026) | BDOI IT; Comptrollership | OPEN
DMQ13 | - | Commission state | Realised / unrealised commission, deferred output VAT, commission collected by remittance, per invoice | F01 opening entry | M1 (16 Oct 2026) | Head, Comptrollership | OPEN
DMQ14 | DCR-204 | UPP receipt and statuses | New BIBS AR, reprint of the legacy AR, or none for a migrated UPP; legacy UPP statuses and dispositions in progress | F02 | M1 (16 Oct 2026) | Operations - Financial Transactions | OPEN
DMQ15 | - | UPP matching references | References held per UPP; automatch rerun frequency after cutover | F02 ref_ columns | M2 (30 Oct 2026) | Operations - Financial Transactions | OPEN
DMQ16 | DCR-198, DCR-205 | Reclassification to income | Who is top management; criteria, frequency, GL account, customer notice, reversal | FR-DM-055 configuration | M2 (30 Oct 2026) | Head, Comptrollership | OPEN
DMQ17 | - | Legacy UPP refunds | Same approvers and Disbursement flow as new UPP refunds | FR-DM-054 configuration | M2 (30 Oct 2026) | Operations - Financial Transactions | OPEN
DMQ18 | DCR-197 | Legacy sub-ledgers and GL | Separate legacy control accounts and Migration Clearing; end state after run-off; whole opening TB per branch and currency; GL ageing of legacy PR | R08, G01; accounting rules | M1 (16 Oct 2026) | Head, Comptrollership | OPEN
DMQ19 | DCR-198, DCR-206 | DPPR | Definition, entries including Commission Receivable, source of the approved list, approver | FR-DM-070 rules | M2 (30 Oct 2026) | Head, Comptrollership | OPEN
DMQ20 | - | PR2307 reversal | Entries, evidence, approver | FR-DM-071 rules | M2 (30 Oct 2026) | Head, Comptrollership | OPEN
DMQ21 | - | Remittance positions | Batches in process, holds and special remittances at cutover - completed in legacy or carried; insurer ORs outstanding | F04 decision | M2 (30 Oct 2026) | Operations - Remittance | OPEN
DMQ22 | DCR-194 | Endorsement coexistence | Confirm legacy invoices are endorsed in BIBS from cutover; types; service invoice numbering; renewal uses BIBS values | P01 condition | M1 (16 Oct 2026) | Head, Operations | OPEN
DMQ23 | - | Legacy change report | Which changes count; fields, period, frequency, recipients | FR-DM-100 report | M2 (30 Oct 2026) | Operations - Prod Recon | OPEN
DMQ24 | DCR-209 | Read-only legacy or archive | Per legacy system - read-only (how long, who hosts, access logging) or archived in BIBS before decommissioning; record types, search keys, retention | H01, H02, C04 | M2 (30 Oct 2026) | Audit / Compliance; BDOI IT | OPEN
DMQ25 | DCR-200, DCR-242 | Cutover date and window | Go-live month (M1) and exact date (M6); freeze length; last legacy EOD; month-end alignment; blackout dates | Whole calendar; runbook | M1 (16 Oct 2026) (month), M6 (1 Oct 2027) (date) | Program Manager | PARTIAL | Month answered by the BDOI timeline (26-Sep-2026) - January 2028; full migration and cut-over Nov 2027-Jan 2028. Date 3 January 2028 at the year-end boundary recommended with DMQ39; confirmed by Comptrollership at M6
DMQ26 | DCR-199, DCR-240 | RMEL transition | Cohorts already extracted in legacy carried into BIBS or finished in legacy; first cohort extracted by BIBS; path of legacy renewals | P01 scope; Renewal | M1 (16 Oct 2026) | Heads, Retail and Corporate Marketing | ANSWERED | Answered by DMQ37 (26-Sep-2026) - no cohort is carried; the expiries from T to 31-May-2028 are extracted by BIBS at go-live from the migrated headers; the daily extraction then starts at the expiry of 1-Jun-2028 (extracted 13-Jan-2028)
DMQ27 | - | Decommissioning criteria | Criteria and owner per legacy system; retention of the legacy data | Decommissioning checklists | M6 (1 Oct 2027) | Program Manager; BDOI IT | OPEN
DMQ28 | DCR-193 | Volumes and quality | Row counts per object and source, growth to go-live, known quality issues, history depth, extract owner and delta frequency | Register volumes; performance test | M3 (29 Jan 2027) | BDOI IT | OPEN
DMQ29 | DCR-193 | Consolidated NFR | Name, version and owner of the consolidated NFR; cutover window, load time, retention of migration evidence | NFR targets | M2 (30 Oct 2026) | Program Manager | OPEN
DMQ30 | DCR-196 | Objects not in the BRD | Open claims, EB programmes, submitted-policy masterlists, payees, open disbursements, PDCs, users - in scope? | R09, P04, P05, F06, F07 | M1 (16 Oct 2026) | Program Manager | OPEN
DMQ31 | DCR-200 | Rehearsals and test data | Number of trial migrations and the dress rehearsal; masked production extracts in SIT / UAT; who masks and approves | Migration cycles | M2 (30 Oct 2026) | Program Manager; Compliance | OPEN
DMQ32 | DCR-200 | Fallback | Point of no return; fallback to legacy after go-live; who decides | Runbook rollback | M6 (1 Oct 2027) | Program Manager | OPEN
DMQ33 | DCR-200 | In-flight items at the freeze | Pending endorsements, un-booked accounts, placements, PDCs, pick-ups and refunds - completed before the freeze, carried or re-keyed | F06; freeze plan | M2 (30 Oct 2026) | Head, Operations | OPEN
DMQ34 | DCR-203 | Collection history | Carry open dispositions, promises, installment plans and collector assignments | F03 | M2 (30 Oct 2026) | Head, Operations (Collections) | OPEN
DCR-202 | DCR-202 | Write-back to legacy | Confirm that no contact or client update is written back to QPS / EBIX after the freeze (legacy read-only; proposal) | C01 deltas; CSF contact write-back | M1 (16 Oct 2026) | Product Owner, MBS | OPEN
DMQ35 | - | Foreign currency | Rate for the openings of USD invoices and UPP (legacy booking rate or cutover BOOK rate); FX difference at collection | F01, F02, G01 | M2 (30 Oct 2026) | Head, Comptrollership | OPEN
DMQ36 | DCR-241 | Package remapping | At upload (migration intake) or during Renewal sanitation; owner of the decision and of the map; legacy packages that split and on which attributes | R06, P01; package code map; package check of the Renewal sanitation | M1 (16 Oct 2026) | Product Owner, MBS; TSU | ANSWERED | BDOI 26-Sep-2026 - at sanitation in Renewal, not at migration intake. The migration loads the package code map as reference data only (R06); P01 keeps the legacy package; the package check of the Renewal sanitation sends unmapped packages to the Exception bucket, worked by the Renewal processing team
DMQ37 | DCR-199, DCR-240 | January-May 2028 renewals | Prepared in legacy and carried at the freeze, or processed in BIBS after go-live | P01 scope; P03; Renewal go-live extraction | M1 (16 Oct 2026) | Heads, Retail and Corporate Marketing | ANSWERED | BDOI 26-Sep-2026 - processed in BIBS after go-live; no carried candidates. Go-live extraction of every expiry from T to 31-May-2028 from the migrated headers (P01), prioritised by expiry date, January expiries flagged urgent; RAs already sent by hand loaded as a small reference file (P03) and not re-sent
DMQ38 | DCR-243 | RMEL and disposition sources | Where the RMEL, dispositions and RAs are kept; who reviews rejected rows | P03 template and review | M2 (30 Oct 2026) | Head of the Renewal processing team | ANSWERED | BDOI 26-Sep-2026 - RMEL and dispositions are kept in Excel; rejected rows are reviewed by the Renewal processing team, maker and checker. Only the RAs already sent are taken from the trackers (XLSX template, rejection report with correction columns, maker-checker resubmission)
DMQ39 | DCR-242 | Year-end cut-over | Go-live at the year-end boundary; last business day; year-end close; late 2027 and audit adjustments after go-live | Runbook calendar; G01, G03; true-up journals | M6 (1 Oct 2027) | Program Manager; Head of Comptrollership | RECOMMENDED | BDOI 26-Sep-2026, recommendation awaiting Comptrollership confirmation - option A - go-live Mon 3-Jan-2028; legacy closes FY2027; provisional opening TB (balance sheet only) from the preliminary December TB; legacy GL open only for FY2027 closing and audit adjustments; true-ups as opening-balance adjustment journals after the legacy close (about mid-late January 2028) and after the audited FS (about March-April 2028); December soft close by about 20-Dec-2027. Options B (April 2028, YTD P&L) and C (two books in Q1 2028) not recommended

## Proposed rules
Proposed rules
Proposed business rules and clarifications for confirmation (Handbook chapter of the same name)
Ref | Topic | Proposed rule | Reason | Decision requested | Open decisions | Needed by | BDOI decision | Change or comment | Decided by | Decided on
PR-DM-01 | Year-end cut-over: option A or B | Option A: go live on Monday 3 January 2028 at the year-end boundary. Legacy processes to 31 December 2027 and closes FY2027; BIBS opens with the open items at 31 December and a provisional GL opening (balance sheet only, the FY2027 result in retained earnings). The legacy GL stays open only for the FY2027 closing and audit adjustments of named Comptrollership users; each reaches BIBS as an opening-balance adjustment after the legacy close (about mid-January 2028) and after the audited statements (about March-April 2028). Option B (go-live after the first-quarter close, April 2028, with a year-to-date P&L migration) is not proposed; option C (two sets of books in the first quarter) is not proposed | One fiscal year per system; no P&L migration; books of accounts and BIR returns are never split inside a year; the go-live stays on the BDOI timeline. Option B moves go-live by three months, splits FY2028 across two systems and needs a month-by-month P&L reconciliation | Comptrollership confirms option A, or chooses option B, with the date of the December soft close | DMQ39, DMQ25 | M6 (1 Oct 2027)
PR-DM-02 | Legacy control accounts and Migration Clearing | Separate legacy control accounts hold the positions of the migrated invoices and unapplied payments: Premium Receivable - Legacy (by component), PR 2307 - Legacy, Due to Insurers - Legacy, Commission Receivable - Legacy, Unrealised Commission and Deferred Output VAT - Legacy, Unapplied Collections - Legacy, and a Migration Clearing account that must net to 0.00. The account codes are assigned by Comptrollership in the production chart; the handbook names the accounts only | The legacy positions run off visibly and apart from new business; Migration Clearing proves that the invoice and payment detail equals the legacy GL | Comptrollership assigns the codes of the seven accounts in the production chart and confirms the end state of the accounts after the run-off | DMQ18 | M1 (16 Oct 2026); production set-up at T-25
PR-DM-03 | Extract volumes and the secure file drop | BDOI IT supplies the row count per object and source system with the first full extracts (29 January 2027) and at each trial migration. Files are received through the Extracts screen of the Migration Console until BDOI IT names a secure file drop in the BIBS environment; files are never e-mailed | The volumes size the load windows and the dress rehearsal; a single agreed transfer path keeps the files encrypted and logged | BDOI IT confirms the volumes per object, the owner of each extract and whether a secure file drop is set up (host, account, schedule) | DMQ28 | M3 (29 Jan 2027)
PR-DM-04 | Legacy document folder and read-only links | Legacy documents (policies, SOAs, ORs, certificates, letters, KYC files) are copied by BDOI IT into a transfer folder with an index file (layout H02) and a SHA-256 per file; BIBS archives them with their record. Each legacy application stays available read-only until it is decommissioned; its address is shown in Legacy Inquiry for the users who still need it | History stays retrievable with logged access without converting it into BIBS transactions | BDOI IT names the transfer folder and the read-only address of EBIX and QPS; Audit / Compliance confirms per system whether history is archived in BIBS or read in legacy until decommissioning | DMQ24, DMQ07 | M2 (30 Oct 2026)
PR-DM-05 | Conditional objects F04-F07, P04 and P05 | Remittance in flight (F04): complete the legacy batches before the freeze; carry only holds and special remittances that cannot complete. DP billing in process (F05): carried inside the open invoices (F01), no separate file. PDCs, cheque pick-ups and refunds in process (F06): carry the PDCs in the warehouse; complete pick-ups and refunds in legacy before the freeze. Open claims (F07), submitted-policy masterlists (P04) and Employee Benefits programmes (P05): migrated through the uploads of their own modules only if BDOI brings them into scope | Each object is either completed before the freeze or carried, so that no item is lost or processed twice; the uploads of Claims, Submitted Policies and Employee Benefits already exist and need no separate migration layout | Operations, Claims, Marketing and the EB Head decide per object: carried, completed before the freeze, or out of scope | DMQ21, DMQ30, DMQ33 | M1 (16 Oct 2026)
PR-DM-06 | Approval levels of the legacy batches | Unapplied to Income: requested by a Cashiering user, approved by the Cashiering team lead and then by top management (two different people). Legacy PR 2307 Reversal: requested by a Cashiering user, approved by the Cashiering team lead. DP PR Legacy Reversal: requested by a Commission user, approved by the Commission team lead. In every batch the requester never approves | The reclassification to income changes the P&L and needs a management approval; the two reversals move balances between the legacy accounts of one invoice and follow the team-lead approval of the other Cashiering and Commission batches | Comptrollership confirms the approvers per batch, names top management, and gives the income account and the minimum age of an unapplied payment for the reclassification | DMQ16, DMQ19, DMQ20 | M2 (30 Oct 2026)
PR-DM-07 | Decision rule of an object | Migrate when the object is needed on Day 1 and is master or reference data; Carry forward when it is an open item BDOI must still act on; Conditional when BDOI states the condition; Archive when it is not needed on Day 1 but must be kept; Excluded otherwise. The Data Migration Lead proposes; the business owner of the object approves (gate G1) | The BRD gives the four criteria but not the rule that turns them into a class | The Program Manager confirms the rule and the approver | DMQ02, DMQ01 | M2 (30 Oct 2026)
PR-DM-08 | Client scope: 2020 to present | Migrate every client created from 1 January 2020, plus older clients with an in-force policy, an open item or activity since 2020; load them two weeks before go-live and keep them current with daily deltas until the freeze; no client feed after go-live | The umbrella BRD asks for clients from 2020 and daily client batches; after the freeze legacy is read-only and BIBS is the client master | The Product Owner of MBS confirms the period and the filter, and that the daily batches stop at the freeze | DMQ05, DCR-173, DCR-202 | M1 (16 Oct 2026)
PR-DM-09 | Client matching keys and thresholds | Keys: TIN; ID type and number; name and birth date; corporate name with registration number; bank CIF if confirmed; e-mail and mobile as soft keys. Pairs scoring 90 or more merge; 60 to 89 go to the Data Steward's review queue; the client load waits until the queue is empty. Per field the first non-blank value wins by source priority (QPS for contact data, EBIX for billing data) | One client master without duplicates, with every lost value kept for review | The Product Owner of MBS confirms the keys (is the bank CIF a key?), the thresholds and the source priority | DMQ04 | M2 (30 Oct 2026)
PR-DM-10 | Loading thresholds | Master data may be loaded with at most 0.5 percent of rows rejected or waived; open invoices, unapplied payments and the trial balance only with no error, or with each excluded row approved by its owner with a manual-entry plan | Master data can be completed after go-live; a missing financial item would break the ledger and the reconciliation | Comptrollership and the data owners confirm the two thresholds | DMQ29 | M2 (30 Oct 2026)
PR-DM-11 | In-force policy headers | Migrate the header of every policy in force at go-live (and in every case every expiry from go-live to 31 May 2028 and every renewal term booked in legacy that starts on or after go-live) | Headers are needed to find active cover, to endorse legacy invoices and to renew in BIBS; the go-live renewal extraction works only from them | Operations confirms the scope and the header fields | DMQ09, DMQ22 | M1 (16 Oct 2026)
PR-DM-12 | Open invoice content | Each open invoice is sent with its components (basic premium, DST, premium tax or VAT, LGT, FST, other charges, DTIP, commission, VAT on commission, withholding tax, PR 2307) and their booked, adjusted, paid, remitted and written-off amounts, per insurer share. Invoice numbers are kept; a number found in two source systems is prefixed with the source system | The open balance in BIBS must equal the legacy open balance per component so that payments, remittances and reversals work on the right amounts | BDOI IT confirms that legacy can give the components and shares, and that EBIX and QPS numbers are unique; Comptrollership gives the commission state per invoice | DMQ10, DMQ11, DMQ12, DMQ13 | M1 (16 Oct 2026)
PR-DM-13 | Unapplied payments | A migrated unapplied payment keeps its legacy AR number and date; no new BIBS AR is issued for money already acknowledged in legacy; it is matched by automatch on its references after every payment upload and hourly | No duplicate receipt for the same cash; the references the payor gave are used again | Operations - Financial Transactions confirms the receipt handling, the statuses and the matching references | DMQ14, DMQ15, DMQ17 | M1 (16 Oct 2026)
PR-DM-14 | Foreign-currency openings | USD invoices and unapplied payments open at their legacy booking rate; the difference at collection is an exchange difference as for a BIBS invoice | The legacy receivable is carried at the value in the legacy books | Comptrollership confirms the rate | DMQ35 | M2 (30 Oct 2026)
PR-DM-15 | Trial migrations, masking and the dress rehearsal | Four trial migrations (April, July, August and October 2027) and a dress rehearsal (November 2027) on masked extracts; masking when the file is received in BIBS; unmasked files never leave production | Every step of the cut-over is timed and proven on full data before production | The Program Manager and Compliance confirm the number of runs and the masking | DMQ31 | M2 (30 Oct 2026)
PR-DM-16 | Point of no return | Until the go / no-go decision the rollback restores the snapshot and legacy reopens. After go-live, the point of no return is the end of the first business day (18:00); later issues are fixed forward in BIBS | A clear point after which legacy is never reopened for business | The Program Manager confirms the point of no return and who decides the rollback | DMQ32 | M6 (1 Oct 2027)
PR-DM-17 | Items in process at the freeze | Endorsements, un-booked accounts, placements, cheque pick-ups and refunds in process are completed in legacy before the freeze; what cannot complete is carried (F04, F06) or keyed in BIBS after go-live from a list signed by its owner | No item is lost at the freeze or processed in both systems | Operations confirms the completion drives and the re-keying list | DMQ33, DMQ21 | M2 (30 Oct 2026)
PR-DM-18 | Collection state | Carry the open dispositions, promises to pay, instalment plans and collector assignments of the open invoices; the history stays in the archive | Collectors continue their follow-up without re-keying | Collections confirms | DMQ34 | M2 (30 Oct 2026)
PR-DM-19 | Screening of migrated clients | No screening per migrated client during the load; one full screening run of all migrated clients before go-live; legacy screening results archived | Current results for every client without thousands of screening requests during the load | Compliance confirms | DMQ06 | M2 (30 Oct 2026)
PR-DM-20 | Retention of the migration evidence | Staged rows and files are deleted within 5 days of the batch sign-off; counts, hashes, totals, reports and sign-offs are kept 10 years; the archive and its access log follow the retention of historical data (5 years online, 15 years archive) | The personal data of the extracts is not kept longer than needed while the evidence of the migration stays available for audit | Compliance confirms the retention of the evidence | DMQ29, DMQ24 | M2 (30 Oct 2026)
PR-DM-21 | Decommissioning of a legacy system | A legacy system is switched off only against a signed checklist: final extracts reconciled, the final opening-balance adjustment reconciled (EBIX, ISYS), archive loaded and reconciled, Legacy Inquiry verified by Audit / Compliance, no open item or claim needing it, access logs archived, retention covered, owners signed | History and audit evidence stay available; nothing still open depends on the system | The Program Manager and BDOI IT confirm the criteria and the owner per system | DMQ27 | M6 (1 Oct 2027)
PR-DM-22 | No write-back to legacy | After the freeze no client or contact change is written back to QPS or EBIX; legacy is read-only | One system of record per item from the freeze | The Product Owner of MBS confirms | DCR-202 | M1 (16 Oct 2026)
PR-DM-23 | Treatment of a legacy invoice | A legacy invoice is not re-booked in BIBS: it enters the Operations ledger with its open balances per component and insurer share, keeps its legacy number, and is processed like a BIBS invoice (payments, remittance, reversals, endorsements) with its postings on the legacy control accounts | The legacy books stay traceable item by item and the processes after go-live are the ones users already learn for BIBS invoices | Comptrollership and Operations confirm the treatment | DMQ10, DMQ18 | M1 (16 Oct 2026)
PR-DM-24 | Package remapping at Renewal sanitation | The migration loads the policy headers with the legacy package as given and loads the package code map (object R06) prepared by TSU; each candidate is remapped at the package check of the Renewal sanitation, and a package without a map entry goes to the Exception bucket | BDOI decision of 26 September 2026; no package is guessed at load | The Product Owner of Marketing Business System confirms the decision and names the TSU preparer of the map | DMQ36 | M2 (30 Oct 2026)
PR-DM-25 | Renewals of the January-May 2028 expiries | No renewal cohort is carried from legacy: the expiries from go-live to 31 May 2028 are extracted at go-live and processed in BIBS, January expiries first and flagged Urgent; the renewal advices already sent are loaded from the Excel trackers of the Renewal processing team (object P03) with a maker and a checker | BDOI decisions of 26 September 2026; the renewal lead time of the first months is protected | The Heads of Retail and Corporate Marketing and the Head of the Renewal processing team confirm | DMQ26, DMQ37, DMQ38 | M2 (30 Oct 2026)
PR-DM-26 | Objects outside the migration | Open claims, Employee Benefits programmes, the Excel masterlists of submitted policies, payees and users are not migrated until BDOI decides; users are created through User Access requests and legacy user IDs are only mapped; an object brought into scope uses the same layouts, gates and reconciliation | The scope of these objects is open in the BRD | The Program Manager decides the scope of each object | DMQ30 | M2 (30 Oct 2026)
PR-DM-27 | Loading through the BIBS functions | Each row is loaded through the same BIBS function that the screens use, so every rule, audit entry and accounting entry applies, without notifications to clients or insurers; each record keeps a cross-reference to its legacy key | Migrated data meets the same rules as data keyed on the screens and every load is reconcilable | The Program Manager confirms the approach | - | M1 (16 Oct 2026)
PR-DM-28 | Reconciliation tolerance | An amount difference between the control total, staging and BIBS is a break unless it is within the amount tolerance per currency (proposed 0.00); every break is fixed by a rerun or explained with a reason from the list and approved by the reconciliation approver | Financial objects must reconcile to the centavo; the BRD gives no tolerance | Comptrollership confirms the tolerance | - | M2 (30 Oct 2026)

## Screen standards
Screen standards
Elements and standards shared by every screen (workflow stepper and history, pills, dates, uploads, messages, notifications); described once, not repeated per screen
No. | Element | What the user sees and does | BU review | BU comment | Reviewer | Review date
1 | Page header and section | Every page shows its section (Data Migration, Legacy Inquiry, Cashiering or Commission) and title, a one-line description and its actions on the right. The migration screens are the Migration Console: one catalogue of objects, layouts, code maps and rules for the programme, and the extracts, batches, reconciliations and plans of the company chosen in the header.
2 | Work lists and record panels | Lists show a filter row where the list has filters and a paged table ("Showing 1 to n of N results"). A row opens its record in a panel under the list (object, code map, layout, reconciliation, cut-over plan, legacy record) or on a page of its own (batch, legacy batch). Dates show as dd-MMM-yyyy and times as dd-MMM-yyyy HH:mm in Philippine time; amounts with two decimals and thousand separators.
3 | Status pills and the batch steps | Statuses are pills of one colour per state group (Proposed, For decision, Decided; Planned, Validated, Loaded, Loaded with rejects, Reconciled, Accepted, Rolled back; Matched, Break, Explained). A batch shows its steps as a stepper: Planned, Validated, Load approved, Loaded, Reconciled, Accepted, with the steps done marked.
4 | Confirmation and reason | Every submit, approve, return, sign, load, rollback, post and decide action opens a confirmation dialog that names the record and the effect of the action. A return, a rejection, a rollback request, a NO-GO and a blocked task need a reason; an approval takes an optional comment. The reason is kept with the record and in the audit trail.
5 | Maker-checker and gates | The user who prepares a decision, code map version, load, rollback, opening-balance adjustment, resubmission or legacy batch never approves it: the approve button is not offered to that user and the system refuses it. The operator who ran a batch cannot sign its reconciliation or acceptance, and one person cannot sign two gates of the same batch. Gates G1 to G7 are signed in order.
6 | Downloads | Templates, workbooks, rejection files, evidence and reports download as Excel or CSV files. Extract files and staged rows are kept only until the staging purge (5 days after the batch is accepted or rolled back); counts, totals and sign-offs stay.
7 | Migrated records in the business screens | A record migrated from a legacy system shows a LEGACY badge next to its number on its list and record, with the source system, legacy reference and migration batch in the tooltip. Lists that hold migrated records have an Origin filter (All origins, BIBS, Migrated). Migrated records raise no notification to clients or insurers.
8 | Messages | Field errors appear under the field in red; a banner at the top of a dialog or card lists the refusal of a business rule with its message and a reference for support. Success is confirmed by a short message at the bottom right of the page. Intake, validation and load results are also written to the run log of the batch.
9 | Notifications and alerts | The migration raises alerts to the Data Migration Lead and the owners concerned: extract rejected, load failed, unmapped codes, reconciliation break, Migration Clearing not zero, staging purge overdue, unusual access to the legacy archive, and a break of an opening-balance adjustment. The bell in the header opens them.

## Screen catalogue
Screen catalogue
One row per Data Migration screen
Screen ID | Area | Screen | Menu path | Personas | Permission | Purpose | Other entry points | Expected outcome | FRs | Test cases | Screenshots | Fields | Actions | BU review | BU comment | Reviewer | Review date
SCR-DM-01 | Migration Console | Migration Home | Data Migration › Data Migration › Migration Home | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | Shows the progress of the migration at a glance: objects decided and waiting for a decision, batches in progress, failed or with rejects, open reconciliation breaks, unmapped legacy codes, open validation errors and client pairs to review, with the next cut-over tasks and the run-off of the legacy policies. Each tile opens the screen where the item is worked. | Sidebar › Data Migration › Migration Home Landing page after sign-in of the migration roles | The Data Migration Lead sees what blocks the next gate and opens it in one click. | FR-DM-003, FR-DM-120, FR-DM-122 | TC-DM-SCR-01 | Migration Home with the tiles | 10 | 4
SCR-DM-02 | Migration Console | Data Objects and the decision of an object | Data Migration › Data Migration › Data Objects | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The register of the legacy data objects: what moves, in which class (migrate, carry forward, conditional, archive or excluded), from which systems, into which part of BIBS and in which load order. An object opens in a panel with the four criteria of the BRD, the owners, the rationale and the decision history; the Data Migration Lead submits the proposed class and the business owner approves or returns it (gate G1). The load template of each object downloads from its row. | Migration Home › Objects decided Sign-off › object | Every object has a decided class signed by its business owner (gate G1) and its load template. | FR-DM-001, FR-DM-002, FR-DM-003 | TC-DM-001.1-01, TC-DM-001.2-01, TC-DM-001.4-01, TC-DM-002.1-01, TC-DM-002.2-01, TC-DM-002.4-01, TC-DM-SCR-02, TC-DM-MSG-01 | Data Objects register with the class and status of each object Object C01 with the four criteria, the rationale and the decision history | 17 | 6
SCR-DM-03 | Migration Console | Code Maps and the versions of a code map | Data Migration › Data Migration › Code Maps | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The code maps that turn the legacy codes of each source system into BIBS values (lists of values, insurers, products, packages, branches, sales units, users, GL accounts, statuses and more). A code map opens with its versions and the entries of the chosen version. The Data Steward prepares a draft version on screen or in Excel and submits it; the business owner approves or returns it (gate G2). The Unmapped Codes tab lists the legacy codes found without an entry in the batches under validation. | Migration Home › Unmapped legacy codes Batch › Issues | Every legacy code used by a record in scope has an approved entry, and every batch records the versions it used. | FR-DM-011, FR-DM-012, FR-DM-034 | TC-DM-011.1-01, TC-DM-011.2-01, TC-DM-011.3-01, TC-DM-011.4-01, TC-DM-012.1-01, TC-DM-012.2-02, TC-DM-034.4-01, TC-DM-034.6-01, TC-DM-SCR-03, TC-DM-MSG-02 | Code Maps with the approved and open version of each map Code map INSURER with its versions and the entries of the version Add Entry dialog of a draft version Unmapped Codes tab | 16 | 7
SCR-DM-04 | Migration Console | Layouts and Rules | Data Migration › Data Migration › Layouts and Rules | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The extract layouts in force with their columns: the single source of the load templates BDOI fills. A layout opens with its columns (name, description, type and length, mandatory, code map, format, example, validation). The screen downloads the CSV template of a layout, the workbook of an object, the workbook of all templates and the control-file template. The Data-Quality Rules tab lists the checks run on every row; the Masking Rules tab lists the personal data masked outside production. | Migration Home › Load Templates Data Objects › All Load Templates | BDOI IT and the stewards download the templates that match the layouts in force, and see every check a row must pass. | FR-DM-010, FR-DM-013, FR-DM-003 | TC-DM-SCR-04, TC-DM-MSG-03 | Layouts in force with their key columns and hash total Columns of layout F01C (open invoice components) Data-Quality Rules tab Masking Rules tab | 9 | 5
SCR-DM-05 | Migration Console | Extracts | Data Migration › Data Migration › Extracts | Migration Operator | Data migration intake | Receives each legacy extract with its control file and runs the intake checks: file name, checksum, header, row count, amount totals and hash total. A file that passes is staged (masked outside production); a file that fails is rejected as a whole, with every failed check and its reason. The list shows every extract with its layout, source, as-of date, rows received and staged, masking, who received it and its status. | Migration Home › Upload Extract | Every file BDOI sends is either staged exactly as extracted or rejected with the reason and the difference. | FR-DM-010 | TC-DM-010.1-01, TC-DM-010.2-01, TC-DM-010.2-02, TC-DM-010.2-03, TC-DM-010.3-01, TC-DM-125.1-01, TC-DM-SCR-05, TC-DM-MSG-04 | Extracts with the upload card (Still needed: the files to choose) and the intake results An extract rejected at intake with every failed check and its reason | 13 | 2
SCR-DM-06 | Migration Console | Batches and resubmissions | Data Migration › Data Migration › Batches | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | Every load batch with its object, environment, counts, error rate and status. The Migration Operator plans a batch from the staged extracts of a decided object; a batch opens on its own page. The Resubmissions tab lists the corrected rejected rows that a maker has prepared and that a checker approves before they load (used for the renewal advices already sent, object P03). | Migration Home › Batches Extracts › Plan Batch | Each object is loaded in batches that can be followed from planning to acceptance, and corrected rows load only after a checker approves them. | FR-DM-014, FR-DM-015, FR-DM-125 | TC-DM-001.3-01, TC-DM-011.5-01, TC-DM-012.2-01, TC-DM-013.3-01, TC-DM-013.4-01, TC-DM-014.1-01, TC-DM-014.3-01, TC-DM-014.4-01, TC-DM-014.4-02, TC-DM-015.1-01, TC-DM-015.2-01, TC-DM-015.3-01, TC-DM-015.4-01, TC-DM-015.5-01, TC-DM-022.3-01, TC-DM-030.1-01, TC-DM-030.2-01, TC-DM-031.3-01, TC-DM-032.3-01, TC-DM-032.4-01, TC-DM-034.1-01, TC-DM-051.4-01, TC-DM-120.4-01, TC-DM-125.3-02, TC-DM-125.4-01, TC-DM-SCR-06, TC-DM-MSG-05 | Batches with their counts and status Plan Batch dialog Resubmissions of corrected rows waiting for the checker | 9 | 4
SCR-DM-07 | Migration Console | Batch | Data Migration › Data Migration › Batches › Batch | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | One batch from validation to acceptance. The header shows the status and the actions allowed now: validate, sign the validation (G3), approve the load (G4), load, reconcile, rerun the rejected rows, sign the reconciliation (G5), accept the object as data owner and as Data Migration Lead (G6), request, approve or reject a rollback. The steps, the counts and the facts of the batch are followed by tabs for the issues, the rows (with waivers and exclusions), the reconciliation, the gates signed with their evidence and the run log. | Batches › a batch row Sign-off › Latest batch | The batch is loaded, reconciled and accepted by its owner and the Data Migration Lead, or rolled back, with every step recorded. | FR-DM-013, FR-DM-014, FR-DM-015, FR-DM-003, FR-DM-020 | TC-DM-001.3-01, TC-DM-010.4-01, TC-DM-011.5-01, TC-DM-012.2-01, TC-DM-013.1-01, TC-DM-013.1-02, TC-DM-013.2-01, TC-DM-013.3-01, TC-DM-013.4-01, TC-DM-014.1-01, TC-DM-014.3-01, TC-DM-014.4-01, TC-DM-014.4-02, TC-DM-015.1-01, TC-DM-015.2-01, TC-DM-015.3-01, TC-DM-015.4-01, TC-DM-015.5-01, TC-DM-022.3-01, TC-DM-022.5-01, TC-DM-023.3-01, TC-DM-023.6-01, TC-DM-030.1-01, TC-DM-030.2-01, TC-DM-031.3-01, TC-DM-032.3-01, TC-DM-032.4-01, TC-DM-034.1-01, TC-DM-034.5-01, TC-DM-040.3-01, TC-DM-050.4-01, TC-DM-051.3-01, TC-DM-051.4-01, TC-DM-120.4-01, TC-DM-125.2-01, TC-DM-125.3-01, TC-DM-125.5-01, TC-DM-125.6-01, TC-DM-SCR-07, TC-DM-MSG-06, TC-DM-MSG-07 | A validated batch: steps, counts, facts and the Issues tab Rows tab with the waiver and exclusion of failing rows Waive Rows dialog Sign-offs tab of an accepted batch Run Log tab | 15 | 15
SCR-DM-08 | Migration Console | Client Matching | Data Migration › Data Migration › Client Matching | Data Steward | Data migration match decide | The review queue of the client pairs whose match score is between the review and the automatic thresholds: two legacy client records, or a legacy record and a BIBS client, side by side with the keys that matched. The Data Steward merges them into one client or keeps them separate; the load of a client batch waits until the queue is empty. | Migration Home › Client pairs to review Batch › Client pairs to review | One BIBS client per person or company, with every legacy client number pointing to it. | FR-DM-030, FR-DM-031 | TC-DM-031.1-01, TC-DM-031.2-01, TC-DM-031.4-01, TC-DM-SCR-08, TC-DM-MSG-08 | Client pairs waiting for review A pair side by side with the matched keys marked | 6 | 2
SCR-DM-09 | Migration Console | Reconciliation | Data Migration › Data Migration › Reconciliation | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The loaded batches with their reconciliation and, for the chosen batch, the lines by level: L1 counts, L2 amounts, L3 hash totals, L4 fields, L5 general ledger, and the opening-balance adjustment checks. Every difference is a break; the Data Steward or the operator explains it with a reason and the reconciliation approver approves the explanation. | Migration Home › Open reconciliation breaks Batch › Reconciliation tab | Every loaded object is reconcilable from source to target, each break explained and approved before G5. | FR-DM-020, FR-DM-021 | TC-DM-020.1-01, TC-DM-020.2-01, TC-DM-020.3-01, TC-DM-021.1-01, TC-DM-021.3-01, TC-DM-021.4-01, TC-DM-040.5-01, TC-DM-SCR-09, TC-DM-MSG-09 | A loaded batch and its reconciliation lines by level Explain Break dialog | 9 | 2
SCR-DM-10 | Migration Console | Sign-off | Data Migration › Data Migration › Sign-off | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The gates G1 to G7 of every object and of its latest batch as a matrix: decision, mapping, validation, load approval, reconciliation, acceptance and go-live, each with who signed and when. The business owner signs the mapping of an object here (gate G2); the other batch gates are signed on the batch page. | Sidebar › Data Migration › Sign-off | The Data Migration Lead sees what is missing per object before a trial migration or the cut-over. | FR-DM-003 | TC-DM-003.1-01, TC-DM-003.1-02, TC-DM-003.2-01, TC-DM-003.3-01, TC-DM-003.4-01, TC-DM-SCR-10 | Gate matrix per object with the signer and date of each gate | 3 | 2
SCR-DM-11 | Cut-over, adjustments and run-off | Opening-Balance Adjustments | Data Migration › Data Migration › Opening Adjustments | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The FY2027 closing and audit adjustments of the legacy books after go-live (year-end option A). The Comptrollership GL lead prepares an adjustment on a validated batch of the adjustment journals (object G03) and the legacy trial balance of the same version (object G01); the Head of Comptrollership approves or returns it. The load of the batch posts the opening-balance adjustment journals into the opening period (value date 1 January 2028) and adjusts the open legacy items; the adjustment is then reconciled to the legacy trial balances and signed. | Sidebar › Data Migration › Opening Adjustments | Every FY2027 adjustment made in legacy after the freeze is in the BIBS opening balances, approved and reconciled. | FR-DM-022, FR-DM-023, FR-DM-024 | TC-DM-023.1-01, TC-DM-023.4-01, TC-DM-023.5-01, TC-DM-024.2-01, TC-DM-024.3-01, TC-DM-024.4-01, TC-DM-SCR-11, TC-DM-MSG-10 | Opening-balance adjustments with their batches and status Prepare Adjustment dialog | 9 | 6
SCR-DM-12 | Cut-over, adjustments and run-off | Cutover | Data Migration › Data Migration › Cutover | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The mock runs, the dress rehearsal and the production cut-over, each a plan with its runbook of tasks planned from the go-live date, the twelve go / no-go criteria and the decisions of the board. Task owners start, complete or block their tasks; the criteria are measured by BIBS or recorded with their evidence; the board decides GO or NO-GO. The runbook downloads as a workbook. | Migration Home › Next cut-over tasks | The cut-over follows a rehearsed plan and go-live is decided on measured criteria. | FR-DM-120, FR-DM-121 | TC-DM-120.1-01, TC-DM-120.2-01, TC-DM-120.3-01, TC-DM-120.5-01, TC-DM-120.5-02, TC-DM-120.6-01, TC-DM-121.1-01, TC-DM-121.2-01, TC-DM-121.3-01, TC-DM-121.4-01, TC-DM-121.5-01, TC-DM-SCR-12, TC-DM-MSG-11 | Cut-over plans and the runbook of a mock run Go / No-Go Criteria and Decisions of a plan New Cutover Plan dialog | 11 | 8
SCR-DM-13 | Cut-over, adjustments and run-off | Run-off and Decommissioning | Data Migration › Data Migration › Run-off and Decommissioning | Data Migration Lead, Data Steward, Data owner (business owner of an object), Migration Operator, Reconciliation approver (Head of Comptrollership), Go / no-go board, Comptrollership GL lead | Data migration view | The monthly run-off of the legacy policies in force at go-live by expiry month and source system (renewed in BIBS, not renewed, lapsed, still open), and the checklists that close each legacy system and, once every legacy item is settled, the legacy context of BIBS. | Migration Home › Run-off of the legacy policies | The run-off of the legacy policies is visible month by month and each legacy system is closed against a signed checklist. | FR-DM-122, FR-DM-123 | TC-DM-123.1-01, TC-DM-123.2-01, TC-DM-123.3-01, TC-DM-123.4-01, TC-DM-SCR-13, TC-DM-MSG-12 | Run-off by expiry month and the decommissioning checklists | 8 | 3
SCR-DM-14 | Legacy Inquiry | Legacy Inquiry | Data Migration › Legacy Inquiry › Legacy Inquiry | Audit / Compliance user | Legacy inquiry view | The read-only archive of the legacy systems for Audit and Compliance: closed clients, policies, invoices, receipts, remittances, endorsements, claims, GL journals, renewal advices and letters with their documents. The user gives the reason of the inquiry once per session; each search, view, download and export is logged with it. A record opens read-only with all its legacy columns and documents. | Sidebar › Data Migration › Legacy Inquiry | Legacy history stays retrievable with its documents, and every access is logged with its reason. | FR-DM-110 | TC-DM-110.1-01, TC-DM-110.2-01, TC-DM-110.3-01, TC-DM-SCR-14, TC-DM-MSG-13 | Reason of the Inquiry asked once per session Search criteria and the legacy records found A legacy record with its legacy details and documents | 13 | 5
SCR-DM-15 | Legacy Inquiry | Access Log | Data Migration › Legacy Inquiry › Access Log | Compliance reviewer of the access log | Legacy access log view | Every access to the legacy archive with the user, the time and address, the action, the criteria, the records and the reason, for the Compliance reviewer. The log cannot be changed or deleted; a monthly digest is sent to the reviewers. | Sidebar › Data Migration › Access Log | Compliance sees who looked at which legacy records, when and why. | FR-DM-111 | TC-DM-111.1-01, TC-DM-111.3-01, TC-DM-SCR-15 | Access Log with its filters | 7 | 1
SCR-DM-16 | Migrated data on the business screens | LEGACY badge and Origin filter on the lists | Client & Policy › Clients › Clients | Comptrollership GL lead, Cashiering user, Cashiering team lead, Commission user, Commission team lead, Marketing Account Officer | Client view | Records migrated from a legacy system are used with the normal BIBS screens. They are told apart from records created in BIBS by a LEGACY badge next to their number on the lists and records (Clients, Accounts, Invoice Search, Unapplied Payments, the PR Worklist and its accounts, Products, Insurers, Payees), with the source system, the legacy reference and the migration batch in its tooltip, and by the Origin filter of the lists that hold migrated records. | Client & Policy › Clients › Clients Client & Policy › Accounts & Placement › Accounts Operations › Operations › Invoice Search Finance › Cashiering › Unapplied Payments Finance › Collections › PR Worklist | Users work migrated and new records on the same screens and always know which is which. | FR-DM-032, FR-DM-033, FR-DM-040 | TC-DM-014.2-01, TC-DM-032.1-01, TC-DM-032.2-01, TC-DM-033.1-01, TC-DM-033.2-01, TC-DM-033.3-01, TC-DM-040.1-01, TC-DM-040.2-01, TC-DM-040.4-01, TC-DM-041.1-01, TC-DM-041.2-01, TC-DM-041.3-01, TC-DM-090.3-01, TC-DM-SCR-16 | Clients list with a migrated client marked LEGACY Unapplied Payments with the Origin filter set to Migrated | 4 | 1
SCR-DM-17 | Migrated data on the business screens | Legacy invoice on Invoice 360 | Operations › Operations › Invoice Search › Invoice 360 | Comptrollership GL lead, Cashiering user, Cashiering team lead, Commission user, Commission team lead, Marketing Account Officer | Ops view | An open legacy invoice is carried into the BIBS Operations ledger with its open balances and processed like a BIBS invoice. Invoice 360 shows its LEGACY badge and legacy invoice number, and a Legacy Invoice card with the source system, the legacy reference, the migration batch and the values at cut-over, kept as loaded: the original gross premium, commission and VAT, and per component what was booked, adjusted, paid and remitted in legacy, written off and open at cut-over. | Operations › Operations › Invoice Search › a legacy invoice PR Worklist › a legacy item | The user sees what was open at cut-over and what has happened in BIBS since, on one screen. | FR-DM-050, FR-DM-051, FR-DM-060, FR-DM-100 | TC-DM-023.2-01, TC-DM-050.1-01, TC-DM-050.3-01, TC-DM-SCR-17 | Invoice 360 of a legacy invoice with the Legacy Invoice card | 8 | 1
SCR-DM-18 | Legacy batches | Unapplied to Income | Finance › Cashiering › Unapplied to Income | Cashiering user, Cashiering team lead, Top management approver | Cash UPP income request or Cash UPP income approve or Cash disposition approve | Batches of old unapplied payments, new and legacy, reclassified to other income (unclaimed collections). A Cashiering user opens a batch with its reason and currency and adds the unapplied payments received at least a chosen number of days ago; the Cashiering team lead approves, then top management; after the second approval each line posts on its own and the payment closes. Legacy items come from Unapplied Collections - Legacy, new ones from Unapplied Collections. | Finance › Cashiering › Unapplied to Income Unapplied Payments › an old item | Old unapplied payments are taken to income under two approvals, line by line. | FR-DM-055 | TC-DM-055.1-01, TC-DM-055.4-01, TC-DM-055.4-02, TC-DM-SCR-18, TC-DM-MSG-14 | Unapplied to Income batches A draft batch with its lines and the payments that may be added A batch waiting for top management | 13 | 7
SCR-DM-19 | Legacy batches | Legacy PR 2307 Reversal | Finance › Cashiering › Legacy PR 2307 Reversal | Cashiering user, Cashiering team lead, Commission user, Commission team lead | Legacy reversal request or Legacy reversal approve | Batches that settle the PR 2307 balance of legacy invoices against the amount due to the insurer. A Cashiering user adds each legacy invoice with the amount to reverse; when the PR 2307 is short, the premium receivable needed is first moved to PR 2307. The Cashiering team lead approves and each line posts on its own. | Finance › Cashiering › Legacy PR 2307 Reversal | The PR 2307 balances of legacy invoices are settled against the insurer, line by line. | FR-DM-071 | TC-DM-071.1-01, TC-DM-071.2-01, TC-DM-071.2-02, TC-DM-SCR-19 | A draft PR 2307 reversal batch with the legacy invoice to add | 5 | 3
SCR-DM-20 | Legacy batches | DP PR Legacy Reversal | Finance › Commission Receivables › DP PR Legacy Reversal | Cashiering user, Cashiering team lead, Commission user, Commission team lead | Legacy reversal request or Legacy reversal approve | Batches that reverse the open premium receivable of legacy invoices paid directly to the insurer, with the same amount of the due to insurer; what was collected through the broker stays to remit. The candidates are the legacy invoices that Collections tagged "DP PR for reversal", or any legacy invoice with an open premium. A Commission user prepares the batch, the Commission team lead approves it and each invoice posts on its own. | Finance › Commission Receivables › DP PR Legacy Reversal | Legacy invoices paid directly to the insurer leave the legacy receivable and payable in one approved batch. | FR-DM-070 | TC-DM-070.1-01, TC-DM-070.2-01, TC-DM-070.3-01, TC-DM-070.3-02, TC-DM-SCR-20 | A draft batch with the tagged legacy invoices to add | 5 | 3

## Field register
Field register
Every field and list column of every screen
Screen ID | Screen | No. | Section | Field | Type | Length / format | Mandatory | Source / list | Default | Editable in | Validation rule | Message when it fails | BU review | BU comment | Reviewer | Review date
SCR-DM-01 | Migration Home | 1 | Tiles | Objects decided | Tile | Count | - | Data objects | - | - | - | -
SCR-DM-01 | Migration Home | 2 | Tiles | Objects waiting for a decision | Tile | Count of Proposed and For decision objects | - | Data objects | - | - | - | -
SCR-DM-01 | Migration Home | 3 | Tiles | Batches in progress | Tile | Count of Planned, Validated, Load approved and Loading batches | - | Batches | - | - | - | -
SCR-DM-01 | Migration Home | 4 | Tiles | Batches failed or with rejects | Tile | Count; Needs attention when above 0 | - | Batches | - | - | - | -
SCR-DM-01 | Migration Home | 5 | Tiles | Open reconciliation breaks | Tile | Count; Needs attention when above 0 | - | Reconciliation | - | - | - | -
SCR-DM-01 | Migration Home | 6 | Tiles | Unmapped legacy codes | Tile | Count; Needs attention when above 0 | - | Code Maps, Unmapped Codes tab | - | - | - | -
SCR-DM-01 | Migration Home | 7 | Tiles | Open validation errors | Tile | Count; Needs attention when above 0 | - | Batch issues | - | - | - | -
SCR-DM-01 | Migration Home | 8 | Tiles | Client pairs to review | Tile | Count | - | Client Matching | - | - | - | -
SCR-DM-01 | Migration Home | 9 | Next cut-over tasks | Plan, Task, Owner, Planned start, Status | Columns | dd-MMM-yyyy HH:mm | - | Open tasks of the cut-over plans | - | - | - | -
SCR-DM-01 | Migration Home | 10 | Run-off of the legacy policies | Expiry month, In force, Renewed, Not renewed, Still open | Columns | Month yyyy-MM | - | Latest run-off snapshot | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 1 | Filter | Category | Drop-down | All categories, Reference, Client, Policy, Open item, GL, History | N | Categories of the register | All categories | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 2 | Register | Order | Column | Load order | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 3 | Register | Object | Column | Code and name, category under it | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 4 | Register | Sources | Column | Legacy systems | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 5 | Register | Class | Column | Decided class, or the proposed class marked Proposed | - | Decision | Proposed class | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 6 | Register | Financial and After tags | Tag | Financial object; objects it loads after | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 7 | Register | Business owner | Column | Name | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 8 | Register | Status | Pill | Proposed, For decision, Decided | - | Decision | Proposed | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 9 | Object panel | Category, Sources, Target in BIBS | Text | - | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 10 | Object panel | Proposed class, Decided class | Text | Migrate, Carry forward, Conditional, Archive, Excluded | - | Decision | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 11 | Object panel | Condition | Text | Condition of a conditional object | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 12 | Object panel | Day-1 need, Compliance need, Archive option | Text | Yes or No, with the note | - | The four criteria of the BRD | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 13 | Object panel | Data trust | Text | High, Medium, Low | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 14 | Object panel | Business owner, Data steward | Text | Name, or the proposed role until named | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 15 | Object panel | Depends on, Load order | Text | Objects and number | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 16 | Object panel | Rationale | Text | Up to 2,000 characters | - | Object | - | - | - | -
SCR-DM-02 | Data Objects and the decision of an object | 17 | Decision history | Decision, Class, Submitted by, Submitted, Decided by, Return reason, Status | Columns | Decision number MGD-yyyy-nnnnnn | - | Decisions of the object | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 1 | Code Maps tab | Search code map | Search | Code or name | N | - | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 2 | Code Maps tab | Code map | Column | Set code with its name under it | - | Code map sets | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 3 | Code Maps tab | BIBS values | Column | What the codes map to | - | Code map sets | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 4 | Code Maps tab | Used by | Column | Layouts whose columns use the map | - | Code map sets | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 5 | Code Maps tab | Approved version | Column | vN, or None in red | - | Versions | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 6 | Code Maps tab | Open version | Pill | Draft or Submitted | - | Versions | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 7 | Versions | Version, Comment, Prepared by, Approved by, Approved, Return reason, Status | Columns | Draft, Submitted, Approved, Superseded | - | Versions of the map | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 8 | Entries | Source, Legacy code, Legacy description, Condition, Action, BIBS value, Remarks | Columns | - | - | Entries of the version | - | - | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 9 | Add Entry | Source | Drop-down | EBIX, QPS, ISYS, EXCEL, CMS | Y | Source systems | QPS | Draft | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 10 | Add Entry | Legacy code | Text | Up to 80 characters | Y | - | - | Draft | Unique per source and condition in the version | Legacy code <legacy code> of <source system> is mapped twice
SCR-DM-03 | Code Maps and the versions of a code map | 11 | Add Entry | Legacy description | Text | Up to 250 characters | N | - | - | Draft | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 12 | Add Entry | Action | Drop-down | Map to a BIBS value, Create in BIBS, Use the default value, Reject the record | Y | - | Map to a BIBS value | Draft | - | Enter the source system, the legacy code and the action
SCR-DM-03 | Code Maps and the versions of a code map | 13 | Add Entry | BIBS value | Text | A value of the BIBS master | C | The master of the map | - | Draft | Mandatory for Map; the value exists in BIBS | Enter the target code of legacy code <legacy code>
SCR-DM-03 | Code Maps and the versions of a code map | 14 | Add Entry | Condition column, Condition value | Text | Column and value of a conditional entry, for example insurer_code | N | Layout columns | - | Draft | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 15 | Add Entry | Remarks | Text | Up to 300 characters | N | - | - | Draft | - | -
SCR-DM-03 | Code Maps and the versions of a code map | 16 | Unmapped Codes tab | Code map, Source, Legacy code, Rows, Example records, Blocks the load | Columns | Blocks the load Yes for a mandatory column | - | Validation issues of the batches | - | - | - | -
SCR-DM-04 | Layouts and Rules | 1 | Layouts tab | Layout | Column | Code and version, title under it | - | Layouts in force | - | - | - | -
SCR-DM-04 | Layouts and Rules | 2 | Layouts tab | Object | Column | Object code | - | Layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 3 | Layouts tab | Key columns | Column | Legacy key of a row | - | Layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 4 | Layouts tab | Hash total | Column | Count of distinct keys, Row count, Sum of the numeric part | - | Layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 5 | Layouts tab | Frozen | Column | dd-MMM-yyyy HH:mm | - | Layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 6 | Layouts tab | Status | Pill | Draft, Frozen, Retired | - | Layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 7 | Columns | #, Column, Type, Mandatory, Code map, Format, Example, Validation | Columns | Type with its length; description under the column name | - | Columns of the layout | - | - | - | -
SCR-DM-04 | Layouts and Rules | 8 | Data-Quality Rules tab | Rule, Layouts, Columns, Check, Severity, Fixed by, Active | Columns | Severity Error or Warning; the message under the check | - | Rule catalogue | - | - | - | -
SCR-DM-04 | Layouts and Rules | 9 | Masking Rules tab | Layout, Column, Masking, Active | Columns | - | - | Masking rules | - | - | - | -
SCR-DM-05 | Extracts | 1 | Upload an extract | Data file | File | LAYOUT_SOURCE_yyyyMMdd_nn.csv or .xlsx | Y | - | - | - | Name, layout, source system and date of the name are valid; the object is decided | Name the file <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv or .xlsx, for example F01C_EBIX_20271231_01.csv
SCR-DM-05 | Extracts | 2 | Upload an extract | Control file | File | <data file name>.ctl.csv | Y | - | - | - | Row count, hash total, amount totals and SHA-256 agree with the data file | The file has <n> rows; the control file says <m>
SCR-DM-05 | Extracts | 3 | Upload an extract | Mode | Drop-down | Full extract, Delta since the previous extract | Y | - | Full extract | - | A delta is later than the previous extract of the layout | -
SCR-DM-05 | Extracts | 4 | Filter | Object | Text | Object code, for example C01 | N | - | All objects | - | - | -
SCR-DM-05 | Extracts | 5 | Extracts | Extract | Column | MGX-yyyy-nnnnnn with the file name under it | - | Extracts | - | - | - | -
SCR-DM-05 | Extracts | 6 | Extracts | Layout | Column | Layout and version; source system and mode under it | - | Extracts | - | - | - | -
SCR-DM-05 | Extracts | 7 | Extracts | As of | Column | dd-MMM-yyyy HH:mm | - | Control file | - | - | - | -
SCR-DM-05 | Extracts | 8 | Extracts | Rows Received | Column | Number of rows read from the data file | - | Intake | - | - | - | -
SCR-DM-05 | Extracts | 9 | Extracts | Rows Staged | Column | Number of rows staged (0 when rejected) | - | Intake | - | - | - | -
SCR-DM-05 | Extracts | 10 | Extracts | Masked | Column | Yes or No | - | Environment | - | - | - | -
SCR-DM-05 | Extracts | 11 | Extracts | Received On | Column | Date and time, user under it | - | Intake | - | - | - | -
SCR-DM-05 | Extracts | 12 | Extracts | Rejection Reason | Column | Each failed check with its reason (Row count, Checksum, Columns, Amount total, Hash total) | - | Intake | - | - | - | -
SCR-DM-05 | Extracts | 13 | Extracts | Status | Pill | Received, Checked, Staged, Rejected, Purged | - | Intake | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 1 | Batches tab | Batch | Column | MGB-yyyy-nnnnn; Full, Delta or Rerun of the parent batch under it | - | Batches | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 2 | Batches tab | Object, Environment | Column | Object code; SIT, UAT, performance or production | - | Batch | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 3 | Batches tab | Staged, Loaded, Rejected | Column | Counts | - | Batch | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 4 | Batches tab | Error rate | Column | Percent | - | Validation | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 5 | Batches tab | Planned | Column | Date and time; user under it | - | Batch | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 6 | Batches tab | Status | Pill | Planned, Validated, Load approved, Loading, Loaded, Loaded with rejects, Failed, Reconciled, Accepted, Rollback requested, Rolled back | - | Batch | - | - | - | -
SCR-DM-06 | Batches and resubmissions | 7 | Plan Batch | Object | Drop-down | Objects decided as Migrate, Carry forward or Conditional | Y | Data objects | - | - | The object has a staged extract | Object <code> has no staged extract to load
SCR-DM-06 | Batches and resubmissions | 8 | Plan Batch | Extracts | Text | Extract numbers separated by commas; empty for the latest staged extract of each layout | N | Staged extracts | - | - | Same as-of date; staged; not in another batch | The extracts of a batch must have the same as-of date: <days>
SCR-DM-06 | Batches and resubmissions | 9 | Resubmissions tab | Resubmission, Object, Corrected rows, Prepared, Decided by, Note, Status | Columns | Prepared, Approved, Returned | - | Resubmissions | - | - | - | -
SCR-DM-07 | Batch | 1 | Steps | Planned, Validated, Load approved, Loaded, Reconciled, Accepted | Stepper | Steps done are marked | - | Batch status | - | - | - | -
SCR-DM-07 | Batch | 2 | Counts | Staged, Valid, Invalid, Loaded | Tile | Warnings, excluded and waived, unchanged and rejected under them | - | Batch | - | - | - | -
SCR-DM-07 | Batch | 3 | Batch | Extracts, Rerun of, Code map versions | Text | Extract numbers; parent batch; map and version | - | Batch | - | - | - | -
SCR-DM-07 | Batch | 4 | Batch | Error rate, Unmapped codes, Client pairs to review | Text | Percent; counts | - | Validation | - | - | - | -
SCR-DM-07 | Batch | 5 | Batch | Validated by, Load approved by, Loaded by | Text | Name, date and time | - | Batch | - | - | - | -
SCR-DM-07 | Batch | 6 | Batch | Load started, Load ended, Accepted | Text | dd-MMM-yyyy HH:mm | - | Batch | - | - | - | -
SCR-DM-07 | Batch | 7 | Batch | Rollback reason, Staging purged on | Text | Text; date | - | Batch | - | - | - | -
SCR-DM-07 | Batch | 8 | Issues tab | Rule, Severity, Field, Message, Resolution | Columns | Error or Warning; the value under the field; Open, Fixed at source, Mapped, Waived | - | Validation issues | - | - | - | -
SCR-DM-07 | Batch | 9 | Rows tab | Row status | Drop-down | All rows, Valid, Warning, Invalid, Loaded, Skipped, Rejected, Excluded, Waived | N | - | All rows | - | - | -
SCR-DM-07 | Batch | 10 | Rows tab | Layout, Row, Legacy key, BIBS record, Message, Status | Columns | The BIBS record created, with its kind under it | - | Staged rows | - | - | - | -
SCR-DM-07 | Batch | 11 | Waive Rows / Exclude Rows | Reason | Drop-down | Record not needed in BIBS, Entered manually in BIBS after go-live | Y | Waiver reasons | Record not needed in BIBS | Validated | - | -
SCR-DM-07 | Batch | 12 | Waive Rows / Exclude Rows | Note / Manual-entry plan | Text area | Free text | Y | - | - | Validated | Not blank | Enter the reason and the manual-entry plan of the excluded rows
SCR-DM-07 | Batch | 13 | Resubmit Corrected Rows | Extract of the corrected rows | Text | Extract number of the uploaded correction file | Y | Staged extracts of the object | - | - | Staged extract of the same object | Extract <extract no> is not a staged extract of object <object code>
SCR-DM-07 | Batch | 14 | Sign-offs tab | Gate, Role, Signed by, Signed, Comment, Decision, Evidence | Columns | Gate and its name; evidence file | - | Gates signed | - | - | - | -
SCR-DM-07 | Batch | 15 | Run Log tab | Time, Step, Level, Message, Counts, By | Columns | - | - | Run log | - | - | - | -
SCR-DM-08 | Client Matching | 1 | Queue | Batch, Cluster, Legacy client | Column | Batch number; cluster number; legacy client number | - | Matching | - | - | - | -
SCR-DM-08 | Client Matching | 2 | Queue | Matched with | Column | Legacy client or BIBS client | - | Matching | - | - | - | -
SCR-DM-08 | Client Matching | 3 | Queue | Score | Column | 60 to 89 in the queue | - | Matching keys | - | - | - | -
SCR-DM-08 | Client Matching | 4 | Queue | Keys matched | Column | TIN, ID, name and birth date, corporate name, CIF, e-mail, mobile, similar name | - | Matching | - | - | - | -
SCR-DM-08 | Client Matching | 5 | Queue | Decision | Pill | To review, Merged, Kept separate, Merged automatically | - | Matching | To review | - | - | -
SCR-DM-08 | Client Matching | 6 | Pair | Field | Column | Matched fields shown as tags | - | Both records | - | - | - | -
SCR-DM-09 | Reconciliation | 1 | Loaded batches | Batch, Object, Loaded, Load ended, Status | Columns | - | - | Batches loaded, reconciled or accepted | - | - | - | -
SCR-DM-09 | Reconciliation | 2 | Reconciliation | Title | Text | Run number, date and time, user; status on the right | - | Latest run | - | - | - | -
SCR-DM-09 | Reconciliation | 3 | Reconciliation | Level | Column | L1 Counts, L2 Amounts, L3 Hash totals, L4 Fields, L5 General ledger, Opening-balance adjustment | - | Run | - | - | - | -
SCR-DM-09 | Reconciliation | 4 | Reconciliation | Measure, Currency | Column | Measure with its detail under it | - | Run | - | - | - | -
SCR-DM-09 | Reconciliation | 5 | Reconciliation | Source, Staged, BIBS, Difference | Amount | Two decimals | - | Control file, staging, BIBS | - | - | Difference within the tolerance (0.00) | -
SCR-DM-09 | Reconciliation | 6 | Reconciliation | Explanation | Column | Text; reason, who explained, who approved under it | - | Break | - | - | - | -
SCR-DM-09 | Reconciliation | 7 | Reconciliation | Status | Pill | Matched, Break, Explained | - | Run | - | - | - | -
SCR-DM-09 | Reconciliation | 8 | Explain Break | Reason | Drop-down | Timing difference between extract and ledger, Rounding in the legacy extract, Rows excluded by the data owner, Error in the legacy source corrected by manual entry, Code map difference, Other | Y | Break reasons | Timing difference between extract and ledger | Break | - | -
SCR-DM-09 | Reconciliation | 9 | Explain Break | Explanation | Text area | Free text | Y | - | - | Break | Not blank | Enter the explanation of the break
SCR-DM-10 | Sign-off | 1 | Matrix | Object | Column | Code and name; class under it | - | Data objects | - | - | - | -
SCR-DM-10 | Sign-off | 2 | Matrix | Latest batch | Column | Batch number and status | - | Batches | - | - | - | -
SCR-DM-10 | Sign-off | 3 | Matrix | Decision, Mapping, Validation, Load approval, Reconciliation, Acceptance, Go-live | Column | One column per gate G1 to G7; decision pill with the signer and date | - | Gates signed | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 1 | List | Adjustment | Column | Reference MIG-TU-n; as-of date under it | - | Adjustments | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 2 | List | Batches | Column | Adjustment batch; trial balance batch under it | - | Adjustment | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 3 | List | Posted | Column | Journals and items adjusted; date and time | - | Posting | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 4 | List | Prepared / Approved / Signed | Column | Names | - | Adjustment | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 5 | List | Status | Pill | Prepared, For approval, Approved, Posted, Reconciled, Signed | - | Adjustment | Prepared | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 6 | Prepare Adjustment | Adjustment | Drop-down | 1 after the legacy year-end close, 2 interim, 3 interim, F final after the audited statements | Y | - | 1 | - | Not yet prepared | Opening-balance adjustment <no> already exists
SCR-DM-11 | Opening-Balance Adjustments | 7 | Prepare Adjustment | Legacy Trial Balance As Of | Date | dd-MMM-yyyy | Y | - | - | - | - | -
SCR-DM-11 | Opening-Balance Adjustments | 8 | Prepare Adjustment | Adjustment Batch | Drop-down | A validated batch of the adjustment journals (G03) | Y | Batches of object G03 | - | - | A batch of the adjustment object | Batch <batch no> is not a batch of object <object>
SCR-DM-11 | Opening-Balance Adjustments | 9 | Prepare Adjustment | Legacy Trial Balance Batch | Drop-down | The trial balance of the same version (G01), or None | N | Batches of object G01 | None | - | - | -
SCR-DM-12 | Cutover | 1 | Plans | Plan | Column | Name; plan number under it | - | Plans | - | - | - | -
SCR-DM-12 | Cutover | 2 | Plans | Kind | Column | Mock run with its number, Dress rehearsal, Production cut-over | - | Plan | - | - | - | -
SCR-DM-12 | Cutover | 3 | Plans | Environment, Go-live, Status | Column | SIT, UAT, PERF or PROD; dd-MMM-yyyy | - | Plan | - | - | - | -
SCR-DM-12 | Cutover | 4 | New Cutover Plan | Name | Text | Up to 120 characters | Y | - | - | - | Not blank | -
SCR-DM-12 | Cutover | 5 | New Cutover Plan | Kind | Drop-down | Mock run, Dress rehearsal, Production cut-over | Y | - | Mock run | - | - | -
SCR-DM-12 | Cutover | 6 | New Cutover Plan | Mock No. | Number | 1 or more | N | - | - | - | For a mock run | -
SCR-DM-12 | Cutover | 7 | New Cutover Plan | Environment | Text | SIT, UAT, PERF or PROD | Y | - | SIT | - | Not blank | -
SCR-DM-12 | Cutover | 8 | New Cutover Plan | Go-live Date | Date | dd-MMM-yyyy | Y | - | - | - | - | Give the go-live date of the plan
SCR-DM-12 | Cutover | 9 | Runbook | No., Task, Owner, After, Planned, Actual, Status | Columns | Phase under the task; object under the owner; reason under the status | - | Runbook tasks | - | - | - | -
SCR-DM-12 | Cutover | 10 | Go / No-Go Criteria | No., Criterion, Kind, Measured, Result | Columns | Threshold under the criterion; Measured or Recorded; Open, Met, Not met | - | Criteria | - | - | - | -
SCR-DM-12 | Cutover | 11 | Decisions | Decision, Criteria met, Decided by, At, Comment | Columns | GO or NO-GO | - | Decisions of the board | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 1 | Run-off | Expiry Month, System | Column | yyyy-MM; EBIX, QPS, ISYS, CMS | - | Run-off snapshot | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 2 | Run-off | In Force, Premium in Force | Column | Count; amount | - | Run-off snapshot | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 3 | Run-off | Renewed, Not Renewed, Lapsed, Still Open | Column | Counts | - | Run-off snapshot | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 4 | Decommissioning Checklists | Legacy System | Drop-down | EBIX, QPS, ISYS, CMS without an open checklist | Y | Legacy systems | EBIX | - | - | The checklist of <system> is already open
SCR-DM-13 | Run-off and Decommissioning | 5 | Decommissioning Checklists | System | Column | System, or Legacy context; the milestone under it | - | Checklist | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 6 | Decommissioning Checklists | Criterion | Column | Name; description under it | - | Checklist template | - | - | - | -
SCR-DM-13 | Run-off and Decommissioning | 7 | Decommissioning Checklists | Evidence | Column | Text; who signed and when under it | - | Checklist | - | - | Evidence given | Give the evidence of the criterion
SCR-DM-13 | Run-off and Decommissioning | 8 | Decommissioning Checklists | Status | Pill | Open, Met, Signed, Not applicable | - | Checklist | Open | - | - | -
SCR-DM-14 | Legacy Inquiry | 1 | Reason of the Inquiry | Reason | Drop-down | Reasons of the list | Y | Access reasons | - | - | - | Give the reason for opening the legacy archive
SCR-DM-14 | Legacy Inquiry | 2 | Reason of the Inquiry | Details | Text | Audit reference, request or case; up to 500 characters | C | - | - | - | Mandatory for the reason Other | -
SCR-DM-14 | Legacy Inquiry | 3 | Search | Client Name or No., Policy / Cover No., Invoice No., Receipt No., Claim No. | Text | - | C | - | - | - | At least one criterion | Give a client, policy, invoice, receipt or claim, a record type or a date range
SCR-DM-14 | Legacy Inquiry | 4 | Search | Record Type | Drop-down | All, client, policy, invoice, receipt, remittance, endorsement, claim, GL journal, renewal advice, letter, other | N | - | All | - | - | -
SCR-DM-14 | Legacy Inquiry | 5 | Search | Date From, Date To | Date | dd-MMM-yyyy | N | - | - | - | Valid dates | Give the date as yyyy-MM-dd: <value>
SCR-DM-14 | Legacy Inquiry | 6 | Legacy Records | Record | Column | Legacy key; source system and record type under it | - | Archive | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 7 | Legacy Records | Client | Column | Name; legacy client number under it | - | Archive | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 8 | Legacy Records | Policy / Invoice / Receipt | Column | Policy; invoice, receipt and claim under it | - | Archive | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 9 | Legacy Records | Date, Amount, Legacy Status, Documents | Column | dd-MMM-yyyy; currency and amount; status; count | - | Archive | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 10 | Record | Legacy system, Client, Policy / cover, Invoice, Receipt, Claim | Text | - | - | Archive record | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 11 | Record | Date, Period, Amount, Legacy status, Archived | Text | dd-MMM-yyyy; amounts with two decimals | - | Archive record | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 12 | Record | Legacy details | Text | Every legacy column with its label | - | Archive record | - | - | - | -
SCR-DM-14 | Legacy Inquiry | 13 | Record | File, Document, Size | Columns | Documents archived with the record | - | Archive documents | - | - | - | -
SCR-DM-15 | Access Log | 1 | Filters | User | Text | User name | N | - | - | - | - | -
SCR-DM-15 | Access Log | 2 | Filters | Action | Drop-down | All, Search, View, Download, Export | N | - | All | - | - | -
SCR-DM-15 | Access Log | 3 | Filters | From, To | Date | dd-MMM-yyyy | N | - | - | - | - | -
SCR-DM-15 | Access Log | 4 | Log | When | Column | dd-MMM-yyyy HH:mm; source address under it | - | Access log | - | - | - | -
SCR-DM-15 | Access Log | 5 | Log | User, Action | Column | Name; Search, View, Download or Export | - | Access log | - | - | - | -
SCR-DM-15 | Access Log | 6 | Log | Criteria / Records | Column | Search criteria; record keys under them | - | Access log | - | - | - | -
SCR-DM-15 | Access Log | 7 | Log | Count, Reason | Column | Records returned; reason and details | - | Access log | - | - | - | -
SCR-DM-16 | LEGACY badge and Origin filter on the lists | 1 | Every list with migrated records | LEGACY | Badge | Next to the number; tooltip: Migrated from <system>, legacy reference <ref>, batch <batch> | - | Origin of the record | - | - | - | -
SCR-DM-16 | LEGACY badge and Origin filter on the lists | 2 | Lists with the Origin filter | Origin | Drop-down | All origins, BIBS, Migrated | N | - | All origins | - | - | -
SCR-DM-16 | LEGACY badge and Origin filter on the lists | 3 | Client search | Legacy client number | Text | A legacy client number finds the BIBS client it was merged into | N | Key cross-reference | - | - | - | -
SCR-DM-16 | LEGACY badge and Origin filter on the lists | 4 | Account search | Legacy policy reference | Text | A legacy policy number finds the migrated policy header | N | Key cross-reference | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 1 | Header | LEGACY | Badge | Next to the invoice number | - | Origin | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 2 | Header | Legacy Invoice | Chip | Legacy invoice number when it differs from the BIBS number | - | Legacy invoice | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 3 | Legacy Invoice | Source System, Legacy Invoice No., Legacy Reference, Legacy Service Invoice | Text | - | - | Values at cut-over | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 4 | Legacy Invoice | Invoice Date, Due Date | Date | dd-MMM-yyyy | - | Values at cut-over | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 5 | Legacy Invoice | Original Gross Premium, Original Commission / VAT | Amount | Two decimals | - | Values at cut-over | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 6 | Legacy Invoice | Commission Realised in Legacy, Deferred VAT Open | Amount | Two decimals | - | Values at cut-over | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 7 | Legacy Invoice | Insurer Shares, Migration Batch | Text | - | - | Values at cut-over | - | - | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | 8 | Legacy positions at cut-over | Component, Booked, Adjusted, Paid in Legacy, Remitted in Legacy, Written Off, Open at Cut-over | Columns | One row per component | - | Values at cut-over | - | - | - | -
SCR-DM-18 | Unapplied to Income | 1 | List | Batch | Column | Batch number; reason under it | - | Batches | - | - | - | -
SCR-DM-18 | Unapplied to Income | 2 | List | Lines, Total | Column | Count; amount | - | Batch | - | - | - | -
SCR-DM-18 | Unapplied to Income | 3 | List | Requested / Approved | Column | Requester; approvers under it | - | Batch | - | - | - | -
SCR-DM-18 | Unapplied to Income | 4 | List | Posted | Column | Lines posted and refused; date and time | - | Batch | - | - | - | -
SCR-DM-18 | Unapplied to Income | 5 | List | Status | Pill | Draft, For approval, For top management, Posted, Returned, Cancelled | - | Batch | Draft | - | - | -
SCR-DM-18 | Unapplied to Income | 6 | New Batch | Reason | Text area | Up to 500 characters | Y | - | - | Draft | Not blank | -
SCR-DM-18 | Unapplied to Income | 7 | New Batch | Currency | Drop-down | PHP, USD | Y | - | PHP | Draft | - | -
SCR-DM-18 | Unapplied to Income | 8 | Batch | Status, Reason, Total, Lines, Requested By, Submitted, Approved By, Posted, Returned Because | Text | - | - | Batch | - | - | - | -
SCR-DM-18 | Unapplied to Income | 9 | Lines | #, Unapplied Payment, Amount, Result, Status | Columns | LEGACY tag on a legacy item; age in days under it; journal or refusal message | - | Lines | - | - | - | -
SCR-DM-18 | Unapplied to Income | 10 | Add Unapplied Payments | Received At Least (days ago) | Number | Days | N | - | 365 | Draft | - | -
SCR-DM-18 | Unapplied to Income | 11 | Add Unapplied Payments | Origin | Drop-down | All origins, BIBS, Migrated | N | - | All origins | Draft | - | -
SCR-DM-18 | Unapplied to Income | 12 | Add Unapplied Payments | Reason for the Lines | Text | Up to 250 characters | N | - | - | Draft | - | -
SCR-DM-18 | Unapplied to Income | 13 | Add Unapplied Payments | Unapplied Payment, Payor / Client, Age (days), Stage, Balance | Columns | Legacy AR number under a legacy item | - | Open unapplied payments of the currency, old enough, not in another batch | - | - | - | -
SCR-DM-19 | Legacy PR 2307 Reversal | 1 | New Batch | Reason, Currency | Text area; Drop-down | Up to 500 characters; PHP or USD | Y | - | PHP | Draft | - | -
SCR-DM-19 | Legacy PR 2307 Reversal | 2 | Add a Legacy Invoice | Invoice No. | Text | Legacy invoice number | Y | Legacy invoices | - | Draft | A legacy invoice with an open PR 2307 | -
SCR-DM-19 | Legacy PR 2307 Reversal | 3 | Add a Legacy Invoice | Amount | Amount | Within the open PR 2307 and the due to insurer | Y | - | - | Draft | Above 0 | -
SCR-DM-19 | Legacy PR 2307 Reversal | 4 | Add a Legacy Invoice | Reason | Text | Up to 250 characters | N | - | - | Draft | - | -
SCR-DM-19 | Legacy PR 2307 Reversal | 5 | Lines | #, Invoice, Amount, Result, Status | Columns | LEGACY tag; journal or refusal message | - | Lines | - | - | - | -
SCR-DM-20 | DP PR Legacy Reversal | 1 | New Batch | Reason | Text area | Up to 500 characters | Y | - | - | Draft | Not blank | -
SCR-DM-20 | DP PR Legacy Reversal | 2 | Add Legacy Invoices | Show | Drop-down | Tagged DP PR for reversal by Collections, Every legacy invoice with open premium | N | - | Tagged | Draft | - | -
SCR-DM-20 | DP PR Legacy Reversal | 3 | Add Legacy Invoices | Reason for the Lines | Text | Up to 250 characters | N | - | - | Draft | - | -
SCR-DM-20 | DP PR Legacy Reversal | 4 | Add Legacy Invoices | Invoice, Client / Insurer, Policy, Tagged, Open Premium | Columns | LEGACY tag; source system and legacy number under the invoice | - | Legacy invoices with open premium | - | - | - | -
SCR-DM-20 | DP PR Legacy Reversal | 5 | Lines | #, Invoice, Amount, Result, Status | Columns | The whole open premium receivable of the invoice | - | Lines | - | - | - | -

## Actions
Actions
Every action (button) of every screen
Screen ID | Screen | Button | Who | Enabled when | What happens | Resulting status | Notification
SCR-DM-01 | Migration Home | Load Templates | Every migration role | Always | Opens Layouts and Rules with the templates | - | -
SCR-DM-01 | Migration Home | Batches | Every migration role | Always | Opens the batch list | - | -
SCR-DM-01 | Migration Home | Upload Extract | Migration Operator | Always | Opens Extracts to upload a file with its control file | - | -
SCR-DM-01 | Migration Home | A tile | Every migration role | Always | Opens the screen of the tile | - | -
SCR-DM-02 | Data Objects and the decision of an object | All Load Templates | Every migration role | Always | Downloads the workbook of every load template with the columns, the control file and the How to fill rules | - | -
SCR-DM-02 | Data Objects and the decision of an object | Download on a row | Every migration role | Always | Downloads the load template workbook of the object | - | -
SCR-DM-02 | Data Objects and the decision of an object | Submit for Decision | Data Migration Lead | Object not waiting for a decision | Sends the proposed class to the business owner after a confirmation | For decision | Alert to the business owner
SCR-DM-02 | Data Objects and the decision of an object | Approve | Data owner (business owner of the object) | Decision For decision and submitted by another user | Decides the class of the object (gate G1), with an optional comment | Decided | -
SCR-DM-02 | Data Objects and the decision of an object | Return | Data owner | Decision For decision and submitted by another user | Returns the proposal to the Data Migration Lead with the reason | Proposed | -
SCR-DM-02 | Data Objects and the decision of an object | Close | Every migration role | Always | Closes the panel | - | -
SCR-DM-03 | Code Maps and the versions of a code map | New Version | Data Steward | No version is being edited or waiting for approval | Creates a draft from the approved version, with an optional comment | Draft | -
SCR-DM-03 | Code Maps and the versions of a code map | Import Excel | Data Steward | No open version | Creates a draft version from an Excel file with the columns source_system, legacy_code and action | Draft | -
SCR-DM-03 | Code Maps and the versions of a code map | Export | Every migration role | A version is chosen | Downloads the entries of the version in Excel | - | -
SCR-DM-03 | Code Maps and the versions of a code map | Add Entry | Data Steward | Version is a draft | Adds an entry; a row of a draft opens it for change; the bin removes it | Draft | -
SCR-DM-03 | Code Maps and the versions of a code map | Submit | Data Steward | Version is a draft with at least one entry | Sends the version to the business owner after a confirmation | Submitted | -
SCR-DM-03 | Code Maps and the versions of a code map | Approve | Data owner | Version submitted by another user | Makes the version the approved one; values marked Create are created through the reference-data load | Approved; the previous version Superseded | -
SCR-DM-03 | Code Maps and the versions of a code map | Return | Data owner | Version submitted by another user | Returns the version to the Data Steward as a draft with the reason | Draft | -
SCR-DM-04 | Layouts and Rules | Control File Template | Every migration role | Always | Downloads the header of the control file (CONTROL_template.ctl.csv) | - | -
SCR-DM-04 | Layouts and Rules | Load Templates Workbook | Every migration role | Always | Downloads one workbook with a Start here sheet (the rules of a delivery and the order) and one guided sheet per layout (a guide above every column) | - | -
SCR-DM-04 | Layouts and Rules | Download on a layout row | Every migration role | Always | Downloads the CSV template of the layout (header row only) | - | -
SCR-DM-04 | Layouts and Rules | Object Workbook | Every migration role | A layout is open | Downloads the workbook of the object of the layout | - | -
SCR-DM-04 | Layouts and Rules | Freeze | Data Steward | Layout version is a draft | Makes the version the one in force after a confirmation; extracts and templates follow it and the previous version is retired | Frozen | -
SCR-DM-05 | Extracts | Upload and Check | Migration Operator | A data file and a control file are chosen (until then the card says what is still needed) | Receives the files and runs every intake check; the message gives the extract number and the staged rows, or the rejection with the number of failed checks, listed on the card | Staged or Rejected | Alert Extract rejected to the Data Migration Lead
SCR-DM-05 | Extracts | Download on a row | Migration Operator | File not yet purged | Downloads the data file as received | - | -
SCR-DM-06 | Batches and resubmissions | Plan Batch | Migration Operator | Always | Plans a batch from the staged extracts and opens it | Planned | -
SCR-DM-06 | Batches and resubmissions | A batch row | Every migration role | Always | Opens the batch page | - | -
SCR-DM-06 | Batches and resubmissions | Approve | Checker of the object (resubmission approval) | Resubmission Prepared by another user | Creates a rerun batch of the corrected rows, with an optional note | Approved | -
SCR-DM-06 | Batches and resubmissions | Return | Checker of the object | Resubmission Prepared by another user | Returns the corrected rows to the maker with the reason | Returned | -
SCR-DM-07 | Batch | Validate | Migration Operator | Planned | Maps the rows with the approved code maps and checks them against the data-quality rules | Validated | Alert Unmapped codes when a code has no entry
SCR-DM-07 | Batch | Sign Validation | Data Steward | Validated | Signs gate G3: the error rate is within the limit, no mandatory code is unmapped and no client pair waits for review | Validated (G3 signed) | -
SCR-DM-07 | Batch | Approve Load | Data Migration Lead | Validated, by a user other than the validator | Signs gate G4: the batch may be loaded by an operator other than the approver | Load approved | -
SCR-DM-07 | Batch | Load | Migration Operator | Load approved, by a user other than the approver | Loads the valid rows through the BIBS services without notifications, then reconciles the batch | Loaded or Loaded with rejects | Alert Load failed when a chunk fails
SCR-DM-07 | Batch | Reconcile | Migration Operator | Loaded, Loaded with rejects or Reconciled | Compares counts, amounts, hash totals and fields again between the source, the staging and BIBS | Reconciled when no break is open | Alert Reconciliation break
SCR-DM-07 | Batch | Rerun Rejects | Migration Operator | Rejected rows exist | Plans a new batch of the rejected rows for validation and load | Planned (rerun batch) | -
SCR-DM-07 | Batch | Sign Reconciliation | Reconciliation approver | Loaded and every break explained and approved | Signs gate G5 | Reconciled | -
SCR-DM-07 | Batch | Accept as Data Owner, Accept as Migration Lead | Data owner; Data Migration Lead | Reconciled | Sign gate G6; with both acceptances the object is accepted and its staging data is purged after the retention days | Accepted | -
SCR-DM-07 | Batch | Request Rollback | Data Migration Lead | Loaded, Reconciled, Accepted or Failed | Asks for the records loaded by the batch to be undone, with the reason | Rollback requested | -
SCR-DM-07 | Batch | Approve Rollback, Reject Rollback | Reconciliation approver | Rollback requested by another user | Undoes the records loaded by the batch through the BIBS services, or keeps the batch loaded with the reason | Rolled back, or the previous status | -
SCR-DM-07 | Batch | Rejects | Every migration role | The batch has rejected or invalid rows | Downloads the rejected rows with their messages and the correction columns | - | -
SCR-DM-07 | Batch | Fixed at Source | Data Steward | Issue open | Records that the legacy source is corrected, with a note | Issue Fixed at source | -
SCR-DM-07 | Batch | Waive Rows, Exclude Rows | Data owner | Batch validated; rows selected | Loads the rows despite their errors (waiver), or leaves them out with a manual-entry plan | Rows Waived or Excluded | -
SCR-DM-07 | Batch | Resubmit Corrected Rows | Data Steward or Migration Operator | The batch has rejected rows | Prepares a resubmission of the corrected rows for the checker | Resubmission Prepared | -
SCR-DM-07 | Batch | Attach | The signer of a gate | Own gate without evidence | Attaches the evidence file to the gate signed | - | -
SCR-DM-08 | Client Matching | Merge | Data Steward | Pair To review | Makes the two records one BIBS client; every value that lost is kept for review | Merged | -
SCR-DM-08 | Client Matching | Keep Separate | Data Steward | Pair To review | Keeps two clients | Kept separate | -
SCR-DM-09 | Reconciliation | Explain | Data Steward or Migration Operator | Line in Break | Records the reason and the explanation | Explained | -
SCR-DM-09 | Reconciliation | Approve | Reconciliation approver | Line Explained by another user | Approves the explanation | Explained (approved) | -
SCR-DM-10 | Sign-off | Sign Mapping | Data owner | G1 approved and G2 not yet signed | Signs gate G2: the layouts of the object are frozen and every code map its columns use has an approved version | G2 signed | -
SCR-DM-10 | Sign-off | Latest batch link | Every migration role | A batch exists | Opens the batch page | - | -
SCR-DM-11 | Opening-Balance Adjustments | Prepare Adjustment | Comptrollership GL lead | Year-end option A | Prepares the adjustment on the chosen batches | Prepared | -
SCR-DM-11 | Opening-Balance Adjustments | Submit | Comptrollership GL lead | Prepared | Sends the adjustment to the Head of Comptrollership | For approval | -
SCR-DM-11 | Opening-Balance Adjustments | Approve | Head, Comptrollership | For approval, prepared by another user | Allows the adjustment batch to be loaded; its journals post into the opening period | Approved | -
SCR-DM-11 | Opening-Balance Adjustments | Return | Head, Comptrollership | For approval | Returns the adjustment to the preparer with the reason | Prepared | -
SCR-DM-11 | Opening-Balance Adjustments | Reconcile | Comptrollership GL lead or Head, Comptrollership | Posted or Reconciled | Compares the adjustment with the legacy trial balances and checks that Migration Clearing is zero | Reconciled when every check is met | Alert when a check breaks
SCR-DM-11 | Opening-Balance Adjustments | Sign | Head, Comptrollership | Reconciled | Signs the reconciled adjustment | Signed | -
SCR-DM-12 | Cutover | New Plan | Data Migration Lead | Always | Creates a plan; its runbook tasks and the twelve criteria are created from the go-live date | Planned | -
SCR-DM-12 | Cutover | Create | Data Migration Lead | Name, environment and go-live date given (until then the dialog says what is still needed) | Creates the plan of the New Cutover Plan dialog | Planned | -
SCR-DM-12 | Cutover | Runbook | Every migration role | A plan is open | Downloads the runbook workbook of the plan | - | -
SCR-DM-12 | Cutover | Measure Criteria | Data Migration Lead or the board | A plan is open | Measures the criteria that BIBS measures (acceptance, counts, financial rejects, amounts, clearing, legacy accounts, client queue) | - | -
SCR-DM-12 | Cutover | Start, Done, Block | Data Migration Lead | Task not started, in progress or blocked | Records the actual start or end; a block needs its reason | In progress, Done, Blocked | -
SCR-DM-12 | Cutover | Met, Not met | Data Migration Lead | Recorded criterion | Records a criterion that BIBS does not measure, with its evidence | Met or Not met | -
SCR-DM-12 | Cutover | GO | Go / no-go board | A plan is open | Records GO; when a criterion is not met the justification is mandatory; on the production plan it signs gate G7 | GO | -
SCR-DM-12 | Cutover | NO-GO | Go / no-go board | A plan is open | Records NO-GO with the reason; the cut-over stops and rolls back to the snapshot | NO-GO | -
SCR-DM-13 | Run-off and Decommissioning | Take Snapshot | Data Migration Lead | Always | Takes the run-off snapshot of today (it is also taken on the first of each month) | - | -
SCR-DM-13 | Run-off and Decommissioning | Open Checklist | Data Migration Lead | The system has no checklist | Opens the decommissioning checklist of the system | Open | -
SCR-DM-13 | Run-off and Decommissioning | Met, Sign, Not applicable | Data Migration Lead | Criterion open or met | Records the criterion with its evidence | Met, Signed or Not applicable | -
SCR-DM-14 | Legacy Inquiry | Continue | Audit / Compliance user | A reason is chosen (and details for Other) | Keeps the reason for the session and opens the search | - | -
SCR-DM-14 | Legacy Inquiry | Search | Audit / Compliance user | At least one criterion | Lists the matching records; the search is logged | - | -
SCR-DM-14 | Legacy Inquiry | Export | Audit / Compliance user with the export right | Records found | Exports the records to Excel, up to 1,000 at a time; the export is logged | - | Alert Unusual access when a user exports more than 5,000 records in a day
SCR-DM-14 | Legacy Inquiry | Download a document | Audit / Compliance user | Record open | Downloads the document; the download is logged | - | -
SCR-DM-14 | Legacy Inquiry | Close | Audit / Compliance user | Record open | Closes the record | - | -
SCR-DM-15 | Access Log | Filters | Compliance reviewer | Always | Narrows the log | - | -
SCR-DM-16 | LEGACY badge and Origin filter on the lists | Search and filters | Users of each list | Always | Find migrated records by their BIBS or legacy number, or only the migrated or BIBS records | - | -
SCR-DM-17 | Legacy invoice on Invoice 360 | The actions of Invoice 360 | Users of Invoice 360 | As for a BIBS invoice | Payments, automatch, refunds, reclassifications, remittance and endorsements work on the legacy invoice; its postings go to the legacy accounts | - | -
SCR-DM-18 | Unapplied to Income | New Batch | Cashiering user | Always | Opens a draft batch | Draft | -
SCR-DM-18 | Unapplied to Income | Add | Cashiering user | Draft | Adds the payment as a line | Draft | -
SCR-DM-18 | Unapplied to Income | Remove | Cashiering user | Draft | Removes a line | Draft | -
SCR-DM-18 | Unapplied to Income | Submit | Cashiering user | Draft with lines | Sends the batch to the Cashiering team lead | For approval | -
SCR-DM-18 | Unapplied to Income | Cancel Batch | Cashiering user | Draft | Closes the batch without posting; its lines may be taken again | Cancelled | -
SCR-DM-18 | Unapplied to Income | Approve | Cashiering team lead, then top management | For approval, For top management; never the requester | First approval sends the batch to top management; the second posts each line in its own transaction | For top management, Posted | -
SCR-DM-18 | Unapplied to Income | Return | Approver of the step | For approval, For top management | Returns the batch to its requester as a draft with the reason | Draft | -
SCR-DM-19 | Legacy PR 2307 Reversal | Add Invoice | Cashiering user | Draft; invoice and amount given | Adds the line | Draft | -
SCR-DM-19 | Legacy PR 2307 Reversal | Submit, Cancel Batch | Cashiering user | Draft | Sends the batch for approval, or closes it without posting | For approval, Cancelled | -
SCR-DM-19 | Legacy PR 2307 Reversal | Approve, Return | Cashiering team lead | For approval; never the requester | Posts each line in its own transaction, or returns the batch with the reason | Posted, Draft | -
SCR-DM-20 | DP PR Legacy Reversal | Add | Commission user | Draft | Adds the invoice as a line | Draft | -
SCR-DM-20 | DP PR Legacy Reversal | Submit, Cancel Batch | Commission user | Draft | Sends the batch for approval, or closes it without posting | For approval, Cancelled | -
SCR-DM-20 | DP PR Legacy Reversal | Approve, Return | Commission team lead | For approval; never the requester | Posts each invoice on its own, or returns the batch with the reason | Posted, Draft | -

## Business rules
Business rules
The business rules stated on the screens
Rule ID | Screen ID | Screen | Business rule | FRs | BU review | BU comment | Reviewer | Review date
BR-DM-001 | SCR-DM-01 | Migration Home | A tile marked Needs attention has at least one item that blocks a gate: a failed batch, a break, an unmapped code or an open error. | FR-DM-003
BR-DM-002 | SCR-DM-01 | Migration Home | The migration roles (operator, steward, owner, lead, reconciliation approver, go / no-go board) land on Migration Home after sign-in; My Approvals stays one click away in the header. | FR-DM-003
BR-DM-003 | SCR-DM-01 | Migration Home | The run-off table is the latest monthly snapshot of the legacy policies in force at go-live. | FR-DM-122
BR-DM-004 | SCR-DM-02 | Data Objects and the decision of an object | An object loads only after the objects it depends on are accepted in the same environment; its load order follows theirs. | FR-DM-001
BR-DM-005 | SCR-DM-02 | Data Objects and the decision of an object | The business owner of the object decides its class, never the user who submitted it. | FR-DM-002
BR-DM-006 | SCR-DM-02 | Data Objects and the decision of an object | The class of an object whose batches are loaded changes only after the batches are rolled back. | FR-DM-002
BR-DM-007 | SCR-DM-02 | Data Objects and the decision of an object | Only objects decided as Migrate, Carry forward or Conditional (with its condition met) can be planned in a batch; archive objects load into the legacy archive. | FR-DM-002
BR-DM-008 | SCR-DM-03 | Code Maps and the versions of a code map | Only the approved version of a map is used by a batch, and the batch records the versions it used. | FR-DM-011
BR-DM-009 | SCR-DM-03 | Code Maps and the versions of a code map | A map has one version being edited or waiting for approval at a time. | FR-DM-011
BR-DM-010 | SCR-DM-03 | Code Maps and the versions of a code map | The business owner approves a version, never the Data Steward who submitted it. | FR-DM-011
BR-DM-011 | SCR-DM-03 | Code Maps and the versions of a code map | A batch with an unmapped code in a mandatory column cannot be approved for load. | FR-DM-012
BR-DM-012 | SCR-DM-03 | Code Maps and the versions of a code map | Legacy packages are mapped to package versions in the package code map, which Renewal uses at sanitation; the migration does not resolve packages on the policy headers. | FR-DM-034
BR-DM-013 | SCR-DM-04 | Layouts and Rules | A file whose header does not match the layout version in force is rejected at intake. | FR-DM-010
BR-DM-014 | SCR-DM-04 | Layouts and Rules | The layouts of an object are frozen before its mapping is signed (gate G2). | FR-DM-003
BR-DM-015 | SCR-DM-04 | Layouts and Rules | Outside production the columns listed on Masking Rules are masked before a row is staged. | FR-DM-010
BR-DM-016 | SCR-DM-04 | Layouts and Rules | An error stops the row; a warning loads it and reports it. | FR-DM-013
BR-DM-017 | SCR-DM-05 | Extracts | The file name starts with the layout code, then the source system, the as-of date and the sequence of the day. | FR-DM-010
BR-DM-018 | SCR-DM-05 | Extracts | A file whose checksum, header, row count, amount totals or hash total do not agree with its control file is rejected; nothing of it is staged. Every check runs, and the rejection lists each failed check with its own reason. | FR-DM-010
BR-DM-019 | SCR-DM-05 | Extracts | Extracts are received only for objects decided for migration. | FR-DM-002
BR-DM-020 | SCR-DM-05 | Extracts | Staged rows and files are purged 5 days after the batch is accepted or rolled back, or after the rejection. | FR-DM-010
BR-DM-021 | SCR-DM-06 | Batches and resubmissions | The extracts of one batch have the same as-of date and one layout each. | FR-DM-010
BR-DM-022 | SCR-DM-06 | Batches and resubmissions | Resubmissions of the RA-sent file are accepted until the resubmission deadline (12:00 on the day before go-live). | FR-DM-125
BR-DM-023 | SCR-DM-06 | Batches and resubmissions | The checker of a resubmission is never its maker. | FR-DM-125
BR-DM-024 | SCR-DM-07 | Batch | The load of a batch is approved by the Data Migration Lead and run by an operator other than the approver; the validator does not approve the load. | FR-DM-014
BR-DM-025 | SCR-DM-07 | Batch | Master data loads with at most 0.5 percent of rows failing or waived; open items, unapplied payments and the trial balance load with none, unless each excluded row has a manual-entry plan. | FR-DM-013
BR-DM-026 | SCR-DM-07 | Batch | A row already loaded and unchanged is skipped; a rerun loads only the rejected and changed rows. | FR-DM-015
BR-DM-027 | SCR-DM-07 | Batch | A rollback undoes the records of the batch newest first, unless a record was changed in BIBS since the load; the requester never approves it. | FR-DM-015
BR-DM-028 | SCR-DM-07 | Batch | The operator who ran a batch cannot sign its reconciliation or acceptance; one person cannot sign two gates of one batch. | FR-DM-003
BR-DM-029 | SCR-DM-07 | Batch | The reconciliation cannot be signed while a break is open. | FR-DM-020
BR-DM-030 | SCR-DM-08 | Client Matching | Pairs scoring 90 or more merge automatically; 60 to 89 go to this queue; below 60 are different clients. | FR-DM-031
BR-DM-031 | SCR-DM-08 | Client Matching | The load of a client batch is not approved while pairs wait for review. | FR-DM-031
BR-DM-032 | SCR-DM-08 | Client Matching | Per field the surviving value is the first non-blank value by source priority, or the latest updated value. | FR-DM-031
BR-DM-033 | SCR-DM-09 | Reconciliation | Counts: received equals the control count and loaded + skipped + rejected + excluded equals staged. | FR-DM-020
BR-DM-034 | SCR-DM-09 | Reconciliation | Amounts: the control total, the staged sum and the value in BIBS agree per amount column and currency. | FR-DM-020
BR-DM-035 | SCR-DM-09 | Reconciliation | GL: Migration Clearing is 0.00 per branch and currency and each legacy control account equals its legacy sub-ledger. | FR-DM-021
BR-DM-036 | SCR-DM-09 | Reconciliation | The explanation of a break is approved by a user other than the one who explained it. | FR-DM-020
BR-DM-037 | SCR-DM-10 | Sign-off | Gates are signed in order; a gate refused returns the object to the step of that gate. | FR-DM-003
BR-DM-038 | SCR-DM-10 | Sign-off | The mapping is signed only when the layouts are frozen and every map used has an approved version. | FR-DM-003
BR-DM-039 | SCR-DM-11 | Opening-Balance Adjustments | Only journals dated in FY2027, posted in legacy after the freeze and entered in the FY2027 adjustment register are accepted. | FR-DM-023
BR-DM-040 | SCR-DM-11 | Opening-Balance Adjustments | FY2027 profit and loss lines post to retained earnings; lines on legacy control accounts post to Migration Clearing with their open-item detail. | FR-DM-023
BR-DM-041 | SCR-DM-11 | Opening-Balance Adjustments | The preparer never approves; a wrong adjustment is corrected by the next adjustment, never by changing a posted journal. | FR-DM-023
BR-DM-042 | SCR-DM-11 | Opening-Balance Adjustments | An adjustment is signed only when the cut-off, movement, balance, clearing and opening-period checks are met. | FR-DM-024
BR-DM-043 | SCR-DM-12 | Cutover | A task starts only when the tasks it depends on are done. | FR-DM-120
BR-DM-044 | SCR-DM-12 | Cutover | Criteria measured by BIBS cannot be recorded by hand. | FR-DM-121
BR-DM-045 | SCR-DM-12 | Cutover | A GO with criteria not met needs the board's justification; the financial and clearing criteria of the go-live decision are never waived. | FR-DM-121
BR-DM-046 | SCR-DM-12 | Cutover | Until the go / no-go decision the rollback restores the snapshot taken before the production load. | FR-DM-121
BR-DM-047 | SCR-DM-13 | Run-off and Decommissioning | A legacy system is decommissioned only when every criterion of its checklist is signed. | FR-DM-123
BR-DM-048 | SCR-DM-13 | Run-off and Decommissioning | The legacy context closes when no legacy invoice or unapplied payment is open and the legacy accounts and Migration Clearing are at 0.00. | FR-DM-123
BR-DM-049 | SCR-DM-14 | Legacy Inquiry | The legacy archive is read-only; no record or document is changed. | FR-DM-110
BR-DM-050 | SCR-DM-14 | Legacy Inquiry | A reason is required before the archive is searched and is written with every search, view, download and export. | FR-DM-110
BR-DM-051 | SCR-DM-14 | Legacy Inquiry | An export is limited to 1,000 records; a narrower search is asked for above it. | FR-DM-110
BR-DM-052 | SCR-DM-14 | Legacy Inquiry | The addresses of the read-only legacy applications are shown to the users who still need them until each system is decommissioned. | FR-DM-110
BR-DM-053 | SCR-DM-15 | Access Log | No entry of the access log can be changed or deleted. | FR-DM-111
BR-DM-054 | SCR-DM-15 | Access Log | The reviewers receive a monthly digest of the log. | FR-DM-111
BR-DM-055 | SCR-DM-16 | LEGACY badge and Origin filter on the lists | Every migrated record keeps the origin Migrated, its source system, legacy reference and migration batch. | FR-DM-032
BR-DM-056 | SCR-DM-16 | LEGACY badge and Origin filter on the lists | Migrated records raise no notification to clients or insurers and no outbound integration message. | FR-DM-014
BR-DM-057 | SCR-DM-16 | LEGACY badge and Origin filter on the lists | A migrated client is found by any of its legacy client numbers. | FR-DM-033
BR-DM-058 | SCR-DM-17 | Legacy invoice on Invoice 360 | A legacy invoice is not re-booked; it keeps its legacy number and its postings go to the legacy control accounts. | FR-DM-050
BR-DM-059 | SCR-DM-17 | Legacy invoice on Invoice 360 | The values at cut-over are never changed; the report Changes to Legacy Invoices compares every later change with them. | FR-DM-100
BR-DM-060 | SCR-DM-17 | Legacy invoice on Invoice 360 | When legacy could give only the open balances, the card says so and the original amounts are blank. | FR-DM-050
BR-DM-061 | SCR-DM-18 | Unapplied to Income | Two approvals by two different people, the Cashiering team lead and then top management; the requester approves neither. | FR-DM-055
BR-DM-062 | SCR-DM-18 | Unapplied to Income | A line whose payment changed since it was added is refused at posting; the other lines still post. | FR-DM-055
BR-DM-063 | SCR-DM-18 | Unapplied to Income | Legacy payments post from Unapplied Collections - Legacy, new ones from Unapplied Collections, to other income - unclaimed collections. | FR-DM-055
BR-DM-064 | SCR-DM-19 | Legacy PR 2307 Reversal | The amount of a line is within the open PR 2307 (after the move from the premium receivable) and the due to insurer of the invoice. | FR-DM-071
BR-DM-065 | SCR-DM-19 | Legacy PR 2307 Reversal | The Cashiering team lead approves; the requester never approves. | FR-DM-071
BR-DM-066 | SCR-DM-20 | DP PR Legacy Reversal | The line amount is the whole open premium receivable of the invoice. | FR-DM-070
BR-DM-067 | SCR-DM-20 | DP PR Legacy Reversal | An invoice whose balance changed since it was added is refused at posting; the other lines still post. | FR-DM-070
BR-DM-068 | SCR-DM-20 | DP PR Legacy Reversal | The Commission team lead approves; the requester never approves. | FR-DM-070

## Messages
Messages
Every validation, error, warning and confirmation message
Message ID | Where it appears | Shown by | Code (not shown) | Message | Type | What the user does | BU review | BU comment | Reviewer | Review date
MSG-DM-001 | Migration Home (SCR-DM-01) | Screen | - | No open cut-over task | Information | No action.
MSG-DM-002 | Migration Home (SCR-DM-01) | Screen | - | No run-off snapshot yet | Information | No action.
MSG-DM-003 | Data Objects and the decision of an object (SCR-DM-02) | Screen | - | No data object in the register | Information | No action.
MSG-DM-004 | Data Objects and the decision of an object (SCR-DM-02) | Screen | - | No decision submitted yet | Information | No action.
MSG-DM-005 | Data Objects and the decision of an object (SCR-DM-02) | Screen | - | The proposal goes back to the Data Migration Lead. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-006 | Data Objects and the decision of an object (SCR-DM-02) | Screen | - | The proposed class <proposed class> goes to the business owner for approval. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-007 | Data Objects and the decision of an object (SCR-DM-02) | Server | DUPLICATE | Data object already exists: <key> | Error | Use another code; the code is already used.
MSG-DM-008 | Data Objects and the decision of an object (SCR-DM-02) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-009 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_CLASS_CHANGE_LOADED | Roll back the loaded batches before changing the class of this object | Error | Request the rollback of the loaded batches of the object first.
MSG-DM-010 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_CONDITION_REQUIRED | Enter the condition of a conditional object | Error | Enter the condition of a conditional object.
MSG-DM-011 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_DECISION_NOT_PENDING | Decision <decision no> is not waiting for approval | Error | Refresh the object; the decision was already approved or returned.
MSG-DM-012 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_DECISION_PENDING | A decision of object <code> is already waiting for approval | Error | Wait for the business owner to approve or return the decision already submitted.
MSG-DM-013 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_DEPENDENCY_CYCLE | Object <code> cannot depend on itself through <deps> | Error | Remove the dependency that makes the object depend on itself.
MSG-DM-014 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_LOAD_ORDER | The load order must follow the objects this object depends on | Error | Give a load order after the load order of every object it depends on.
MSG-DM-015 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_NOT_OBJECT_OWNER | Only the business owner of object <code> can decide its class | Error | Ask the business owner of the object to decide; only the owner can.
MSG-DM-016 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_OBJECT_CODE | The object code is 2 to 10 letters and digits | Error | Use 2 to 10 letters and digits for the object code.
MSG-DM-017 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_OBJECT_UNKNOWN | Object <dep> does not exist | Error | Choose objects of the register as dependencies.
MSG-DM-018 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_RATIONALE_LENGTH | The rationale is limited to 2,000 characters | Error | Shorten the rationale to 2,000 characters.
MSG-DM-019 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_RATIONALE_REQUIRED | Enter the rationale for the proposed class | Error | Enter the rationale for the proposed class.
MSG-DM-020 | Data Objects and the decision of an object (SCR-DM-02) | Server | MIG_REASON_REQUIRED | Enter the reason for the return | Error | Enter the reason for the return.
MSG-DM-021 | Code Maps (SCR-DM-03) | Screen | - | A draft is created from the approved version, ready for your changes. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-022 | Code Maps (SCR-DM-03) | Screen | - | Add Entry | Validation | Add Entry.
MSG-DM-023 | Code Maps (SCR-DM-03) | Screen | - | Every legacy code of the batches in validation is mapped | Information | No action.
MSG-DM-024 | Code Maps (SCR-DM-03) | Screen | - | No code map | Information | No action.
MSG-DM-025 | Code Maps (SCR-DM-03) | Screen | - | No entry in this version | Information | No action.
MSG-DM-026 | Code Maps (SCR-DM-03) | Screen | - | No version yet | Information | No action.
MSG-DM-027 | Code Maps (SCR-DM-03) | Screen | - | The version goes back to the Data Steward as a draft. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-028 | Code Maps (SCR-DM-03) | Screen | - | The version goes to the business owner for approval. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-029 | Code Maps (SCR-DM-03) | Screen | - | The version replaces the approved one for the next batches; values marked Create are created through the reference-data load. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-030 | Code Maps (SCR-DM-03) | Screen | - | Use the default value | Validation | Use the default value.
MSG-DM-031 | Code Maps (SCR-DM-03) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-032 | Code Maps (SCR-DM-03) | Server | MIG_MAP_DRAFT_EXISTS | Set <set code> already has a version being edited or waiting for approval | Error | Complete, submit or return the version being edited before starting another.
MSG-DM-033 | Code Maps (SCR-DM-03) | Server | MIG_MAP_DUPLICATE | Legacy code <legacy code> of <source system> is mapped twice | Error | Keep one entry per legacy code and source system (a conditional entry needs its condition).
MSG-DM-034 | Code Maps (SCR-DM-03) | Server | MIG_MAP_EMPTY | Add at least one entry before submitting | Error | Add at least one entry before submitting.
MSG-DM-035 | Code Maps (SCR-DM-03) | Server | MIG_MAP_ENTRY | Enter the source system, the legacy code and the action | Error | Enter the source system, the legacy code and the action.
MSG-DM-036 | Code Maps (SCR-DM-03) | Server | MIG_MAP_IMPORT_ACTION | Row <row no>: the action must be MAP, DEFAULT, REJECT or CREATE | Error | Correct the action of the row to MAP, DEFAULT, REJECT or CREATE.
MSG-DM-037 | Code Maps (SCR-DM-03) | Server | MIG_MAP_IMPORT_LAYOUT | The file must have the columns source_system, legacy_code and action | Error | Use the columns of the exported version in the Excel file (source_system, legacy_code, action and the others).
MSG-DM-038 | Code Maps (SCR-DM-03) | Server | MIG_MAP_NOT_DRAFT | Version <version no> of <set code> is no longer a draft | Error | Create a new version to change the entries; this one is no longer a draft.
MSG-DM-039 | Code Maps (SCR-DM-03) | Server | MIG_MAP_NOT_SUBMITTED | Version <version no> of <set code> is not submitted | Error | Ask the Data Steward to submit the version first.
MSG-DM-040 | Code Maps (SCR-DM-03) | Server | MIG_MAP_TARGET_MISSING | Target code <missing> does not exist in <target domain> | Error | Correct the BIBS value, or create it in its master and have it authorised first.
MSG-DM-041 | Code Maps (SCR-DM-03) | Server | MIG_MAP_TARGET_REQUIRED | Enter the target code of legacy code <legacy code> | Error | Enter the BIBS value of an entry with the action Map to a BIBS value.
MSG-DM-042 | Code Maps (SCR-DM-03) | Server | MIG_REASON_REQUIRED | Enter the reason for the return | Error | Enter the reason for the return.
MSG-DM-043 | Layouts and Rules (SCR-DM-04) | Screen | - | Check | Validation | Check.
MSG-DM-044 | Layouts and Rules (SCR-DM-04) | Screen | - | No column | Information | No action.
MSG-DM-045 | Layouts and Rules (SCR-DM-04) | Screen | - | No layout | Information | No action.
MSG-DM-046 | Layouts and Rules (SCR-DM-04) | Screen | - | No masking rule | Information | No action.
MSG-DM-047 | Layouts and Rules (SCR-DM-04) | Screen | - | No rule | Information | No action.
MSG-DM-048 | Layouts and Rules (SCR-DM-04) | Screen | - | The layout becomes the version in force: extracts and templates follow it and the previous version is retired. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-049 | Layouts and Rules (SCR-DM-04) | Server | MIG_LAYOUT_EMPTY | The layout has no columns | Error | Add the columns of the layout before freezing it.
MSG-DM-050 | Layouts and Rules (SCR-DM-04) | Server | MIG_LAYOUT_FROZEN | Layout <code> version <version no> is frozen | Error | Create a new layout version to change the columns.
MSG-DM-051 | Layouts and Rules (SCR-DM-04) | Server | MIG_LAYOUT_NOT_FROZEN | Layout <code> has no version in force | Error | Ask the Data Steward to freeze the layouts of the object on Layouts and Rules first.
MSG-DM-052 | Layouts and Rules (SCR-DM-04) | Server | MIG_MASKING_EXISTS | Column <column> of <layout code> is already masked | Error | Change the masking rule of the column already listed.
MSG-DM-053 | Layouts and Rules (SCR-DM-04) | Server | MIG_RULE_SEVERITY | The severity is ERROR or WARNING | Error | Choose Error or Warning.
MSG-DM-054 | Extracts (SCR-DM-05) | Screen | - | <extract no> rejected: <length> failed | Error | Read the failed checks listed on the Upload an extract card, correct the extract or its control file and upload both again.
MSG-DM-055 | Extracts (SCR-DM-05) | Screen | - | <extract no> staged with <staged rows> | Confirmation | No action.
MSG-DM-056 | Extracts (SCR-DM-05) | Screen | - | No extract received | Information | No action.
MSG-DM-057 | Extracts (SCR-DM-05) | Server | MIG_FILE_MISSING | The file is no longer kept. | Error | No action; the file was purged after the retention days. Ask BDOI IT for the extract if it is needed again.
MSG-DM-058 | Extracts (SCR-DM-05) | Server | MIG_FILE_NAME | Name the file <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv or .xlsx, for example F01C_EBIX_20271231_01.csv | Error | Rename the file as <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv or .xlsx and upload it again.
MSG-DM-059 | Extracts (SCR-DM-05) | Server | MIG_FILE_NAME | The date in the file name is not a valid yyyyMMdd date | Error | Rename the file as <LAYOUT>_<SOURCE>_<yyyyMMdd>_<nn>.csv or .xlsx and upload it again.
MSG-DM-060 | Extracts (SCR-DM-05) | Server | MIG_FILE_OBJECT | File layout <layout> belongs to object <code>, not <expected object> | Error | Use the layout code of the object in the file name.
MSG-DM-061 | Extracts (SCR-DM-05) | Server | MIG_FILE_SOURCE | Source system <source> is not a source of object <code> | Error | Use a source system of the object in the file name, or ask the Data Migration Lead to add the source to the object.
MSG-DM-062 | Extracts (SCR-DM-05) | Server | MIG_MASKING_KEY | The masking key of this environment is not configured; extracts cannot be staged | Error | Ask the infrastructure team to configure the masking key of the environment.
MSG-DM-063 | Extracts (SCR-DM-05) | Server | MIG_OBJECT_NOT_DECIDED | Object <code> is not decided for migration; extracts cannot be received | Error | Ask the business owner to decide the object for migration first (gate G1).
MSG-DM-064 | Batches and resubmissions (SCR-DM-06) | Screen | - | A rerun batch of the corrected rows is created for validation and load. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-065 | Batches and resubmissions (SCR-DM-06) | Screen | - | Corrected rows | Validation | No action; the screen shows the change.
MSG-DM-066 | Batches and resubmissions (SCR-DM-06) | Screen | - | No batch planned yet | Information | No action.
MSG-DM-067 | Batches and resubmissions (SCR-DM-06) | Screen | - | No resubmission of corrected rows | Information | No action.
MSG-DM-068 | Batches and resubmissions (SCR-DM-06) | Screen | - | The corrected rows go back to the maker. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-069 | Batches and resubmissions (SCR-DM-06) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-070 | Batches and resubmissions (SCR-DM-06) | Server | MIG_ASOF_MISMATCH | The extracts of a batch must have the same as-of date: <days> | Error | Plan the batch with extracts of the same as-of date.
MSG-DM-071 | Batches and resubmissions (SCR-DM-06) | Server | MIG_EXTRACT_NOT_STAGED | Extract <extract no> is not a staged extract of object <code> | Error | Choose a staged extract of the object.
MSG-DM-072 | Batches and resubmissions (SCR-DM-06) | Server | MIG_EXTRACT_USED | Extract <extract no> is already in a batch | Error | Choose an extract that is not in another batch.
MSG-DM-073 | Batches and resubmissions (SCR-DM-06) | Server | MIG_NOTHING_TO_RERUN | Batch <batch no> has no rejected rows to load again | Error | No action; the batch has no rejected rows.
MSG-DM-074 | Batches and resubmissions (SCR-DM-06) | Server | MIG_NO_EXTRACT | Object <code> has no staged extract to load | Error | Upload and stage an extract of the object first.
MSG-DM-075 | Batches and resubmissions (SCR-DM-06) | Server | MIG_OBJECT_NOT_LOADABLE | Object <object code> is not decided as Migrate, Carry-forward or Archive | Error | Choose an object decided as Migrate, Carry forward or Archive.
MSG-DM-076 | Batches and resubmissions (SCR-DM-06) | Server | MIG_REASON_REQUIRED | Enter the reason for the return | Error | Enter the reason for the return.
MSG-DM-077 | Batches and resubmissions (SCR-DM-06) | Server | MIG_RESUBMISSION_DECIDED | Resubmission <resubmission no> is already decided | Error | No action; refresh the list.
MSG-DM-078 | Batches and resubmissions (SCR-DM-06) | Server | MIG_RESUBMISSION_EXTRACT | Extract <extract no> is not a staged extract of object <object code> | Error | Upload the corrected rows as an extract of the same object, then prepare the resubmission.
MSG-DM-079 | Batches and resubmissions (SCR-DM-06) | Server | MIG_RESUBMIT_DEADLINE | Resubmissions were accepted until <resubmit deadline> | Error | No action; rows still rejected are checked against the tracker before any renewal advice is sent.
MSG-DM-080 | Batch (SCR-DM-07) | Screen | - | A new batch is planned with the rejected rows for validation and load. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-081 | Batch (SCR-DM-07) | Screen | - | No data-quality issue | Information | No action.
MSG-DM-082 | Batch (SCR-DM-07) | Screen | - | No gate signed on this batch | Information | No action.
MSG-DM-083 | Batch (SCR-DM-07) | Screen | - | No log line | Information | No action.
MSG-DM-084 | Batch (SCR-DM-07) | Screen | - | No row | Information | No action.
MSG-DM-085 | Batch (SCR-DM-07) | Screen | - | Record the fix of issue <rule code> | Validation | Record the fix of issue <rule code>.
MSG-DM-086 | Batch (SCR-DM-07) | Screen | - | The batch stays loaded. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-087 | Batch (SCR-DM-07) | Screen | - | The legacy source is corrected; the next extract carries the fixed value. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-088 | Batch (SCR-DM-07) | Screen | - | The records loaded by this batch are undone now. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-089 | Batch (SCR-DM-07) | Screen | - | The rows are mapped with the approved code maps and checked against the data-quality rules. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-090 | Batch (SCR-DM-07) | Screen | - | The valid rows are loaded through the BIBS services, without notifications or outbound events, and the batch is reconciled. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-091 | Batch (SCR-DM-07) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-092 | Batch (SCR-DM-07) | Server | MIG_BATCH_STATUS | Batch <batch no> is <status>; it cannot be <action> | Error | Refresh the batch; the action is not allowed in its current status.
MSG-DM-093 | Batch (SCR-DM-07) | Server | MIG_BATCH_STATUS | Batch <batch no> is <status>; it cannot be rolled back | Error | Refresh the batch; the action is not allowed in its current status.
MSG-DM-094 | Batch (SCR-DM-07) | Server | MIG_DEPENDENCY_NOT_ACCEPTED | Object <dep> must be accepted before this object can load | Error | Accept the objects this object depends on first.
MSG-DM-095 | Batch (SCR-DM-07) | Server | MIG_ERROR_RATE | <to plain string> percent of rows have errors; the limit for this object is <to plain string> percent | Error | Fix the failing rows at source, map the codes, or ask the data owner to waive or exclude rows, then validate again.
MSG-DM-096 | Batch (SCR-DM-07) | Server | MIG_GATE_ORDER | Sign gate <gate> (<label>) first | Error | Sign the gates in order.
MSG-DM-097 | Batch (SCR-DM-07) | Server | MIG_GATE_ROLE | Accept the object as data owner or Data Migration Lead | Error | Ask a user who holds the role of the gate.
MSG-DM-098 | Batch (SCR-DM-07) | Server | MIG_GATE_ROLE | This gate is signed in the role <role>, which you do not hold | Error | Ask a user who holds the role of the gate.
MSG-DM-099 | Batch (SCR-DM-07) | Server | MIG_GATE_SIGNED | You have already signed gate <gate> of this batch | Error | Ask another signer; one person signs one gate of a batch.
MSG-DM-100 | Batch (SCR-DM-07) | Server | MIG_LAYOUT_NOT_FROZEN | Freeze the layouts of object <object code> before signing the mapping | Error | Ask the Data Steward to freeze the layouts of the object on Layouts and Rules first.
MSG-DM-101 | Batch (SCR-DM-07) | Server | MIG_LOAD_RUNNING | Another batch of object <object code> is loading | Error | Wait until the other batch of the object has loaded.
MSG-DM-102 | Batch (SCR-DM-07) | Server | MIG_MAP_NOT_APPROVED | These code maps have no approved version: <missing> | Error | Have the listed code maps approved first.
MSG-DM-103 | Batch (SCR-DM-07) | Server | MIG_NOT_RECONCILED | Reconcile the batch before signing it | Error | Reconcile the batch first.
MSG-DM-104 | Batch (SCR-DM-07) | Server | MIG_OPEN_BREAKS | Explain and approve every break before signing the reconciliation | Error | Explain every break and have the explanation approved first.
MSG-DM-105 | Batch (SCR-DM-07) | Server | MIG_REASON_REQUIRED | Enter the reason and the manual-entry plan of the excluded rows | Error | Enter the reason and the manual-entry plan of the excluded rows.
MSG-DM-106 | Batch (SCR-DM-07) | Server | MIG_REASON_REQUIRED | Enter the reason and the remarks of the waiver | Error | Enter the reason and the remarks of the waiver.
MSG-DM-107 | Batch (SCR-DM-07) | Server | MIG_REASON_REQUIRED | Enter the reason for the rejection | Error | Enter the reason for the rejection.
MSG-DM-108 | Batch (SCR-DM-07) | Server | MIG_REASON_REQUIRED | Enter the reason for the rollback | Error | Enter the reason for the rollback.
MSG-DM-109 | Batch (SCR-DM-07) | Server | MIG_RESOLUTION | The Data Steward resolves an issue as fixed at source or mapped | Error | Record the issue as fixed at source, or change the code map; a waiver is recorded on the Rows tab by the data owner.
MSG-DM-110 | Batch (SCR-DM-07) | Server | MIG_REVIEW_QUEUE | <review> client pairs are waiting for review; decide them before approving the load | Error | Decide the client pairs on Client Matching first.
MSG-DM-111 | Batch (SCR-DM-07) | Server | MIG_ROLLBACK_CHANGED | <changed> records were changed after the load and cannot be rolled back | Error | Correct the changed records in BIBS instead; the batch cannot be rolled back.
MSG-DM-112 | Batch (SCR-DM-07) | Server | MIG_ROLLBACK_NOT_SUPPORTED | Object <object code> cannot be rolled back record by record; restore the environment snapshot | Error | Ask the infrastructure team to restore the environment snapshot taken before the load.
MSG-DM-113 | Batch (SCR-DM-07) | Server | MIG_UNMAPPED_CODES | The batch has <unmapped> unmapped codes; map them before approving the load | Error | Add the missing entries to a new version of the code maps, have it approved and validate again.
MSG-DM-114 | Batch (SCR-DM-07): rows refused at load | Server | MIG_ARCHIVE_DETAIL | The other legacy fields must be label and value pairs separated by ;, for example Insurer: MAL; Remitted on: 01-Jul-2022 | Error | Correct the other legacy fields of the record in the extract (label and value pairs separated by ;).
MSG-DM-115 | Batch (SCR-DM-07): rows refused at load | Server | MIG_BRANCH_UNKNOWN | Branch <branch code> not found | Error | Map the legacy branch in the branch code map, or correct the extract.
MSG-DM-116 | Batch (SCR-DM-07): rows refused at load | Server | MIG_BRANCH_UNKNOWN | Branch <branch> not found | Error | Map the legacy branch in the branch code map, or correct the extract.
MSG-DM-117 | Batch (SCR-DM-07): rows refused at load | Server | MIG_BRANCH_UNKNOWN | Branch <code> does not exist in BIBS | Error | Map the legacy branch in the branch code map, or correct the extract.
MSG-DM-118 | Batch (SCR-DM-07): rows refused at load | Server | MIG_BRANCH_UNKNOWN | Branch <code> not found | Error | Map the legacy branch in the branch code map, or correct the extract.
MSG-DM-119 | Batch (SCR-DM-07): rows refused at load | Server | MIG_C01_NOT_LOADED | Client <legacy client> is not migrated | Error | Load the client first, or correct the legacy client number.
MSG-DM-120 | Batch (SCR-DM-07): rows refused at load | Server | MIG_CLIENT_NOT_LOADED | Client <legacy client> is not migrated | Error | Load the client first, or correct the legacy client number.
MSG-DM-121 | Batch (SCR-DM-07): rows refused at load | Server | MIG_CODE_NOT_MAPPED | Legacy code <legacy> is not in the approved <set> map | Error | Add the legacy code to the code map named and have it approved.
MSG-DM-122 | Batch (SCR-DM-07): rows refused at load | Server | MIG_CODE_REQUIRED | The legacy code is missing | Error | Correct the extract; the legacy code is mandatory.
MSG-DM-123 | Batch (SCR-DM-07): rows refused at load | Server | MIG_DATE_REQUIRED | The rate has no effective date | Error | Correct the extract; the date is mandatory.
MSG-DM-124 | Batch (SCR-DM-07): rows refused at load | Server | MIG_DATE_REQUIRED | The record has no document date | Error | Correct the extract; the date is mandatory.
MSG-DM-125 | Batch (SCR-DM-07): rows refused at load | Server | MIG_DOCUMENT_SIZE | The file size is missing | Error | Ask BDOI IT to copy the file again; its size differs from the index.
MSG-DM-126 | Batch (SCR-DM-07): rows refused at load | Server | MIG_F01_NOT_LOADED | Legacy invoice <legacy no> is not loaded | Error | Load the invoice (F01) first, or remove the row.
MSG-DM-127 | Batch (SCR-DM-07): rows refused at load | Server | MIG_HEADER_NOT_LOADED | Policy <legacy key> is not among the migrated headers | Error | Correct the policy reference, or load its policy header first.
MSG-DM-128 | Batch (SCR-DM-07): rows refused at load | Server | MIG_INSURER_NOT_MAPPED | Insurer <legacy> is not in the approved INSURER map | Error | Add the insurer to the insurer code map and have it approved.
MSG-DM-129 | Batch (SCR-DM-07): rows refused at load | Server | MIG_INVOICE_MISSING | Invoice <target code> not found | Error | Rerun the batch; the invoice of the row was not created.
MSG-DM-130 | Batch (SCR-DM-07): rows refused at load | Server | MIG_MAP_TARGET | Code map <set code> names no BIBS list | Error | Ask the Data Steward to name the BIBS list of the code map.
MSG-DM-131 | Batch (SCR-DM-07): rows refused at load | Server | MIG_NO_INSURER | Invoice <legacy key> has no insurer share | Error | Send the insurer share of the invoice (F01S).
MSG-DM-132 | Batch (SCR-DM-07): rows refused at load | Server | MIG_NUMBER_REQUIRED | The <column> is missing | Error | Correct the extract; the number is mandatory.
MSG-DM-133 | Batch (SCR-DM-07): rows refused at load | Server | MIG_OFFICER_UNKNOWN | Account officer <user> is not in the sales organisation | Error | Map the account officer in the user code map, or add the officer to the sales organisation.
MSG-DM-134 | Batch (SCR-DM-07): rows refused at load | Server | MIG_PARENT_NOT_LOADED | Original invoice <legacy parent> is not loaded | Error | Load the original invoice first, or correct the parent invoice number.
MSG-DM-135 | Batch (SCR-DM-07): rows refused at load | Server | MIG_PRODUCT_NOT_MAPPED | Risk code <legacy code> is not in the approved PRODUCT map | Error | Add the risk code to the product code map and have it approved.
MSG-DM-136 | Batch (SCR-DM-07): rows refused at load | Server | MIG_RA_DUPLICATE | An advice of <ref> is already loaded | Error | Keep one renewal advice per expiring policy term.
MSG-DM-137 | Batch (SCR-DM-07): rows refused at load | Server | MIG_SI_BAND | The sum-insured band <value> is not from-to amounts | Error | Write the sum-insured band as from-to amounts.
MSG-DM-138 | Batch (SCR-DM-07): rows refused at load | Server | MIG_SNAPSHOT_MISSING | Invoice <invoice no> has no snapshot | Error | Rerun the batch; the values at cut-over of the invoice were not kept.
MSG-DM-139 | Batch (SCR-DM-07): rows refused at load | Server | MIG_TARGET_MISSING | Value <code> of list <type> does not exist in BIBS | Error | Create the value in its list first, or map the legacy value to an existing value.
MSG-DM-140 | Batch (SCR-DM-07): rows refused at load | Server | MIG_TRUEUP_ITEM_KIND | Unapplied payment <ref> is adjusted with the unapplied payments object | Error | Send the adjustment of an unapplied payment with the unapplied payments.
MSG-DM-141 | Batch (SCR-DM-07): rows refused at load | Server | MIG_TRUEUP_ITEM_MISSING | Legacy invoice <ref> is not loaded | Error | Correct the invoice reference of the detail line; the invoice must be migrated.
MSG-DM-142 | Batch (SCR-DM-07): rows refused at load | Server | MIG_TRUEUP_NOT_APPROVED | The opening-balance adjustment of batch <batch no> is not approved by the Head of Comptrollership | Error | Ask the Head of Comptrollership to approve the adjustment first.
MSG-DM-143 | Batch (SCR-DM-07): rows refused at load | Server | MIG_TRUEUP_OUT_OF_RANGE | The adjustment would take <c> of invoice <ref> below zero; it moved in BIBS since go-live - settle it with Comptrollership | Error | Settle the difference with Comptrollership; the invoice moved in BIBS since go-live.
MSG-DM-144 | Batch (SCR-DM-07): rows refused at load | Server | MIG_UNIT_UNKNOWN | Sales unit <code> does not exist in BIBS | Error | Map the legacy unit in the sales unit code map.
MSG-DM-145 | Batch (SCR-DM-07): rows refused at load | Server | MIG_UPP_MISSING | Unapplied item <target code> not found | Error | Rerun the batch; the unapplied payment of the row was not created.
MSG-DM-146 | Client Matching (SCR-DM-08) | Screen | - | No client pair waiting for review | Information | No action.
MSG-DM-147 | Client Matching (SCR-DM-08) | Screen | - | No values | Information | No action.
MSG-DM-148 | Client Matching (SCR-DM-08) | Server | MIG_PAIR_DECIDED | This pair is already decided | Error | No action; refresh the queue.
MSG-DM-149 | Reconciliation (SCR-DM-09) | Screen | - | No loaded batch to reconcile | Information | No action.
MSG-DM-150 | Reconciliation (SCR-DM-09) | Screen | - | The batch is not reconciled yet | Information | No action.
MSG-DM-151 | Reconciliation (SCR-DM-09) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-152 | Reconciliation (SCR-DM-09) | Server | MIG_BATCH_STATUS | Batch <batch no> is <status>; it has no load to reconcile | Error | Refresh the batch; the action is not allowed in its current status.
MSG-DM-153 | Reconciliation (SCR-DM-09) | Server | MIG_LINE_MATCHED | This line has no difference to explain | Error | No action; the line has no difference.
MSG-DM-154 | Reconciliation (SCR-DM-09) | Server | MIG_NOT_EXPLAINED | Explain the break before approving it | Error | Explain the break first.
MSG-DM-155 | Reconciliation (SCR-DM-09) | Server | MIG_REASON_REQUIRED | Enter the explanation of the break | Error | Enter the explanation of the break.
MSG-DM-156 | Sign-off (SCR-DM-10) | Screen | - | No data object | Information | No action.
MSG-DM-157 | Opening-Balance Adjustments (SCR-DM-11) | Screen | - | No opening-balance adjustment yet | Information | No action.
MSG-DM-158 | Opening-Balance Adjustments (SCR-DM-11) | Screen | - | The Head of Comptrollership approves or returns the adjustment. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-159 | Opening-Balance Adjustments (SCR-DM-11) | Screen | - | The adjustment batch may then be loaded; its journals post into the opening period. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-160 | Opening-Balance Adjustments (SCR-DM-11) | Screen | - | The adjustment goes back to the preparer. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-161 | Opening-Balance Adjustments (SCR-DM-11) | Server | MAKER_CHECKER_VIOLATION | A record cannot be authorized by the user who maintained it | Error | Ask another user with the approval right to approve; the maker, submitter or operator of the record cannot.
MSG-DM-162 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_REASON_REQUIRED | Enter the reason for the return | Error | Enter the reason for the return.
MSG-DM-163 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_TRUEUP_BATCH | Batch <batch no> is not a batch of object <object> | Error | Choose a batch of the adjustment journals (G03), and a trial balance batch (G01).
MSG-DM-164 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_TRUEUP_EXISTS | Opening-balance adjustment <no> already exists | Error | Open the adjustment already prepared.
MSG-DM-165 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_TRUEUP_NO | The adjustment number is 1, 2, 3 or F | Error | Choose 1, 2, 3 or F.
MSG-DM-166 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_TRUEUP_OPTION | Opening-balance adjustments apply to the year-end go-live; the cut-over option is B | Error | No action; opening-balance adjustments apply only to the year-end go-live (option A).
MSG-DM-167 | Opening-Balance Adjustments (SCR-DM-11) | Server | MIG_TRUEUP_STATUS | True-up <trueup no> is <status>; it cannot be <action> | Error | Refresh the adjustment; the action is not allowed in its current status.
MSG-DM-168 | Cutover (SCR-DM-12) | Screen | - | Checklist updated | Validation | No action; the screen shows the change.
MSG-DM-169 | Cutover (SCR-DM-12) | Screen | - | No cutover plan yet | Information | No action.
MSG-DM-170 | Cutover (SCR-DM-12) | Screen | - | No decision yet | Information | No action.
MSG-DM-171 | Cutover (SCR-DM-12) | Screen | - | Recorded | Validation | No action; the screen shows the change.
MSG-DM-172 | Cutover (SCR-DM-12) | Screen | - | The actual end is recorded and the tasks after it may start. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-173 | Cutover (SCR-DM-12) | Screen | - | The actual start is recorded; the tasks it depends on must be finished. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-174 | Cutover (SCR-DM-12) | Screen | - | The cut-over stops and rolls back to the snapshot.<gate> | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-175 | Cutover (SCR-DM-12) | Screen | - | The task is marked blocked with its reason for the cut-over call. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-176 | Cutover (SCR-DM-12) | Server | MIG_CRITERION_MEASURED | Criterion <criterion no> is measured by the system | Error | No action; the criterion is measured by BIBS (Measure Criteria).
MSG-DM-177 | Cutover (SCR-DM-12) | Server | MIG_EVIDENCE_REQUIRED | Give the evidence of the criterion | Error | Give the evidence of the criterion.
MSG-DM-178 | Cutover (SCR-DM-12) | Server | MIG_GOLIVE_REQUIRED | Give the go-live date of the plan | Error | Give the go-live date of the plan.
MSG-DM-179 | Cutover (SCR-DM-12) | Server | MIG_GONOGO_JUSTIFY | <unmet> criteria are not met; give the justification of the GO | Error | Give the justification of the GO, or wait until the criteria are met.
MSG-DM-180 | Cutover (SCR-DM-12) | Server | MIG_REASON_REQUIRED | Give the reason of the NO-GO | Error | Give the reason of the NO-GO.
MSG-DM-181 | Cutover (SCR-DM-12) | Server | MIG_REASON_REQUIRED | Give the reason of the block | Error | Give the reason of the block.
MSG-DM-182 | Cutover (SCR-DM-12) | Server | MIG_TASK_DEPENDENCY | Task <dep> must be finished before task <seq> | Error | Complete the tasks it depends on first.
MSG-DM-183 | Run-off and Decommissioning (SCR-DM-13) | Screen | - | No run-off snapshot yet; the snapshot is taken on the first of each month | Information | No action.
MSG-DM-184 | Run-off and Decommissioning (SCR-DM-13) | Server | MIG_DECOMMISSION_EXISTS | The checklist of <system> is already open | Error | Open the checklist already listed.
MSG-DM-185 | Run-off and Decommissioning (SCR-DM-13) | Server | MIG_EVIDENCE_REQUIRED | Give the evidence of the criterion | Error | Give the evidence of the criterion.
MSG-DM-186 | Legacy Inquiry (SCR-DM-14) | Screen | - | No document archived with this record | Information | No action.
MSG-DM-187 | Legacy Inquiry (SCR-DM-14) | Screen | - | No legacy record matches the search | Information | No action.
MSG-DM-188 | Legacy Inquiry (SCR-DM-14) | Server | MIG_ACCESS_REASON_REQUIRED | Give the reason for opening the legacy archive | Error | Give the reason for opening the legacy archive.
MSG-DM-189 | Legacy Inquiry (SCR-DM-14) | Server | MIG_ARCHIVE_EXISTS | Archive record <record type> <legacy key> is already loaded | Error | No action; the record is already archived.
MSG-DM-190 | Legacy Inquiry (SCR-DM-14) | Server | MIG_ARCHIVE_RECORD_MISSING | Archive record <record type> <legacy key> is not loaded | Error | Load the archive record before its documents.
MSG-DM-191 | Legacy Inquiry (SCR-DM-14) | Server | MIG_CRITERIA_REQUIRED | Give a client, policy, invoice, receipt or claim, a record type or a date range | Error | Give a client, policy, invoice, receipt or claim, a record type or a date range.
MSG-DM-192 | Legacy Inquiry (SCR-DM-14) | Server | MIG_DATE_INVALID | Give the date as yyyy-MM-dd: <value> | Error | Give the date as yyyy-MM-dd.
MSG-DM-193 | Legacy Inquiry (SCR-DM-14) | Server | MIG_DOCUMENT_CHECKSUM | The SHA-256 of file <file name> does not match the index | Error | Ask BDOI IT to copy the file again; it differs from the index.
MSG-DM-194 | Legacy Inquiry (SCR-DM-14) | Server | MIG_DOCUMENT_MISSING | File <file name> is not in the transfer folder | Error | Ask BDOI IT to copy the file into the transfer folder.
MSG-DM-195 | Legacy Inquiry (SCR-DM-14) | Server | MIG_DOCUMENT_SIZE | File <file name> has <length> bytes; the index says <size bytes> | Error | Ask BDOI IT to copy the file again; its size differs from the index.
MSG-DM-196 | Legacy Inquiry (SCR-DM-14) | Server | MIG_EXPORT_TOO_LARGE | <total elements> records match; narrow the search to at most <max> records to export | Error | Narrow the search (dates, record type, client) to export at most the number shown.
MSG-DM-197 | Legacy Inquiry (SCR-DM-14) | Server | MIG_SOURCE_REQUIRED | Give the legacy system | Error | Give the legacy system of the documents.
MSG-DM-198 | Access Log (SCR-DM-15) | Screen | - | No access in the period | Information | No action.
MSG-DM-199 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | No batch yet | Information | No action.
MSG-DM-200 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | No legacy invoice fits | Information | No action.
MSG-DM-201 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | No line yet | Information | No action.
MSG-DM-202 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | No unapplied payment fits | Information | No action.
MSG-DM-203 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | The Cashiering team lead approves first, then top management; the lines post after the second approval. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-204 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | The Cashiering team lead approves; any premium receivable needed is first moved to PR 2307. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-205 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | The Commission team lead approves; each invoice then posts on its own. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-206 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | The batch goes back to its requester as a draft. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-207 | Unapplied to Income and Legacy PR 2307 Reversal (SCR-DM-18, SCR-DM-19) | Screen | - | The batch is closed without posting; its lines may be taken again. | Validation | Confirm to go ahead, or cancel to leave the record as it is.
MSG-DM-208 | Every migration screen (Common screen elements) | Screen | - | Checked | Validation | No action; the screen shows the change.
MSG-DM-209 | Every screen (Common screen elements) | Server | ACCESS_DENIED | You are not permitted to perform this action | Error | Ask for the permission; the menu shows only the screens of your role.
MSG-DM-210 | Every screen (Common screen elements) | Server | CONCURRENT_MODIFICATION | The record was changed by another user. Please reload and try again. | Error | Reload the record; another user changed it. Enter the change again.
MSG-DM-211 | Every screen (Common screen elements) | Server | INTERNAL_ERROR | The system could not complete the request. Try again; if it continues, contact support with the reference. | Error | Report the message with its reference to the System Administrator.
MSG-DM-212 | Every screen (Common screen elements) | Server | MALFORMED_REQUEST | Parameter '<name>' has an invalid value | Error | Reload the screen and try again; if it persists, report it with the time to the System Administrator.
MSG-DM-213 | Every screen (Common screen elements) | Server | MALFORMED_REQUEST | Required parameter '<parameter name>' is missing | Error | Reload the screen and try again; if it persists, report it with the time to the System Administrator.
MSG-DM-214 | Several screens | Server | MIG_NO_LAYOUT | There is no layout in force to export | Error | Freeze a layout of the object first; only the layouts in force have load templates.
MSG-DM-215 | Every screen (Common screen elements) | Server | UPLOAD_TOO_LARGE | The uploaded file is too large | Error | Split the file (for example by branch) and upload the parts, or use the secure file drop when it is named.
MSG-DM-216 | Every screen (Common screen elements) | Server | VALIDATION_FAILED | Invalid request | Error | Correct the fields listed under the message.

## Notifications
Notifications
In-app notifications and e-mails
ID | Channel | Trigger | Recipient | Template and text | Content | Screen | FRs
NT-01 | Alert | An extract does not agree with its control file (checksum, header, row count, amount totals or hash total) and is rejected | Data Migration Lead and the Migration Operators | Migration extract rejected (severity Medium). Text: Extract <file name> rejected: <reason> | The extract number and the reason; the alert opens Extracts | Extracts (SCR-DM-05) | FR-DM-010
NT-02 | Alert | A batch stops, or loads with rejected rows | Data Migration Lead and the Migration Operators | Migration load failed (severity High). Text: Batch <batch no> stopped. / Batch <batch no> loaded with rejects. <counts> | The batch and its counts; the alert opens the batch | Batch (SCR-DM-07) | FR-DM-014
NT-03 | Alert | Validation finds legacy codes without an approved code map entry | Data Steward and the Data Migration Lead | Unmapped legacy codes (severity Medium). Text: Batch <batch no> has <n> unmapped legacy codes | The batch; the codes are on the Unmapped Codes tab of Code Maps | Code Maps (SCR-DM-03) | FR-DM-012
NT-04 | Alert | A reconciliation run has lines that do not match | Reconciliation approver and the Data Migration Lead | Migration reconciliation break (severity High). Text: Reconciliation <run no> of batch <batch no> has <n> open breaks | The run and the batch; the alert opens Reconciliation | Reconciliation (SCR-DM-09) | FR-DM-020
NT-05 | Alert | Migration Clearing is not 0.00 for a branch and currency after an opening load | Head of Comptrollership (reconciliation approver) and the Data Migration Lead | Migration clearing not zero (severity Critical). Text: Migration Clearing of <branch> <currency> is <amount> | The branch, currency and balance; the Migration Clearing report analyses it per legacy control account | Reconciliation (SCR-DM-09), GL level | FR-DM-021
NT-06 | Alert | An accepted or rolled-back batch still holds staging data after its purge date (daily check) | Data Migration Lead and Compliance | Migration staging not purged (severity High). Text: Staging data of batch <batch no> is kept past its purge date <date> | The batch and the purge date | Batch (SCR-DM-07) | FR-DM-010
NT-07 | Alert | A user exports more legacy archive records in a day than the alert limit (5,000) | Compliance reviewers of the access log | Unusual legacy archive access (severity High). Text: User <user> exported <n> legacy archive records today (limit <limit>) | The user and the count; the Access Log shows the exports | Legacy Inquiry (SCR-DM-14); Access Log (SCR-DM-15) | FR-DM-111
NT-08 | Alert | A check of the reconciliation of an opening-balance adjustment fails | Head of Comptrollership and the Comptrollership GL lead | Opening-balance adjustment break (severity Critical). Text: Opening-balance adjustment <reference> has <n> reconciliation break(s) | The adjustment; it cannot be signed until the break is resolved | Opening-Balance Adjustments (SCR-DM-11) | FR-DM-024
NT-09 | E-mail | First day of each month | Compliance reviewers of the access log | Monthly digest of the legacy archive access log: searches, views, downloads and exports of the previous month per user, with the reasons given | The digest of the access log of the month | Access Log (SCR-DM-15) | FR-DM-111
NT-10 | None | Any record created by a migration load (client, account, invoice, unapplied payment, insurer, product, payee) | - | No notification to clients, insurers or users and no outbound integration message is sent for a migrated record | - | Every business screen | FR-DM-014

## Menu by persona
Menu by persona
What each Data Migration persona sees in the sidebar (from the role grants)
Persona | Group | Section | Screen | BRD | Data Migration
Data Migration Lead | Home | Overview | My Approvals | Platform
Data Migration Lead | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Batches | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Data Migration Lead | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Data Migration Lead | Reports | New Business Reports | New Business Reports | BRD-1
Data Migration Lead | Reports | Reports | Report Centre | Platform
Data Migration Lead | Setup & Administration | Help | Help Center | Platform
Data Migration Lead | Setup & Administration | Help | My Profile | Platform
Data Steward | Home | Overview | My Approvals | Platform
Data Steward | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Batches | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Client Matching | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Data Steward | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Data Steward | Reports | New Business Reports | New Business Reports | BRD-1
Data Steward | Reports | Reports | Report Centre | Platform
Data Steward | Setup & Administration | Help | Help Center | Platform
Data Steward | Setup & Administration | Help | My Profile | Platform
Data owner (business owner of an object) | Home | Overview | My Approvals | Platform
Data owner (business owner of an object) | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Batches | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Data owner (business owner of an object) | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Data owner (business owner of an object) | Reports | New Business Reports | New Business Reports | BRD-1
Data owner (business owner of an object) | Reports | Reports | Report Centre | Platform
Data owner (business owner of an object) | Setup & Administration | Help | Help Center | Platform
Data owner (business owner of an object) | Setup & Administration | Help | My Profile | Platform
Migration Operator | Home | Overview | My Approvals | Platform
Migration Operator | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Extracts | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Batches | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Migration Operator | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Migration Operator | Reports | New Business Reports | New Business Reports | BRD-1
Migration Operator | Reports | Reports | Report Centre | Platform
Migration Operator | Setup & Administration | Help | Help Center | Platform
Migration Operator | Setup & Administration | Help | My Profile | Platform
Reconciliation approver (Head of Comptrollership) | Home | Overview | My Approvals | Platform
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Batches | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Reconciliation approver (Head of Comptrollership) | Reports | New Business Reports | New Business Reports | BRD-1
Reconciliation approver (Head of Comptrollership) | Reports | Reports | Report Centre | Platform
Reconciliation approver (Head of Comptrollership) | Setup & Administration | Help | Help Center | Platform
Reconciliation approver (Head of Comptrollership) | Setup & Administration | Help | My Profile | Platform
Go / no-go board | Home | Overview | My Approvals | Platform
Go / no-go board | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Batches | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Go / no-go board | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Go / no-go board | Reports | New Business Reports | New Business Reports | BRD-1
Go / no-go board | Reports | Reports | Report Centre | Platform
Go / no-go board | Setup & Administration | Help | Help Center | Platform
Go / no-go board | Setup & Administration | Help | My Profile | Platform
Comptrollership GL lead | Home | Overview | My Approvals | Platform
Comptrollership GL lead | Home | New Business Dashboard | NB Dashboard | BRD-1
Comptrollership GL lead | Home | My Work | My Work | BRD-1
Comptrollership GL lead | Client & Policy | Clients | Clients | BRD-1
Comptrollership GL lead | Client & Policy | Clients | KYC Reviews Due | BRD-1
Comptrollership GL lead | Client & Policy | Accounts & Placement | Accounts | BRD-1
Comptrollership GL lead | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Comptrollership GL lead | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Comptrollership GL lead | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Comptrollership GL lead | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Comptrollership GL lead | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Comptrollership GL lead | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Comptrollership GL lead | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Comptrollership GL lead | Operations | Operations | Operations Home | BRD-2
Comptrollership GL lead | Operations | Operations | Invoice Search | BRD-2
Comptrollership GL lead | Operations | Operations | Hand-offs and Extracts | BRD-2
Comptrollership GL lead | Operations | Operations | Report Archive | BRD-2
Comptrollership GL lead | Operations | Operations | Notification Settings | BRD-2
Comptrollership GL lead | Finance | Collections | Collections Home | BRD-4
Comptrollership GL lead | Finance | Collections | PR Worklist | BRD-4
Comptrollership GL lead | Finance | Collections | Installment Plans | BRD-4
Comptrollership GL lead | Finance | Collections | Installments Due | BRD-4
Comptrollership GL lead | Finance | Collections | Promises to Pay | BRD-4
Comptrollership GL lead | Finance | Collections | Escalations | BRD-4
Comptrollership GL lead | Finance | Collections | Billing Statements | BRD-4
Comptrollership GL lead | Finance | Collections | Unapplied Payments | BRD-4
Comptrollership GL lead | Finance | Collections | Requests to Cashiering | BRD-4
Comptrollership GL lead | Finance | Collections | Collections Files | BRD-4
Comptrollership GL lead | Finance | Remittance | Remittance Deductions | BRD-2
Comptrollership GL lead | Finance | Commission Receivables | Commission Workbench | BRD-2 / BRD-4
Comptrollership GL lead | Finance | Commission Receivables | BIR Certificates | BRD-2 / BRD-4
Comptrollership GL lead | Finance | Disbursement | Disbursement Workbench | BRD-5
Comptrollership GL lead | Finance | Disbursement | Payees | BRD-5
Comptrollership GL lead | Finance | Disbursement | Disbursement End of Day | BRD-5
Comptrollership GL lead | Finance | Disbursement | Account Funding | BRD-5
Comptrollership GL lead | Finance | Disbursement | Bank Accounts and Checks | BRD-5
Comptrollership GL lead | Finance | Disbursement | Disbursement Reports | BRD-5
Comptrollership GL lead | Finance | ACSL | ACSL Cases | BRD-5
Comptrollership GL lead | Finance | ACSL | Correction Entries | BRD-5
Comptrollership GL lead | Finance | ACSL | Insurer SOA Reconciliation | BRD-5
Comptrollership GL lead | Finance | ACSL | GL-SL Reconciliation | BRD-5
Comptrollership GL lead | Finance | Accounting Reports | Report Pack | BRD-5
Comptrollership GL lead | Finance | Accounting Reports | Account Schedules | BRD-5
Comptrollership GL lead | Finance | Accounting Reports | Service Fee Runs | BRD-5
Comptrollership GL lead | Finance | Accounting Reports | Service Fee Rates | BRD-5
Comptrollership GL lead | Finance | General Ledger | Journals | BRD-5
Comptrollership GL lead | Finance | General Ledger | Recurring Journals | BRD-5
Comptrollership GL lead | Finance | General Ledger | Account Inquiry | BRD-5
Comptrollership GL lead | Finance | General Ledger | Party Statement | BRD-5
Comptrollership GL lead | Finance | Receivables & Banking | Receipts | BRD-5
Comptrollership GL lead | Finance | Receivables & Banking | Cheques & Deposits | BRD-5
Comptrollership GL lead | Finance | Receivables & Banking | PDC Received | BRD-5
Comptrollership GL lead | Finance | Payables & Cash | Supplier Invoices | BRD-5
Comptrollership GL lead | Finance | Payables & Cash | Payment Vouchers | BRD-5
Comptrollership GL lead | Finance | Payables & Cash | PDC Issued | BRD-5
Comptrollership GL lead | Finance | Payables & Cash | Petty Cash | BRD-5
Comptrollership GL lead | Finance | Accounting Engine | Event Register | BRD-5
Comptrollership GL lead | Data Migration | Data Migration | Migration Home | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Data Objects | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Code Maps | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Layouts and Rules | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Batches | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Reconciliation | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Opening Adjustments | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Cutover | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Run-off and Decommissioning | BRD-13 | Yes
Comptrollership GL lead | Data Migration | Data Migration | Sign-off | BRD-13 | Yes
Comptrollership GL lead | Reports | New Business Reports | New Business Reports | BRD-1
Comptrollership GL lead | Reports | Reports | Report Centre | Platform
Comptrollership GL lead | Setup & Administration | Help | Help Center | Platform
Comptrollership GL lead | Setup & Administration | Help | My Profile | Platform
Audit / Compliance user | Home | Overview | My Approvals | Platform
Audit / Compliance user | Data Migration | Legacy Inquiry | Legacy Inquiry | BRD-13 | Yes
Audit / Compliance user | Setup & Administration | Help | Help Center | Platform
Audit / Compliance user | Setup & Administration | Help | My Profile | Platform
Compliance reviewer of the access log | Home | Overview | My Approvals | Platform
Compliance reviewer of the access log | Data Migration | Legacy Inquiry | Access Log | BRD-13 | Yes
Compliance reviewer of the access log | Reports | New Business Reports | New Business Reports | BRD-1
Compliance reviewer of the access log | Reports | Reports | Report Centre | Platform
Compliance reviewer of the access log | Setup & Administration | Help | Help Center | Platform
Compliance reviewer of the access log | Setup & Administration | Help | My Profile | Platform
Cashiering user | Home | Overview | My Approvals | Platform
Cashiering user | Home | New Business Dashboard | NB Dashboard | BRD-1
Cashiering user | Home | My Work | My Work | BRD-1
Cashiering user | Client & Policy | Clients | Clients | BRD-1
Cashiering user | Client & Policy | Clients | KYC Reviews Due | BRD-1
Cashiering user | Client & Policy | Accounts & Placement | Accounts | BRD-1
Cashiering user | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Cashiering user | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Cashiering user | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Cashiering user | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Cashiering user | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Cashiering user | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Cashiering user | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Cashiering user | Client & Policy | Bulk Processing | Bulk Uploads | BRD-1
Cashiering user | Operations | Operations | Operations Home | BRD-2
Cashiering user | Operations | Operations | Invoice Search | BRD-2
Cashiering user | Operations | Operations | Hand-offs and Extracts | BRD-2
Cashiering user | Operations | Operations | Report Archive | BRD-2
Cashiering user | Operations | Operations | Notification Settings | BRD-2
Cashiering user | Finance | Collections | Collections Home | BRD-4
Cashiering user | Finance | Collections | PR Worklist | BRD-4
Cashiering user | Finance | Collections | Installment Plans | BRD-4
Cashiering user | Finance | Collections | Installments Due | BRD-4
Cashiering user | Finance | Collections | Promises to Pay | BRD-4
Cashiering user | Finance | Collections | Escalations | BRD-4
Cashiering user | Finance | Collections | Billing Statements | BRD-4
Cashiering user | Finance | Collections | Unapplied Payments | BRD-4
Cashiering user | Finance | Collections | Requests to Cashiering | BRD-4
Cashiering user | Finance | Collections | Collections Files | BRD-4
Cashiering user | Finance | Cashiering | Cashiering Workbench | BRD-2
Cashiering user | Finance | Cashiering | Receive Payment | BRD-2
Cashiering user | Finance | Cashiering | Receipts | BRD-2
Cashiering user | Finance | Cashiering | Unapplied Payments | BRD-2
Cashiering user | Finance | Cashiering | Incoming Requests | BRD-2
Cashiering user | Finance | Cashiering | Pre-booked Payments | BRD-2
Cashiering user | Finance | Cashiering | Payment Uploads | BRD-2
Cashiering user | Finance | Cashiering | PDC Warehouse | BRD-2
Cashiering user | Finance | Cashiering | Check Pick-up | BRD-2
Cashiering user | Finance | Cashiering | Batch Print | BRD-2
Cashiering user | Finance | Cashiering | BIR 2307 | BRD-2
Cashiering user | Finance | Cashiering | Unapplied to Income | BRD-2
Cashiering user | Finance | Cashiering | Legacy PR 2307 Reversal | BRD-2
Cashiering user | Finance | Cashiering | Commission ORs | BRD-2
Cashiering user | Finance | Cashiering | Receipt Series | BRD-2
Cashiering user | Finance | Cashiering | Cashiering Setup | BRD-2
Cashiering user | Finance | Commission Receivables | DP PR Legacy Reversal | BRD-2 / BRD-4
Cashiering user | Reports | New Business Reports | New Business Reports | BRD-1
Cashiering user | Reports | Reports | Report Centre | Platform
Cashiering user | Setup & Administration | Help | Help Center | Platform
Cashiering user | Setup & Administration | Help | My Profile | Platform
Cashiering team lead | Home | Overview | My Approvals | Platform
Cashiering team lead | Home | New Business Dashboard | NB Dashboard | BRD-1
Cashiering team lead | Home | My Work | My Work | BRD-1
Cashiering team lead | Client & Policy | Clients | Clients | BRD-1
Cashiering team lead | Client & Policy | Clients | KYC Reviews Due | BRD-1
Cashiering team lead | Client & Policy | Accounts & Placement | Accounts | BRD-1
Cashiering team lead | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Cashiering team lead | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Cashiering team lead | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Cashiering team lead | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Cashiering team lead | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Cashiering team lead | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Cashiering team lead | Client & Policy | Booking | Booking Setup | BRD-1
Cashiering team lead | Client & Policy | Product Maintenance | Products | BRD-3
Cashiering team lead | Client & Policy | Product Maintenance | Coverages & Clauses | BRD-3
Cashiering team lead | Client & Policy | Product Maintenance | Insurers | BRD-3
Cashiering team lead | Client & Policy | Product Maintenance | Rates & Taxes | BRD-3
Cashiering team lead | Client & Policy | Product Maintenance | Sales Organisation | BRD-3
Cashiering team lead | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Cashiering team lead | Client & Policy | Bulk Processing | Bulk Uploads | BRD-1
Cashiering team lead | Operations | Operations | Operations Home | BRD-2
Cashiering team lead | Operations | Operations | Invoice Search | BRD-2
Cashiering team lead | Operations | Operations | Hand-offs and Extracts | BRD-2
Cashiering team lead | Operations | Operations | Report Archive | BRD-2
Cashiering team lead | Operations | Operations | Notification Settings | BRD-2
Cashiering team lead | Finance | Collections | Collections Home | BRD-4
Cashiering team lead | Finance | Collections | PR Worklist | BRD-4
Cashiering team lead | Finance | Collections | Installment Plans | BRD-4
Cashiering team lead | Finance | Collections | Installments Due | BRD-4
Cashiering team lead | Finance | Collections | Promises to Pay | BRD-4
Cashiering team lead | Finance | Collections | Escalations | BRD-4
Cashiering team lead | Finance | Collections | Billing Statements | BRD-4
Cashiering team lead | Finance | Collections | Unapplied Payments | BRD-4
Cashiering team lead | Finance | Collections | Requests to Cashiering | BRD-4
Cashiering team lead | Finance | Collections | Collections Files | BRD-4
Cashiering team lead | Finance | Cashiering | Cashiering Workbench | BRD-2
Cashiering team lead | Finance | Cashiering | Receive Payment | BRD-2
Cashiering team lead | Finance | Cashiering | Receipts | BRD-2
Cashiering team lead | Finance | Cashiering | Unapplied Payments | BRD-2
Cashiering team lead | Finance | Cashiering | Incoming Requests | BRD-2
Cashiering team lead | Finance | Cashiering | Pre-booked Payments | BRD-2
Cashiering team lead | Finance | Cashiering | Payment Uploads | BRD-2
Cashiering team lead | Finance | Cashiering | PDC Warehouse | BRD-2
Cashiering team lead | Finance | Cashiering | Check Pick-up | BRD-2
Cashiering team lead | Finance | Cashiering | Batch Print | BRD-2
Cashiering team lead | Finance | Cashiering | BIR 2307 | BRD-2
Cashiering team lead | Finance | Cashiering | Unapplied to Income | BRD-2
Cashiering team lead | Finance | Cashiering | Legacy PR 2307 Reversal | BRD-2
Cashiering team lead | Finance | Cashiering | Commission ORs | BRD-2
Cashiering team lead | Finance | Cashiering | Receipt Series | BRD-2
Cashiering team lead | Finance | Cashiering | Cashiering Setup | BRD-2
Cashiering team lead | Finance | Commission Receivables | DP PR Legacy Reversal | BRD-2 / BRD-4
Cashiering team lead | Finance | General Ledger | Chart of Accounts | BRD-5
Cashiering team lead | Finance | General Ledger | Financial Periods | BRD-5
Cashiering team lead | Finance | Payables & Cash | Bank Accounts | BRD-5
Cashiering team lead | Finance | Assets & Investments | Asset Categories | BRD-5
Cashiering team lead | Finance | Assets & Investments | Asset Register | BRD-5
Cashiering team lead | Finance | Assets & Investments | Depreciation Run | BRD-5
Cashiering team lead | Finance | Assets & Investments | Investment Portfolios | BRD-5
Cashiering team lead | Finance | Assets & Investments | Investments | BRD-5
Cashiering team lead | Finance | Assets & Investments | Accrual & Amortization | BRD-5
Cashiering team lead | Finance | Assets & Investments | Maturities & Sales | BRD-5
Cashiering team lead | Finance | Accounting Engine | Event Types | BRD-5
Cashiering team lead | Finance | Accounting Engine | Accounting Rules | BRD-5
Cashiering team lead | Finance | Accounting Engine | Rule Simulator | BRD-5
Cashiering team lead | Reports | New Business Reports | New Business Reports | BRD-1
Cashiering team lead | Reports | New Business Reports | Production Targets | BRD-1
Cashiering team lead | Reports | Reports | Report Centre | Platform
Cashiering team lead | Setup & Administration | Broking Setup | Data Retention | BRD-1
Cashiering team lead | Setup & Administration | Broking Setup | Document Templates | BRD-1
Cashiering team lead | Setup & Administration | Setup | Companies | Platform
Cashiering team lead | Setup & Administration | Setup | Branches | Platform
Cashiering team lead | Setup & Administration | Setup | Currencies & Rates | Platform
Cashiering team lead | Setup & Administration | Setup | Dimensions | Platform
Cashiering team lead | Setup & Administration | Setup | Business Partners | Platform
Cashiering team lead | Setup & Administration | Setup | Employees | Platform
Cashiering team lead | Setup & Administration | Setup | Cost-Centre Rules | Platform
Cashiering team lead | Setup & Administration | Setup | Holiday Calendar | Platform
Cashiering team lead | Setup & Administration | Help | Help Center | Platform
Cashiering team lead | Setup & Administration | Help | My Profile | Platform
Top management approver | Home | Overview | My Approvals | Platform
Top management approver | Finance | Cashiering | Unapplied to Income | BRD-2
Top management approver | Setup & Administration | Help | Help Center | Platform
Top management approver | Setup & Administration | Help | My Profile | Platform
Commission user | Home | Overview | My Approvals | Platform
Commission user | Home | New Business Dashboard | NB Dashboard | BRD-1
Commission user | Home | My Work | My Work | BRD-1
Commission user | Client & Policy | Clients | Clients | BRD-1
Commission user | Client & Policy | Clients | KYC Reviews Due | BRD-1
Commission user | Client & Policy | Accounts & Placement | Accounts | BRD-1
Commission user | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Commission user | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Commission user | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Commission user | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Commission user | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Commission user | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Commission user | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Commission user | Client & Policy | Bulk Processing | Bulk Uploads | BRD-1
Commission user | Operations | Operations | Operations Home | BRD-2
Commission user | Operations | Operations | Invoice Search | BRD-2
Commission user | Operations | Operations | Hand-offs and Extracts | BRD-2
Commission user | Operations | Operations | Report Archive | BRD-2
Commission user | Operations | Operations | Notification Settings | BRD-2
Commission user | Finance | Cashiering | Legacy PR 2307 Reversal | BRD-2
Commission user | Finance | Commission Receivables | Commission Workbench | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | DP Lists | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | DP Accounts | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | DP Billings | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | Insurer Responses | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | Incentive Schemes | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | Incentive Runs | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | BIR Certificates | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | DP PR Legacy Reversal | BRD-2 / BRD-4
Commission user | Finance | Commission Receivables | Estimated Items | BRD-2 / BRD-4
Commission user | Reports | New Business Reports | New Business Reports | BRD-1
Commission user | Reports | Reports | Report Centre | Platform
Commission user | Setup & Administration | Help | Help Center | Platform
Commission user | Setup & Administration | Help | My Profile | Platform
Commission team lead | Home | Overview | My Approvals | Platform
Commission team lead | Home | New Business Dashboard | NB Dashboard | BRD-1
Commission team lead | Home | My Work | My Work | BRD-1
Commission team lead | Client & Policy | Clients | Clients | BRD-1
Commission team lead | Client & Policy | Clients | KYC Reviews Due | BRD-1
Commission team lead | Client & Policy | Accounts & Placement | Accounts | BRD-1
Commission team lead | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Commission team lead | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Commission team lead | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Commission team lead | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Commission team lead | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Commission team lead | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Commission team lead | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Commission team lead | Client & Policy | Bulk Processing | Bulk Uploads | BRD-1
Commission team lead | Operations | Operations | Operations Home | BRD-2
Commission team lead | Operations | Operations | Invoice Search | BRD-2
Commission team lead | Operations | Operations | Hand-offs and Extracts | BRD-2
Commission team lead | Operations | Operations | Report Archive | BRD-2
Commission team lead | Operations | Operations | Notification Settings | BRD-2
Commission team lead | Finance | Cashiering | Legacy PR 2307 Reversal | BRD-2
Commission team lead | Finance | Commission Receivables | Commission Workbench | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | DP Lists | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | DP Accounts | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | DP Billings | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | Insurer Responses | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | Incentive Schemes | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | Incentive Runs | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | BIR Certificates | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | DP PR Legacy Reversal | BRD-2 / BRD-4
Commission team lead | Finance | Commission Receivables | Estimated Items | BRD-2 / BRD-4
Commission team lead | Reports | New Business Reports | New Business Reports | BRD-1
Commission team lead | Reports | New Business Reports | Production Targets | BRD-1
Commission team lead | Reports | Reports | Report Centre | Platform
Commission team lead | Setup & Administration | Help | Help Center | Platform
Commission team lead | Setup & Administration | Help | My Profile | Platform
Marketing Account Officer | Home | Overview | My Approvals | Platform
Marketing Account Officer | Home | New Business Dashboard | NB Dashboard | BRD-1
Marketing Account Officer | Home | My Work | My Work | BRD-1
Marketing Account Officer | Client & Policy | Clients | Clients | BRD-1
Marketing Account Officer | Client & Policy | Clients | New Client | BRD-1
Marketing Account Officer | Client & Policy | Clients | KYC Reviews Due | BRD-1
Marketing Account Officer | Client & Policy | Quotation / Proposal | Quotations | BRD-1
Marketing Account Officer | Client & Policy | Quotation / Proposal | New Quotation | BRD-1
Marketing Account Officer | Client & Policy | Quotation / Proposal | Quotation Requests | BRD-1
Marketing Account Officer | Client & Policy | Accounts & Placement | Accounts | BRD-1
Marketing Account Officer | Client & Policy | Accounts & Placement | New Account | BRD-1
Marketing Account Officer | Client & Policy | Accounts & Placement | FFY Register | BRD-1
Marketing Account Officer | Client & Policy | Accounts & Placement | Direct Payment | BRD-1
Marketing Account Officer | Client & Policy | Non-Package Management | Proposal Requests | BRD-1
Marketing Account Officer | Client & Policy | Non-Package Management | New Proposal Request | BRD-1
Marketing Account Officer | Client & Policy | Placement & Booking | Placement Workbench | BRD-1
Marketing Account Officer | Client & Policy | Placement & Booking | Placement Slips | BRD-1
Marketing Account Officer | Client & Policy | Policy Issuance | Issuance Workbench | BRD-1
Marketing Account Officer | Client & Policy | Policy Issuance | Insurance Advice | BRD-1
Marketing Account Officer | Client & Policy | Renewal | Renewal Home | BRD-6
Marketing Account Officer | Client & Policy | Renewal | Expiry List | BRD-6
Marketing Account Officer | Client & Policy | Renewal | My Dispositions | BRD-6
Marketing Account Officer | Client & Policy | Renewal | Transfers | BRD-6
Marketing Account Officer | Client & Policy | Renewal | Letters | BRD-6
Marketing Account Officer | Client & Policy | Submitted Policies | Submitted Policies Home | -
Marketing Account Officer | Client & Policy | Submitted Policies | Masterlist | -
Marketing Account Officer | Client & Policy | Submitted Policies | Extraction Review | -
Marketing Account Officer | Client & Policy | Submitted Policies | Processing Runs | -
Marketing Account Officer | Client & Policy | Submitted Policies | Reviews & IAAF | -
Marketing Account Officer | Client & Policy | Submitted Policies | Terms of Reference | -
Marketing Account Officer | Client & Policy | Submitted Policies | Renewal Work List | -
Marketing Account Officer | Client & Policy | Product Maintenance | Product Maintenance Home | BRD-3
Marketing Account Officer | Client & Policy | Product Maintenance | Package Requests | BRD-3
Marketing Account Officer | Client & Policy | Product Maintenance | Products | BRD-3
Marketing Account Officer | Client & Policy | Product Maintenance | Coverages & Clauses | BRD-3
Marketing Account Officer | Client & Policy | Product Maintenance | Incentive Criteria | BRD-3
Marketing Account Officer | Client & Policy | Product Maintenance | Premium Calculator | BRD-3
Marketing Account Officer | Client & Policy | Bulk Processing | Bulk Uploads | BRD-1
Marketing Account Officer | Operations | Operations | Operations Home | BRD-2
Marketing Account Officer | Operations | Operations | Invoice Search | BRD-2
Marketing Account Officer | Operations | Operations | Hand-offs and Extracts | BRD-2
Marketing Account Officer | Operations | Operations | Notification Settings | BRD-2
Marketing Account Officer | Finance | Collections | Collections Home | BRD-4
Marketing Account Officer | Finance | Collections | PR Worklist | BRD-4
Marketing Account Officer | Finance | Collections | Installment Plans | BRD-4
Marketing Account Officer | Finance | Collections | Installments Due | BRD-4
Marketing Account Officer | Finance | Collections | Promises to Pay | BRD-4
Marketing Account Officer | Finance | Collections | Escalations | BRD-4
Marketing Account Officer | Finance | Collections | Billing Statements | BRD-4
Marketing Account Officer | Finance | Collections | Unapplied Payments | BRD-4
Marketing Account Officer | Finance | Collections | Requests to Cashiering | BRD-4
Marketing Account Officer | Finance | Collections | Collections Files | BRD-4
Marketing Account Officer | Finance | Refund & Cash Advance Requests | Requests Home | BRD-5
Marketing Account Officer | Finance | Refund & Cash Advance Requests | New Refund Request | BRD-5
Marketing Account Officer | Finance | Refund & Cash Advance Requests | New Cash Advance | BRD-5
Marketing Account Officer | Finance | Refund & Cash Advance Requests | Cancel a Check | BRD-5
Marketing Account Officer | Claims & Insurance | Claims Handling | Claims Reports | BRD-7
Marketing Account Officer | Reports | New Business Reports | New Business Reports | BRD-1
Marketing Account Officer | Reports | Reports | Report Centre | Platform
Marketing Account Officer | Setup & Administration | Help | Help Center | Platform
Marketing Account Officer | Setup & Administration | Help | My Profile | Platform

## Cross-BRD contract
Cross-BRD contract
What Data Migration takes from and hands to the other BRDs and systems; a change is a change request
ID | BRD or system | Direction | What | When and how | Owner of the data | Screens | FRs
IC-01 | BRD-1 New Business | Out | Migrated clients (C01) with their identity, contacts, addresses, segment, AO and KYC status; payout accounts (C03); one BIBS client per matched cluster, found by any legacy client number | Loaded two weeks before go-live through the client registration of BIBS, then daily deltas until the freeze; no onboarding workflow and no notification | Product Owner, Marketing Business System (data owner of C01) | Client Matching; Clients (LEGACY badge, Origin filter) | FR-DM-030, FR-DM-031, FR-DM-032, FR-DM-033
IC-02 | BRD-1 New Business; BRD-2 Operations | Out | In-force policy headers (P01, P01S) as booked accounts of origin Migrated with the legacy package as given; the legacy invoices link to them | Loaded at the cut-over weekend after the freeze; the headers are used for endorsements, servicing and renewal | Head, Operations | Accounts (LEGACY badge) | FR-DM-040, FR-DM-041
IC-03 | BRD-2 Operations | Out | Open legacy invoices (F01, F01S, F01C) in the Operations ledger with their components, insurer shares and values at cut-over; endorsements of legacy invoices booked in the legacy context | Loaded after the freeze with an opening entry per insurer share; processed on Invoice 360, payments, remittance and endorsements after go-live; Changes to Legacy Invoices report for Prod Recon | Operations - Financial Transactions; Head, Comptrollership | Invoice 360 (Legacy Invoice card); Invoice Search | FR-DM-050, FR-DM-051, FR-DM-060, FR-DM-080, FR-DM-090, FR-DM-091, FR-DM-092, FR-DM-100
IC-04 | BRD-2 Operations (Cashiering) | Out | Legacy unapplied payments (F02) with the legacy AR, references and disposition in progress; the Unapplied to Income and Legacy PR 2307 Reversal batches | Loaded after the freeze with an opening entry; matched by automatch on their references; worked on the Unapplied workbench and in the legacy batches | Operations - Financial Transactions | Unapplied Payments; Unapplied to Income; Legacy PR 2307 Reversal | FR-DM-052, FR-DM-053, FR-DM-054, FR-DM-055, FR-DM-061, FR-DM-071
IC-05 | BRD-4 Collections | Out | Open collection state (F03) - dispositions, promises to pay, instalment plans and collector assignments of the open legacy invoices, carried as the legacy follow-up of the worklist item; tags "DP PR for reversal" | Loaded after the freeze; legacy items appear on the PR Worklist with the LEGACY badge | Head, Operations (Collections) | PR Worklist; Collection Account | FR-DM-052
IC-06 | BRD-2 Operations (Commission); BRD-4 | Out | The DP PR Legacy Reversal of legacy invoices paid directly to the insurer | Batch requested by a Commission user and approved by the Commission team lead; candidates tagged by Collections | Commission team lead | DP PR Legacy Reversal | FR-DM-070
IC-07 | BRD-5 Accounting (FRBS, ACSL) | In and Out | In: the chart of accounts, the legacy control accounts and Migration Clearing, and the accounting rules of the legacy components (set up by Comptrollership). Out: the provisional GL opening (G01), the opening entries of the invoices and unapplied payments, the opening-balance adjustments (G03); the legacy context of the GL to sub-ledger reconciliation | Opening journals dated 1 January 2028; Migration Clearing 0.00 per branch and currency; each adjustment approved by the Head of Comptrollership | Head, Comptrollership | Opening-Balance Adjustments; Reconciliation (GL level); journal inquiry | FR-DM-021, FR-DM-022, FR-DM-023, FR-DM-024
IC-08 | BRD-6 Renewal | Out | The migrated policy headers expiring from go-live to 31 May 2028 and the renewal advices already sent (P03) for the go-live renewal extraction; the package code map (R06) for the package check at sanitation; the migrated headers for the daily extraction from 1 June 2028 | Go-live extraction at 04:00 on go-live day, January expiries flagged urgent; the map is maintained in Renewal after go-live | Heads, Retail and Corporate Marketing; Head, Renewal processing team; TSU (package map) | Code Maps (package code map); Batches (P03 resubmissions); Renewal candidates | FR-DM-034, FR-DM-122, FR-DM-124, FR-DM-125
IC-09 | BRD-3 Product Maintenance | In | Products, package versions, insurers and commission rates of BIBS, which the code maps target; values created from the migration (CREATE entries) are authorised in their masters | Before the load of any dependent object; the package code map names only released package versions | Marketing Business System; TSU | Code Maps; Products; Insurers (LEGACY badge) | FR-DM-011, FR-DM-034
IC-10 | BRD-10 Sanction Screening | Out | Migrated clients for one full screening run after the client load (no screening per client during the load) | Periodic screening with the full re-screen option before go-live; hits in the screening queue for Compliance | Compliance | Screening queue | FR-DM-030
IC-11 | BRD-11 User Access Maintenance | In | The users of the migration roles and of every persona, created through User Access requests; legacy user IDs are only mapped (user code map) | Before each trial migration and before the production cut-over (T-27) | BDOI IT; user access administration | Code Maps (USER) | FR-DM-011
IC-12 | BDOI IT (legacy EBIX, QPS, ISYS, CMS) | In | Extracts in the load templates with their control files; the legacy freeze and read-only mode; the document transfer folder; the read-only addresses of the legacy applications | Console upload (or the secure file drop when named); final extracts after the last legacy EOD | Head, BDOI IT | Extracts; Legacy Inquiry | FR-DM-010, FR-DM-110

## Comments log
Comments log
Questions, corrections and change requests raised during the review, with the answer
ID | Raised by | Date | Page / screen | Template | Column | Type | Comment | Response | Status | Closed on
C-001
C-002
C-003
C-004
C-005
C-006
C-007
C-008
C-009
C-010
C-011
C-012
C-013
C-014
C-015
C-016
C-017
C-018
C-019
C-020
C-021
C-022
C-023
C-024
C-025
C-026
C-027
C-028
C-029
C-030
C-031
C-032
C-033
C-034
C-035
C-036
C-037
C-038
C-039
C-040
C-041
C-042
C-043
C-044
C-045
C-046
C-047
C-048
C-049
C-050

## Meeting minutes
Meeting minutes
Minutes of the review sessions
Date | Session | Planned | Attendees | Discussion | Decisions | Actions | Owner | Due date
| Kick-off and walkthrough of the Migration Console on SIT | 3 sessions, 7 to 9-Oct-2026
| Comments consolidated and a Q&A session | 3 working days, Q&A on Mon 26-Oct-2026
| Sign-off meeting and signature | Fri 30-Oct-2026 (M2)

## Version history
Version history
Versions of this release set (a revision after review is v2.1; after sign-off, a change request)
Version | Date | Author | Change | Rows changed
2.0 | 5 October 2026 | iorta TechNXT project team | First issue of the business sign-off pack, from the Data Migration Handbook of the same version | All

## Sign-off certificate
Sign-off certificate
By signing, the signatories confirm the BRD-13 Data Migration – Business Sign-off Pack v2.0: its content, screens and navigation are frozen; the screenshots use fictitious seed data; later changes go through the Change Management Register
Capacity | Role | Organisation | Confirms | On the BRD approval sheet | Name | Decision | Comments | Signature | Date
Prepared by | iorta TechNXT project team: Project Manager, Business Analysis, Migration Lead, test lead | iorta TechNXT | The set is complete and consistent as issued, traced to the BRD and to the Migration Console; every comment is answered in the comments log | Added for this set (author of the Handbook and the Migration Workbook)
Prepared by | Program Manager, Enterprise Services Group - Business Project Services (BPS) | BDO Unibank ESG | The set states the BRD requirements as written (author of the BRD); traceability of every BRD requirement and completeness of the set; chairs the go / no-go board | Prepared by (p.15)
Input provided by | Data Migration Lead | BDOI | The object decisions, the trial migrations, the gates and the cut-over plan match the business input | Added for this set
Input provided by | Data owners of the objects (department representatives named per object) | BDOI | Their objects, load templates, code maps and reconciliation | Added for this set (named per object in the Migration Workbook)
Reviewed by | Marketing Business System (MBS) | BDOI | The lists of values, products, packages, clients and payout accounts and their code maps | Reviewed by (p.15)
Reviewed by | BDOI Information Technology Group (BDOI IT) | BDOI | Extracts and their transfer, the legacy freeze and read-only access, decommissioning, and the Technical Specification (a separate document); not the business content | Added for this set
Approved by | Product Owner, Marketing Business System | BDOI | Owns the set and approves all of its contents | Approved by (p.15)
Approved by | Product Owner - Comptrollership - Disbursement | BDOI | Payees and open disbursements | Approved by (p.15)
Approved by | Product Owner - Comptrollership - FRBS and ACSL | BDOI | GL opening, legacy accounts and the subsidiary ledger | Approved by (p.15)
Approved by | Operations: Financial Transactions and Processing | BDOI | Open invoices, unapplied payments, collection state and remittance | Approved by (p.15)
Approved by | Head - Operations | BDOI | Insurers, commission rates and policy headers | Approved by (p.15)
Approved by | Unit Head - Analytics and Risk Management | BDOI | KYC documents, the archive, Legacy Inquiry and its access log | Approved by (p.15)
Approved by | Unit Head - Claims, Analytics, Risk Management, Reinsurance and Technical Underwriting | BDOI | The renewal advices already sent and the day-1 renewal queue | Approved by (p.16)
Approved by | Unit Head - Combank and Corbank | BDOI | Clients and the sales organisation of Combank and Corbank | Approved by (p.16)
Approved by | Head - Comptrollership | BDOI | Open items, GL opening, reconciliation and the opening-balance adjustments | Approved by (p.16)
Approved by | Head - Retail Marketing | BDOI | Clients and the sales organisation of Retail Marketing | Approved by (p.16)
Approved by | Head - Corporate and Retail Marketing | BDOI | Clients and the sales organisation of Corporate Marketing | Approved by (p.16)

## _lists (hidden)
Migrate | Accept | Accept | Accept | Accept | ROW_COUNT | MATCHED | Accept | EBIX | MAP | Accept | Accept | NOT STARTED | Accept | Y | Accept | Accept | Accept | OPEN | Accept | Trial migration 1 | Matched | Accept | OPEN | Agree | Accept | Accept | Accept | Accept | Validation | Accept | Clarification | Open | Approved
Carry forward | Change requested | Change requested | Change requested | Change requested | HASH_TOTAL | BREAK | Change requested | QPS | DEFAULT | Change requested | Change requested | IN PROGRESS | Change requested | N | Change requested | Change requested | Change requested | DONE | Change requested | Trial migration 2 | Explained | Change requested | PARTIAL | Agree with change | Change requested | Change requested | Change requested | Change requested | Error | Change requested | Correction | Answered | Approved with comments
Conditional | Comment | Comment | Comment | Comment | AMOUNT_TOTAL | EXPLAINED | Comment | ISYS | REJECT | Comment | Comment | DONE | Comment |  | Comment | Comment | Comment | N/A | Comment | Trial migration 3 | Break | Comment | ANSWERED | Disagree | Comment | Comment | Comment | Comment | Warning | Comment | Change request | Closed | Not approved
Archive |  |  |  |  | SHA256 |  |  | CMS | CREATE |  |  | BLOCKED | [7 empty] | Trial migration 4 |  |  | RECOMMENDED | Need more information |  |  |  |  | Confirmation
Excluded | [7 empty] | EXCEL |  |  |  | N/A | [7 empty] | Dress rehearsal | [8 empty] | Information
Production